## Noisy Activities
Southern North Sea (SNS) Special Area Of Conservation (SAC) Noise Tracker |  | Daily Threshold: Harbour porpoise not excluded from more than 20% of the SAC on any day. |  |  |  | Winter 25/26 | 2025-10-01 | Summer 25 | 2025-04-01 |  | Summer Area (km2) | 27028 | Summer Days | 183
|  | Seasonal Threshold: Harbour porpoise not excluded for more than 10% of the SAC per day, on average over the season. |  |  |  |  | 2026-03-31 |  | 2025-09-30 |  | Winter Area (km2) | 12696 | Winter Days | 182
Project/Activity Name | Applicant | Regulator | Activity Type | Which seasonal area of the SAC does this activity impact? | Quad/Block (OPRED only) | Case Reference | Wildlife Licence Reference | Case Status | Tracker Last Updated | Start Date | End Date | Duration of Activity Impacting SAC (days) | Area Overlap with SAC (km2) | Magnitude (OPRED only) | Area Overlap with Summer SAC (km2) (NEW) | Area Overlap with Winter SAC (km2) (NEW) | Abatement/Mitigation (MMO only) | Include in Winter Calendar | Include in Summer Calendar | % of Winter SAC Impacted (NEW) | % of Summer SAC Impacted (NEW) | % of Winter SAC Impacted | % of Summer SAC Impacted | TrackerID
Sizewell C - Pin Piling | EDF Energy | MMO | Pin Piling | Winter |  | DCO/2013/00021 |  | Submitted | 2025-10-21 | 2026-04-30 | 2027-02-28 | 30 | 0.1 |  |  |  | Soft / slow start and marine mammal obervers | TRUE | FALSE | 0 | 0 | 0.00078765 | 0 | 54
Norfolk Vanguard West - UXO Clearance (LO) | RWE Renewables UK | MMO | UXO Low Order | Winter |  | MLA/2025/00512 |  | Submitted | 2025-10-21 | 2026-04-01 | 2026-07-30 | 6 | 201.06 |  |  |  |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 59
Norfolk Vanguard West - UXO Clearance (HO) | RWE Renewables UK | MMO | UXO High Order | Summer |  | MLA/2025/00512 |  | Submitted | 2025-10-21 | 2026-04-01 | 2025-07-30 | 1 | 380.13 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 1.4064
Sizewell C - Pin Piling | EDF Energy | MMO | Pin Piling | Winter |  | DCO/2013/00021 |  | Submitted | 2025-10-21 | 2025-11-01 | 2026-09-01 | 55 | 0.1 |  |  |  | Soft / slow start and marine mammal obervers | TRUE | FALSE | 0 | 0 | 0.00078765 | 0 | 53
Platypus | Perenco | OPRED | Geophysical Survey | Summer |  | GS/1976/0 |  | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | 15 | 275.2 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 1.0182 | 61
Rough Storage - Geophysical Survey | Centrica Energy Storage Ltd | OPRED | Geophysical Survey | Winter | 47/2, 47/3, 4/7, 47/8 | GS/1822/0 |  | Postponed | 2025-07-15 | 2025-09-01 | 2026-03-31 | 3 | 586 | 160 cu in |  |  |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 30
EA3 - Pin Piling | Scottish Power Renewables | MMO | Pin Piling | Both |  | DCO/2018/00001 |  | Completed | 2025-09-09 | 2025-08-11 | 2025-08-11 | 1 | 706 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 12
Hornsea Three - UXO Clearance (Generation) (LO) | Orsted | MMO | UXO Low Order | Summer |  | MLA/2024/00675 |  | Completed | 2025-09-29 | 2025-08-08 | 2025-09-08 | 1 | 79 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.29229 | 22
Dogger Bank C - Monopiling (Unabated) | SSE Renewables | MMO | Piling | Summer |  | DCO/2016/00018 |  | Completed | 2025-10-23 | 2025-08-03 | 2025-08-16 | 3 | 150.7 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.55757 | 7
Expansion Seismic Part 1 (CS007) (NEP Expansion Stores) | BP | OPRED | Seismic Survey | Summer | Various | GS/1867 |  | Approved | 2025-07-29 | 2025-08-01 | 2025-09-02 | 32 | 744 | 400 cu in |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.7527 | 51
NEP - EPCI 1 Geophysical Pipeline | BP | OPRED | Geophysical Survey | Both | Various | GS/1913 |  | Approved | 2025-07-29 | 2025-07-28 | 2025-10-01 | 18 | 99 | N/A |  |  |  | TRUE | TRUE | 0 | 0 | 0.77977 | 0.36629 | 49
Baker and Abbey Site Surveys (Sub-Bottom Profiler) | Petrogas | OPRED | Geophysical Survey | Both | Various | GS/1900/0 |  | Submitted | 2025-07-15 | 2025-07-01 | 2025-12-01 | 2 | 12 |  |  |  |  | TRUE | TRUE | 0 | 0 | 0.094518 | 0.044398 | 52
EA3 - Monopiling (Abated) | Scottish Power Renewables | MMO | Piling Abated | Both |  | DCO/2018/00001 |  | Approved | 2025-07-15 | 2025-05-21 | 2026-09-30 | 100 | 1520 |  |  |  | MENCK Hammer | TRUE | TRUE | 0 | 0 | 11.9723 | 5.6238 | 11
Dogger Bank D - Geophysical Survey 1 | SSE Renewables | MMO | Geophysical Survey | Summer |  | DCO/2023/00001 |  | Completed | 2025-07-15 | 2025-05-10 | 2025-05-12 | 3 | 0.2 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.00073997 | 9
Sofia - Monopiling (Unabated) | Sofia Offshore Wind Farm Ltd | MMO | Piling | Summer |  | DCO/2013/00011 |  | Completed | 2025-07-15 | 2025-04-30 | 2025-07-13 | 4 | 1928.38 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 7.1347 | 32
NEP - EPCI 3 Geophysical Offshore Cable | BP | OPRED | Geophysical Survey | Summer | Various | GS/1871 |  | Completed | 2025-07-29 | 2025-04-22 | 2025-05-09 | 12 | 121 | N/A |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.44768 | 17
Pegasus West - Pipeline and Site Geophysical Survey (Sub-Bottom Profiler) | INEOS | OPRED | Geophysical Survey |  |  | GS/1886/0 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-05-26 | 36 | 471 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 1.7426 | 27
Cyngus - Conductor Driving of the 44/12a-AFF Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | 44/12 | DR/2500/5 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-04-24 | 1 | 706 | 90 KJ |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 45
Cyngus - Conductor Driving of the 44/12a-AJ Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | 44/12 | DR/2528/0 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-04-24 | 1 | 706 | 90 KJ |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 46
Cyngus - Conductor Driving of the 44/12a-Slot 1 Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | 44/12 | DR/2532/0 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-04-24 | 1 | 706 | 90 KJ |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 47
Cyngus - Conductor Driving of the 44/12a-Slot 6 Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | 44/12 | DR/2533/0 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-04-24 | 1 | 706 | 90 KJ |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 48
Dogger Bank B -Monopiling (Unabated) | SSE Renewables | MMO | Piling | Summer |  | DCO/2016/00024 |  | Completed | 2025-07-15 | 2025-04-17 | 2025-04-18 | 2 | 2873 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 10.6297 | 6
EA3 - Monopiling (Unabated) | Scottish Power Renewables | MMO | Piling | Both |  | DCO/2018/00001 |  | Approved | 2025-07-15 | 2025-04-17 | 2026-09-30 | 100 | 1927 |  |  |  |  | TRUE | TRUE | 0 | 0 | 15.178 | 7.1296 | 10
NEP - EPCI 2 Geophysical Infield | BP | OPRED | Geophysical Survey | Summer | Various | GS/1866 |  | Completed | 2025-07-29 | 2025-04-15 | 2025-05-07 | 20 | 115 | N/A |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.42548 | 16
Sofia - Monopiling (Abated) | Sofia Offshore Wind Farm Ltd | MMO | Piling Abated | Summer |  | DCO/2013/00011 |  | Completed | 2025-07-15 | 2025-04-02 | 2025-06-15 | 23 | 871.58 |  |  |  | BBC | FALSE | TRUE | 0 | 0 | 0 | 3.2247 | 31
NEP - Phase 1 2DHR | BP | OPRED | Seismic Survey | Summer | 42/25, 42/30, 43/21, 43/26 | GS/1853 |  | Completed | 2025-07-29 | 2025-04-01 | 2025-04-09 | 8 | 798 | 160 cu in |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.9525 | 28
Sizewell C - Nearshore (Subtidal) UXO Investigations | Sizewell C Ltd | MMO | Geophysical Survey | Winter |  | MLA/2024/00601 |  | Completed | 2025-07-15 | 2025-03-25 | 2025-05-17 | 81 | 434 |  |  |  |  | TRUE | FALSE | 0 | 0 | 3.4184 | 0 | 40
Norfolk Vanguard West - UXO Investigations (Marine Licence Application 2) | RWE Renewables UK | MMO | Geophysical Survey | Both |  | MLA/2024/00419 |  | Approved | 2025-07-15 | 2025-01-29 | 2026-01-29 | 365 | 0.000156 |  |  |  |  | TRUE | TRUE | 0 | 0 | 1.2287e-06 | 5.7718e-07 | 36
Norfolk Vanguard West - UXO Investigations (Marine Licence Application 1) | RWE Renewables UK | MMO | Geophysical Survey | Both |  | MLA/2024/00345 |  | Approved | 2025-07-15 | 2025-01-01 | 2025-12-31 | 365 | 0.00051 |  |  |  |  | TRUE | TRUE | 0 | 0 | 4.017e-06 | 1.8869e-06 | 35
Hornsea Three - UXO Clearance (Transmission) (HO) | Orsted | MMO | UXO High Order | Summer |  | MLA/2024/00088/1 |  | Completed | 2025-07-15 | 2024-11-07 | 2024-11-07 | 1 | 707 |  |  |  | BBC | FALSE | TRUE | 0 | 0 | 0 | 2.6158 | 23
Hornsea Three - UXO Clearance (Transmission) (LO) | Orsted | MMO | UXO Low Order | Summer |  | MLA/2024/00088/1 |  | Completed | 2025-07-15 | 2024-10-01 | 2025-04-15 | 24 | 79 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.29229 | 21
Sofia - UXO Investigations | RWE Ltd | MMO | Geophysical Survey | Summer |  | MLA/2020/00489 |  | Approved | 2025-07-15 | 2024-10-01 | 2028-05-31 | 0 | 133.37 |  |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.49345 | 33
EA3 - UXO Clearance (LO) | Scottish Power Renewables | MMO | UXO Low Order | Both |  | MLA/2023/00532/3 |  | Completed | 2025-07-15 | 2024-07-08 | 2025-04-27 | 55 | 79 |  |  |  |  | TRUE | TRUE | 0 | 0 | 0.62224 | 0.29229 | 14
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 65
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 66
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 67
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 68
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 69
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 70
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 71
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 72
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 73
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 74
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 75
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 76
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 77
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 78
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 79
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 80
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 81
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 82
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 83
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 84
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 85
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 86
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 87
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 88
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 89
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 90
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 91
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 92
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 93
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 94
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 95
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 96
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 97
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 98
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 99
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 100
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 101
[18 empty] | TRUE | TRUE | 0 | 0 | 0 | 0 | 102

## Assessment summary (New) (hidden)
| Select Season | Summer |  | Season start | 2025-04-01 | Days in season | 183
| Date of assessment: | 2025-11-10 |  | Season end | 2025-09-30 | SAC Area (km2) | 27028
Projected disturbance levels - worst case scenario
|  | Projected maximum daily disturbance (% of the SAC disturbed) | 0% | Projected seasonal disturbance (Absolute worst case scenario) | 0%
|  | Number of days with >20% disturbance | 0 | Projected seasonal disturbance (Realistic worst case scenario) | 0%
These summary figures are based on a worst case scenario, and further management measures will be employed to ensure that there is no AEOI. Please see Desk Note for guidance on how these figures have been calculated.
The following projects were included in the in-combination assesssment -
Tracker ID | Project name | Activity Type | Proposed Start Date | Proposed End Date | Proposed days | Impact on SAC (km2) | Impact on SAC (%) | Contribution to seasonal disturbance (absolute worst case) | Contribution to seasonal disturbance (realistic worst case)
#REF!
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
| Norfolk Vanguard West - UXO Clearance (HO) | UXO High Order | 2026-04-01 | 2025-07-30 | 1 | 0 | 0% | 0% | 0%
Formulas:
Proposed Start Date = IFERROR(XLOOKUP([Tracker ID],Table13[TrackerID],Table13[Start Date]),"")
Proposed End Date = IFERROR(XLOOKUP([Tracker ID],Table13[TrackerID],Table13[End Date]),"")