TERMS OF REFERENCE / Study Title: Mapping and Evaluating UK–Southern Africa Higher Education Research Partnerships: Evidence for Strategic Engagement

1. BACKGROUND

1.1 About the Evidence Fund
The Foreign, Commonwealth & Development Office (FCDO) wants accessible high-quality research, evaluation and evidence products which target policy, country-specific and regional priorities and are available for use by FCDO and the international development sector. FCDO’s Research and Evidence Directorate (RED) has as its mission to develop and deliver new technologies and innovations that can help solve development challenges, test high potential interventions, and support the delivery of His Majesty’s Government (HMG) objectives. The Evidence Fund is a co-ordinated effort to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub-contracted Research Pool providers, where relevant, and ​​​​manage research and evaluation contracting.
1.2 Details on the Research Context
FCDO’s priorities emphasise strengthening the UK’s global influence, promoting science and technology (S&T) partnerships, and supporting sustainable development through modern, mutually beneficial partnerships.
Mapping and assessing UK-Southern Africa university partnerships will help the UK Government to identify and champion impactful collaborations that foster inclusive growth, enhance research and innovation capacity, and amplify UK influence in the region. The research will support British High Commissions and Embassies across Southern Africa to target support and advocacy towards initiatives that deliver mutual benefit, development impact, and diplomatic value.
This work builds on recent academic partnership mapping conducted by the UK’s Science and Technology Network (STN) in Africa. The study will address the need for more systematic qualitative and quantitative evidence and is aligned with UK country business plans across the Southern African region which aim to strengthen equitable science, research, innovation and technology partnerships that address shared challenges.
The findings will inform FCDO policy, funding, and diplomatic engagement, ensuring future partnerships are equitable, impactful, and closely aligned with UK and Southern African priorities. This will help to strengthen the UK’s global leadership in research and innovation.
2. KEY EVIDENCE GAPS

There is currently limited understanding of higher education partnerships between the UK and Southern African universities due to challenges in data availability, outside of what is funded by Official Development Assistance (ODA) and available on MODARI. Without comprehensive mapping and analysis, His Majesty’s Government’s (HMG’s) efforts and engagements in this area risk being misaligned with local priorities, missing opportunities for impactful collaboration, and failing to address barriers to equitable partnership. This research will address critical evidence gaps by systematically mapping the landscape of UK–Southern Africa university partnerships, assessing effectiveness, value, and sustainability of these partnerships, and identifying lessons learned and future opportunities. The findings will support HMG’s strategic planning, policy development, and engagement with key stakeholders, ensuring that future partnerships are coherent, equitable, and aligned with both UK and Southern African objectives.
Two recent UK led consultations (carried out in July/August 2025) provide some evidence about the state of university partnerships between the UK and Africa (including the focus countries):
- The Africa Approach Consultation led by FCDO and DSIT, reached out to UK universities and research institutions such as UK Research and Innovation, Royal Society, etc. to share insights on how UK and African universities can work together for mutual benefit, including sharing views on key barriers and challenges to overcome. A total of 13 UK universities responded to the consultation.
- The UK-Africa University Partnerships Survey led by STN Africa gathered data on existing UK-Africa university partnerships, sharing with contacts in UK universities in UUKi’s Africa and Middle East network, with responses received from 21 UK universities.

The data from these consultations will be made available to the successful Supplier, however these efforts have led to fragmented and incomplete datasets from UK universities. In addition, there is little evidence collected directly from Southern African institutions themselves. As the UK shifts towards a modern development partnership with reduced ODA, there is a need and significant demand from British High Commissions and Embassies across the region for robust evidence to identify, map and inform a strategic, mutually beneficial approach to university partnerships that delivers mutual growth and development impact.
Several other studies have been conducted, including The British Council’s Bridging the Gap: Enabling Effective UK–Africa University Partnerships (2015) which provides a useful typology of partnership models and the different funding schemes offered by diverse UK bodies. It highlights the importance of mutual benefit, institutional commitment, and responsiveness to local need, and notes that while many partnerships exist, there is limited systematic mapping of their scope, value, sectoral focus, and duration as well as a lack of research into which factors are most critical for making these partnerships effective. The Association of Commonwealth University (ACU) has also published a study on Africa-UK Research Partnerships for Development (2021) which sets out recommendations for enabling sustained, equitable, and impactful partnerships, and calls for better evidence on the outcomes and value of such collaborations.
3. OBJECTIVES AND SCOPE OF WORK

3.1. Objectives
Research objectives:
- Map the current landscape of UK–Southern Africa university partnerships, with a deep dive on South Africa and Zambia.
- Identify the challenges to equitable partnerships for Historically Disadvantaged Institutions (HDI) in South Africa and provide recommendation for UK partners (British High Commissions and Embassies, UK universities, UUKi and other relevant groups) to address these.
- Assess the effectiveness, value, and sustainability[1] of these partnerships, including their contributions to economic growth, skills development, and bilateral collaboration.
  [1] Definitions of effectiveness (do they achieve stated research and partnership goals), value (what impact do partnerships have/achieve) and sustainability (are they one-off or enduring, long term reciprocal relationships) to be agreed with the successful Supplier and the FCDO project team through inception discussions. We would welcome Suppliers indicating in their proposals how these could be defined and measured.
- Identify lessons learned, gaps, and opportunities to inform future HMG engagement and policy. This could include drawing on documented experience internationally, where appropriate.
- Engage key FCDO and partner country stakeholders to support strategic planning and alignment with British High Commissions and Embassies and country business plans where available.
- Deliver actionable recommendations and tools (report, database, policy brief, presentation, infographics) to inform a more coherent and impactful approach to UK higher education partnerships in Southern Africa.
3.2 Scope
The phased research will be conducted over a four-month (January to April 2026) period, commencing upon contract award. Key milestones include inception (Month 1), data collection and analysis (Months 2–3), validation, stakeholder engagement and final reporting and dissemination (Month 4).
Phase 1: Inception
The Supplier will work with FCDO’s Southern African Research and Innovation Hub (SARIH) and Africa STN to refine the research objectives, methodology, and stakeholder lists. The inception meeting will involve a review of the ToR, agree on the final objectives of the study (including its intended use), the proposed approach and methodology, consider the research questions and parameters, roles and responsibilities, any risks to delivery especially in-country data collection, the timeline, and deliverables, as well as starting to gather a list of key informants for consultation.
During this phase, the team will produce an inception report (no more than 10 pages) which will include:
- Research questions and parameters that will be prioritised.
- Existing datasets, reports and sources of information which will be identified for the desk-based analysis.
- A list of key stakeholders to be interviewed during the fieldwork phase including academic institutions in UK, Zambia and South Africa, funding agencies, government officials, development partners, and other relevant stakeholders.
- The proposed methodology for research, including details of how the approach will be adaptive and respond to changes, and ensuring this is relevant to the needs of government, industry, academia and investors.
- A detailed work plan for conducting the remainder of the study, including details of data collection tools and stakeholder engagement strategy.
Phase 2: Research and Analysis
The following will be informed and refined following the inception period.
- Desk-Based Analysis: Review existing datasets, literature, and reports to map current UK–Southern Africa university partnerships, focusing on types, thematic areas, and geographic distribution.
- Primary Research: Conduct semi-structured interviews, focus groups, and online surveys with stakeholders from UK, South African, and Zambian universities, government agencies, industry partners, and development organisations. Select case studies will provide in-depth insights into successful and sustainable partnership models.
- Stakeholder Consultation: Engage a wide range of stakeholders to validate findings. This will include workshops and roundtable discussions in South Africa and Zambia focusing on hearing from our partners in-country.
Phase 3: Validation and dissemination
The research will deliver:
- A comprehensive report mapping UK–Southern Africa higher education partnerships.
- A searchable database of partnership models and stakeholders (to complement the work of FCDO’s East Africa Research and Innovation Hub (EARIH).
- A policy brief with strategic recommendations for HMG, funding bodies such as UKRI, UK universities and others that might be valuable (e.g. recommendations for Southern African universities when engaging with UK universities).
- Presentation materials and infographics for dissemination.
These outputs will provide actionable evidence to inform HMG’s future engagement, support strategic planning for British High Commissions and Embassies in Southern Africa, and foster more equitable, impactful partnerships. The findings will address critical evidence gaps, enabling HMG and partners to align efforts with local priorities, maximise mutual benefits, and proactively address barriers and risks. The research will contribute to a more coherent and strategic approach to UK–Southern Africa higher education collaboration, supporting economic growth, skills development, and bilateral relations.
Outputs will be shared with FCDO, British High Commissions and Embassies across Southern Africa, Department of Science, Innovation and Technology (DSIT), UK Research and Innovation (UKRI), other UK research funding bodies, UK universities, as well as partner country research bodies and institutions. Findings will be disseminated via targeted communications to maximise uptake and impact.
3.3 Research/Evaluation Questions
These will be discussed/refined in the inception phase, but are likely to include:
1. What are the prevailing models and structures of UK–Southern Africa academic research partnerships?
2. What are the key enablers and barriers to effective and equitable collaboration?
3. Are additional considerations required for HDI’s?
4. How do these partnerships contribute to capacity building, knowledge exchange, and policy influence in Southern Africa?
5. To what extent do current partnerships align with UK and Southern African development priorities?
6. What lessons from existing partnerships can inform a more strategic UK approach?
7. How do local partnerships, academic networks, and the specific contexts of South Africa and Zambia, influence the outcomes and impact of UK–Southern Africa higher education collaborations?
8. What lessons from previous UK–Southern Africa university partnerships can inform the development of new partnerships and programmes that promote equitable and sustainable collaboration?
9. How can effective partnership models and approaches be integrated into future programme design, and what is their potential for adaptation and replication across the wider Southern Africa region?
10. What new opportunities or models could deepen collaboration, especially in priority areas such as science, technology, and innovation, linked to UK science and technology priorities (including those documented in the Science and Technology Framework (2025)?
11. What are the major gaps and risks, and how can HMG proactively address these to strengthen future partnerships?
3.4 Research/Evaluation Methodology
This will be a mixed methodology study, incorporating quantitative and qualitative approaches. This includes desk study of the current state of UK-Southern Africa higher education partnerships, key informant interviews and focus groups with local stakeholders, with a focus in South Africa and Zambia.
3.5 Theory of Change
By systematically mapping and evaluating UK–Southern Africa higher education research partnerships, the project will generate robust, actionable evidence that directly informs policy, programming, and diplomatic engagement. This evidence will enable FCDO and its partners to design and support more equitable, impactful, and sustainable collaborations between UK and Southern African universities.
At its core, the theory of change assumes that current gaps in knowledge—particularly around the effectiveness, value, and sustainability of partnerships—limit the ability of both UK and Southern African stakeholders to align their efforts with local priorities and maximise mutual benefit. By addressing these evidence gaps through a mixed-methods approach (combining desk-based analysis, stakeholder interviews, and validation workshops), the research will identify lessons learned, best practices, and opportunities for improvement. This, in turn, will empower decision-makers to refine strategies, allocate resources more effectively, and foster partnerships that contribute to mutual priorities including economic growth.
The anticipated outputs are designed to maximise uptake and impact, supporting a more coherent and strategic approach to higher education collaboration across the region.
3.6 Required Skills
The core team will have the requisite technical and contextual experience in the collection, interpretation, synthesis, and wide dissemination of research findings and recommendations. The team should include experts on higher education and research collaboration in both the UK and Southern Africa.
Preference will be given to bidders with established networks and contacts within the Southern Africa region, enabling effective evidence gathering through existing relationships and proven experience in delivering similar research in the region, particularly given the short timeframes available for this study. Research teams that bring together both international and local expertise and meaningfully include researchers from the focus countries (e.g. as principal or co-investigators), will be prioritised. Applications are especially welcomed from consortia that unite institutions in the UK and Africa.
Thematic and Contextual Expertise
- Internationally recognised experience and expertise in conducting similar research studies in the field of higher education in both UK and Southern Africa.
- Proven experience in political economy analysis, international development or geopolitics in Southern Africa.
- Familiarity with the UK and Southern Africa’s higher education landscape including the key actors, sectoral policies and policy frameworks.
- Demonstrated experience conducting research in Southern Africa, and strong academic and policy networks in each of the focus countries.
- Knowledge of soft power dynamics, public diplomacy and influence mechanisms in development cooperation.
Research Design and Delivery
- Strong capabilities in mixed method research and demonstrated experience in conducting similar research projects.
- Methodological expertise to carry out the study including data analysis, mapping and matrix development, qualitative research, and political economy analysis.
- Strong collaborative and facilitation skills with demonstrable expertise in developing and maintaining positive working relationships with all research stakeholders.
Ability to work ethically and sensitively in politically complex environments with a deep understanding of local context and political sensitivities.
Communication
- Proven ability to synthesise complex evidence into actionable policy recommendations.
- Proven ability to produce technical reports and policy briefs, meeting international standards within short timeframes.
- Experience preparing and presenting matrices and mappings, strategic briefings, and short policy products.
The proposed team composition should bring together
- A lead researcher or team leader with at 10 years' experience in education research, political economy analysis or international development.
- A communication and research uptake specialist to ensure findings are accessible and engaging for diverse audiences (e.g., policy briefs, infographics, digital content, stakeholder events).
4. PROJECT MANAGEMENT ARRANGEMENTS

The Supplier will lead the research design, data collection, analysis, and reporting. SARIH, STN and FCDO advisers in Southern African countries will provide oversight and strategic guidance. Regular coordination meetings will be held to ensure alignment.
The Supplier will be responsible for:
- Designing and delivering all research activities
- Producing interim and final outputs for review by FCDO
- Participating in validation workshops and dissemination events
The FCDO will:
- Chair a study steering committee which will review and sign off all deliverables. Deliverables must be shared a minimum of 5 working days in advance of comments. Deliverable will not be considered final until FCDO confirm all comments have been addressed.
- Hold monthly update meetings to review progress against the agreed workplan. Additional meetings will be held to discuss ad hoc matters or milestone deliverables.
5. ADMINISTRATIVE ARRANGEMENT

The study would be supported through The Evidence Fund, an FCDO programme intended to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2023, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects and conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant.
FCDO is the sole contracting authority for all projects funded through the Evidence Fund. FCDO holds full responsibility for issuing contracts and managing all contract and project management activities throughout the lifecycle of each project. The Fund Manager’s role is limited to pre-contracting activities and does not extend to contract execution or post-award management.
6. TIMEFRAME, EXPECTED DELIVERABLES, AND OVERALL BUDGET

The study should be completed in a maximum period of 4 months, starting January 2026. The budget for the study should not exceed £50,000 (excluding UK VAT and inclusive of all other applicable taxes).
The deliverables and timelines/milestones expected of the Supplier are as follows:
Milestone	Description	Budget Payment (% of Overall Budget)	Delivery Timeline	Acceptance Criteria	Page Limit/Format
1. Inception Report	Submission of a detailed inception report, including refined research questions, methodology, stakeholder list, work plan, and risk assessment.	20%	End of Month 1	Report addresses all ToR requirements, is clear, actionable, and approved by FCDO steering committee.	Max 10 pages (Word/PDF)
2. Draft Report	Submission of a comprehensive draft report mapping UK–Southern Africa higher education partnerships, including initial findings and analysis.	30%	End of Month 2	Draft report meets scope, includes desk-based and primary research, and is ready for stakeholder review.	Max 40 pages (Word/PDF)
3. Validation Workshop	Organisation and delivery of a validation workshop with key stakeholders to test findings, gather feedback, and build consensus.	20%	Month 3	Workshop delivered, feedback documented, and recommendations for report revision provided.	Workshop summary (5 pages)
4. Final Report & Database	Submission of final report, searchable database of partnership models, policy brief, presentation materials, and infographics.	20%	Mid Month 4	All outputs meet ToR requirements, incorporate stakeholder feedback, and are approved by FCDO.	Final report (max 40 pages), database, policy brief (max 4 pages), infographics, presentation slides
5. Dissemination	Delivery of dissemination activities, including targeted communications to FCDO, DSIT, UKRI, regional partners, and publication of outputs.	10%	End of Month 4	Dissemination plan executed, outputs shared with all relevant stakeholders, and uptake tracked.	Dissemination summary (3 pages)

7. BIDDING PROCESS

The tender documents must be sent to the e-mail address of the Evidence Fund Manager (uk_evidence_fund_administration@pwc.com) by 9 January 2026 (23:59 GMT). Clarification Questions (CQs) (if any) can be submitted by 5 January 2026 (23:59 GMT) to the same e-mail address as mentioned above. CQs will be responded to by 6 January 2026 (23:59 GMT).
The instructions for submitting the tender and details on scoring methodology and evaluation criteria are detailed in ITT Volume 1. ITT Volume 3 contains the application forms for submitting the organisation details and technical tender. ITT Volume 4 provides the Pro Formas for the commercial proposal. Any Contract awarded will be based Volume 5. ITT Volume 6 contains the Conflict of Interest. Volume 7 contains the Letter and Declaration to accompany tenders.
8. QUALITY ASSURANCE MECHANISMS

Please indicate by ticking the appropriate box/s below the level of Peer Review/Quality Assurance required for the project. This includes peer review, data quality assurance, and feedback from the FCDO.
Peer review/Quality Assurance Required
Peer review/ quality assurance completed in-house by FCDO	X
Peer review/ quality assurance arranged by the research provider as part of their contract	X
Independent peer review independently carried out, through a contract with the Fund Manager
Further EqUALS review for all evaluation products

9. COMPETENCIES

It is expected that the core team delivering this work will have the requisite technical and contextual experience in the collation, interpretation, synthesis, and communication of the research findings and recommendations.
10. SUBMISSIONS

The Supplier is required to submit all outputs in accordance with the expectations and page limits set out in sections 3, 4 and 5 above.
11. MANAGEMENT ARRANGEMENTS

- The Supplier will design and manage this research study, including drawing together the findings for reporting.
- This project will be administered by FDCO’s SARIH lead adviser.
- The Supplier will quality-assure all outputs before submission to the SARIH lead adviser. The Supplier will be required to comply with FCDO reporting requirements. The Supplier will be responsible for alerting the SARIH lead adviser as early as possible of any emerging issues and risks, to ensure that the project is staying on track.
- All deliverables will need to be reviewed and approved by the FCDO technical steering group; however, the Supplier is encouraged to embed their own internal mechanisms for quality assurance.
- The Supplier will be required to review and outline how they plan to manage any potential conflicts of interest identified during proposal development.
- The Supplier will be required to attend several meetings during all phases of the work, comprising largely of virtual meetings.
12. DUTY OF CARE ARRANGEMENTS

The Supplier should set out duty of care arrangements for any country visits or field-based activities.
13. ETHICAL CONSIDERATIONS, DATA PROTECTION, AND SAFEGUARDING

The Supplier must ensure that all research activities are designed and conducted in a manner that actively promotes GESI. Ethical protocols should address the risks and barriers faced by women and marginalised groups and ensure that their voices are meaningfully included in all stages of the research process.
Suppliers to refer to and ensure compliance with FCDO:
- Safeguarding Guidelines: Safeguarding and protection from sexual exploitation and abuse and harassment (SEAH) in the aid sector - GOV.UK
- UK GDPR Guidance: UK GDPR guidance and resources | ICO
14. GENERAL DATA PROTECTION REGULATIONS (GDPR)

Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Annex 1: Guidance on Communication and Research Uptake Strategy.
15. RISK MANAGEMENT

Successful supplier will be expected to include a risk and mitigation assessment as part of the inception process. The recommendations below are indicative and not exhaustive.
Risk Management Recommendations:
1. Stakeholder Engagement Risks. Mitigation: Suppliers with established networks in Southern Africa will be prioritised to facilitate access to key informants and institutions. Develop a clear stakeholder engagement plan early in the inception phase, including contingency contacts.
2. Data Collection Risks. Mitigation: Use mixed methods (desk review, online surveys, virtual interviews) to reduce exclusive reliance on in-person fieldwork. Ensure ethical clearance and data protection compliance in all countries. Build flexibility into the workplan to adapt to local disruptions.
3. Timeframe Risks. Mitigation: Set clear internal deadlines for each deliverable and monitor progress through regular project management meetings. Allocate additional resources if delays occur and maintain close communication with FCDO for rapid issue resolution.
4. Quality Assurance Risks. Mitigation: Implement peer review and internal quality checks for all outputs. Schedule interim reviews with FCDO and the steering committee to ensure deliverables meet expectations and allow for early identification of issues.
5. Political and Contextual Risks. Mitigation: Include team members with local contextual expertise to navigate political sensitivities. Monitor local developments and adjust research activities as needed to avoid reputational or operational risks.
6. Safeguarding and Ethical Risks. Mitigation: Adhere strictly to FCDO safeguarding guidelines and UK GDPR requirements. Ensure all team members are familiar with ethical research practices and safeguarding and establish clear reporting channels for any concerns.
7. Conflicts of Interest. Mitigation: Require all team members to declare any potential conflicts of interest at project outset and update declarations as needed. Develop a transparent process for managing and reporting conflicts.
8. Dissemination and Uptake Risks. Mitigation: Develop a robust communications and research uptake strategy, tailored to different audiences. Track dissemination and uptake and be prepared to adjust methods if engagement is lower than expected.
Annex 1: Guidance on Communication and Research Uptake Strategy
Stakeholder Mapping and Research Uptake Strategy
	Key communications and research uptake considerations
Audience mapping	Which organisations are the main intended audiences for the research? Who are the key decision-makers in the policy area and are they involved and aware of the research (and how are they involved in the research design and intent)? Are there other actors who may use findings or are involved in this policy area? / Within FCDO – which teams and departments are involved?
Knowledge requirements of stakeholders	What are the evidence gaps that actors are interested in? Are there key statistics or data that can define the research? What new evidence does the research offer to both strategic planning and informing programming?
Decisions to be influenced	What are the key programming decisions that the research will influence – both for FCDO policy teams and country offices? Will the research support decision-making among other actors? E.g., multilateral, and bilateral donors, non-government organisations, regional governments? What decisions are those?
What are the outputs?	Largely defined by the ToR, but what outputs will be produced? I.e., will there be supporting infographics, summary briefs, or single case studies in order to land the research more effectively/efficiently with particular audiences? How do these map to particular stakeholders?
How will outputs be communicated?	How will various audiences be kept abreast or informed about the research? Will different audiences require different communications? What will be the balance of different dissemination techniques: i.e., seminars, emails, social media, meetings, slide decks, use of the internet or published documentation?
Relevance of research products	The communications plan (and research products) should be iterative and reflect research needs from all stakeholders. Considering responses to the points outlined above, how will the research be designed, produced, and disseminated to meet these needs?
How will research impact be measured?	What methods and indicators can be used to measure or assess how useful the research is? I.e., to what extent has it been used and by which audiences, what are the outcomes of the research, and what impact has it had on policy making and programming?