## Noisy Activities
Southern North Sea (SNS) Special Area Of Conservation (SAC) Noise Tracker |  | Daily Threshold: Harbour porpoise not excluded from more than 20% of the SAC on any day. |  |  |  | Winter 25/26 | 2025-10-01 | Summer 26 | 2026-04-01 |  | Summer Area (km2) | 27028 | Summer Days | 183
|  | Seasonal Threshold: Harbour porpoise not excluded for more than 10% of the SAC per day, on average over the season. |  |  |  |  | 2026-03-31 |  | 2026-09-30 |  | Winter Area (km2) | 12696 | Winter Days | 182
Project/Activity Name | Applicant | Regulator | Activity Type | Which seasonal area of the SAC does this activity impact? | Quad/Block (OPRED only) | Case Reference | Wildlife Licence Reference | Case Status | Tracker Last Updated | Start Date | End Date | Duration of Activity Impacting SAC (days) | Area Overlap with SAC (km2) | Magnitude (OPRED only) | Abatement/Mitigation (MMO only) | Any Other Comments | Include in assessment? | Include in Winter Calendar | Include in Summer Calendar | % of Winter SAC Impacted | % of Summer SAC Impacted | TrackerID
Dogger Bank B -Monopiling (Unabated) | SSE Renewables | MMO | Piling | Summer |  | DCO/2016/00024 |  | Completed | 2025-07-15 | 2025-04-17 | 2025-04-18 | 2 | 2873 |  |  |  | No | FALSE | TRUE | 0 | 10.63 | 6
Dogger Bank C - Monopiling (Unabated) | SSE Renewables | MMO | Piling | Summer |  | DCO/2016/00018 |  | Completed | 2025-10-23 | 2025-08-03 | 2025-08-16 | 3 | 150.7 |  |  |  | No | FALSE | TRUE | 0 | 0.56 | 7
Dogger Bank D - Geophysical Survey 1 | SSE Renewables | MMO | Geophysical Survey | Summer |  | DCO/2023/00001 |  | Completed | 2025-07-15 | 2025-05-10 | 2025-05-12 | 3 | 0.2 |  |  |  | No | FALSE | TRUE | 0 | 0 | 9
EA3 - Pin Piling | Scottish Power Renewables | MMO | Pin Piling | Both |  | DCO/2018/00001 |  | Completed | 2025-09-09 | 2025-08-11 | 2025-08-11 | 1 | 706 |  |  |  | No | FALSE | TRUE | 0 | 2.61 | 12
EA3 - UXO Clearance (LO) | Scottish Power Renewables | MMO | UXO Low Order | Both |  | MLA/2023/00532/3 |  | Completed | 2025-07-15 | 2024-07-08 | 2025-04-27 | 55 | 79 |  |  |  | No | TRUE | TRUE | 0.62 | 0.29 | 14
NEP - EPCI 2 Geophysical Infield | BP | OPRED | Geophysical Survey | Summer | Various | GS/1866 |  | Completed | 2025-07-29 | 2025-04-15 | 2025-05-07 | 20 | 115 | N/A |  | Sub-Bottom Profiler, Mu;tibeam Echosounder, Sidescan Sonar, Magnetometer | No | FALSE | TRUE | 0 | 0.43 | 16
NEP - EPCI 3 Geophysical Offshore Cable | BP | OPRED | Geophysical Survey | Summer | Various | GS/1871 |  | Completed | 2025-07-29 | 2025-04-22 | 2025-05-09 | 12 | 121 | N/A |  | Sub-Bottom Profiler, Multibeam, Sidecan Sonar, Magnetometer. Potentially two full route runs (148km) in 48 hours. | No | FALSE | TRUE | 0 | 0.45 | 17
Hornsea Three - UXO Clearance (Transmission) (LO) | Orsted | MMO | UXO Low Order | Summer |  | MLA/2024/00088/1 |  | Completed | 2025-07-15 | 2024-10-01 | 2025-04-15 | 24 | 79 |  |  |  | No | FALSE | TRUE | 0 | 0.29 | 21
Hornsea Three - UXO Clearance (Generation) (LO) | Orsted | MMO | UXO Low Order | Summer |  | MLA/2024/00675 |  | Completed | 2025-09-29 | 2025-08-07 | 2025-09-07 | 27 | 79 |  |  |  | No | FALSE | TRUE | 0 | 0.29 | 22
Hornsea Three - UXO Clearance (Transmission) (HO) | Orsted | MMO | UXO High Order | Summer |  | MLA/2024/00088/1 |  | Completed | 2025-07-15 | 2024-11-07 | 2024-11-07 | 1 | 707 |  | BBC | Only X1 HO detonation was required as part of this campagin. | No | FALSE | TRUE | 0 | 2.62 | 23
Pegasus West - Pipeline and Site Geophysical Survey (Sub-Bottom Profiler) | INEOS | OPRED | Geophysical Survey |  |  | GS/1886/0 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-05-26 | 36 | 471 |  |  | Sub-Bottom Profiler | No | FALSE | TRUE | 0 | 1.74 | 27
NEP - Phase 1 2DHR | BP | OPRED | Seismic Survey | Summer | 42/25, 42/30, 43/21, 43/26 | GS/1853 |  | Completed | 2025-07-29 | 2025-04-01 | 2025-04-09 | 8 | 798 | 160 cu in |  | 2D High-Resolution Seismic | No | FALSE | TRUE | 0 | 2.95 | 28
Sofia - Monopiling (Abated) | Sofia Offshore Wind Farm Ltd | MMO | Piling Abated | Summer |  | DCO/2013/00011 |  | Completed | 2025-07-15 | 2025-04-02 | 2025-06-15 | 23 | 871.58 |  | BBC |  | No | FALSE | TRUE | 0 | 3.22 | 31
Sofia - Monopiling (Unabated) | Sofia Offshore Wind Farm Ltd | MMO | Piling | Summer |  | DCO/2013/00011 |  | Completed | 2025-07-15 | 2025-04-30 | 2025-07-13 | 4 | 1928.38 |  |  |  | No | FALSE | TRUE | 0 | 7.13 | 32
Sizewell C - Nearshore (Subtidal) UXO Investigations | Sizewell C Ltd | MMO | Geophysical Survey | Winter |  | MLA/2024/00601 |  | Completed | 2025-07-15 | 2025-03-25 | 2025-05-17 | 81 | 434 |  |  | Sofia have confirmed that no geophysical surveys will be conducted in 2025. | No | TRUE | FALSE | 3.42 | 0 | 40
Cyngus - Conductor Driving of the 44/12a-AFF Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | 44/12 | DR/2500/5 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-04-24 | 1 | 706 | 90 KJ |  | Conductor driving with 15km EDR | No | FALSE | TRUE | 0 | 2.61 | 45
Cyngus - Conductor Driving of the 44/12a-AJ Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | 44/12 | DR/2528/0 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-04-24 | 1 | 706 | 90 KJ |  | Conductor driving with 15km EDR | No | FALSE | TRUE | 0 | 2.61 | 46
Cyngus - Conductor Driving of the 44/12a-Slot 1 Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | 44/12 | DR/2532/0 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-04-24 | 1 | 706 | 90 KJ |  | Conductor driving with 15km EDR | No | FALSE | TRUE | 0 | 2.61 | 47
Cyngus - Conductor Driving of the 44/12a-Slot 6 Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | 44/12 | DR/2533/0 |  | Completed | 2025-07-29 | 2025-04-21 | 2025-04-24 | 1 | 706 | 90 KJ |  | Conductor driving with 15km EDR | No | FALSE | TRUE | 0 | 2.61 | 48
NEP - EPCI 1 Geophysical Pipeline | BP | OPRED | Geophysical Survey | Both | Various | GS/1913 |  | Approved | 2025-07-29 | 2025-07-28 | 2025-10-01 | 18 | 99 | N/A |  | Geophysical Unexploded Ordnance Survey utilising Sub-Bottom Profiler, Sidescan Sonar, Multibeam Echo Sounder and Magnetometer | No | TRUE | TRUE | 0.78 | 0.37 | 49
Expansion Seismic Part 1 (CS007) (NEP Expansion Stores) | BP | OPRED | Seismic Survey | Summer | Various | GS/1867 |  | Approved | 2025-07-29 | 2025-08-01 | 2025-09-02 | 32 | 744 | 400 cu in |  | 3D Seismic Survey, Multibeam Echosounder, Acoustic Doppler Current Profiler | No | FALSE | TRUE | 0 | 2.75 | 51
Baker and Abbey Site Surveys (Sub-Bottom Profiler) | Petrogas | OPRED | Geophysical Survey | Both | Various | GS/1900/0 |  | Submitted | 2025-07-15 | 2025-07-01 | 2025-12-01 | 2 | 12 |  |  | Sub-Bottom Profiler Survey | No | TRUE | TRUE | 0.09 | 0.04 | 52
Sizewell C - Pin Piling | EDF Energy | MMO | Pin Piling | Winter |  | DCO/2013/00021 |  | Submitted | 2025-10-21 | 2025-11-01 | 2026-03-30 | 55 | 0.1 |  | Soft / slow start and marine mammal obervers | 55 piling days within a 180 day window | Yes | TRUE | FALSE | 0 | 0 | 53
Sizewell C - Pin Piling | EDF Energy | MMO | Pin Piling | Winter |  | DCO/2013/00021 |  | Submitted | 2025-10-21 | 2026-04-30 | 2027-02-28 | 30 | 0.1 |  | Soft / slow start and marine mammal obervers | 30 piling days within a 180 day window | Yes | TRUE | FALSE | 0 | 0 | 54
Hornsea Three - Pin Piling | Orsted | MMO | Pin Piling Abated | Summer |  | DCO/2016/00001 |  | Proposed | 2025-09-08 | 2026-03-02 | 2026-04-11 | 4 | 36.9 |  | Single bubble curtain | 4 piling days within a 41 day window | Yes | FALSE | TRUE | 0 | 0.14 | 55
Ithaca - Conductor Piling | Ithaca | OPRED | Conductor Piling | Summer |  |  |  | Proposed | 2025-09-08 | 2026-07-01 | 2026-09-30 | 3 | 706.9 |  | Soft start, marine mammal observer | Conductor piling | Yes | FALSE | TRUE | 0 | 2.62 | 56
Hoton Platform - New Well Conductor | Perenco | OPRED | Conductor Piling | Summer |  |  |  | Proposed | 2025-09-08 | 2026-03-01 | 2026-05-31 | 3 | 706 |  | None | Conductor piling | Yes | FALSE | TRUE | 0 | 2.61 | 57
Platypus | Perenco | OPRED | Geophysical Survey | Summer |  | GS/1976/0 |  | Approved | 2025-09-15 | 2025-09-15 | 2025-09-30 | 15 | 275.2 |  |  |  | No | FALSE | TRUE | 0 | 1.02 | 61
Harbour Energy - Geophysical Survey |  | OPRED | Geophysical Survey | Winter |  |  |  | Proposed | 2025-10-21 | 2026-01-01 | 2026-06-30 |  |  |  |  | Awaiting further information from the developer. | Yes | TRUE | FALSE | 0 | 0 | 62
East Anglia Two - UXO Clearance (LO) | Scottish Power Renewables | MMO | UXO Low Order | Both |  | DCO/2022/00005 |  | Proposed | 2025-11-25 | 2026-05-01 | 2026-07-31 | 80 | 0 |  | N/A | With the new EDRs, this activity no longer overlaps with the SNS SAC. Currently awaiting confirmation from case teams whether or not a SIP is required. If a SIP is not required, ask Becca if this activity should be removed from the tracker. | No | FALSE | TRUE | 0 | 0 | 63
East Anglia Two - UXO Clearance (HO) | Scottish Power Renewables | MMO | UXO High Order | Both |  | DC0/2022/00005 |  | Proposed | 2025-11-25 | 2026-05-01 | 2026-07-31 | 3 | 0 |  | Bubble Curtain | With the new EDRs, this activity no longer overlaps with the SNS SAC. Currently awaiting confirmation from case teams whether or not a SIP is required. If a SIP is not required, ask Becca if this activity should be removed from the tracker. | No | FALSE | TRUE | 0 | 0 | 64
NEP Phase 1 UXO Clearance (LO) | BP | OPRED | UXO Low Order | Summer |  |  |  |  | 2025-11-05 | 2026-04-01 | 2026-09-30 | 10 | 100 |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | Main UXO clearance planned fro winter months outside the SAC. Contingency for 'low order' clearance of up to 10 chance encountered UXO during construction | Yes | FALSE | TRUE | 0 | 0.37 | 65
NEP Phase 1 UXO Clearance (HO Contingency) | BP | OPRED | UXO High Order | Summer |  |  |  |  | 2025-11-05 | 2026-04-01 | 2026-09-30 | 3 | 1950 |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | Main UXO clearance planned fro winter months outside the SAC. Contingency for 'high order' clearance of up to 3 chance encountered UXO during construction | Yes | FALSE | TRUE | 0 | 7.21 | 66
NEP Expansion Pipeline Routing Geophysical Survey | BP | OPRED | Geophysical Survey | Summer |  |  |  |  | 2025-11-05 | 2026-05-01 | 2026-06-30 | 5 | 650 |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines |  | Yes | FALSE | TRUE | 0 | 2.4 | 67
NEP Phase 1 Pin Piling Monitoring Equipment | BP | OPRED | Pin Piling | Summer |  |  |  |  | 2025-11-05 | 2026-07-01 | 2026-08-31 | 6 | 700 |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | Instalation methodology tbc. Pin piling worst case assumption | Yes | FALSE | TRUE | 0 | 2.59 | 68
NEP Expansion (C5025) Seismic Survey | BP | OPRED | Seismic Survey | Summer |  |  |  |  | 2025-11-05 | 2026-04-01 | 2026-06-30 | 18 | 800 |  | 400 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines |  | Yes | FALSE | TRUE | 0 | 2.96 | 69
NEP Phase 1 Development Wells Vertical Seismic Profiling | BP | OPRED | Seismic Survey | Summer |  |  |  |  | 2025-11-05 | 2026-04-01 | 2026-09-30 | 3 | 450 |  | 450 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines |  | Yes | FALSE | TRUE | 0 | 1.66 | 70
NEP Expansion Appraisal Well Vertical Seismic Profiling | BP | OPRED | Seismic Survey | Summer |  |  |  |  | 2025-11-05 | 2026-04-01 | 2026-06-30 | 2 | 800 |  | 400 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines |  | Yes | FALSE | TRUE | 0 | 2.96 | 71
2D High Resolution Shallow Siesmic Survey | Dana Petroleum | OPRED | Geophysical Survey | Summer |  |  |  | Proposed | 2025-11-18 | 2026-04-01 | 2026-05-30 | 4 |  |  |  |  | Yes | FALSE | TRUE | 0 | 0 | 72
Norfolk Vanguard West - UXO Clearance (HO) | RWE Renewables UK | MMO | UXO High Order | Summer |  | MLA/2025/00512 |  | Submitted | 2025-10-21 | 2026-04-01 | 2026-07-30 | 1 | 380.13 |  |  | Data has been provided with and without NAS. Without NAS the area overlap would be 938.31. | No | FALSE | TRUE | 0 | 1.41 | 73
East Anglia Three - Monopiling (Abated Scenario 1) | Scottish Power Renewables | MMO | Piling Abated | Both |  | DCO/2018/00001 |  | Approved | 2025-11-25 | 2025-05-21 | 2025-09-30 | 100 |  |  | MENCK Hammer | Worst case scenario - X2 piles per day. This is outlined in the SIP, but is logisitcially and operationally unlikely. | No | FALSE | TRUE | 0 | 0 | 74
Norfolk Vanguard West - UXO Clearance (HO) | RWE Renewables UK | MMO | UXO High Order | Summer |  | MLA/2025/00512 |  | Submitted | 2025-10-21 | 2026-04-01 | 2026-07-30 | 1 | 380.13 |  |  | Data has been provided with and without NAS. Without NAS the area overlap would be 938.31. | No | FALSE | TRUE | 0 | 1.41 | 75
Hornsea Three - Contingency UXO Clearance (Transmission & Generation) (LO) | Orsted | MMO | UXO Low Order | Summer |  | MLA/2025/00366 |  | Submitted | 2025-12-02 | 2025-12-01 | 2028-09-30 | 9 | 79 |  | MMMP ( MMObs, PAM, ADD's), 500m safety zone, Ntms, post-clearance MBES surveys | LO deflagration only. | Yes | FALSE | TRUE | 0 | 0.29

## Assessment summary (New) (hidden)
| Select Season | Summer |  | Season start | 2026-04-01 | Days in season | 183
| Date of assessment: | 2025-12-15 |  | Season end | 2026-09-30 | SAC Area (km2) | 27028
Projected disturbance levels - worst case scenario
|  | Projected maximum daily disturbance (% of the SAC disturbed) | 0% | Projected seasonal disturbance (Absolute worst case scenario) | 0%
|  | Number of days with >20% disturbance | 0 | Projected seasonal disturbance (Realistic worst case scenario) | 0%
These summary figures are based on a worst case scenario, and further management measures will be employed to ensure that there is no AEOI. Please see Desk Note for guidance on how these figures have been calculated.
The following projects were included in the in-combination assesssment -
Tracker ID | Project name | Activity Type | Proposed Start Date | Proposed End Date | Proposed days | Impact on SAC (km2) | Impact on SAC (%) | Contribution to seasonal disturbance (absolute worst case) | Contribution to seasonal disturbance (realistic worst case)
#REF!