## Cover
Building Safety Remediation Data Release, England: 30 September 2025
Back to Contents
Background
This publication provides data on 1) the remediation progress across MHCLG’s Building Safety Remediation portfolio, covering buildings in the ACM programme, Building Safety Fund, Cladding Safety Scheme, developer remediation contract and reported by registered providers of social housing, 2) Progress with remediation of high-rise (18 metres and over in height) residential buildings (including student accommodation and hotels) and publicly owned buildings with ACM cladding systems unlikely to meet Building Regulations in the ACM programme, 3) the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund, 4) progress with remediation of high-rise residential buildings with non-ACM cladding systems assessed as eligible for funding from the Building Safety Fund , 5) Progress with the applications for and remediation of medium-rise (11 – 18 metres in height) residential buildings in England and high-rise residential buildings outside of London with non-ACM cladding systems in the Cladding Safety Scheme, 6) progress of remediation of residential buildings 11 metres and over in height with life-safety defects under the developer remediation contract, 7) progress of remediation of residential buildings 11 metres and over in height with unsafe cladding reported by registered providers of social housing, 8) enforcement action taken by local authorities against 11m+ residential buildings with cladding defects under the Housing Act 2004.
Tables on the ACM programme, BSF, CSS, developer remediation contract and social housing surveys include buildings which can be in multiple schemes or data collections so counting across tables can result in double counting. Tab Combined_2 provides an overall summary of all remediation progress, without double counting.
Publication dates
The data tables in this spreadsheet were originally published on 23 October 2025.
The next publication is scheduled for 20 November 2025.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
We are committed to improving and broadening this data release further in the months ahead and would welcome feedback both on the content of this data release and what could be further done in the future.
BuildingSafetyData2@communities.gov.uk
NewsDesk@communities.gov.uk
Date published: 23 October 2025

## Table_of_Contents
Building Safety Remediation Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 30 September 2025
ACM_2	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 30 September 2025
ACM_3	Remediation status of buildings yet to complete ACM remediation by tenure, England, 30 September 2025
ACM_4	ACM remediation progress by local authority, England, 30 September 2025
ACM_5	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 30 September 2025
ACM_6	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 30 September 2025
ACM_7	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 30 September 2025
ACM_8	ACM remediation progress by sources of funding, England, 30 September 2025
ACM_9	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 30 September 2025
ACM_10	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 30 September 2025
ACM_11	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 30 September 2025
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 30 September 2025
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 30 September 2025
WWRF_3	Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 30 September 2025
BSF_1	Remediation status of eligible buildings within BSF by tenure, England, 30 September 2025
BSF_2	BSF remediation progress of eligible buildings by region, England, 30 September 2025
BSF_3	BSF number of eligible buildings with funding approved and expenditure amounts by tenure, England, 30 September 2025
BSF_4	BSF remediation progress of eligible buildings by local authority, England, 30 September 2025
BSF_5	Remediation status of eligible buildings within BSF, time series, England, 30 September 2025
Combined_1	Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 30 September 2025
Combined_2	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 30 September 2025
Combined_3	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 30 September 2025
Combined_4	Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 30 September 2025
Combined_5	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by tenure, 30 September 2025
Combined_6	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, time series, 30 September 2025
Combined_7	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by region, 30 September 2025
Combined_8	Remediation progress for unique buildings being remediated or mitigated as part of a government funded scheme, 11 metres and over in height, England, 30 September 2025
CSS_1	Application status of buildings within the CSS, England, 30 September 2025
CSS_2	CSS remediation progress by region, England, 30 September 2025
CSS_3	CSS remediation progress by height, England, 30 September 2025
CSS_4	CSS remediation progress by tenure, England, 30 September 2025
CSS_5	CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 30 September 2025
CSS_6	CSS remediation progress, time series, England, 30 September 2025
Social_1	Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 30 September 2025
Social_2	Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 June 2025
Social_3	Provider by provider breakdown of buildings, by assessment status, England, 30 June 2025
Social_4	Provider by provider breakdown of buildings, by remediation status, England, 30 June 2025
Social_5	Remediation status of buildings with cladding defects monitored under the social housing surveys, time series, England, 31 August 2025
Developer_1	Remediation status of buildings covered by the developer remediation contracts by height group, England, 30 September 2025
Developer_2	Estimated cost of buildings requiring works under the developer remediation contract by height, England, 30 September 2025
Developer_3	Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 July 2025
Developer_4	Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 July 2025
Developer_5	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 July 2025
Developer_6	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 July 2025
Developer_7	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 July 2025
Developer_8	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 July 2025
Developer_9	Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 July 2025
Developer_10	Remediation status of buildings requiring works under the developer remediation contract, time series, England, 30 September 2025
Developer_11	Estimated number of determinations, starts and completions made each quarter for buildings under the developer remediation contract, by height group, England, 31 July 2025
Developer_12	Developer by developer update against RAP Joint Plan targets, 31 July 2025
Enforcement_1	Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 19 September 2025
Enforcement_2	Building inspections conducted by local authorities, England, 19 September 2025
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 19 September 2025
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 19 September 2025
JIT_1	Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 30 September 2025
Estimated_1	Estimates of the number of residential buildings, containing dwellings, that have or had unsafe cladding requiring work, 11 metres and over in height, England, January 2025
Estimated_2	Estimates of the number of residential buildings, that have or had unsafe cladding requiring work, expected to be remediated or mitigated as part of a government remediation programme, 11 metres and over in height, England, January 2025
Estimated_3	Estimated proportion of buildings with unsafe cladding expected to be remediated or mitigated in a government remediation programme that are currently monitored in a government remediation programme, 30 September 2025
Estimated_4	Estimates of the number of residential buildings, that have or had unsafe cladding requiring remediation or mitigation work, expected to be remediated or mitigated as part of a government funded scheme, based on January 2025 eligibility criteria, 11 metres and over in height, England, January 2025

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in table ACM_1 and ACM_2.	ACM_3
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_4, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to complete remediation works on-site	ACM_7
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_8
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period. 12 private sector buildings are receving government funding from the Building Safety Fund or Cladding Safety Scheme, so do not appear in the totals in table ACM_9, but do in ACM_8.	ACM_8, ACM_9
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_10
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_10
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_10
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_10
[note 10]	Total figures may not sum due to rounding.	ACM_11, WWRF_1, WWRF_2, WWRF_3, BSF_1, BSF_2, BSF_3, BSF_5, Combined_4, Estimated_1, Estimated_2
[note 11]	The first tranche of the Waking Watch Relief Fund was administered by eight local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Relief Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_2
[note 12]	The Waking Watch Replacement Fund was administered by five local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Replacement Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_3
[note 13]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2, CSS_1, CSS_2, CSS_3, CSS_4, CSS_6, Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8
[note 14]	Private sector and social sector financial viability buildings can receive pre-tender support allocation in addition to their full applications funding, but not all buildings receive this therefore these numbers cannot be added together to directly give a total.	BSF_3
[note 15]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_3
[note 16]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1
[note 17]	Buildings can be in multiple schemes and data collections. These tables show the unique number of buildings across the schemes without double counting buildings where they are in multiple schemes. The total here will be lower than the summed total number of buildings reported in each scheme.	Combined_1, Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8
[note 18]	Where buildings are in multiple programmes, a combined remediation stage is first assigned for buildings in more than one of the ACM programme, BSF and CSS. 'In programme' is assigned for buildings that are eligible for but have not started works in any programme, or on one type of cladding (ACM or non-ACM). 'Remediation Underway' is assigned for buildings where work has started on remediation in at least one programme, or on one type of cladding. 'Remediation complete' is assigned for buildings that have completed remediation on site in all programmes or on all types of cladding. / For further overlaps, remediation stages are assigned from programmes in priority order: ACM, BSF, CSS (or a combined stage across these programmes), developer returns, social housing returns.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8
[note 19]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 20]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 21]	The Government-funded Joint Inspection Team, hosted by the Local Government Association, carries out building inspections on behalf of local authorities and provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4
[note 22]	The number of training sessions for Wandsworth and Richmond are combined as Merton, Wandsworth and Richmond operate a joint service where Merton officers attend training on behalf of Richmond and Wandsworth.	JIT_1
[note 23]	Buildings confirmed by delivery partners to be transferred to developers or the Cladding Safety Scheme have been withdrawn from the Building Safety Fund, which has led to a decrease in the number of eligible buildings in the Fund. The number of eligible buildings may continue to decrease as more buildings are confirmed as developer or CSS transfers out of the fund.	BSF_1, BSF_2, BSF_4, BSF_5
[note 24]	The Building Safety Fund first opened to registrations from June to July 2020 receiving registrations from 3,488 buildings. In July 2022 the Building Safety Fund reopened to new applications; this remains open to new applications from buildings in London over 18 metres in height (high-rise buildings outside of London can apply for remediation via the Cladding Safety Scheme). Buildings from both application periods are now combined as one Building Safety Fund, so numbers include both application periods. It is possible for a building to submit a new application to the fund after having completed remediation if it originally applied in 2020, therefore buildings could be double counted. As of the latest reporting period one building had undertaken remediation work from both application periods, so is double counted.	BSF_1, BSF_2, BSF_3, BSF_4, BSF_5
[note 25]	Some buildings have an unknown remediation status reported by the developer. These have been interpreted as ‘Remediation not started – no plans in place’. Furthermore, some buildings have an unknown defect type. These are interpreted as cladding related defects.	Developer_1, Developer_4, Developer_10
[note 26]	The buildings reported in this table as requiring remediation are estimated by MHCLG using information provided by developers in their data return and other data available within the department. In this table, a building is defined as requiring works under the developer remediation contract if it is either self-reported by the developer as requiring (or having previously required) remedial works; is an eligible building in the BSF or ACM and the developer has agreed to re-imburse the funds; has had money paid out by the BSF or ACM; or has a self-reported work status of either: works completed, works started, or works not started but plans in place. / They therefore differ from other published tables which reference only to the number of 'self-reported' buildings requiring works.	Developer_1, Developer_10
[note 27]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which the developer is remediating directly (please see note 28). The tables shows the number of buildings which have not yet started works; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Plans under Development' or where no status was provided. The table shows the estimated or actual start date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet started remediation work, but have an estimated or actual start date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_5, Developer_6
[note 28]	This represents buildings that developers are solely responsible for. These exclude buildings that are being remediated solely under a government remediation scheme, for which the developer will reimburse taxpayers. However, some buildings being remediated under a government remediation scheme will be included if other relevant fire safety defects have been found, which were not eligible for a government remediation scheme and which the developer is remediating themselves.	Developer_3
[note 29]	The tables report data for 53 developers who have signed the Developer Remediation Contract. Data for one developer who has gone into administration is not included in this release. / Where tables show the breakdown of data for each developer, there are 12 developers with 5 or fewer builidings who have been supressed to avoid inadvertently identifying buildings with life-critical fire safety defects. They are grouped in the category 'Other (combined total for all developers with five or fewer buildings each'. This includes: Abbey Developments, Allison Homes, Bloor, CG Fry, Courdace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata and William Davis. These developers will be represented in the data with a dash (-) in tables	Developer_1, / Developer_2, / Developer_3, Developer_4, Developer_5, Developer_6, Developer_7, Developer_8, Developer_9, Developer_10
[note 31]	This represents buildings which have been found to require remediation, for which the developer is directly responsible for the works. It excludes buildings being remediated solely under a government remediation scheme, for which the developer will reimburse taxpayers (see Note 28), as the developer cannot influence the pace of remediation on these buildings. However, some buildings being remediated under a government remediation scheme will be included if other relevant fire safety defects have been found, which were not eligible for a government remediation scheme and which the developer is remediating themselves.	Developer_3, Developer_4
[note 32]	The data here is comprised of of buildings where the response to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?’ was either left blank or reported as ‘Don’t Know – no assessment made’, ‘Don’t Know’ or ‘No – Declaration 5.4B.	Developer_3
[note 33]	The total estimated cost of remediation is based on the actual or estimated cost of remediating EWS and non-EWS defects, as reported by developers, and an assumed average where a cost has not been reported (averages are based on the developer-reported costs, by height).	Developer_2
[Note 34]	Data is taken from a building level survey issued to Registered Providers of Social Housing on their 11 metre plus buildings and is correct as at 30 June 2025. / Landlords were asked to respond to the survey for buildings in which they are the responsible entity. A 'Responsible Entity' is the organisation that has the legal obligation or right to carry out the remediation works. The Responsible Entity may be the building’s freeholder or head leaseholder, registered provider of social housing or a management company or Right To Manage (RTM) company that has primary responsibility for the repair of the property. / As a result, buildings within the survey may comprise of mixed tenure dwellings e.g., private leasehold and social rented dwellings, however remedial works will fall under the responsibility of the responding landlord. / Furthermore, landlords were asked to provide information on any life critical fire safety (LCFS) defects, which the survey defined as defects, shrinkages, faults or other failings in a building that give rise to fire safety risks. These are identified by: / 1) a Fire Risk Appraisal of External Wall construction (FRAEW) undertaken in accordance with PAS 9980 that assesses the external wall construction or cladding as not “medium - tolerable” (or better); or / 2) a fire risk assessment (FRA) that assesses the relevant parts of the building as high risk or medium risk or equivalent according to industry standards.	Social_1; Social_5
[Note 35]	A building with EWS 'cladding defects' is defined as a building which has at least one Life-critical Fire-safety defect relating to an External Wall System (EWS) cladding defect. These buildings may also include non-cladding associated defects.	Social_1; Social_2; Social_3; Social_4; Social_5
[Note 36]	The number of buildings identified as 'Remediation complete' may not match the number of social buildings being reported and complete under the BSF, ACM, CSS or developer contract due to the following: / 1) Non-responses to building level survey issued to Registered Providers of Social Housing - a small number or landlords did not respond to the survey, which means some buildings remediated through other remediation schemes may not be captured. / 2) Differences in how buildings are reported in the building level survey issued to Registered Providers of Social Housing - some buildings which have already completed remediation via other schemes have been reported as having no Life-Critical Fire-Safety defects in the survey, as the latest fire safety assessment has concluded that the the building is safe. Subsequently, the landlord has reported that no defects are present in the survey and have left the remediation category blank.	Social_1
[Note 37]	The data here includes buildings in the building level survey issued to Registered Providers of Social Housing, which may have also applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract. These are not excluded from the Social Housing Sector Management Information tables (Social_1).	Social_1
[note 38]	The total number of social high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 2 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 39]	The total number of social high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 1 building that falls under the developer remediation contract.	ACM_8
[note 40]	The total number of private high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 21 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 41]	The total number of private high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 68 buildings that fall under the developer remediation contract.	ACM_8
[note 42]	Data for the ACM, BSF and CSS are updated monthly. Developer data and data reported by Registered Providers of social housing are updated quarterly.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7
[note 43]	The number of buildings associated with particular expenditures paid out may also include buildings where a full reimbursement of funding has taken place, including those where required under the developer contract.	BSF_3
[note 44]	Buildings receive expenditure funding in stages and therefore these figures should not be used to calculate the average expenditure paid out to each building.	BSF_3, CSS_5
[note 45]	In this table where a local authority has 5 or fewer eligible BSF buildings, the numbers provided are banded. In all other cases the numbers are provided. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	BSF_4
[note 47]	Three buildings with live applications to the CSS are in Northern Ireland, the remainder are in England.	CSS_1
[note 48]	Four eligible buildings in the CSS are in Northern Ireland, the remainder are in England.	CSS_1, CSS_2, CSS_3, CSS_4
[Note 50]	The data in this table is derived from the building level survey which has been submitted by Registered Providers of Social Housing on their 11 metre plus buildings and is correct as at 30 September 2024. It covers buildings in England over 11m which contain at least 1 unit of social housing for which the social housing provider is the Responsible Entity. / Some buildings in this table may have applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract.	Social_2; Social_3; Social_4
[Note 51]	Registered social housing providers who have five or fewer 11m+ buildings (which may or may not require EWS life-critical fire-safety works) have been grouped together in the ‘Other RPs’ row in the data table, in order to avoid inadvertently identifying individual buildings with EWS life-critical fire-safety defects.	Social_2; Social_3; Social_4
[Note 52]	A building works assessments should comply with the requirements of the Fire Safety Order, for example a Fire Risk Assessment or Fire Risk Appraisal of External Walls assessment (FRAEW).	Social_2; Social_3
[Note 54]	Buildings reported as having completed remediation in the building level survey may require reassessment to confirm the building is now safe.	Social_1; Social_4
[Note 55]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which the developer is remediating directly (please see note 28). The tables shows the number of buildings which have not yet completed remediation; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Remediation Started' or where a remediation status was not provided. The table shows the estimated or actual completion date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet completed remediation work, but have an estimated or actual completion date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_7, / Developer_8
[Note 56]	Funding allocations of Full Applications Approved has reduced from previously published figures. This is the result of a data reconciliation exercise, where buildings transferring from the BSF to the Responsible Actors Scheme and Cladding Safety Scheme have had their BSF funding allocation removed.	BSF_3
[Note 57]	The 'Other' tenure includes buildings that are recorded in the ACM programme as student, hotel or public buildings.	Combined_5
[Note 58]	The estimates in this table include buildings which are: / a) reported in the latest survey (as at 30 June 2025) as having unsafe cladding at the time of their most recent assessment; / b) reported in the latest survey (as at 30 June 2025) as having unsafe cladding found since June 2017 but prior to the most recent survey, which have since been remediated; / c) being monitored under another government programme (BSF, ACM, CSS or RAS) due to having unsafe cladding.	Social_1
[Note 59]	Until May 2024, private sector funding allocations and expenditures included buildings which have successful social sector financial viability claims. This is because both private sector and social sector financial viability buildings receive full government funding, whereas those in the social sector receive partial funding dependant on the number of eligible leaseholders who pay a service charge. For full details please refer to the accompanying technical note.	[BSF_3]
[Note 60]	Until the May 2024 data release, social sector buildings with a successful financial viability claim were included in the "Private" figures due to them receiving funding for all work, rather than a percentage based on the number of leaseholders that pay a service charge. These buildings are now split out into the "social sector financially viability" category. Further details on the difference between these can be found in the accompanying technical note.	[BSF_1]
[Note 61]	This table depicts the number of buildings that are estimated to require works which have transferred from the Building Safety Fund (BSF). This figure is based on the developer's dataset definition of a building and differs to the number reported by the BSF because of difference in building definitions.	Developer_1
[Note 62]	The estimates in this table include buildings which are reported in the latest survey (as at 30 June 2025) as having unsafe cladding at the time of their most recent works assessment. They do not include buildings which are reported in the latest survey (30 June 2025) as having unsafe cladding found since June 2017, which have since been remediated. / They also do not include buildings that were identified through other government programmes (BSF, ACM, CSS or RAS) which have not been reported by social housing providers as having unsafe cladding.	Social_1; Social 2; Social_3; Social 4
[Note 63]	The December 2018 and December 2019 ACM remediation progress figures did not include the breakdowns for 'remediation started - cladding removed' and 'works complete awaiting building control signoff'. Those buildings which had started remediation and removed unsafe cladding are included in the 'remediation started' category, and those that were awaiting building control sign off may have been included in the 'completed remediation' category	ACM_11
[Note 64]	Up to October 2023 combined remediation progress in the Building Safety Fund (BSF) and ACM programme is shown. Between June 2023 and September 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers. From October 2023 onwards combined remediation progress is shown across the BSF, ACM programme, Cladding Safety Scheme, developer remediation contract and as reported by registered providers of social housing.	Combined_6
[Note 65]	Between June 2023 and July 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers.	BSF_5
[Note 66]	This table is updated quarterly with the latest data and therefore may not align with monthly figures where the programme data is updated.	Developer_10
[Note 67]	The estimates in this table include buildings which are reported in the latest survey (as at 30 June 2025) as having unsafe cladding: / a) at the time of their most recent assessment. / b) found since June 2017 but prior to the most recent survey, which have since been remediated. / The estimates in this table do not include buildings that were identified through other government programmes (BSF, ACM, CSS or RAS) which have not been reported by social housing providers as having unsafe cladding.	Social_1; Social 2; Social 4
[Note 68]	In previous Building Safety Remediation releases, this table was known as 'Building inspections conducted by local authorities'. As of the August 2024 release, this table reports the category assigned from the most recent building inspection.	Enforcement_2
[Note 69]	The Mar-24 and Jun-24 estimates are not comparable to previous quarters due to a change in methodology in reporting social housing sector remediation. Since Mar-24, the estimates include buildings which have been reported by Registered Providers to have completed remediation since June 2017 but prior to the most recent assessment. They also include social buildings the department has identified in other remediation programmes as having unsafe cladding and are also being monitored in those programmes.	Social_5
[Note 70]	This table excludes local authorities with fewer than 10 11m+ buildings monitored with unsafe cladding. These disclosure control measures are in place to prevent the identification of one or more buildings with unsafe cladding in these areas.	Combined_3
[Note 71]	As of the November 2024 data release, there is only one column covering Level 2 training. This is a sum of the data from Level 2 Part 1 and Level 2 Part 2. To make comparisons with previous JIT training data, the values in columns C and D should be totalled. When training is delivered as Level 1 and Level 2 in the same session, the training is recorded only in the Level 2 column.	JIT_1
[Note 72]	The reported number of buildings to have started or completed remediation works has fallen between August 2024 data release and November 2024 data release mainly due to data revisions from some Registered Providers of social housing following the addition of more detailed questions on start and completion dates.	Social_5
[Note 73]	The figures from before December 2022 for BSF remediation progress did not distinguish between 'Remediation plans in place' and 'Intent to remediate'; they were recorded as 'Remediation not yet started.' Therefore, before December 2022, buildings that would have been categorised as 'Remediation not yet started' are now classified as 'Intent to remediate.'	BSF_5
[Note 74]	It is possible for a building to submit 2 applications to the Building Safety Fund after having completed remediation if it originally applied in 2020, to avoid duplication on a portfolio level these buildings are combined into 1 entry. This means that the total of Non-ACM cladding only in the BSF and Both ACM and non-ACM cladding in the BSF won't match the total number of BSF buildings seen in the BSF tables. As of 30 June 2025 one building had undertaken remediation work from both application periods.	Combined_1
[Note 75]	The number of buildings inspected with support from the Joint Inspection Team may not match the overall number of inspections carried out with their support, as some buildings may have been inspected more than once.	Enforcement_4
[Note 76]	The numbers of notices, inspections etc. may decrease as a result of revisions submitted.	Enforcement_1, Enforcement_4
[Note 77]	These figures exclude CSS buildings in Northern Ireland.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8, Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 78]	A government funded scheme includes the ACM programme (including buildings not receiving government funding), the BSF and the CSS.	Combined_8, Estimated_4
[Note 79]	These figures represent MHCLG's best estimates of the number of 11m+ residential buildings that have or had unsafe cladding, in England, as at January 2025. The estimates of 11-18m buildings with unsafe cladding replace estimates first published in 2022. New estimates use the recently released Ordnance Survey National Geographic Database (OS NGD) data, alongside the original sample survey used in 2021. The estimates of 18m+ buildings with unsafe cladding use known building numbers as at July 2024, alongside individual assumptions of further buildings to be identified in different categories. Full methodology is available in the Technical Note.	Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 80]	The estimate of the number of 11-18m buildings in England used to calculate the prevalence of unsafe cladding is an updated estimate, replacing the original estimates first published in 2021. Further information is available in the Technical Note.	Estimated_1
[Note 81]	These figures include buildings which have already undergone remediation or mitigation of unsafe cladding.	Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 82]	The estimates in Estimated_2 differ from the estimates in Estimated_1 as Estimated_2 includes 18m+ hotels, student accommodation or public buildings identified with unsafe ACM cladding, because these buildings are remediated through the ACM programme. At the time the estimate was made there were 98 of these buildings. These are excluded from Estimated_1 because the buildings do not contain dwellings. The estimated number of 11m+ buildings which are assumed to be remediated privately, outside of one of the department’s remediation programmes, are included in Estimated_1 but excluded from the Estimated_2.	Estimated_1, Estimated_2
[Note 83]	MHCLG have collected quarterly data returns from developers since 31 July 2023. However, it is not possible to show a breakdown of determinations made between 31 July 2023 and 31 January 2024 due to an amendment which was made to the question used to track determinations in January 2024. Determinations are based on the survey question 'Does this building require works, or has it previously been identified with defects, as per the contract?' Prior to January 2024 the response options for this question were 'Yes', 'No' and 'Don't Know', however as the response 'No' comprised a combination of buildings which had received a qualifying assessment and buildings which hadn't, it was not possible to accurately identify buildings which had recieved a determination on whether remedial works are required. Therefore, in January 2024 the options were amended to 'No - as shown by assessment', 'Yes - as shown by assessment', 'Don't Know - no assessment made' and 'Don't Know - further assessment required'. This enables developers to more accurately report on whether a determination has been made for each building.	Developer_11
[Note 84]	Determinations are based on a developers response to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?'. To estimate the quarterly number of buildings where determinations were made, MHCLG uses the most recent quarterly returns submitted by developers. Buildings reported with a determination in the most recent quarterly return are compared against previous returns and categorised based on the earliest quarterly return in which they were reported to have had a determination, providing they continue to be reported as determined in subsequent quarters. If a determination alternates across returns, the most recent reported data return is used. See the Technical Note for further information.	Developer_11
[Note 85]	To estimate the number of buildings where works were started or works were completed in each quarter, MHCLG have used the most recent quarterly returns submitted by developers. Using developer responses to the question 'Status of Works', buildings reported as Started or Completed in the most recent quarterly return are compared against previous returns and categorised based on the earliest quarterly return in which they were reported to have started or completed works, providing they continue to be reported as started or completed in subsequent quarters. If the response to 'Status of Works' alternates across returns, the most recent reported data return is used. / In January 2025, as part of data validation improvements, an additional response of 'Yes - the building previously required works which are now fixed' was added to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?'. For buildings where the 'Status of Works' has changed from not started/blank to using this new response in consecutive quarters, the start and completion dates reported by developers are used to categorise the quarter in which they started or completed. For buildings where valid dates were not reported by developers, it is assumed that they had started and completed works before 31 July 2023; the first point at which developers submitted data to MHCLG." See the Technical Note for further information.	Developer_11
[Note 86]	The statistics in these tables are experimental and as such will be subject to methodology refinements as more data becomes available. See the Technical Note for further information.	Developer_11
[Note 87]	The total is the same as the row above since there is only one Administering Authority for the 2023 Replacement Fund	WWRF_4
[Note 88]	Figures in this table are based on funding eligibility criteria as at June 2025.	Estimated_4
[Note 89]	Running total of training for the year to date (or total for that year if not current year)	JIT_1
[Note 90]	Total attendees on training for all the years we have received data. May not be a sum of the individual years' data.	JIT_1
[Note 91]	Two providers – London Borough of Brent and Brighton and Hove City Council – reported they were not able to confidently provide further information on their 11m+ buildings as of 30 June 2025 while they were undertaking a review of their data. As a result, this data release includes only their total number of 11m+ buildings which they confirmed as at 30 June 2025. No information is included for the assessment status, presence of life-critical fire safety defects related to the external wall system or remediation status of their buildings. MHCLG and RSH are working with these two providers to support their reviews and future data submission.	Social_1; Social_2; Social_3; Social_4; Social_5
[Note 92]	The Jun-25 estimates are not comparable to previous quarters due to two social housing providers - London Borough of Brent and Brighton and Hove City Council - reporting that they were not able to confidently provide information on whether their 11m+ buildings have life-critical fire safety defects related to the EWS.These two social housing providers previously jointly reported 43 11m+ buildings with life-critical fire safety defects related to the EWS (which are included in the Mar-25 estimates).	Social_1; Social_5
[Note 93]	Two providers – London Borough of Brent and Brighton and Hove City Council – reported they were not able to confidently provide further information on their 11m+ buildings as at 30 June 2025 while they were undertaking a review of their data. As a result, this data release includes only their total number of 11m+ buildings, which they confirmed as at 30 June 2025. No information is included for the assessment status, presence of life-critical fire safety defects related to the external wall system or remediation status of their buildings. London Borough of Brent and Brighton and Hove City Council's figures are included in the total number of 11m+ buildings to calculate the percentage of 11+m buildings which have had or have not had a recent building works assessments (social_2) and to calculate the percentage of 11+m buildings which have been assessed and identified life-critical fire safety defects related to the EWS since June 2017 or in their most recent building works assessment (social_3).	Social_2; Social_3; Social_4
[Note 94]	Following publication of the public inquiry report into the Grenfell Tower Fire, the Prime Minister made clear that unsafe buildings must be remediated more quickly. The joint plan was published alongside the government’s broader Remediation Acceleration Plan. 39 developers have signed up to the Joint Plan, where they have committed to making every effort to achieve several stretch targets: / • Finish assessing all their buildings to determine which require works by end July 2025 / • Start or complete remedial works on 80% of their buildings by end July 2026 / • Start or complete remedial works on all their buildings by end July 2027 / • Resolve extant cost-recovery negotiations with social housing providers by end July 2025	Developer_12
[Note 95]	Under the joint plan, developers committed to complete determinations for all buildings for which they are responsible under the contract by end July 2025, and to provide evidence to MHCLG in any cases where a building missed the stretch target for reasons outside the developer’s control. MHCLG committed to consider any such evidence and take it into account when reporting on developer progress. This column shows the number of buildings where a reasonable exception has been requested by a developer and accepted by MHCLG. / To calculate the estimated percentage of buildings that would have a determination if buildings with exceptions are accounted for, the 'number of buildings where an exception request has been accepted' is subtracted from the 'number of contract buildings where the developer is directly responsible for remediation' and this is used as the denominator. The 'number of buildings for which the developer has determined whether works are required' is used as the numerator	Developer_12

## One_source_pro
RecordCutDate	MHCLG_Code	BuildingName	LocalAuthority	Tenure	Payer	Category	SubcategoryRS	CombinedCategory	PhasedCombinedCategory	StartedDate	StartedDatePlanned	CompleteDate	CompleteDatePlanned	CladdingRemoved	CladdingRemovedPlanned	Vacant	Interims	SocialLAorHA	PrivateFundDP	PrivateFundStatusFF	PrivateFundStatusDR	PreTenderSupport	Development	Street	Town	Postcode	RemediationOwner	Freeholder	Agent	Developer	UnitsEngagement	UnitsVOA	HeightMetres	HeightStoreys	EWS_Status	Constituency	ParlConstituencyCode	LocalAuthorityCode	UPRN	Geoplace_UPRNs	InDec19	InDec20	InDec21	InDec22	InDec23	InDec24	CrossoverFlag	CSSCrossoverFlag	DeveloperCrossoverFlag	Address for Lenders	Min Units	Max Units	Units to use for portfolio	UPRN for lenders	Portfolio category from latest portfolio list	Funder - for portfolio	DP
30/09/2025	P_BARK0042	The Ropeworks	Barking and Dagenham	private residential	bsf	Remediation completed		Remediation completed	Remediation completed	06/06/2022	06/06/2022	18/10/2024	16/12/2024	19/04/2023	06/04/2023		yes							1 Aboretum Place	Barking	IG11 7GU		Head Lessee (GRIF051 Limited (GRIF)	BSMC Ltd)	Redrow Regeneration (Barking) Ltd were the developer and Ardmore Construction Ltd was the main contractor.		246	21	8	Complete	Barking	E14000540	E09000002		10002170558	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1		1	The Ropeworks, 1 Aboretum Place, IG11 7GU	246	246	246	10002170558	ACM/BSF RAS reimbursements	Developer	GLA
30/09/2025	HA60009	1 - 93 Kings House	Barking and Dagenham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/09/2017	19/11/2018	21/07/2019	31/08/2019				yes	HA						NORTH STREET	London	IG11 8FH	Estuary Housing Association Ltd	Estuary Housing Association Ltd			79	79	23	8	Complete	Barking	E14000540	E09000002	100058448	100058448	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			1 - 93 Kings House, NORTH STREET, IG11 8FH	79	79	79	100058448	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_BARN0106	Groupama House 17	Barnet	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	05/05/2022	05/05/2022	13/05/2022	25/05/2022	05/05/2022	06/05/2022		yes							Station Road	London	EN5 1TS		New 17 Station Road Ltd	Theori Housing Management Services Ltd			36	24	8	Complete	Chipping Barnet	E14000636	E09000003		200107674	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Groupama House 17, Station Road, EN5 1TS	36	36	36	200107674	ACM only	Private	MHCLG
30/09/2025	HA99095	Goldfinch Court	Barnet	social	social-fund	Remediation completed		Remediation completed	Remediation completed	28/10/2019	14/10/2019	30/11/2020	30/11/2020				yes	HA						FINCHLEY ROAD	London	NW11 8AT	Origin Housing	Origin Housing			31	31	21.4	7	Complete	Finchley and Golders Green	E14000703	E09000003	10091037527	10091037527	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Goldfinch Court, FINCHLEY ROAD, NW11 8AT	31	31	31	10091037527	ACM only	Government	MHCLG
30/09/2025	LA11087	Granville Point	Barnet	social	social-fund	Remediation completed		Remediation completed	Remediation completed	20/04/2018	20/04/2018	01/12/2018	31/12/2018				complete	LA						Granville Road	London	NW2 2LJ	Barnet Council	London Borough of Barnet			60	60	39	15	Complete	Finchley and Golders Green	E14000703	E09000003	200220614	200220614	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Granville Point, Granville Road, NW2 2LJ	60	60	60	200220614	ACM only	Government	MHCLG
30/09/2025	LA11086	Harpenmead Point	Barnet	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	20/04/2018	01/12/2018	31/12/2018				complete	LA						Granville Road	London	NW2 2LL	Barnet Council	London Borough of Barnet			60	60	39	15	Complete	Finchley and Golders Green	E14000703	E09000003	200220615	200220615	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Harpenmead Point, Granville Road, NW2 2LL	60	60	60	200220615	ACM only	Government	MHCLG
30/09/2025	MR HA Genesis 00009	LARK COURT	Barnet	social	social	Remediation completed		Remediation completed	Remediation completed	01/10/2017	01/04/2018	01/06/2018	30/11/2018				yes	HA						104 LANACRE AVENUE	London	NW9 5QD	Notting Hill Genesis	Notting Hill Genesis		Countryside	49	49	28	10	Complete	Hendon	E14000741	E09000003	200156356	200156356	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				LARK COURT, 104 LANACRE AVENUE, NW9 5QD	49	49	49	200156356	ACM only	Social	MHCLG
30/09/2025	P_BARN03	Mar House 50	Barnet	private residential	private-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	25/04/2022	25/04/2022		06/04/2026	09/04/2024	10/04/2024		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	FALSE		The Hyde	London	NW9 5NG	Annabelle Godber	South Staffs Group Limited		Mar City Homes	95	95	20	7	Complete	Hendon	E14000741	E09000003	10091040557	10091040557	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Mar House 50, The Hyde, NW9 5NG	95	95	95	10091040557	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_BARN04	Premier House	Barnet	private residential	private-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	27/11/2023	27/11/2023		17/11/2025	01/10/2024	18/07/2025		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	TRUE		112, Station Road	London	HA8 7BJ	Tony Eisen	Betterpride Limited	BLR Property Management	Reichmann Properties Plc	126	121	42.4	14	Complete	Hendon	E14000741	E09000003	200107967	200107967	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier House, 112, Station Road, HA8 7BJ	121	126	126	200107967	ACM only	Government	GLA
30/09/2025	P_BARN0019	Stay Club 18	Barnet	student	student	Remediation completed		Remediation completed	Remediation completed	09/11/2020	09/11/2020	30/09/2022	30/09/2022				yes							Charcot Road	London	NW9 5WU						0	51	17	Complete	Hendon	E14000741	E09000003	10091041422	10091041422	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				Stay Club 18, Charcot Road, NW9 5WU	0	0		10091041422	ACM only	Private	MHCLG
30/09/2025	LA11085	Templewood Point	Barnet	social	social-fund	Remediation completed		Remediation completed	Remediation completed	20/04/2018	20/04/2018	01/12/2018	31/12/2018				complete	LA						Granville Road	London	NW2 2AX	Barnet Council	London Borough of Barnet			60	60	39	15	Complete	Finchley and Golders Green	E14000703	E09000003	200220618	200220618	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Templewood Point, Granville Road, NW2 2AX	60	60	60	200220618	ACM only	Government	MHCLG
30/09/2025	MR HA Genesis 00022	Aragon Court	Basildon	social	social-fund	Remediation completed		Remediation completed	Remediation completed	19/08/2019	19/08/2019	24/03/2020	29/11/2019				complete	HA						STATION LANE	Basildon	SS13 3EZ	Notting Hill Genesis	Notting Hill Genesis			40	40	30	6	Complete	South Basildon and East Thurrock	E14000933	E07000066		10094391772	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Aragon Court, STATION LANE, SS13 3EZ	40	40	40	10094391772	ACM only	Government	MHCLG
30/09/2025	MR HA Genesis 00023	Cleves Court	Basildon	social	social-fund	Remediation completed		Remediation completed	Remediation completed	19/08/2019	19/08/2019	24/03/2020	01/05/2020				complete	HA						STATION LANE	Basildon	SS13 3FB	Notting Hill Genesis	Notting Hill Genesis			56	56	25	9	Complete	South Basildon and East Thurrock	E14000933	E07000066		10094391773	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Cleves Court, STATION LANE, SS13 3FB	56	56	56	10094391773	ACM only	Government	MHCLG
30/09/2025	P_BEDF01	Premier Inn Bedford	Bedford	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/08/2018	01/08/2018	01/05/2019	01/05/2019				yes							Riverside North	Bedford	MK40 3TD	Premier Inn	Whitbread	TowerEight	Bouygues	100		30.5		Complete	Bedford	E14000552	E06000055		10093201558	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn Bedford, Riverside North, MK40 3TD	100	100		10093201558	ACM only	Private	MHCLG
30/09/2025	P_BIRM0350	105 Bell Barn Road	Birmingham	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed			10/03/2020					yes							Bell Barn Road	Birmingham	B15 2GL			Broadoak Management Company	Crest Nicholson		56				Birmingham Ladywood	E14000564	E08000025		10090437568	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE			1	105 Bell Barn Road, Bell Barn Road, B15 2GL	56	56	56	10090437568	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_BIRM0351	61 Mason Way	Birmingham	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	02/03/2020		12/03/2020	30/04/2020				yes							Mason Way	Birmingham	B15 2GE			Broadoak Management Company	Crest Nicholson		76				Birmingham Ladywood	E14000564	E08000025		10090437625	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE			1	61 Mason Way, Mason Way, B15 2GE	76	76	76	10090437625	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	HA46015	CROCODILE COURT	Birmingham	social	social	Plans in place		Plans in place	Plans in place		06/04/2026		01/07/2026									FALSE		209 ALMA STREET	Birmingham	B19 2AF		Midland Heart				93	20.8	8	Complete	Birmingham Ladywood	E14000564	E08000025	10090432054	10090432054	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE				CROCODILE COURT, 209 ALMA STREET, B19 2AF	93	93	93	10090432054	ACM only	Social	MHCLG
30/09/2025	P_BIRM01	Lucas Studios	Birmingham	student	student	Remediation completed		Remediation completed	Remediation completed			01/09/2018					yes							291-295 Corporation Street	Birmingham	B4 7DP	Trustees of the Stagecoach Pension Scheme c/o Barings Real Estate Advisors									Birmingham Ladywood	E14000564	E08000025	10091518334	10091518334	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Lucas Studios / , 291-295 Corporation Street / , B4 7DP				10091518334	ACM only	Private	MHCLG
30/09/2025	P_BIRM03	Pentahotel	Birmingham	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	22/03/2021	22/03/2021	30/11/2021	05/11/2021	06/08/2021	06/08/2021		yes							Ernest Street/ Holloway Head	Birmingham	B1 1NS	Pentahotel Birmingham	Pentahotel	AroundTown holdinds						Complete	Birmingham Ladywood	E14000564	E08000025	10090256843	10090256843	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Pentahotel, Ernest Street/ Holloway Head, B1 1NS				10090256843	ACM only	Private	MHCLG
30/09/2025	P_BIRM02	Penworks	Birmingham	student	student	Remediation completed		Remediation completed	Remediation completed	01/09/2018		19/09/2019	19/09/2020				yes							5 Moland Street	Birmingham	B4 7AS	Hermes Asset Group								Complete	Birmingham Ladywood	E14000564	E08000025	10090438247	10090438247	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Penworks, 5 Moland Street, B4 7AS				10090438247	ACM only	Private	MHCLG
30/09/2025	P_BOUR0122	Terrace Mount Residences	Bournemouth, Christchurch and Poole	private residential	developer	Remediation completed		Remediation completed	Remediation completed	07/03/2022		12/08/2022	29/07/2022				yes							Terrace Road	Bournemouth	BH2 5EL		That group		That Group		14				Bournemouth West	E14000585	E06000058			FALSE	FALSE	FALSE	TRUE	TRUE	TRUE				Terrace Mount Residences, Terrace Road, BH2 5EL	14	14	14		ACM only	Private	MHCLG
30/09/2025	P_BOUR0021	B Central	Bournemouth, Christchurch and Poole	private residential	private-fund	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	24/04/2023	08/05/2023	28/04/2023	12/05/2023	23/04/2023	28/04/2023		do not know		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		Commercial Road	Bournemouth	BH2 5AT		Britannia Hotels				62		9	Complete	Bournemouth West	E14000585	E06000058	10014278977	10014278977	FALSE	FALSE	FALSE	TRUE	TRUE	TRUE				B Central, Commercial Road, BH2 5AT	62	62	62	10014278977	ACM only	Government	HE
30/09/2025	P_POOL02	Harbour Sail	Bournemouth, Christchurch and Poole	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	14/09/2021	05/09/2022	15/05/2023	05/05/2023	21/10/2022	06/10/2022	Vacant decanted	yes							71 West Quay Road	Poole	BH15 1JH		MCLAGAN INVESTMENTS LIMITED		Stonewater Housing Association	32	32	33.11	11	Incomplete - requires follow up	Poole	E14000881	E06000058	10001094268	10001094268	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Harbour Sail, 71 West Quay Road, BH15 1JH	32	32		10001094268	ACM only	Private	MHCLG
30/09/2025	P_BOUR01	Lansdowne Point	Bournemouth, Christchurch and Poole	student	student	Remediation completed		Remediation completed	Remediation completed	02/11/2020	07/12/2020	30/09/2022	30/09/2022	14/02/2022	11/02/2022		yes							51-65 Holdenhurst Road	Bournemouth	BH8 8GN	KAPLAN INTERNATIONAL COLLEGES, 2ND FLOOR, WARWICK BUILDING, KENSINGTON VILLAGE, AVONMORE ROAD, LONDON W14 8HQ	Legal and General	Kaplan					16	Complete	Bournemouth West	E14000585	E06000058	100041058819	100041058819	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Lansdowne Point, 51-65 Holdenhurst Road, BH8 8GN				100041058819	ACM only	Private	MHCLG
30/09/2025	P_POOL01	Orchard Plaza	Bournemouth, Christchurch and Poole	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	01/12/2021	29/11/2021	19/07/2023	28/07/2023	21/12/2022	21/12/2022		yes							High Street	Poole	BH15 1EH		SECURE REVERSIONS LIMITED	Orchard Plaza Management Company Limited	Balfour Beatty	115	103	32	12	Complete	Poole	E14000881	E06000058	10022814425	10022814425	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Orchard Plaza, High Street, BH15 1EH	103	115	115	10022814425	ACM only	Private	MHCLG
30/09/2025	P_BRAC01	Grange Bracknell Hotel	Bracknell Forest	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	04/07/2022		31/03/2023	31/03/2023		03/03/2023	Vacant not currently occupied	yes							Charles Square	Bracknell	RG12 1DF	Grange Hotels	Aviva	0	0	120		25		Complete	Bracknell	E14000586	E06000036	200000324900	200000324900	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Grange Bracknell Hotel, Charles Square, RG12 1DF	120	120		200000324900	ACM only	Private	MHCLG
30/09/2025	P_BRAD02	Appleton Point	Bradford	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	16/12/2020	14/12/2020	26/08/2021	20/08/2021	09/09/2021	03/09/2021	Vacant decanted	not required		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		2 Hamm Strasse	Bradford	BD1 4NT	Managed now by RGM	E&J Ground Rents	Residential Management Group		160	160	18.75	7		Bradford West	E14000589	E08000032	200004705930	200004705930	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Appleton Point, 2 Hamm Strasse, BD1 4NT	160	160		200004705930	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	NHS00011	Decontamination Block	Bradford	public	public	Remediation completed		Remediation completed	Remediation completed			28/02/2019					yes								Bradford	BD9 6RJ	Bradford Teaching Hospital NHS Foundation Trust	Bradford Teaching Hospital NHS Foundation Trust								Bradford West	E14000589	E08000032	100051155784	100051155784	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Decontamination Block, , BD9 6RJ				100051155784	ACM only	Private	MHCLG
30/09/2025	P_BRAD04	Landmark House	Bradford	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	15/02/2021	25/01/2021	17/09/2021	17/09/2021	09/04/2021	09/04/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		11 Broadway	Bradford	BD1 1JB	Richard Worrall	CITY OF BRADFORD METROPOLITAN DISTRICT COUNCIL	Hunters	Broadford Estates	91	91	20.38	6	Incomplete - requires follow up	Bradford West	E14000589	E08000032	100051929622	100051929622	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Landmark House, 11 Broadway, BD1 1JB	91	91	91	100051929622	ACM only	Government	HE
30/09/2025	P_BREN0246	Novotel	Brent	hotel	other	Remediation started		Remediation started	Remediation started	08/05/2023	08/05/2023		25/06/2027		30/06/2025		not required							5 Olympic Way	London	HA9 0NP		Wembley Properties		Wembley Properties			33	11	Complete	Brent Central	E14000591	E09000005		202205711	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Novotel, 5 Olympic Way, HA9 0NP				202205711	ACM only	Private	MHCLG
30/09/2025	HA00712	1-23 George House	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2018	23/07/2018	31/03/2020	31/03/2020				yes	HA						Albert Road	London	NW6 5BR	London and Quadrant Housing Trust	London and Quadrant Housing Trust			25	25	36	11	Incomplete - requires follow up	Hampstead and Kilburn	E14000727	E09000005		202203495	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			1-23 George House, Albert Road, NW6 5BR	25	25	25	202203495	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	HA00811_166	67-88 George House	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2018	23/07/2018	31/03/2020	31/03/2020				yes	HA						Albert Road	London	NW6 5BR	London and Quadrant Housing Trust	London and Quadrant Housing Trust			22	22	36		Incomplete - requires follow up	Hampstead and Kilburn	E14000727	E09000005	202203495	202203495	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				67-88 George House, Albert Road, NW6 5BR	22	22	22	202203495	ACM only	Government	MHCLG
30/09/2025	HA00811_163	Block B Core 2, Flats 34 40 46 52-55 George House	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2018	23/07/2018	29/05/2020	29/05/2020				yes	HA						ALBERT ROAD	London	NW6 5BR	London and Quadrant Housing Trust	London and Quadrant Housing Trust			30	30	36	8	Complete	Hampstead and Kilburn	E14000727	E09000005		202203495	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Block B Core 2, Flats 34 40 46 52-55 George House, ALBERT ROAD, NW6 5BR	30	30	30	202203495	ACM only	Government	MHCLG
30/09/2025	HA21003	Block C Core 3, Flats 56 58 60 62-66 George House	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2018	23/07/2018	31/03/2020	31/03/2020				yes	HA						Albert Road	London	NW6 5BR	London and Quadrant Housing Trust	London and Quadrant Housing Trust			11	11	36	10	Complete	Hampstead and Kilburn	E14000727	E09000005	202203495	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Block C Core 3, Flats 56 58 60 62-66 George House, Albert Road, NW6 5BR	11	11	11	202203495	ACM only	Government	MHCLG
30/09/2025	HA00811_162	Block E Core 5, Flats 1-17 Swift House	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	23/07/2018	23/07/2018	29/05/2020	29/05/2020				yes	HA						Albert Road	London	NW6 5BW	London and Quadrant Housing Trust	London and Quadrant Housing Trust			22	22	33	11	Complete	Hampstead and Kilburn	E14000727	E09000005		202203584	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Block E Core 5, Flats 1-17 Swift House, Albert Road, NW6 5BW	22	22	22	202203584	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	HA99202	Dan Court	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	08/12/2019	05/11/2018	24/05/2021	28/05/2021	28/08/2020	28/08/2020		yes	HA						LAKESIDE DRIVE	London	NW10 7FU	Catalyst Housing Limited	Catalyst Housing Limited			138	138	28.4	8	Incomplete - requires follow up	Brent Central	E14000591	E09000005	202209409	202209409	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Dan Court, LAKESIDE DRIVE, NW10 7FU	138	138	138	202209409	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	HA77002	Elizabeth House	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/09/2019	30/09/2019	22/12/2021	22/12/2021	30/08/2021	30/08/2021		yes	HA						High Road	Wembley	HA9 6BF	Octavia Housing	Octavia housing			115	115	39	13	Complete	Brent North	E14000592	E09000005		202204319	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Elizabeth House, High Road, HA9 6BF	115	115	115	202204319	ACM only	Government	MHCLG
30/09/2025	P_BREN07	Felda House	Brent	student	freeholder	Remediation completed		Remediation completed	Remediation completed	07/03/2022	07/04/2022	20/12/2023	20/12/2023	30/12/2022	30/12/2022		yes							575 North Road	Wembley	HA9 0UU		FIC GLOBAL LIMITED						18	Complete	Brent Central	E14000591	E09000005		202214191	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Felda House, 575 North Road, HA9 0UU				202214191	ACM only	Private	MHCLG
30/09/2025	P_BREN01	Forum House	Brent	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/04/2018		01/04/2018					yes							25 Olympic Way	London	HA9 0AB	Quintain	GIDEON 4 LIMITED		Quintain		286	25.5	8	Complete	Brent Central	E14000591	E09000005	202191733	202191733	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Forum House, 25 Olympic Way, HA9 0AB	286	286	286	202191733	ACM only	Private	MHCLG
30/09/2025	P_BREN08	Grand Felda House	Brent	student	freeholder	Remediation started		Remediation started	Remediation started	23/06/2025	28/07/2025		31/08/2026				yes							Empire Way	Wembley	HA9 0EF		FIC GLOBAL LIMITED					54.5	18	Complete	Brent Central	E14000591	E09000005		202217442	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Grand Felda House, Empire Way, HA9 0EF				202217442	ACM only	Private	MHCLG
30/09/2025	P_BREN0117	ibis London Wembley Hotel	Brent	hotel	hotel	Remediation plan unclear		Remediation plan unclear	Remediation plan unclear													FALSE		South Way	Wembley	HA9 6BA							47.1	13	Complete	Brent North	E14000592	E09000005		202018225	FALSE	FALSE	FALSE	FALSE	FALSE	FALSE				ibis London Wembley Hotel, South Way, HA9 6BA				202018225	ACM only	Private	MHCLG
30/09/2025	HA99240	Merle Court	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	03/02/2020	03/02/2020	29/03/2024	30/09/2024	24/07/2020	24/07/2020		yes	HA						CARLTON VALE	London	NW6 5HH	Catalyst Housing Limited	Catalyst Housing Limited			50	50	20	7	Complete	Hampstead and Kilburn	E14000727	E09000005	202201448	202201448	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Merle Court, CARLTON VALE, NW6 5HH	50	50	50	202201448	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_BREN0073	Pinnacle Tower	Brent	private residential	developer	Remediation completed		Remediation completed	Remediation completed	16/01/2023	16/01/2023	10/12/2024	10/12/2024	28/04/2023	28/04/2023		yes							23 Fulton Road	London	HA9 0GB		HEB Residential		HEB Residential		131	60.8	19	Complete	Brent Central	E14000591	E09000005	202205756	202205756	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Pinnacle Tower, 23 Fulton Road, HA9 0GB	131	131	131	202205756	ACM only	Private	MHCLG
30/09/2025	P_BREN04	Quadrant Court	Brent	private residential	developer	Remediation completed		Remediation completed	Remediation completed	20/02/2019	01/03/2019	01/04/2019	30/03/2019				complete							Empire Way	London	HA9 0BY	Quintain	Quintain		Quintain	78	234	16	7	Complete	Brent Central	E14000591	E09000005	202196777	202196777	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Quadrant Court, Empire Way, HA9 0BY	78	234	78	202196777	ACM /BSF crossovers only - no RAS	Private	MHCLG
30/09/2025	HA00811_180	Swift house (Block 2)	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	23/07/2018	23/07/2018	29/05/2020	29/05/2020				yes	HA						ALBERT ROAD	London	NW6 5BW	London and Quadrant Housing Trust	London and Quadrant Housing Trust			22	22	33	10		Hampstead and Kilburn	E14000727	E09000005	202203584	202203584	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Swift house (Block 2), ALBERT ROAD, NW6 5BW	22	22	22	202203584	ACM only	Government	MHCLG
30/09/2025	HA00811_165	Swift house (Block 3)	Brent	social	social-fund	Remediation completed		Remediation completed	Remediation completed	23/07/2018	23/07/2018	29/05/2020	29/05/2020				yes	HA						ALBERT ROAD	London	NW6 5BW	London and Quadrant Housing Trust	London and Quadrant Housing Trust			21	21	33	5		Hampstead and Kilburn	E14000727	E09000005	202203584	202203584	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Swift house (Block 3), ALBERT ROAD, NW6 5BW	21	21	21	202203584	ACM only	Government	MHCLG
30/09/2025	P_BREN02	Unite Student Accommodation	Brent	student	student	Remediation completed		Remediation completed	Remediation completed	01/03/2018		01/09/2018					complete							23 Olympic Way	Wembley	HA9 0FR	Unite Students	UNITE					54.6	19	Incomplete - requires follow up	Brent Central	E14000591	E09000005		202213528	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Unite Student Accommodation, 23 Olympic Way, HA9 0FR				202213528	ACM only	Private	MHCLG
30/09/2025	P_BREN03	Victoria Halls of Residence	Brent	student	student	Remediation completed		Remediation completed	Remediation completed	01/10/2020	01/10/2020	17/12/2021	17/12/2021	16/04/2021	16/04/2021	Vacant not currently occupied	yes							North End Road	London	HA9 0UU	MPS Property GP Limited (managed by Victoria Hall Management Company)	Coal Pension Properties Limited	Host Students				64.7	20	Complete	Brent Central	E14000591	E09000005	202201585	202201585	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Victoria Halls of Residence, North End Road, HA9 0UU				202201585	ACM only	Private	MHCLG
30/09/2025	P_BREN05	Wembley International Hotel	Brent	hotel	hotel	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	01/12/2020	01/12/2020			06/02/2023			not required							Empire Way	London	HA9 0NH	Exeter Properties Limited				165		32	10	Complete	Brent Central	E14000591	E09000005	202100059	202100059	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Wembley International Hotel, Empire Way, HA9 0NH	165	165		202100059	ACM only	Private	MHCLG
30/09/2025	P_BRIG0132	Ibis Brighton	Brighton and Hove	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	04/10/2021	05/10/2021	31/03/2022	25/03/2022				not required							Queens Road	Brighton	BN1 3XE							19.7	10	Complete	Brighton Pavilion	E14000598	E06000043		22170000	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Ibis Brighton, Queens Road, BN1 3XE				22170000	ACM only	Private	MHCLG
30/09/2025	P_BRIS03	Eclipse Tower	Bristol, City of	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	24/08/2020	24/08/2020	28/09/2022	23/09/2022	04/05/2022	30/06/2022		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		Broad Weir	Bristol	BS1 3DH	Hammerson	The City Council Of Bristol	Savills	Bristol Alliance Ltd Partnership (BALP) (collectively formed of Hammerson and Land Securities). The alliance appointed Sir Robert McAlpine (SRM) to build (started in 2004)	76	76	39.8	18	Complete	Bristol West	E14000602	E06000023	322437	322437	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Eclipse Tower, Broad Weir, BS1 3DH	76	76	76	322437	ACM only	Government	HE
30/09/2025	P_BRIS02	Fresh Student Living New Bridewell	Bristol, City of	student	student	Remediation completed		Remediation completed	Remediation completed	01/09/2018	01/10/2018	27/11/2019	27/11/2019				yes							Nelson Street	Bristol	BS1 2BA									Complete	Bristol West	E14000602	E06000023	364231	364231	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Fresh Student Living New Bridewell, Nelson Street, BS1 2BA				364231	ACM only	Private	MHCLG
30/09/2025	P_BRIS04	Fusion Tower	Bristol, City of	student	student	Remediation completed		Remediation completed	Remediation completed	29/06/2020	22/06/2020	04/12/2020	04/12/2020				yes							Rupert Street	Bristol	BS1 2AL	Collegiate AC	Stellar (Bristol Tower) Investments Limited	Collegiate-ac						Complete	Bristol West	E14000602	E06000023	98929	98929	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Fusion Tower, Rupert Street, BS1 2AL				98929	ACM only	Private	MHCLG
30/09/2025	P_BRIS16	Number One Bristol	Bristol, City of	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	24/02/2020	24/02/2020	28/02/2021	28/02/2021	05/03/2021	05/03/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		Lewins Mead	Bristol	BS1 2NR		PG Lewins Ltd			148	145		14	Complete	Bristol West	E14000602	E06000023	98138	98138	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Number One Bristol, Lewins Mead, BS1 2NR	145	148	148	98138	ACM only	Government	HE
30/09/2025	P_BRIS06	Premier Inn (Lewins Mead)	Bristol, City of	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/10/2018	01/10/2018	01/05/2019	01/03/2019				yes							Lewins Mead	Bristol	BS1 2PY	Premier Inn	Whitbread	TowerEight						Complete	Bristol West	E14000602	E06000023	371647	371647	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn (Lewins Mead), Lewins Mead, BS1 2PY				371647	ACM only	Private	MHCLG
30/09/2025	P_BRIS01	The Courtrooms	Bristol, City of	student	student	Remediation completed		Remediation completed	Remediation completed			01/07/2018	01/08/2018				not required							Rupert Street	Bristol	BS1 2AF	Fresh Student Living (part of Watkins Jones). Managed by Bristol University. Updated FRA approved by Avon Fire and Rescue. Building meets BR's 2016. 24/7 management. No intention to replace. Low risk.								Complete	Bristol West	E14000602	E06000023	357271	357271	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Courtrooms, Rupert Street, BS1 2AF				357271	ACM only	Private	MHCLG
30/09/2025	P_BRIS05	Waverley House	Bristol, City of	student	student	Remediation completed		Remediation completed	Remediation completed			01/09/2018					complete							Queen Charlotte Street	Bristol	BS1 1WH	Unite Students						36		Complete	Bristol West	E14000602	E06000023	260594	260594	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Waverley House, Queen Charlotte Street, BS1 1WH				260594	ACM only	Private	MHCLG
30/09/2025	P_BROM02	Northpoint	Bromley	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	11/09/2020	21/03/2022	09/02/2024	09/02/2024	11/12/2020	04/12/2020		yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		Sherman Road	London	BR1 3JN	Northpoint (Bromley) Management Company (represented by JFM Management Ltd)	Citistead Limited	Northpoint (Bromley) Management Company	Taylor Wimpey	57	57	25.2	10	Complete	Bromley and Chislehurst	E14000604	E09000006	100023630947	100023630947	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	Northpoint, Sherman Road, BR1 3JN	57	57	57	100023630947	ACM/BSF RAS reimbursements	Developer	GLA
30/09/2025	P_AYLE01	Friars House	Buckinghamshire	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	15/12/2020	15/12/2020	13/12/2021	21/12/2021	28/05/2021	21/12/2021		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		4 Great Western Street	Aylesbury	HP20 2PL	Eitan Freilich	Friars House (Aylesbury) Limited	Moorland Estates		50	50	25.7	7	Complete	Aylesbury	E14000538	E06000060	766252759	766252759	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Friars House, 4 Great Western Street, HP20 2PL	50	50	50	766252759	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_BURY01	16 St. Johns Gardens - Block C	Bury	private residential	developer	Remediation completed		Remediation completed	Remediation completed	24/08/2020	31/08/2020	19/03/2021	28/05/2021	19/03/2021	30/04/2021		yes						The Rock	16 St. Johns Gardens	Bury	BL9 0NP		THORNFIELD PROPERTIES (BURY) LIMITED	Residential Management Group	Laing O'Rourke	86		19.7		Complete	Bury North	E14000611	E08000002	4210011183	4210011183	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				16 St. Johns Gardens - Block C, 16 St. Johns Gardens, BL9 0NP	86	86	86	4210011183	ACM only	Private	MHCLG
30/09/2025	HA80105	Jumples Court	Calderdale	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2017		01/06/2018	16/07/2018				yes	HA						Jumples Close	Halifax	HX2 8NS		Together Housing Group Limited			96	94	44	16	Complete	Halifax	E14000723	E08000033	10033880997	10033880997	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Jumples Court, Jumples Close, HX2 8NS	94	96	96	10033880997	ACM only	Government	MHCLG
30/09/2025	HA80109	Mixenden Court	Calderdale	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2017		01/06/2018	16/07/2018				yes	HA						LOWER MIXENDEN	Halifax	HX2 8QH		Together Housing Group Limited			96	92	44	16	Complete	Halifax	E14000723	E08000033	10010175632	10010175632	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Mixenden Court, LOWER MIXENDEN, HX2 8QH	92	96	96	10010175632	ACM only	Government	MHCLG
30/09/2025	HA80115	Wheatley Court	Calderdale	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2017		01/07/2018	16/07/2018				yes	HA						Mixenden Road	Halifax	HX2 8QL		Together Housing Group Limited			96	96	44	16	Complete	Halifax	E14000723	E08000033		10010175741	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Wheatley Court, Mixenden Road, HX2 8QL	96	96	96	10010175741	ACM only	Government	MHCLG
30/09/2025	P_CAMB0030	Meade House, 2	Cambridge	private residential	developer	Remediation started		Remediation started	Remediation started	18/12/2023			25/12/2026											Mill Park	Cambridge	CB1 2FL						37	15		Complete	Cambridge	E14000617	E07000008			FALSE	FALSE	FALSE	FALSE	FALSE	TRUE			1	Meade House, 2, Mill Park, CB1 2FL	37	37	37		ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_CAMB01	The Belvedere (Central Tower)	Cambridge	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2020	27/07/2020	12/02/2021	01/03/2021	31/01/2021	31/01/2021		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		Homerton Street	Cambridge	CB2 8NZ	Adriatic Land	Adriatic Land	Encore estates	Highland Property Limited	139	136	18.1	10	Complete	Cambridge	E14000617	E07000008	10002568860	10002568860	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			The Belvedere (Central Tower), Homerton Street, CB2 8NZ	136	139	139	10002568860	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_WAND0288	27 Hardwicks Square	Camden	private residential	bsf	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	31/10/2022			30/09/2025											Hardwicks Square	London	SW18 4AL					63		31			Putney	E14000887	E09000007			FALSE	FALSE	FALSE	FALSE	FALSE	FALSE	1		1	27 Hardwicks Square, Hardwicks Square, SW18 4AL	63	63	63		ACM/BSF RAS reimbursements	Developer	GLA
30/09/2025	P_CAMD0744	4 Star Yard	Camden	private residential	other	Remediation plan unclear		Remediation plan unclear	Remediation plan unclear								not approved							Star Yard	London	WC2A 2JL		Raingate Limited	Yorke Property Management Ltd/ Global Holdings	Raingate Ltd		5	18.1	6	Complete	Holborn and St Pancras	E14000750	E09000007	5105928	5105928	FALSE	FALSE	FALSE	TRUE	TRUE	TRUE				4 Star Yard, Star Yard, WC2A 2JL	5	5	5	5105928	ACM only	Private	MHCLG
30/09/2025	MR LA Camden 00176	Blashford	Camden	social	social-fund	Remediation started	Cladding removed	Remediation started - cladding removed	Phase 1 complete phase 2 yet to commence	01/10/2017	22/11/2022		30/04/2026				yes	LA						Adelaide Road	London	NW3 3RX	LB Camden	London Borough of Camden			72	73	54			Hampstead and Kilburn	E14000727	E09000007	5105013	5105013	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Blashford, Adelaide Road, NW3 3RX	72	73	72	5105013	ACM only	Government	MHCLG
30/09/2025	MR LA Camden 00177	Bray	Camden	social	social-fund	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	01/10/2017	07/03/2022		30/09/2025				yes	LA						Fellows Road	London	NW3 3JX	LB Camden	London Borough of Camden			161	159	62			Hampstead and Kilburn	E14000727	E09000007	5105026	5105026	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Bray, Fellows Road, NW3 3JX	159	161	161	5105026	ACM only	Government	MHCLG
30/09/2025	MR LA Camden 00179	Burnham	Camden	social	social-fund	Remediation started	Cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	01/10/2017	08/03/2022		27/02/2026				yes	LA						Fellows Road	London	NW3 3JR	LB Camden	London Borough of Camden			161	160	62			Hampstead and Kilburn	E14000727	E09000007	5105047	5105047	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Burnham, Fellows Road, NW3 3JR	160	161	161	5105047	ACM only	Government	MHCLG
30/09/2025	MR LA Camden 00181	Dorney	Camden	social	social-fund	Remediation started	Cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	01/10/2017	07/03/2022		30/01/2026				yes	LA						Adelaide Road	London	NW3 3PP	LB Camden	London Borough of Camden			158	157	62			Hampstead and Kilburn	E14000727	E09000007	5105122	5105122	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Dorney, Adelaide Road, NW3 3PP	157	158	158	5105122	ACM only	Government	MHCLG
30/09/2025	P_CAMD03	Jury Inn Holborn	Camden	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/07/2020	01/10/2019	29/10/2020	31/07/2020				Yes							50-56 Southampton Row	London	WC1B 4AR	Jurys Inn Group	Jurys Inn & Leonardo Hotels UK and Ireland		Grange Construction	210		40			Holborn and St Pancras	E14000750	E09000007	5082317	5082317	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Jury Inn Holborn, 50-56 Southampton Row, WC1B 4AR	210	210		5082317	ACM only	Private	MHCLG
30/09/2025	MR LA Camden 00184	Taplow	Camden	social	social-fund	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	01/10/2017	07/03/2022		31/10/2025				yes	LA						Adelaide Road	London	NW3 3NY	LB Camden	London Borough of Camden			161	160	62			Hampstead and Kilburn	E14000727	E09000007	5105605	5105605	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Taplow, Adelaide Road, NW3 3NY	160	161	161	5105605	ACM only	Government	MHCLG
30/09/2025	P_CAMD01	UNITE STUDENTS ST PANCRAS	Camden	student	student	Remediation completed		Remediation completed	Remediation completed	10/05/2019	01/05/2019	09/09/2019					complete							11 ST PANCRAS WAY	London	NW1 0PT	Unite Students	UNITE	UNITE	Balfour Beatty	425		26	9	Complete	Holborn and St Pancras	E14000750	E09000007	5171702	5171702	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				UNITE STUDENTS ST PANCRAS, 11 ST PANCRAS WAY, NW1 0PT	425	425		5171702	ACM only	Private	MHCLG
30/09/2025	P_CITY01	Leonardo Royal London City Hotel	City of London	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	04/08/2020	01/08/2020	10/09/2021	31/08/2021				yes							8-10 Coopers Row	London	EC3N 2BQ	Grange Hotels	Jurys Inn & Leonardo Hotels UK and Ireland						12		Cities of London and Westminster	E14000639	E09000001	95506036	95506036	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Leonardo Royal London City Hotel, 8-10 Coopers Row, EC3N 2BQ				95506036	ACM only	Private	MHCLG
30/09/2025	P_CRAW0015	Platform	Crawley	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	05/10/2020	05/10/2020	29/01/2021	01/02/2021				yes							11 The Boulevard	Crawley	RH10 1DJ		Grey GR Limited Partnership	Live Group			184		8	Complete	Crawley	E14000652	E07000226		100062472264	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				Platform, 11 The Boulevard, RH10 1DJ	184	184	184	100062472264	ACM only	Private	MHCLG
30/09/2025	P_CRAW02	Premier Inn Hotel, London Gatwick	Crawley	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/01/2019	01/01/2019	01/05/2019	23/08/2019				yes							North Terminal	Gatwick Airport	RH6 0GQ	TowerEight on behalf of Premier Inn Hotels Ltd, Whitbread Court, Houghton Hall Business Park, Porz Avenue, Dunstable, Bedfordshire, LU5 5XE	Whitbread	TowerEight on behalf of Whitbread						Complete	Crawley	E14000652	E07000226	10024120810	10024120810	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn Hotel, London Gatwick, North Terminal, RH6 0GQ				10024120810	ACM only	Private	MHCLG
30/09/2025	P_CROY28	20 Mint Walk	Croydon	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	17/12/2020	14/12/2020	12/05/2021	07/05/2021	12/02/2021	12/02/2021		not required		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		20 Mint Walk	Croydon	CR0 1EA		David Hamilton			25	25	21	7	Complete	Croydon Central	E14000654	E09000008	100023640598	100023640598	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			20 Mint Walk, 20 Mint Walk, CR0 1EA	25	25	25	100023640598	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	HA70063	4 Leaden Hill	Croydon	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/01/2018	01/04/2018	01/06/2018	31/12/2018				yes	HA						LEADEN HILL	London	CR5 2BW		Optivo			14	14	22	6	Complete	Croydon South	E14000656	E09000008	10090927601	10090927601	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				4 Leaden Hill, LEADEN HILL, CR5 2BW	14	14	14	10090927601	ACM only	Government	MHCLG
30/09/2025	HA70065	8 Leaden Hill	Croydon	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/01/2018	01/04/2018	01/06/2018	31/12/2018				yes	HA						LEADEN HILL	London	CR5 2BZ		Optivo			31	31	18.2	7	Complete	Croydon South	E14000656	E09000008	10090927603	10090927603	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				8 Leaden Hill, LEADEN HILL, CR5 2BZ	31	31	31	10090927603	ACM only	Government	MHCLG
30/09/2025	P_CROY03	CANIUS HOUSE	Croydon	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	11/09/2023	11/09/2023	18/06/2024	18/06/2024	24/10/2023	11/06/2024		yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		1 SCARBROOK ROAD	Croydon	CR0 1FQ		Adriatic Land 5 Limited	D&GBM	Inspired Canius Limited	39	39	6	25	Complete	Croydon Central	E14000654	E09000008	10093048850	10093048850	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			CANIUS HOUSE, 1 SCARBROOK ROAD, CR0 1FQ	39	39	39	10093048850	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_CROY02	Centrillion Point	Croydon	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	24/02/2020	24/02/2020	19/11/2021	19/11/2021	08/10/2021	06/10/2021		yes							2 MASONS AVENUE	London	CR0 9WY	Wallace Estates Limited	Wallace Estates Limited	PBM (Premier Block Management)	Durkan	189	190	31.4	13	Complete	Croydon Central	E14000654	E09000008	10001008632	10001008632	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Centrillion Point, 2 MASONS AVENUE, CR0 9WY	189	190	189	10001008632	ACM only	Private	MHCLG
30/09/2025	P_CROY04	CITISCAPE	Croydon	private residential	developer	Remediation completed		Remediation completed	Phase 1 complete phase 2 yet to commence	21/01/2019	21/01/2019	23/09/2024	30/09/2024	26/06/2020		Vacant decanted	yes							25 FRITH ROAD	London	CR0 1TH	Proxima GR Properties Ltd	Proxima GR Properties	Firstport	Barratt	95	95	21.4	10		Croydon North	E14000655	E09000008	10001007587	10001007587	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				CITISCAPE, 25 FRITH ROAD, CR0 1TH	95	95		10001007587	ACM only	Private	MHCLG
30/09/2025	HA00040	Fitze Millenium Centre	Croydon	social	social-fund	Remediation completed		Remediation completed	Remediation completed	16/02/2020	17/02/2020	09/10/2020	09/10/2020				yes	HA						Sylvan Hill	London	SE19 2QF	Evolve	Evolve Housing + Support			80	80	18.2	7	Complete	Croydon North	E14000655	E09000008	10090382267	10090382267	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Fitze Millenium Centre, Sylvan Hill, SE19 2QF	80	80	80	10090382267	ACM only	Government	MHCLG
30/09/2025	P_CROY0090	The Exchange	Croydon	private residential	bsf	Remediation started		Remediation started	Remediation started	27/03/2024	25/03/2024		30/04/2026				do not know							6 Scarbrook Road	Croydon	CR0 1UH		The Exchange RtM Co Ltd.				66		7	Complete	Croydon Central	E14000654	E09000008	10014050884	10014050884	FALSE	FALSE	FALSE	FALSE	TRUE	TRUE	1			The Exchange, 6 Scarbrook Road, CR0 1UH	66	66	66	10014050884	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_DACO01	Hemel Central Premier Inn	Dacorum	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/02/2019	01/02/2019	01/05/2019	02/09/2019				yes						Riverside	Moor End Road	Hemel Hempstead	HP1 1DL	Whitbread	Akaria Investments	TowerEight	Barratt	120		25			Hemel Hempstead	E14000739	E07000096	10002010705	10002010705	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Hemel Central Premier Inn, Moor End Road, HP1 1DL	120	120		10002010705	ACM only	Private	MHCLG
30/09/2025	LA10090	Silverwood House	Doncaster	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017		01/04/2018	02/05/2018				complete	LA						Elsworth Close	Doncaster	DN1 3RN	Doncaster Metropolitan Borough Council	Doncaster Metropolitan Borough Council			129	129	46	17	Complete	Doncaster Central	E14000668	E08000017	100052238157	100052238157	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Silverwood House, Elsworth Close, DN1 3RN	129	129	129	100052238157	ACM/CSS crossovers	Government	MHCLG
30/09/2025	P_EALI03	Arc Tower	Ealing	private residential	private-fund	Remediation started		Remediation started	Remediation started	16/12/2020	14/12/2020		23/01/2026		29/08/2025		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	TRUE		32 Uxbridge Road	London	W5 2SN	Adriatic Land	Adriatic Land	Residential Management Group	Frogmore Estates	95	93	57	20	Complete	Ealing Central and Acton	E14000674	E09000009	12178860	12178860	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Arc Tower, 32 Uxbridge Road, W5 2SN	93	95	95	12178860	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_EALI07	Premier Inn And Data Centre	Ealing	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	13/07/2020	13/07/2020	14/01/2021	01/03/2021				yes							24 Uxbridge Road	London	W5 2RJ	Leaseholder - Premier Inn Ltd Landlord- Viper Ltd, First Names House, Victoria Road, Douglas, Isle of Man	Red Wire Data Centre	TowerEight				20		Complete	Ealing Central and Acton	E14000674	E09000009	12175307	12175307	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn And Data Centre, 24 Uxbridge Road, W5 2RJ				12175307	ACM only	Private	MHCLG
30/09/2025	P_EALI06	Trs Apartments	Ealing	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	22/07/2020	22/07/2019	18/11/2020	17/11/2020				yes							The Green	London	UB2 4FF		TRS ASSET Management LIMITED	London Block Management	TRS Asset Management Ltd	149	149	29.6		Complete	Ealing Southall	E14000676	E09000009	12175908	12175908	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Trs Apartments, The Green, UB2 4FF	149	149	149	12175908	ACM only	Private	MHCLG
30/09/2025	P_EALI05	Woodward Buildings	Ealing	student	student	Remediation completed		Remediation completed	Remediation completed	10/12/2020	07/12/2020	09/03/2022	28/02/2022	14/01/2022	14/01/2022		yes							1 Victoria Road	London	W3 6FA	Imperial College	Imperial College London	Meedhurst Project Management	Berkeley	691		51	19	Complete	Ealing Central and Acton	E14000674	E09000009	12010434	12010434	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Woodward Buildings, 1 Victoria Road, W3 6FA	691	691		12010434	ACM only	Private	MHCLG
30/09/2025	P_ELMB01	The Heart	Elmbridge	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	18/12/2020	14/12/2020	14/04/2022	11/04/2022	13/02/2022	20/01/2022		not required		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		New Zealand Avenue	Walton On Thames	KT12 1GH	O and H	Elmbridge Borough Council	Savills		379	379	18.3	7	Complete	Esher and Walton	E14000697	E07000207	10095342938	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			The Heart, New Zealand Avenue, KT12 1GH	379	379	379	10095342938	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_EPPI01	10 Landmark House	Epping Forest	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/06/2020	01/06/2020	27/11/2020	29/01/2021	30/11/2020	30/11/2020		yes							The Broadway	Loughton	IG10 3SX	Higgins Homes	EPPING FOREST DISTRICT COUNCIL OF Civic Offices		Higgins Homes	64		21	7	Complete	Epping Forest	E14000693	E07000072	10093180509	10093180509	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				10 Landmark House, The Broadway, IG10 3SX	64	64	64	10093180509	ACM only	Private	MHCLG
30/09/2025	NHS00013	Emergency Care Centre	Gateshead	public	public	Remediation completed		Remediation completed	Remediation completed	05/02/2020	05/02/2020	20/11/2020	12/12/2020				yes							Queen Elizabeth Avenue	Gateshead	NE9 6SX	Gateshead Health NHS Foundation Trust	Gateshead Health NHS Foundation Trust								Gateshead	E14000709	E08000037	100000529682	100000529682	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Emergency Care Centre, Queen Elizabeth Avenue, NE9 6SX				100000529682	ACM only	Private	MHCLG
30/09/2025	P_GREE04	Babbage Point	Greenwich	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	10/06/2019	01/06/2019	19/12/2019	19/12/2019	19/12/2019	19/12/2019		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		20 Norman Road	London	SE10 9FA	Brendan Sarsfield (CEO)	Glenageary Estates Llp	Glengeary Estates	Glenageary Estates Llp	90	85		8	Complete	Greenwich and Woolwich	E14000718	E09000011	100023228493	100023228493	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Babbage Point, 20 Norman Road, SE10 9FA	85	90	90	100023228493	ACM only	Government	GLA
30/09/2025	P_GREE0096	Block A, Daniel Defoe Hall	Greenwich	student	student	Remediation completed		Remediation completed	Remediation completed	18/11/2024	18/11/2024	26/11/2024	28/02/2025									FALSE		10 Lovibond Lane	London	SE10 9FY										Greenwich and Woolwich	E14000718	E09000011	10010254325	10010254325	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE				Block A, Daniel Defoe Hall, 10 Lovibond Lane, SE10 9FY				10010254325	ACM only	Private	MHCLG
30/09/2025	P_GREE01	Novotel Greenwich	Greenwich	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/02/2019	01/02/2019	01/05/2019	30/09/2019				yes							Greenwich High Road	London	SE10 8JA	Accor Hotels	Accorinvest	Accorinvest						Complete	Greenwich and Woolwich	E14000718	E09000011	200001082722	200001082722	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Novotel Greenwich, Greenwich High Road, SE10 8JA				200001082722	ACM only	Private	MHCLG
30/09/2025	P_GREE0224	Union House	Greenwich	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	30/11/2020	30/11/2020	23/08/2021	16/09/2021	07/05/2021	14/05/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		11 Bunton Street	London	SE18 6LS		GRANGEWALK DEVELOPMENTS LIMITED			17	17	19	7	Complete	Greenwich and Woolwich	E14000718	E09000011	10010231520	10010231520	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Union House, 11 Bunton Street, SE18 6LS	17	17	17	10010231520	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_GREE27	City Peninsula	Greenwich	private residential	developer	Remediation started		Remediation started	Remediation started	22/09/2020	21/09/2020		27/03/2026		28/04/2023		yes						City Peninsula	25 Barge Walk	London	SE10 0FN	Bellway	GLA LAND AND PROPERTY LIMITED	Pinnacle Places	Bellway	229	177	22.9		Complete	Greenwich and Woolwich	E14000718	E09000011	10010237522	10010237522	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	City Peninsula, 25 Barge Walk, SE10 0FN	177	229	229	10010237522	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE05	Barquentine Heights	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	24/08/2020	22/08/2020	15/01/2021	15/01/2021				not required						Greenwich Millennium Village	4 Peartree Way	London	SE10 0GU	GLA LAND AND PROPERTY LIMITED	GLA LAND AND PROPERTY LIMITED	Rendall and Rittner	Joint Venture (GMVL) Taylor Wimpey and Countryside	74	71			Complete	Greenwich and Woolwich	E14000718	E09000011	10010244734	10010244734	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Barquentine Heights, 4 Peartree Way, SE10 0GU	71	74	74	10010244734	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE17	Landmann Point	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	24/08/2020	22/08/2020	15/01/2021	15/01/2021				not required						Greenwich Millennium Village	6 Peartree Way	London	SE10 0GW	GLA LAND AND PROPERTY LIMITED	GLA LAND AND PROPERTY LIMITED	Rendall and Rittner	Joint Venture (GMVL) Taylor Wimpey and Countryside	74	72			Complete	Greenwich and Woolwich	E14000718	E09000011	10010244735	10010244735	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Landmann Point, 6 Peartree Way, SE10 0GW	72	74	74	10010244735	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE10	Swiftstone Tower	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	24/08/2020	22/08/2020	21/12/2020	21/12/2020				not required						Greenwich Millennium Village	2 Peartree Way	London	SE10 0GT	GLA LAND AND PROPERTY LIMITED	GLA LAND AND PROPERTY LIMITED	Rendall and Rittner	Joint Venture (GMVL) Taylor Wimpey and Countryside	37	37			Complete	Greenwich and Woolwich	E14000718	E09000011	10010244737	10010244737	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Swiftstone Tower, 2 Peartree Way, SE10 0GT	37	37	37	10010244737	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE20	1 Hawthorne Crescent	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/04/2019	01/04/2019	09/07/2020	31/07/2019				Yes						Greenwich Square	Hawthorne Crescent	London	SE10 9GA	Mace	GLA LAND AND PROPERTY LIMITED	Ringley	Mace	139	26			Complete	Greenwich and Woolwich	E14000718	E09000011	10010248262	10010248262	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				1 Hawthorne Crescent, Hawthorne Crescent, SE10 9GA	26	139	139	10010248262	ACM only	Private	MHCLG
30/09/2025	P_GREE25	1 Hazel Lane	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	06/01/2020	01/10/2019	11/03/2021	03/03/2021	22/12/2020	03/02/2021		yes						Greenwich Square	Hazel Lane	London	SE10 9FZ	Mace	GLA LAND AND PROPERTY LIMITED	Ringley	Mace	123	38			Complete	Greenwich and Woolwich	E14000718	E09000011	10010245697	10010245697	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				1 Hazel Lane, Hazel Lane, SE10 9FZ	38	123	123	10010245697	ACM only	Private	MHCLG
30/09/2025	P_GREE21	11 Lambarde Square	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/04/2019	29/04/2019	05/06/2020	30/07/2020				yes						Greenwich Square	3 Woolwich Road	London	SE10 9GF	Mace	GLA LAND AND PROPERTY LIMITED	Ringley	Mace	36	32			Complete	Greenwich and Woolwich	E14000718	E09000011	10010248296	10010248296	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				11 Lambarde Square, 3 Woolwich Road, SE10 9GF	32	36	36	10010248296	ACM only	Private	MHCLG
30/09/2025	P_GREE18	120 Vanbrugh Hill	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/04/2019	01/04/2019	24/07/2020	31/07/2020				Yes						Greenwich Square	Vanbrugh Hill	London	SE10 9HB	Mace	GLA LAND AND PROPERTY LIMITED	Ringley	Mace	77	27			Complete	Greenwich and Woolwich	E14000718	E09000011	10010248495	10010248495	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				120 Vanbrugh Hill, Vanbrugh Hill, SE10 9HB	27	77	77	10010248495	ACM only	Private	MHCLG
30/09/2025	P_GREE23	2 Fenton Parade	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	06/01/2020	01/10/2019	11/03/2021	03/03/2021	06/10/2020	06/10/2020		yes						Greenwich Square	Woolwich Road	London	SE10 0FY	Mace	GLA LAND AND PROPERTY LIMITED	Ringley	Mace	123	36			Complete	Greenwich and Woolwich	E14000718	E09000011	10010248380	10010248380	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				2 Fenton Parade, Woolwich Road, SE10 0FY	36	123	123	10010248380	ACM only	Private	MHCLG
30/09/2025	P_GREE19	4 Lambarde Square	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	31/10/2018	01/04/2019	08/11/2019	31/07/2020				yes						Greenwich Square	3 Woolwich Road	London	SE10 9GB	Mace	GLA LAND AND PROPERTY LIMITED	Ringley	Mace	36	48			Complete	Greenwich and Woolwich	E14000718	E09000011	10010248291	10010248291	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				4 Lambarde Square, 3 Woolwich Road, SE10 9GB	36	48	36	10010248291	ACM only	Private	MHCLG
30/09/2025	P_GREE22	8 Lambarde Square	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/04/2019	30/08/2019	18/12/2019	31/07/2020				yes						Greenwich Square	3 Woolwich Road	London	SE10 9GB	Mace	GLA LAND AND PROPERTY LIMITED	Ringley	Mace	36	36			Complete	Greenwich and Woolwich	E14000718	E09000011	10010248421	10010248421	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				8 Lambarde Square, 3 Woolwich Road, SE10 9GB	36	36	36	10010248421	ACM only	Private	MHCLG
30/09/2025	P_GREE24	9 Hazel Lane	Greenwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	06/01/2020	01/10/2019	11/03/2021	03/03/2021	22/12/2020	03/02/2021		yes						Greenwich Square	Hazel Lane	London	SE10 9FZ	Mace	GLA LAND AND PROPERTY LIMITED	Ringley	Mace	123	36			Complete	Greenwich and Woolwich	E14000718	E09000011	10010248186	10010248186	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				9 Hazel Lane, Hazel Lane, SE10 9FZ	36	123	123	10010248186	ACM only	Private	MHCLG
30/09/2025	P_GREE02	Admirals Tower	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	19/06/2020	19/09/2020	18/05/2021	28/05/2021	10/05/2021			yes						New Capital Quay	8 Dowells Street	London	SE10 9FQ	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes	136	136	38.6		Complete	Greenwich and Woolwich	E14000718	E09000011	10010242100	10010242100	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Admirals Tower, 8 Dowells Street, SE10 9FQ	136	136	136	10010242100	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE06	Beacon Point	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	23/09/2019	29/10/2019	02/11/2020	02/11/2020				yes						New Capital Quay	12 Dowells Street	London	SE10 9DX	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes	122	112	28.1		Complete	Greenwich and Woolwich	E14000718	E09000011	10010242306	10010242306	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Beacon Point, 12 Dowells Street, SE10 9DX	112	122	122	10010242306	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE07	Canary View	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	08/12/2019	27/08/2019	09/09/2020	14/09/2020				yes						New Capital Quay	23 Dowells Street	London	SE10 9DY	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes	93	93	35.4		Complete	Greenwich and Woolwich	E14000718	E09000011	10010242433	10010242433	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Canary View, 23 Dowells Street, SE10 9DY	93	93	93	10010242433	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE09	Dundas Court	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	17/06/2019	29/07/2019	11/08/2020	21/08/2020				yes						New Capital Quay	29 Dowells Street	London	SE10 9EA	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes	79	79	35.4		Complete	Greenwich and Woolwich	E14000718	E09000011	10010242548	10010242548	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Dundas Court, 29 Dowells Street, SE10 9EA	79	79	79	10010242548	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE11	Empire Reach	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	09/03/2020	01/07/2020	18/12/2020	18/12/2020				yes						New Capital Quay	4 Dowells Street	London	SE10 9EB	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes	75	66	25.1		Complete	Greenwich and Woolwich	E14000718	E09000011	10010242835	10010242835	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Empire Reach, 4 Dowells Street, SE10 9EB	66	75	75	10010242835	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE28	Freemantle House	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	20/01/2020	26/03/2020	02/11/2020	02/11/2020				yes						New Capital Quay	37 Dowells Street	London	SE10 9FE	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes		84		10	Complete	Greenwich and Woolwich	E14000718	E09000011	10010242746	10010242746	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Freemantle House, 37 Dowells Street, SE10 9FE	84	84	84	10010242746	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE12	Gladstone House	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	25/11/2019	06/01/2020	06/10/2020	01/02/2021				yes						New Capital Quay	31 Dowells Street	London	SE10 9FF	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes	197	107	21.2		Complete	Greenwich and Woolwich	E14000718	E09000011	10010242631	10010242631	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Gladstone House, 31 Dowells Street, SE10 9FF	107	197	197	10010242631	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE13	Hargood House	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed		24/06/2019	18/05/2021	02/03/2020				yes						New Capital Quay	7 Norway Street	London	SE10 9FG	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes	59	59	26.6			Greenwich and Woolwich	E14000718	E09000011	10010242241	10010242241	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE			1	Hargood House, 7 Norway Street, SE10 9FG	59	59	59	10010242241	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_GREE15	Jubilee Court	Greenwich	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	25/02/2019	25/02/2019	12/12/2019	01/09/2021				yes						New Capital Quay	76 Thames Street	London	SE10 9FH	Galliard Homes	Galliard Homes Limited	PMM	Galliard Homes	195	187	35		Complete	Greenwich and Woolwich	E14000718	E09000011	10010241909	10010241909	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Jubilee Court, 76 Thames Street, SE10 9FH	187	195	195	10010241909	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_MANC0092	Castlegate Apartments	Manchester	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	17/12/2020	20/06/2022	08/04/2025	14/04/2025	10/07/2024	31/01/2024		yes		HE	19. Practical completion - Retention Period (12m)	Applications approved: for full costs	TRUE		2 Chester Road	Manchester	M15 4QG		The Manchester Ground Rent Company Ltd	Rendall and Rittner	Barratt	84	84	18	8	Complete	Manchester Central	E14000807	E08000003	10023059982	10023059982	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	Castlegate Apartments, 2 Chester Road, M15 4QG	84	84	84	10023059982	ACM/BSF RAS reimbursements	Developer	HE
30/09/2025	HA99076	Burbage House	Hackney	social	social	Remediation completed		Remediation completed	Remediation completed	03/11/2020	02/11/2020	20/08/2021	13/08/2021	19/02/2021	19/02/2021		yes	HA						Poole Street	London	N1 5ES	Islington and Shoreditch Housing Association	Islington and Shoreditch Housing Association			27	23	21.75	7	Complete	Hackney South and Shoreditch	E14000721	E09000012	100023651137	100023651137	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Burbage House, Poole Street, N1 5ES	23	27	27	100023651137	ACM only	Social	MHCLG
30/09/2025	P_HACK0012	Gainsborough Studios East & South	Hackney	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	29/03/2021	29/03/2021	16/12/2021	17/12/2021	21/10/2021	21/10/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		1 Poole Street	London	N1 5EE		Gainsborough Studios Ltd	IDM Property Management		142	140		8	Complete	Hackney South and Shoreditch	E14000721	E09000012	10008239941	10008239941	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Gainsborough Studios East & South, 1 Poole Street, N1 5EE	140	142	142	10008239941	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_HACK08	Gainsborough Studios West	Hackney	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	18/05/2020	30/11/2020	30/06/2021	02/07/2021	30/06/2021	30/06/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		1 Poole Street	London	N1 5EA		Gainsborough Studios Limited	IDM Property Management		76	76	35	12	Complete	Hackney South and Shoreditch	E14000721	E09000012	10008289343	10008289343	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Gainsborough Studios West, 1 Poole Street, N1 5EA	76	76	76	10008289343	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	HA99077	Lyme Grove House	Hackney	social	social-fund	Remediation completed		Remediation completed	Remediation completed	25/02/2019	24/02/2019	01/08/2019	01/08/2019				yes	HA						LODDIGES ROAD	London	E9 6FF	Islington and Shoreditch Housing Association	Islington and Shoreditch Housing Association			27		21	7	Complete	Hackney South and Shoreditch	E14000721	E09000012	100023650526	100023650526	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Lyme Grove House, LODDIGES ROAD, E9 6FF	27	27	27	100023650526	ACM only	Government	MHCLG
30/09/2025	P_HACK07	Regal Wharf	Hackney	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/12/2020	07/12/2020	17/08/2021	02/08/2021	01/07/2021	31/03/2021		yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		De Beauvoir Crescent	London	N1 5TZ	Regal Homes				80	21	22	7	Complete	Hackney South and Shoreditch	E14000721	E09000012	10008326523	10008326523	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Regal Wharf, De Beauvoir Crescent, N1 5TZ	21	80	80	10008326523	ACM only	Government	GLA
30/09/2025	Genesis01	Riverside Apartments	Hackney	social	developer	Remediation completed		Remediation completed	Remediation completed	01/07/2017		01/07/2018	01/09/2018				complete	HA						Coster Avenue	London	N4 2BA	Notting Hill Genesis	Notting Hill Genesis		Berkeley		63		23	Incomplete - requires follow up	Hackney North and Stoke Newington	E14000720	E09000012	10008326112	10008326112	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Riverside Apartments, Coster Avenue, N4 2BA	63	63	63	10008326112	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_HACK0036	Sky Apartments	Hackney	private residential	developer	Remediation completed		Remediation completed	Remediation completed															Homerton Road	London	E9 5FA						87	42.9		Complete	Hackney South and Shoreditch	E14000721	E09000012	10008325710	10008325710	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE			1	Sky Apartments, Homerton Road, E9 5FA	87	87	87	10008325710	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_HACK05	Soda Studios	Hackney	private residential	private-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	26/02/2024	26/02/2024		10/10/2025	31/10/2024			yes		GLA	8.3. Pre-Tender support costs paid	Applications approved: for pre-contract support	TRUE		260-268 Kingsland Road	London	E8 4DG		Investland Ltd	Live Let Ltd			51	22		Complete	Hackney South and Shoreditch	E14000721	E09000012		10008317696	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			Soda Studios, 260-268 Kingsland Road, E8 4DG	51	51	51	10008317696	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_HACK0289	Vanguard House	Hackney	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	31/03/2021	31/03/2021	27/09/2021	17/09/2021	23/08/2021	23/08/2021		not required		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		70 Martello Street	London	E8 3QQ		Proxima GR Properties Limited	Urang Group	Barratts (2005)	81	69	51	16	Complete	Hackney South and Shoreditch	E14000721	E09000012	10008294872	10008294872	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Vanguard House, 70 Martello Street, E8 3QQ	69	81	81	10008294872	ACM RAS reimbursements	Developer	GLA
30/09/2025	P_HACK01	Emerald Apartments	Hackney	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/03/2018	20/12/2020	31/03/2018	31/03/2018	03/04/2018	03/04/2018		complete						Matchmakers Wharf	Homerton Road	London	E9 5FF	Rendall and Rittner	Adriatic Land	Rendall and Rittner	Telford Homes	81	28	44.3	9	Complete	Hackney South and Shoreditch	E14000721	E09000012	10008325899	10008325899	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Emerald Apartments, Homerton Road, E9 5FF	28	81	81	10008325899	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_HACK02	Jade Apartments	Hackney	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/03/2018	20/12/2020	31/03/2018	31/03/2018	03/04/2018	03/04/2018		complete						Matchmakers Wharf	Homerton Road	London	E9 5GN	Rendall and Rittner	Adriatic Land	Rendall and Rittner	Telford Homes	91	32	22.1	9	Complete	Hackney South and Shoreditch	E14000721	E09000012	10008325793	10008325793	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Jade Apartments, Homerton Road, E9 5GN	32	91	91	10008325793	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_HACK03	Opal Apartments	Hackney	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/03/2018	20/12/2020	31/03/2018	31/03/2018	03/04/2018	03/04/2018		complete						Matchmakers Wharf	Homerton Road	London	E9 5GP	Rendall and Rittner	Adriatic Land	Rendall and Rittner	Telford Homes	81	39	18.5	9	Complete	Hackney South and Shoreditch	E14000721	E09000012	10008325829	10008325829	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Opal Apartments, Homerton Road, E9 5GP	39	81	81	10008325829	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	HA99672	CAIRNS HOUSE	Hammersmith and Fulham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	20/09/2021	20/09/2021	30/06/2023	30/06/2023	12/11/2021	12/11/2021		yes	HA						291 WANDSWORTH BRIDGE ROAD	Fulham	SW6 2NX	Shepherds Bush Housing Association	Shepherds Bush Housing Association			26	26	17.9	7	Complete	Chelsea and Fulham	E14000629	E09000013	34141271	34141271	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			CAIRNS HOUSE, 291 WANDSWORTH BRIDGE ROAD, SW6 2NX	26	26	26	34141271	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	NottingHill01	Cranston Court	Hammersmith and Fulham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/01/2018		08/07/2019	21/06/2019				not required	HA						56 Bloemfontein Road	London	W12 7FG	Notting Hill Genesis	Notting Hill Genesis			175	170	18	7	Complete	Hammersmith	E14000726	E09000013	34152587	34152587	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Cranston Court, 56 Bloemfontein Road, W12 7FG	170	175	175	34152587	ACM only	Government	MHCLG
30/09/2025	P_HAMM01	Doubletree Hilton Hotel	Hammersmith and Fulham	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	04/12/2020	04/12/2020	30/07/2021	29/07/2021	25/06/2021	25/06/2021		yes							Imperial Road	London	SW6 2GA	St George Ltd Berkeley House 19 Portsmouth Road Cobham Surrey KT11 1JG	St George	Amaris Hospitality Limited	Berkeley						Chelsea and Fulham	E14000629	E09000013		34137244	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Doubletree Hilton Hotel, Imperial Road, SW6 2GA				34137244	ACM only	Private	MHCLG
30/09/2025	HA99673	DWYER HOUSE	Hammersmith and Fulham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	20/09/2021	20/09/2021	30/06/2023	23/06/2023	14/01/2022	26/01/2022		yes	HA						2 TOWNMEAD ROAD	Fulham	SW6 2NZ	Shepherds Bush Housing Association	Shepherds Bush Housing Association			26	26	17.9	7	Complete	Chelsea and Fulham	E14000629	E09000013	34141346	34141346	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			DWYER HOUSE, 2 TOWNMEAD ROAD, SW6 2NZ	26	26	26	34141346	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_HAMM02	Glenbrook Apartments	Hammersmith and Fulham	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/10/2019		12/11/2020	12/11/2020				not required							85 Glenthorne Road	London	W6 0DJ	Appleglass Properties Ltd, PO Box 1075 Elizabeth House 9 Castle Street St Helier Jersey SE4 2QP	Appleglass Properties Ltd		Loncors Homes	52	52	18.65	6		Hammersmith	E14000726	E09000013	34158276	34158276	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Glenbrook Apartments, 85 Glenthorne Road, W6 0DJ	52	52	52	34158276	ACM only	Private	MHCLG
30/09/2025	HA35001	KELWAY HOUSE	Hammersmith and Fulham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	27/09/2021	27/09/2021	11/12/2023	07/12/2023				yes	HA						162 NORTH END ROAD	London	W14 9PR	Shepherds Bush Housing Association	Shepherds Bush Housing Association			50	50	19.1	7	Complete	Hammersmith	E14000726	E09000013	34142167	34142167	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			KELWAY HOUSE, 162 NORTH END ROAD, W14 9PR	50	50	50	34142167	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	S_HARI0082	67-96 Communal Roden Court-HORNSE679600	Haringey	social	social-fund	Remediation completed		Remediation completed	Remediation completed	14/01/2019	30/11/2018	10/10/2019	30/09/2019				yes	HA						Roden Court	London	N6 5FD								7	Complete	Hornsey and Wood Green	E14000752	E09000014	100023657656	100023657656	FALSE	FALSE	FALSE	FALSE	TRUE	TRUE		1		67-96 Communal Roden Court-HORNSE679600, Roden Court, N6 5FD				100023657656	ACM/CSS crossovers - transferred from BSF	Government	MHCLG
30/09/2025	HA99440	Albemarle Court	Haringey	social	social-fund	Remediation completed		Remediation completed	Remediation completed	30/03/2020	16/03/2020	17/12/2021	17/12/2021	02/07/2021	23/09/2021		yes	HA						WATERSIDE WAY	London	N17 9FW		Newlon Housing Trust			110	110	23	7	Complete	Tottenham	E14001002	E09000014	10090477566	10090477566	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Albemarle Court, WATERSIDE WAY, N17 9FW	110	110	110	10090477566	ACM only	Government	MHCLG
30/09/2025	HA99436	Ambrose Court	Haringey	social	social-fund	Remediation completed		Remediation completed	Remediation completed	18/11/2019	11/10/2018	30/11/2020	30/11/2020				yes	HA						CANNON ROAD	London	N17 8EU		Newlon Housing Trust			57	57	28	9	Complete	Tottenham	E14001002	E09000014	10090478407	10090478407	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Ambrose Court, CANNON ROAD, N17 8EU	57	57	57	10090478407	ACM only	Government	MHCLG
30/09/2025	HA99410	Coppermill Heights	Haringey	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2017	09/01/2019	30/09/2019	21/06/2019				yes	HA						2 Daneland Walk	London	N17 9FF		Newlon Housing Trust			154	112	28	8	Complete	Tottenham	E14001002	E09000014	10022943089	10022943038	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Coppermill Heights, 2 Daneland Walk, N17 9FF	112	154	154	10022943089	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	Newlon01	Mallory Court	Haringey	social	social-fund	Remediation completed		Remediation completed	Remediation completed	18/11/2019	11/10/2018	30/11/2020	30/11/2020				yes	HA						CANNON ROAD	London	N17 8ET		Newlon Housing Trust			44	44	19	6	Complete	Tottenham	E14001002	E09000014	10090478362	10090478362	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Mallory Court, CANNON ROAD, N17 8ET	44	44	44	10090478362	ACM only	Government	MHCLG
30/09/2025	P_HARI02	Premier Inn Tottenham Hale	Haringey	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/08/2018	01/08/2018	04/07/2022	27/05/2022	20/10/2021	08/09/2021		yes							Station Road	London	N17 9LR							29.2		Complete	Tottenham	E14001002	E09000014	10094748204	10094748204	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn Tottenham Hale, Station Road, N17 9LR				10094748204	ACM only	Private	MHCLG
30/09/2025	HA99437	Rivers Apartments	Haringey	social	social-fund	Remediation completed		Remediation completed	Remediation completed	18/11/2019	11/10/2018	19/02/2021	26/02/2021	19/02/2021	19/02/2021		yes	HA						CANNON ROAD	London	N17 8FE		Newlon Housing Trust			100	100	70	22	Complete	Tottenham	E14001002	E09000014	10090478361	10090478361	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Rivers Apartments, CANNON ROAD, N17 8FE	100	100	100	10090478361	ACM only	Government	MHCLG
30/09/2025	P_HARI01	Roden Court Communal Area 1-66 - HORNSE019600	Haringey	social	social-fund	Remediation completed		Remediation completed	Remediation completed	14/01/2019	30/11/2018	10/10/2019	30/09/2019				yes	HA						Hornsey Lane	London	N6 5EF	Richard Hill	One Housing Group Limited	One Housing Group	Galliford Homes	136	136	21	10	Incomplete - requires follow up	Hornsey and Wood Green	E14000752	E09000014	100023657657	100023657656	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Roden Court Communal Area 1-66 - HORNSE019600, Hornsey Lane, N6 5EF	136	136	136	100023657657	ACM/CSS crossovers - transferred from BSF	Government	MHCLG
30/09/2025	P_HARR01	Bradstowe House	Harrow	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	30/11/2020	30/11/2020	20/06/2022	20/06/2022	31/03/2022	08/04/2022		yes							Headstone Road	London	HA1 1EH	Mary Hamilton (PGIM, on behalf of Hincroft)	Comer Homes (Hincroft Ltd)	Greystar	Comer Homes	88	177			Incomplete - requires follow up	Harrow West	E14000732	E09000015	10070263245	10070263245	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Bradstowe House, Headstone Road, HA1 1EH	88	177	88	10070263245	ACM only	Private	MHCLG
30/09/2025	P_HARR02	Spire House	Harrow	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	14/12/2020	14/12/2020	05/10/2022	30/09/2022	24/06/2022	24/06/2022		complete		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		1 Peterborough Road	Harrow	HA1 2HF		Three M's Harrow Ltd			18	18	22	7	Incomplete - requires follow up	Harrow West	E14000732	E09000015		10070263103	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				Spire House, 1 Peterborough Road, HA1 2HF	18	18	18	10070263103	ACM only	Government	GLA
30/09/2025	HA60010	Vickers House	Havering	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/07/2017	30/07/2018	19/02/2019	01/01/2019				yes	HA						365 SOUTH STREET	London	RM1 2BP	Estuary Housing Association Ltd	Estuary Housing Association Ltd			93	93	26	10	Complete	Romford	E14000900	E09000016	10024389667	10024389667	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Vickers House, 365 SOUTH STREET, RM1 2BP	93	93	93	10024389667	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_HILL0057	The Gatefold Building	Hillingdon	private residential	other	Plans in place		Plans in place	Plans in place		06/04/2026		30/04/2027		22/05/2026		no							36 Blyth Road	London	UB3 1AJ		Saltgate (UK) Ltd	APO Group/BEHERE HAYES			132	19.27	7		Hayes and Harlington	E14000737	E09000017			FALSE	FALSE	FALSE	FALSE	TRUE	TRUE				The Gatefold Building, 36 Blyth Road, UB3 1AJ	132	132	132		ACM only	Private	MHCLG
30/09/2025	HA33004	Norwich Union House - Now Movia Appartments	Hillingdon	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2018	23/07/2018	26/04/2019	01/03/2019				yes	HA						1-3 Bakers Road	London	UB8 1RG	Inquilab Housing Assoication	Inquilab Housing Association			37		29	9	Complete	Uxbridge and South Ruislip	E14001007	E09000017	10093733344	10093733344	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Norwich Union House - Now Movia Appartments, 1-3 Bakers Road, UB8 1RG	37	37	37	10093733344	ACM only	Government	MHCLG
30/09/2025	P_HOUN05	Premier Inn - London Heathrow T4	Hillingdon	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/03/2019	01/03/2019	04/09/2020	29/02/2020				yes							Sheffield Road,	Hounslow	TW6 3SY	Whitbread	Whitbread	TowerEight on behalf of Whitbread				26	8	Complete	Hayes and Harlington	E14000737	E09000017		10009947928	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn - London Heathrow T4, Sheffield Road,, TW6 3SY				10009947928	ACM only	Private	MHCLG
30/09/2025	LA00142	Clements Court	Hounslow	social	social-fund	Remediation completed		Remediation completed	Remediation completed	05/08/2017	05/08/2017	01/10/2017	27/10/2017				complete	LA						Green Lane	London	TW4 6ED		London Borough of Hounslow			78	78	32	13	Complete	Feltham and Heston	E14000701	E09000018	100023662397	100023662397	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Clements Court, Green Lane, TW4 6ED	78	78	78	100023662397	ACM only	Government	MHCLG
30/09/2025	P_HOUN03	Park Grand Hotel	Hounslow	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	29/07/2019		13/02/2020	28/02/2020				yes							Great West Road	London	TW5 0BU	RED GATE PROPERTIES LIMITED - Third Floor, 37 Esplanade St Helier Jersey JE2 3QA	Redgate Property Ltd	Precis Management Services Ltd					7	Complete	Feltham and Heston	E14000701	E09000018	100023405365	100023405365	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Park Grand Hotel, Great West Road, TW5 0BU				100023405365	ACM only	Private	MHCLG
30/09/2025	P_HOUN01	Premier Inn Brentford	Hounslow	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/02/2019	01/02/2019	01/05/2019	01/07/2019				yes							Great West Road	London	TW8 9AD	Ropemaker Properties Ltd - Whitbread group PLC	Whitbread	TowerEight				29.84	10	Complete	Brentford and Isleworth	E14000593	E09000018	10091692517	10091692517	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn Brentford, Great West Road, TW8 9AD				10091692517	ACM only	Private	MHCLG
30/09/2025	P_HOUN02	The Blenheim Centre	Hounslow	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	15/04/2019	01/04/2019	01/11/2019	30/11/2019				yes						The Blenheim Centre	Prince Regent Road	Hounslow	TW3 1NB	Barratt	Legal and General	Rendall and Rittner	Barratt	334	334	20.3			Brentford and Isleworth	E14000593	E09000018	10024281599	10024281599	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	The Blenheim Centre, Prince Regent Road, TW3 1NB	334	334	334	10024281599	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_PORT02	Greetham Street	Portsmouth	student	student	Remediation completed		Remediation completed	Remediation completed	17/01/2024	15/01/2024	07/05/2025	07/05/2025	28/03/2025	29/11/2024		yes							Greetham Street	Portsmouth	PO5 4FB		USAF NOMINEE NO.1 LIMITED (Co. Regn. No. 05855598) and USAF NOMINEE NO.1A LIMITED (Co. Regn. No. 05835512)	Unite Group PLC	DMWR Architects Limited				24	Complete	Portsmouth South	E14000884	E06000044		1775122095	FALSE	FALSE	FALSE	FALSE	TRUE	TRUE				Greetham Street, Greetham Street, PO5 4FB				1775122095	ACM only	Private	MHCLG
30/09/2025	HA00541	253 Hungerford Road (Bridge Academy)	Islington	social	social-fund	Remediation completed		Remediation completed	Remediation completed	24/08/2020	31/08/2020	16/08/2021	13/08/2021	17/03/2021	17/03/2021		yes	LA						Hungerford Road	London	N7 9LL		London Borough of Islington		Taylor Wimpey	38	38	18			Islington South and Finsbury	E14000764	E09000019	10012788886	10012788886	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	253 Hungerford Road (Bridge Academy), Hungerford Road, N7 9LL	38	38	38	10012788886	ACM RAS reimbursements	Developer	MHCLG
30/09/2025	MR HA Notting Hill 00043	25B Goswell Road	Islington	social	developer	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	18/03/2020	31/08/2019		31/12/2026	27/03/2020	27/03/2020		yes	HA						GOSWELL ROAD	London	EC1M 7AJ	Notting Hill Genesis	Barts Hospital Trust and Surrey Trust Corporation		Ardmore	62	61	27	9	Incomplete - requires follow up	Islington South and Finsbury	E14000764	E09000019	10012790448	10012790448	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				25B Goswell Road, GOSWELL ROAD, EC1M 7AJ	61	62	62	10012790448	ACM only	Private	MHCLG
30/09/2025	LA00019	Braithwaite House	Islington	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/09/2017	01/06/2018	18/10/2019	30/08/2019				not required	LA						Bunhill Row	London	EC1Y 8NE		London Borough of Islington			108	108	61	19	Complete	Islington South and Finsbury	E14000764	E09000019	5300012612	5300012612	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Braithwaite House, Bunhill Row, EC1Y 8NE	108	108	108	5300012612	ACM only	Government	MHCLG
30/09/2025	P_ISLI0280	Charterhouse Buildings Block C	Islington	private residential	bsf	Remediation completed		Remediation completed	Remediation completed	13/11/2023	13/11/2023	27/05/2025	27/05/2025	31/10/2024	11/09/2024		not required							9 Clerkenwell Road	London	EC1M 5PN		The Secretary, The Medical College of St Bartholomew's Hospital Trust	London Residential Management	Thornsett Homes Ltd		29				Islington South and Finsbury	E14000764	E09000019	10012790309		FALSE	FALSE	FALSE	TRUE	TRUE	TRUE	1			Charterhouse Buildings Block C, 9 Clerkenwell Road, EC1M 5PN	29	29	29	10012790309	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_ISLI0045	Lexington Apartments	Islington	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	16/11/2020	16/11/2020	10/11/2022	11/11/2022	11/10/2022	10/10/2022		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		40 City Road	London	EC1Y 2AN		Gray's Inn Securities Limited			92	88	32	12	Complete	Islington South and Finsbury	E14000764	E09000019		5300019782	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Lexington Apartments, 40 City Road, EC1Y 2AN	88	92	92	5300019782	ACM only	Government	GLA
30/09/2025	P_ISLI01	New Hall	Islington	student	student	Remediation completed		Remediation completed	Remediation completed	06/01/2020		22/01/2021	22/01/2021				yes							465 Caledonian Road	London	N7 9BA	Univesity College London	University College London	0	Balfour Beatty			33	10	Complete	Islington South and Finsbury	E14000764	E09000019	10090551912	10090551912	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				New Hall, 465 Caledonian Road, N7 9BA				10090551912	ACM only	Private	MHCLG
30/09/2025	P_ISLI02	Pure City	Islington	student	student	Remediation completed		Remediation completed	Remediation completed	20/01/2020		31/08/2020	31/08/2020				yes							122-130 Goswell Road/15 Bastwick Street	London	EC1V 3AT	IQSA (Hermes) Ltd						36	11	Complete	Islington South and Finsbury	E14000764	E09000019	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Pure City, 122-130 Goswell Road/15 Bastwick Street, EC1V 3AT				0	ACM only	Private	MHCLG
30/09/2025	P_ISLI0110	Xchange Point	Islington	private residential	private-fund	Plans in place		Plans in place	Plans in place		05/01/2026		28/06/2027				yes		GLA	16. Full Works Approved	Applications approved: for full costs	TRUE		14-26 Market Road	London	N7 9GS					169	147	24.5	7	Complete	Islington South and Finsbury	E14000764	E09000019	10090550524	10090550524	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			Xchange Point, 14-26 Market Road, N7 9GS	147	169	169	10090550524	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_KENS01	Collier House	Kensington and Chelsea	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	27/01/2020	01/04/2020	11/08/2020	01/06/2020	22/05/2020	22/05/2020		complete		GLA	16. Full Works Approved	Applications approved: for full costs	FALSE		163-169 Brompton Road	London	SW3 1PY	Tony Bones (Tideway)	CRESTER LIMITED	Tideway Property	SAL Pension Fund Ltd	15	13	21.9	7	Complete	Kensington	E14000768	E09000020	217007506	217007506	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Collier House, 163-169 Brompton Road, SW3 1PY	13	15	15	217007506	ACM only	Government	GLA
30/09/2025	P_KENS02	Marriott Residence Inn	Kensington and Chelsea	hotel	developer	Remediation completed		Remediation completed	Remediation completed	05/08/2020		21/09/2020					complete							181-183 Warwick Road	London	W14 8PU	SOF-10 STARLIGHT 12 GBP S.A.R.L. and SOF-10 STARLIGHT 12 OPERATIONS LIMITED	SOF-10 STARLIGHT 12 GBP S.A.R.L. and SOF-10 STARLIGHT 12 OPERATIONS LIMITED					31.2	11	Complete	Kensington	E14000768	E09000020	217121086	217121086	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Marriott Residence Inn, 181-183 Warwick Road, W14 8PU				217121086	ACM only	Private	MHCLG
30/09/2025	P_KINGT01	ViBe Student Living	Kingston upon Thames	student	student	Remediation completed		Remediation completed	Remediation completed			01/02/2018					complete							66-70 Cambridge Road	London	KT1 3LA							19	8	Complete	Kingston and Surbiton	E14000770	E09000021	128045094	128045094	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				ViBe Student Living, 66-70 Cambridge Road, KT1 3LA				128045094	ACM only	Private	MHCLG
30/09/2025	P_KIRK02	Cormorant House	Kirklees	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	18/07/2022	18/07/2022	07/08/2023	04/08/2023	04/08/2023	04/08/2023	Vacant never occupied	yes							Manchester Road	Huddersfield	HD1 3FH	Casserly Property Management	Mederco	Residential Management Group				29.8	11	Incomplete - requires follow up	Huddersfield	E14000756	E08000034		83243215	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Cormorant House, Manchester Road, HD1 3FH				83243215	ACM only	Private	MHCLG
30/09/2025	P_KIRK03	Crane Court	Kirklees	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	18/07/2022	18/07/2022	07/08/2023	04/08/2023			Vacant never occupied	yes							Manchester Road	Huddersfield	HD1 3HR	Casserly Property Management	Mederco	Residential Management Group				29.8	11	Incomplete - requires follow up	Huddersfield	E14000756	E08000034		10094113907	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Crane Court, Manchester Road, HD1 3HR				10094113907	ACM only	Private	MHCLG
30/09/2025	P_KIRK01	Kingfisher Court	Kirklees	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	16/12/2021	04/08/2021	17/08/2023	04/08/2023	28/04/2023	28/04/2023	Vacant decanted	yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		Manchester Road	Huddersfield	HD1 3FH	Casserly Property Management	Mederco	Residential Management Group	Mederco	252		29.8	11	Incomplete - requires follow up	Huddersfield	E14000756	E08000034	10093462665	10093462665	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Kingfisher Court, Manchester Road, HD1 3FH	252	252		10093462665	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_LAMB0315	The Print House Block A , 2 - 4	Lambeth	private residential	bsf	Plans in place		Plans in place	Plans in place		18/05/2026		06/04/2027				do not know							Leigham Court Road	London	SW16 2PD		KEDAI				18	20.74	7	Complete	Streatham	E14000978	E09000022			FALSE	FALSE	FALSE	FALSE	TRUE	TRUE	1			The Print House Block A , 2 - 4, Leigham Court Road, SW16 2PD	18	18	18		ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_LAMB0314	The Print House Block B , 2 - 4	Lambeth	private residential	bsf	Plans in place		Plans in place	Plans in place		18/05/2026		06/04/2027				do not know							Leigham Court Road	London	SW16 2PD						17	20.73	7	Complete	Streatham	E14000978	E09000022			FALSE	FALSE	FALSE	FALSE	TRUE	TRUE	1			The Print House Block B , 2 - 4, Leigham Court Road, SW16 2PD	17	17	17		ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_LAMB0008	1-3 Murphy Street	Lambeth	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	17/05/2021	17/05/2021	10/12/2021	10/12/2021	13/09/2021	13/09/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		1-3 Murphy Street	London	SE1 7FP	David Flack at HML	MURPHY STREET HOLDINGS LIMITED	SP Property Group	0	10	58				Vauxhall	E14001008	E09000022		10090204078	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				1-3 Murphy Street, 1-3 Murphy Street, SE1 7FP	10	58	10	10090204078	ACM only	Government	GLA
30/09/2025	P_LAMB02	Norwich House	Lambeth	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	14/12/2020	14/12/2020	06/05/2022	06/05/2022	22/07/2021	26/08/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		11 STREATHAM HIGH ROAD	London	SW16 1DG	SUNBEL DEVELOPMENT LIMITED	SUNBEL DEVELOPMENT LIMITED	Sterling Estates	SUNBEL DEVELOPMENT LIMITED	103	103	22.5	7	Complete	Streatham	E14000978	E09000022	100023315957	100023315957	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Norwich House, 11 STREATHAM HIGH ROAD, SW16 1DG	103	103	103	100023315957	ACM only	Government	GLA
30/09/2025	HA80064	Park Heights	Lambeth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/12/2018	04/03/2019	01/06/2021	30/04/2021	28/05/2021	30/04/2021		yes	HA						1-156, 25 Robsart Street	London	SW9 0FA	Network Homes	Network Homes			159	156	73	8		Vauxhall	E14001008	E09000022	10091118884	10091118884	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Park Heights, 1-156, 25 Robsart Street, SW9 0FA	156	159	159	10091118884	ACM only	Government	MHCLG
30/09/2025	P_LAMB04	Premier Inn Lambeth	Lambeth	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	16/03/2020	01/03/2019	22/04/2021	28/04/2021	28/04/2021	28/04/2021		yes							85 York Road	London	SE1 7NJ	Whitbread	Whitbread	TowerEight				48	14	Complete	Vauxhall	E14001008	E09000022	200000487488	200000487488	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn Lambeth, 85 York Road, SE1 7NJ				200000487488	ACM only	Private	MHCLG
30/09/2025	MR LA Lambeth 00057	Southwyck House - stairwell 1	Lambeth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017	04/09/2017	01/08/2018	28/09/2018				yes	LA						Clarewood Walk	London	SW9 8TW	Lambeth Council	London Borough of Lambeth			116	116	27	20		Dulwich and West Norwood	E14000673	E09000022	200000459383	200000459383	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Southwyck House - stairwell 1, Clarewood Walk, SW9 8TW	116	116	116	200000459383	ACM only	Government	MHCLG
30/09/2025	MR LA Lambeth 00058	Southwyck House - stairwell 2	Lambeth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017	04/09/2017	01/08/2018	28/09/2018				yes	LA						Clarewood Walk	London	SW9 8TW	Lambeth Council	London Borough of Lambeth			57	58	27	31		Dulwich and West Norwood	E14000673	E09000022	200000459383	200000459383	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Southwyck House - stairwell 2, Clarewood Walk, SW9 8TW	57	58	57	200000459383	ACM only	Government	MHCLG
30/09/2025	HA99726	The Junction SW9	Lambeth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	30/03/2020	30/03/2020	16/04/2021	24/04/2021	20/02/2021	12/02/2021		yes	HA						4 Stockwell Park Walk	London	SW9 0FF	Network Homes	Network Homes			41	41	26	9		Vauxhall	E14001008	E09000022	10091119981	10091119981	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Junction SW9, 4 Stockwell Park Walk, SW9 0FF	41	41	41	10091119981	ACM only	Government	MHCLG
30/09/2025	P_LAMB03	PALM HOUSE	Lambeth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	21/08/2019	30/09/2019	26/02/2020	31/01/2020				not required						Love Lambeth	SANCROFT STREET	London	SE11 5AH	Adriatic Land	Adriatic Land	DJC Property Management	Bellway	75	49	27	8	Complete	Vauxhall	E14001008	E09000022	10090203911	10090203911	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	PALM HOUSE, SANCROFT STREET, SE11 5AH	49	75	75	10090203911	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_ISLI0046	Charterhouse Buildings Block A	Islington	private residential	bsf	Remediation completed		Remediation completed	Remediation completed	13/11/2023	13/11/2023	27/05/2025	27/05/2025	31/10/2024	11/09/2024		not required							9 Clerkenwell Road	London	EC1M 5PN		The Secretary, The Medical College of St Bartholomew's Hospital Trust	London Residential Management	Thornsett Homes Ltd		22	17.95	6	Complete	Islington South and Finsbury	E14000764	E09000019	10012790309	10012790309	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			Charterhouse Buildings Block A, 9 Clerkenwell Road, EC1M 5PN	22	22	22	10012790309	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_LEED02	Concept Place	Leeds	student	student	Remediation completed		Remediation completed	Remediation completed			01/09/2018					complete							Park Lane	Leeds	LS3 1DN	Unite Students						32	11	Complete	Leeds Central	E14000777	E08000035	72655249	72655249	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Concept Place, Park Lane, LS3 1DN				72655249	ACM only	Private	MHCLG
30/09/2025	P_LEED05	Park Plaza Hotel Leeds	Leeds	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	04/05/2020		04/08/2020	31/05/2020				yes							42, Boar Lane	Leeds	LS1 5DD	Park Plaza Hotels Ltd.	PPHE	Radisson Group/Park Plaza Hotels	Radisson Group/Park Plaza Hotels			50	20	Complete	Leeds Central	E14000777	E08000035	72516044	72516044	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Park Plaza Hotel Leeds, 42, Boar Lane, LS1 5DD				72516044	ACM only	Private	MHCLG
30/09/2025	P_LEED10	Quay One	Leeds	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	08/06/2020	08/06/2020	30/09/2020	30/09/2020	10/06/2020	10/06/2020		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		Neptune Street	Leeds	LS9 8DS	Nixon Homes	Nco (One) Limited	Smiths Service Charge Company	0	35	35	18.6	7	Complete	Leeds Central	E14000777	E08000035	72653852	72653852	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Quay One, Neptune Street, LS9 8DS	35	35	35	72653852	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_LEED07	Sentinel Towers	Leeds	student	student	Remediation completed		Remediation completed	Remediation completed	01/07/2018		01/09/2018					yes							Burley Street	Leeds	LS3 1LD	University of Leeds		Rushbond				29	9	Complete	Leeds Central	E14000777	E08000035	72033458	72033458	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Sentinel Towers, Burley Street, LS3 1LD				72033458	ACM only	Private	MHCLG
30/09/2025	P_LEED06	Sky Plaza	Leeds	student	student	Remediation completed		Remediation completed	Remediation completed			01/09/2018					complete							Claypit Lane	Leeds	LS2 8AR	Unite Students		Rushbond				103	34	Complete	Leeds Central	E14000777	E08000035	72662101	72662101	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Sky Plaza, Claypit Lane, LS2 8AR				72662101	ACM only	Private	MHCLG
30/09/2025	P_LEED11	Skyline Apartments	Leeds	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2020	01/06/2020	14/04/2021	17/04/2021	01/04/2021	26/03/2021		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		1 St Peters Square	Leeds	LS9 8BN	Liv group	Welbeck Land	Wellbeck Land		132	130	32.1	14	Complete	Leeds Central	E14000777	E08000035	72659617	72659617	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Skyline Apartments, 1 St Peters Square, LS9 8BN	130	132	132	72659617	ACM only	Government	HE
30/09/2025	P_LEED01	20:20 Block B Flats	Leeds	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/12/2020	07/12/2020	17/11/2021	18/11/2021	13/08/2021	31/10/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE	20:20 House	Skinner Lane	Leeds	LS7 1BB	20:20 House (Residential Management) Limited	Triplerose Limited	London Block Management	Morris Properties	265	291	22.66	7	Complete	Leeds Central	E14000777	E08000035	72656299	72656299	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			20:20 Block B Flats, Skinner Lane, LS7 1BB	265	291	265	72656299	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_LEED04	One Brewery Wharf	Leeds	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/05/2019	26/05/2019	28/02/2021	01/03/2021	28/02/2020	31/01/2020		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE	Brewery Wharf	Waterloo Street	Leeds	LS10 1GX	Chris Hildreth	ONE BREWERY WHARF LIMITED	Rushbond	ONE BREWERY WHARF LIMITED	150	150	34.95	12	Complete	Leeds Central	E14000777	E08000035	72656085	72656085	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			One Brewery Wharf, Waterloo Street, LS10 1GX	150	150	150	72656085	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_LEED08	Aruba	Leeds	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	01/09/2019	01/09/2019	04/12/2020	04/12/2020				yes						Waterside Apartments	Gotts Road	Leeds	LS12 1DW	Creston Residential (General Partner) LLP	Creston Residential (General Partner) LLP	Savills	0	81					Leeds Central	E14000777	E08000035	72655217	72655217	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Aruba, Gotts Road, LS12 1DW	81	81	81	72655217	ACM only	Private	MHCLG
30/09/2025	P_LEED03	Montague	Leeds	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	01/09/2019	01/09/2019	04/12/2020	04/12/2020				yes						Waterside Apartments	Gotts Road	Leeds	LS12 1DN	Creston Residential (General Partner) LLP	Creston Residential (General Partner) LLP	Savills	0	123	102	32.1			Leeds Central	E14000777	E08000035	72653476	72653476	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Montague, Gotts Road, LS12 1DN	102	123	123	72653476	ACM only	Private	MHCLG
30/09/2025	P_LEIC01	Merlin Heights (Block A)	Leicester	student	student	Remediation completed		Remediation completed	Remediation completed	01/07/2017		01/12/2018	01/10/2018				yes							65 Bath Lane	Leicester	LE3 5AU	Goldcharm Ltd c/o Watkin Jones & Sons Ltd., Llandygai Industrial Estate, Llandygai, Bangor, Gwynedd LL57 4YH				601		42	14	Info Provided	Leicester West	E14000784	E06000016	48125098	2465198943	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Merlin Heights (Block A), 65 Bath Lane, LE3 5AU	601	601		48125098	ACM only	Private	MHCLG
30/09/2025	P_LEIC02	The Summit	Leicester	student	student	Remediation completed		Remediation completed	Remediation completed	29/07/2019		12/08/2020	07/08/2020				complete							100 Eastern Boulevard	Leicester	LE2 7JD	Student Roost	PBSA 3 S.a.r.l.	Johnson Associates Ltd				66	22	Incomplete - requires follow up	Leicester South	E14000783	E06000016	2465187879	2465187879	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Summit, 100 Eastern Boulevard, LE2 7JD				2465187879	ACM only	Private	MHCLG
30/09/2025	P_LEWI0125	Kent Wharf	Lewisham	private residential	developer	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	04/08/2020	26/05/2021	08/06/2021	28/05/2021	27/07/2020			complete							26 Creekside	London	SE8 3GP		Adriatic Land	Kent Wharf Property Management	Bellway Homes Ltd	143	67	50.7	15	Complete	Lewisham Deptford	E14000789	E09000023		200000556187	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Kent Wharf, 26 Creekside, SE8 3GP	67	143	143	200000556187	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	LA90702	1-48 Hatfield Close	Lewisham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/10/2017	30/04/2019	30/06/2021	30/06/2021				yes	LA						Hatfield Close	London	SE14 5DP	Lewisham Council	Lewisham Council			48	50	36	13	Complete	Lewisham Deptford	E14000789	E09000023	100021966832	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				1-48 Hatfield Close, Hatfield Close, SE14 5DP	48	50	48	100021966832	ACM only	Government	MHCLG
30/09/2025	LA90608	1-51 Gerrard House	Lewisham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/10/2017	30/04/2019	30/06/2021	30/06/2021				yes	LA						Kender Estate	London	SE14 5HT	Lewisham Council	Lewisham Council			51	51	36	13	Complete	Lewisham Deptford	E14000789	E09000023	100023677420	100023677420	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				1-51 Gerrard House, Kender Estate, SE14 5HT	51	51	51	100023677420	ACM only	Government	MHCLG
30/09/2025	LA90609	49-96 Hatfield Close	Lewisham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/10/2017	30/04/2019	30/06/2021	30/06/2021				yes	LA						Hatfield Close	London	SE14 5DW	Lewisham Council	Lewisham Council			48	48	36	13	Complete	Lewisham Deptford	E14000789	E09000023	100021966880	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				49-96 Hatfield Close, Hatfield Close, SE14 5DW	48	48	48	100021966880	ACM only	Government	MHCLG
30/09/2025	P_LINC01	Danesgate House	Lincoln	student	student	Remediation completed		Remediation completed	Remediation completed	01/04/2018		01/05/2018					yes							Grantham Street	Lincoln	LN2 1BA			liv-group						Complete	Lincoln	E14000792	E07000138	235028215	235028215	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Danesgate House, Grantham Street, LN2 1BA				235028215	ACM only	Private	MHCLG
30/09/2025	P_LIVE0069	The Atrium	Liverpool	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	19/12/2019	18/12/2020	25/06/2021	30/06/2021	23/12/2019	21/12/2019		not required		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		141 London Road	Liverpool	L3 8JA		Grey GR Limited Partnership	Revolution PM Limited		29	26	22.5	7	Complete	Liverpool Riverside	E14000793	E08000012	38261125	38261125	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Atrium, 141 London Road, L3 8JA	26	29	29	38261125	ACM only	Government	HE
30/09/2025	P_LIVE0080	Wolstenholme Square Block A	Liverpool	private residential	private-fund	Remediation started		Remediation started	Remediation started	05/02/2024	05/02/2024		28/11/2025		09/09/2024		yes		HE	18. On site monitoring	Applications approved: for full costs	TRUE		27 Gradwell Street	Liverpool	L1 4LH		Wolstenholme Square Developments Limited	Urban Evolution	Elliot Group		73				Liverpool Riverside	E14000793	E08000012		38322931	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Wolstenholme Square Block A, 27 Gradwell Street, L1 4LH	73	73	73	38322931	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_LIVE0131	Wolstenholme Square Block B	Liverpool	private residential	private-fund	Remediation started		Remediation started	Remediation started	05/02/2024	05/02/2024		28/11/2025		09/09/2024		yes		HE	18. On site monitoring	Applications approved: for full costs	TRUE		2 Nation Way	Liverpool	L1 4LB		Elliot Group International Limited	Urban Evolution	Wolstenholme Square Developments Limited		149				Liverpool Riverside	E14000793	E08000012			FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Wolstenholme Square Block B, 2 Nation Way, L1 4LB	149	149	149		ACM only	Government	HE
30/09/2025	P_LIVE01	ABLETT HOUSE	Liverpool	student	student	Remediation completed		Remediation completed	Remediation completed			01/07/2018					yes							2 CROSSHALL STREET	Liverpool	L3 2AF	We Are Homes for Students		liv-group				33	11	Complete	Liverpool Riverside	E14000793	E08000012	38304792	38304792	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				ABLETT HOUSE, 2 CROSSHALL STREET, L3 2AF				38304792	ACM only	Private	MHCLG
30/09/2025	P_LIVE05	Byrom Point	Liverpool	student	student	Remediation completed		Remediation completed	Remediation completed	08/01/2019	08/01/2019	22/05/2019	01/03/2019				yes							72 Great Crosshall Street	Liverpool	L3 2AT	Student Roost							14	Complete	Liverpool Riverside	E14000793	E08000012	38310184	38310184	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Byrom Point, 72 Great Crosshall Street, L3 2AT				38310184	ACM only	Private	MHCLG
30/09/2025	P_LIVE14	Days Inn	Liverpool	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/05/2019	01/07/2019	19/12/2019	20/12/2019				not required							James Street	Liverpool	L2 7PQ		Downing								Liverpool Riverside	E14000793	E08000012	38082444	38082444	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Days Inn, James Street, L2 7PQ				38082444	ACM only	Private	MHCLG
30/09/2025	P_LIVE02	HEYSMOOR HEIGHTS	Liverpool	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	20/12/2019	21/12/2020	05/09/2022	05/09/2022		29/10/2021		complete		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		GREENHEYS ROAD	Liverpool	L8 0PY	Adriatic Land	Adriatic Land	Residential Management Group	FM Developments	98	98	45.7	17		Liverpool Riverside	E14000793	E08000012	38249379	38249379	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				HEYSMOOR HEIGHTS, GREENHEYS ROAD, L8 0PY	98	98	98	38249379	ACM only	Government	HE
30/09/2025	P_LIVE03	Hope Street Apartments	Liverpool	student	student	Remediation completed		Remediation completed	Remediation completed	10/06/2019		31/07/2020	31/07/2020				yes							31 Hope Street	Liverpool	L1 9BR	Host Student Accommodation	0	0	0						Liverpool Riverside	E14000793	E08000012	38309784	38309784	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Hope Street Apartments, 31 Hope Street, L1 9BR				38309784	ACM only	Private	MHCLG
30/09/2025	P_LIVE10	No.40-44 Pall Mall	Liverpool	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	08/04/2021	08/04/2021	27/07/2021	02/08/2021	23/07/2021	31/08/2021		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		Pall Mall	Liverpool	L3 6ES	Danny McEvoy	Fairhold Holdings (2006) Appts Ltd	Matthews and Goodman	Bellway	159	159	23.5	8		Liverpool Riverside	E14000793	E08000012	38219172	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	No.40-44 Pall Mall, Pall Mall, L3 6ES	159	159	159	38219172	ACM/BSF RAS reimbursements	Developer	HE
30/09/2025	P_LIVE07	Norfolk House 1	Liverpool	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/09/2020	07/09/2020	29/01/2021	18/03/2021	27/11/2020	27/11/2020		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		68 Norfolk Street	Liverpool	L1 0DB	Urban Bubble / Elliot Lawless	Baltic Developments Limited	Urban Bubble	0	156	156		9		Liverpool Riverside	E14000793	E08000012	38315334	38315334	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Norfolk House 1, 68 Norfolk Street, L1 0DB	156	156	156	38315334	ACM/CSS crossovers - transferred from BSF	Government	HE
30/09/2025	P_LIVE13	Norfolk House 2	Liverpool	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/09/2020	07/09/2020	11/06/2021	04/06/2021	11/06/2021	19/06/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		42 Simpson Street	Liverpool	L1 0AY	Urban Bubble / Elliot Lawless	Baltic Developments Limited	Urban Evolution	0	100	100		9		Liverpool Riverside	E14000793	E08000012	38315334	38315334	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Norfolk House 2, 42 Simpson Street, L1 0AY	100	100	100	38315334	ACM/CSS crossovers - transferred from BSF	Government	HE
30/09/2025	P_LIVE0058	Princes Dock	Liverpool	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	16/05/2019	07/12/2020	08/06/2021	31/08/2021	05/07/2021	30/09/2021		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		1 Willaim Jessop Way	Liverpool	L3 1DZ		Peel Land and Property (Ports) Limited	Rendall & Rittner		162	163	62.13	20	Complete	Liverpool Riverside	E14000793	E08000012	38234320	38234320	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Princes Dock, 1 Willaim Jessop Way, L3 1DZ	162	163	162	38234320	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_LIVE08	Sanctuary Students Grenville Street	Liverpool	student	student	Remediation completed		Remediation completed	Remediation completed	28/11/2019		27/11/2020	27/11/2020				yes							2 Grenville Street	Liverpool	L1 5JR	Sanctuary Student	Grenville St Ltd	0	0						Liverpool Riverside	E14000793	E08000012	38303031	38303031	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Sanctuary Students Grenville Street, 2 Grenville Street, L1 5JR				38303031	ACM only	Private	MHCLG
30/09/2025	P_LIVE06	Tower Building	Liverpool	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2019	05/08/2019	01/11/2019	01/11/2019	03/10/2019	03/10/2019		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		22 Water Street	Liverpool	L3 1BA	Marco Island Developments Limited	RBH Properties	CBRE Ltd	Marco Island Developments Limited	109	104	30.1	9		Liverpool Riverside	E14000793	E08000012	38199648	38199648	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Tower Building, 22 Water Street, L3 1BA	104	109	109	38199648	ACM only	Government	HE
30/09/2025	P_LIVE11	X1 Liverpool One	Liverpool	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/08/2018		01/11/2018	01/10/2018				yes							David Lewis Street	Liverpool	L1 4AX	Savills	x1 Management	Savills	Vermont contractors	228	224				Liverpool Riverside	E14000793	E08000012	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				X1 Liverpool One, David Lewis Street, L1 4AX	224	228	228	0	ACM only	Private	MHCLG
30/09/2025	P_LIVE04	X1 The Studios	Liverpool	student	student	Remediation completed		Remediation completed	Remediation completed	01/02/2018		01/05/2018					complete							25 Plaza Boulevard	Liverpool	L8 5RZ	X1 Lettings									Liverpool Riverside	E14000793	E08000012	38267332	38267332	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		X1 The Studios, 25 Plaza Boulevard, L8 5RZ				38267332	ACM/CSS crossovers - transferred from BSF	Private	MHCLG
30/09/2025	P_LUTO01	Point Red Apartments	Luton	private residential	private-fund	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	05/07/2021	05/07/2021	18/05/2022	27/06/2022	06/12/2021	08/11/2021		yes		HE	18. On Site Monitoring	Applications approved: for full costs	TRUE		146 Midland Road	Luton	LU2 0BL	Henley Homes (Southern) Limited	Henley Homes RF Limited	SR Wood & Son (Property Management)		41	40	19.1	6	Complete	Luton South	E14000801	E06000032	100081191227	100081191227	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Point Red Apartments, 146 Midland Road, LU2 0BL	40	41	41	100081191227	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	HA00117	Bickerdike Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	30/08/2018	16/08/2019	31/07/2019				yes	HA						OFF EAST ROAD	Manchester	M12 5RD	One Manchester Limited	Eastlands Homes Partnership Limited			94	94	43	16	Complete	Manchester Gorton	E14000808	E08000003	77251931	77251931	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Bickerdike Court, OFF EAST ROAD, M12 5RD	94	94	94	77251931	ACM only	Government	MHCLG
30/09/2025	P_MANC10	Bridgewater Heights (formerly Liberty Heights)	Manchester	student	student	Remediation completed		Remediation completed	Remediation completed	01/03/2018		21/10/2018					yes							1 Great Marlborough Street	Manchester	M1 5NR	Liberty Living						104	37	Complete	Manchester Central	E14000807	E08000003	10090423250	10090423250	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Bridgewater Heights (formerly Liberty Heights), 1 Great Marlborough Street, M1 5NR				10090423250	ACM only	Private	MHCLG
30/09/2025	P_SALF01	Fresh	Salford	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	18/12/2020	14/12/2020	09/06/2025	09/06/2025	17/11/2023	15/12/2023		yes		HE	19. Practical completion - Retention Period (12m)	Applications approved: for full costs	FALSE		138 Chapel Street	Salford	M3 6AF	E&J Ground Rents	E&J Ground Rents	Premier Estates	Fresh Developments Ltd SPV	141	141	20.7	10	Complete	Salford and Eccles	E14000911	E08000006	10007897506	10007897506	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Fresh, 138 Chapel Street, M3 6AF	141	141	141	10007897506	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	HA00122	Duffield Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	31/05/2018	01/10/2017	31/08/2018				yes	HA						EPPING WALK	Manchester	M15 6NS	One Manchester Limited	One Manchester Limited			63	63	35	13	Complete	Manchester Central	E14000807	E08000003	77249240	77249240	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Duffield Court, EPPING WALK, M15 6NS	63	63	63	77249240	ACM only	Government	MHCLG
30/09/2025	HA00124	Fulton Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	24/09/2018	01/07/2019	30/06/2019				yes	HA						BOUNDARY LANE	Manchester	M15 6NW	One Manchester Limited	One Manchester Limited			70	70	24	9	Complete	Manchester Central	E14000807	E08000003	77248069	77248069	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Fulton Court, BOUNDARY LANE, M15 6NW	70	70	70	77248069	ACM only	Government	MHCLG
30/09/2025	HA00126	Hopton Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	24/09/2018	31/10/2019	31/10/2019				yes	HA						BOOTH STREET WEST	Manchester	M15 6EP	One Manchester Limited	One Manchester Limited			70	70	24	9	Complete	Manchester Central	E14000807	E08000003	77248062	77248062	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Hopton Court, BOOTH STREET WEST, M15 6EP	70	70	70	77248062	ACM only	Government	MHCLG
30/09/2025	HA00123	Hornchurch Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017		01/10/2017	01/08/2018				yes	HA						BONSALL STREET	Manchester	M15 6DS	One Manchester Limited	One Manchester Limited			63	63	35	13	Complete	Manchester Central	E14000807	E08000003	77248047	77248047	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Hornchurch Court, BONSALL STREET, M15 6DS	63	63	63	77248047	ACM only	Government	MHCLG
30/09/2025	HA00125	Hulme Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	22/01/2018	01/11/2018	01/11/2019				yes	HA						LINBY STREET	Manchester	M15 5AR	One Manchester Limited	One Manchester Limited			50	50	35	13	Complete	Manchester Central	E14000807	E08000003	77249835	77249835	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Hulme Court, LINBY STREET, M15 5AR	50	50	50	77249835	ACM only	Government	MHCLG
30/09/2025	HA00120	Ledburn Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017		01/03/2018	12/04/2018				yes	HA						LEDBURN CLOSE	Manchester	M15 4HR	One Manchester Limited	One Manchester Limited			50	50	35	13	Complete	Manchester Central	E14000807	E08000003	77249820	77249820	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Ledburn Court, LEDBURN CLOSE, M15 4HR	50	50	50	77249820	ACM only	Government	MHCLG
30/09/2025	HA00127	Meredith Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	24/09/2018	31/10/2019	31/10/2019				yes	HA						EPSLEY CLOSE	Manchester	M15 6DZ	One Manchester Limited	One Manchester Limited			70	70	24	9	Complete	Manchester Central	E14000807	E08000003	77249047	77249047	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Meredith Court, EPSLEY CLOSE, M15 6DZ	70	70	70	77249047	ACM only	Government	MHCLG
30/09/2025	P_MANC04	One Smithfield Square	Manchester	private residential	developer	Remediation completed		Remediation completed	Remediation completed	15/02/2020	15/02/2019	06/05/2021	06/05/2021	06/05/2021	06/05/2021		yes							122 High Street	Manchester	M4 5JU	Urban Bubble	Capital Climb	Urban Bubble	Muse and Morgan Sindall	80	77	33	9	Complete	Manchester Central	E14000807	E08000003	10091143362	10091143362	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	One Smithfield Square, 122 High Street, M4 5JU	77	80	80	10091143362	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_MANC18	Pall Mall House	Manchester	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	03/02/2020	07/02/2020	30/07/2020	21/10/2020	30/10/2020	20/10/2020		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		18 Church Street	Manchester	M4 1PN	Urban Bubble	Capital Climb	Urban Bubble	AHL Pall Mall Trading Ltd	60	61	32.6	10	Complete	Manchester Central	E14000807	E08000003	77121567	77121567	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Pall Mall House, 18 Church Street, M4 1PN	60	61	60	77121567	ACM only	Government	HE
30/09/2025	HA00115	Platt Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	31/08/2018	15/04/2019	01/11/2018				yes	HA						WILMSLOW ROAD	Manchester	M14 5LT	One Manchester Limited	Eastlands Homes Partnership Limited			62	62	35	13	Complete	Manchester Gorton	E14000808	E08000003	77253883	77253883	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Platt Court, WILMSLOW ROAD, M14 5LT	62	62	62	77253883	ACM only	Government	MHCLG
30/09/2025	HA00121	Royce Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017		01/10/2017	10/08/2018				yes	HA						ERSKINE CLOSE	Manchester	M15 4BR	One Manchester Limited	One Manchester Limited			63	63	35	13	Complete	Manchester Central	E14000807	E08000003	77249081	77249081	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Royce Court, ERSKINE CLOSE, M15 4BR	63	63	63	77249081	ACM only	Government	MHCLG
30/09/2025	P_MANC05	Sir Charles Grove Halls	Manchester	student	student	Remediation completed		Remediation completed	Remediation completed	01/06/2017		31/12/2017					yes							Booth Street West	Manchester	M15 6PF	Liberty Living						28	9	Complete	Manchester Central	E14000807	E08000003	77253051	77253051	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Sir Charles Grove Halls, Booth Street West, M15 6PF				77253051	ACM only	Private	MHCLG
30/09/2025	P_MANC16	THE QUADRANGLE	Manchester	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	31/03/2021	31/03/2021	15/11/2021	19/11/2021	30/09/2021	24/09/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		1 LOWER ORMOND STREET	Manchester	M1 5QF	Nathan Lumb	Sanhall GR Limited	Revolution Property Management		230	230	33	11	Complete	Manchester Central	E14000807	E08000003	10012205836	10012205836	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				THE QUADRANGLE, 1 LOWER ORMOND STREET, M1 5QF	230	230	230	10012205836	ACM only	Government	HE
30/09/2025	HA00118	Thomas Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017		01/04/2018	12/04/2018				yes	HA						BEATTOCK CLOSE	Manchester	M15 4JA	One Manchester Limited	One Manchester Limited			50	50	35	13	Complete	Manchester Central	E14000807	E08000003	77247939	77247939	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Thomas Court, BEATTOCK CLOSE, M15 4JA	50	50	50	77247939	ACM only	Government	MHCLG
30/09/2025	P_MANC03	Travel Lodge Manchester Central Arena	Manchester	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	29/11/2021	06/12/2021	28/04/2022					yes							Great Ducie Street	Manchester	M3 1PT	Rendall and Rittner						24	7	Complete	Blackley and Broughton	E14000571	E08000003	10090238166	10090238166	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Travel Lodge Manchester Central Arena, Great Ducie Street, M3 1PT				10090238166	ACM only	Private	MHCLG
30/09/2025	HA90519	Village 135 - Block B	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2017		01/12/2017	08/05/2018				yes	HA						3 Hollyhedge Court Road	Manchester	M22 4ZP	Wythenshaw Community Housing	Wythenshaw Community Housing			50	81	23		Complete	Wythenshawe and Sale East	E14001059	E08000003	10093075087	10093075087	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Village 135 - Block B, 3 Hollyhedge Court Road, M22 4ZP	50	81	50	10093075087	ACM only	Government	MHCLG
30/09/2025	P_MANC12	Vita Student - First Street	Manchester	student	student	Remediation completed		Remediation completed	Remediation completed	06/04/2020		12/10/2020	12/10/2020				yes							13 Jack Rosenthal Street	Manchester	M15 4RB	Vita Student	VitaGroup					30	10	Complete	Manchester Central	E14000807	E08000003	10091146833	10091146833	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Vita Student - First Street, 13 Jack Rosenthal Street, M15 4RB				10091146833	ACM only	Private	MHCLG
30/09/2025	P_MANC13	Vita Student Manchester-Circle Square	Manchester	student	student	Remediation completed		Remediation completed	Remediation completed	03/03/2018		26/11/2018					complete							2 Nobel Way	Manchester	M1 7FA	Vita Student	VitaGroup					29.9	11	Complete	Manchester Central	E14000807	E08000003	10093689535	10093689535	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Vita Student Manchester-Circle Square, 2 Nobel Way, M1 7FA				10093689535	ACM only	Private	MHCLG
30/09/2025	HA00119	Westcott Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017		01/04/2018	12/04/2018				yes	HA						DUNMAIL WALK	Manchester	M15 4HS	One Manchester Limited	One Manchester Limited			50	50	35	13	Complete	Manchester Central	E14000807	E08000003	77249926	77249926	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Westcott Court, DUNMAIL WALK, M15 4HS	50	50	50	77249926	ACM only	Government	MHCLG
30/09/2025	P_MANC0231	Wilmslow Park	Manchester	student	student	Remediation completed		Remediation completed	Remediation completed	01/10/2019		23/06/2021	26/06/2021				yes							211 Hathersage Road	Manchester	M13 0JQ		IQ Student Accommodation	IQ Student Accommodation			52		8	Complete	Manchester Central	E14000807	E08000003	10023060494	10023060494	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				Wilmslow Park, 211 Hathersage Road, M13 0JQ	52	52		10023060494	ACM only	Private	MHCLG
30/09/2025	HA00116	Worsley Court	Manchester	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	30/07/2018	15/04/2019	01/11/2018				yes	HA						WILMSLOW ROAD	Manchester	M14 5LU	One Manchester Limited	Eastlands Homes Partnership Limited			70	70	24	9	Complete	Manchester Gorton	E14000808	E08000003	77253887	77253887	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Worsley Court, WILMSLOW ROAD, M14 5LU	70	70	70	77253887	ACM only	Government	MHCLG
30/09/2025	P_MANC20	X1 Eastbank	Manchester	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	15/09/2020	15/09/2020	08/10/2021	08/10/2021	01/10/2021	10/09/2021		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		Great Ancoats Street	Manchester	M4 7DB	X1 Lettings	X1 development	X1 Lettings		111	111	33.46	8	Complete	Manchester Central	E14000807	E08000003	10093074820	10093074820	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				X1 Eastbank, Great Ancoats Street, M4 7DB	111	111	111	10093074820	ACM only	Government	HE
30/09/2025	P_MANC02	Citygate 1	Manchester	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	29/03/2021	29/03/2021	15/01/2024	15/01/2024	08/07/2022	08/11/2021		yes		HE	19. Practical completion - Retention Period (12m)	Applications approved: for full costs	TRUE	Citygate	1 Blantyre Street	Manchester	M15 4JS	E&J Ground Rents	E&J Ground Rents	Rendall and Rittner	Bellway	331	111	19.1	7	Complete	Manchester Central	E14000807	E08000003	10023059776	10023059776	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	Citygate 1, 1 Blantyre Street, M15 4JS	111	331	331	10023059776	ACM/BSF RAS reimbursements	Developer	HE
30/09/2025	P_MANC07	Citygate 2	Manchester	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	29/03/2021	29/03/2021	15/04/2024	15/04/2024	01/07/2022	22/04/2022		yes		HE	19. Practical completion - Retention Period (12m)	Applications approved: for full costs	TRUE	Citygate	3 Blantyre Street	Manchester	M15 4JS	E&J Ground Rents	E&J Ground Rents	Rendall and Rittner	Bellway	114	105	38	13	Complete	Manchester Central	E14000807	E08000003	10023059778	10023059778	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	Citygate 2, 3 Blantyre Street, M15 4JS	105	114	114	10023059778	ACM/BSF RAS reimbursements	Developer	HE
30/09/2025	P_MANC01	Citygate 3	Manchester	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	29/03/2021	29/03/2021	15/01/2024	15/01/2024	01/07/2022	30/06/2022		yes		HE	19. Practical completion - Retention Period (12m)	Applications approved: for full costs	TRUE	Citygate	5 Blantyre Street	Manchester	M15 4JS	E&J Ground Rents	E&J Ground Rents	Rendall and Rittner	Bellway	114	112	22.46	7	Complete	Manchester Central	E14000807	E08000003	10023059779	10023059779	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	Citygate 3, 5 Blantyre Street, M15 4JS	112	114	114	10023059779	ACM/BSF RAS reimbursements	Developer	HE
30/09/2025	P_MANC08	Cypress Place	Manchester	private residential	developer	Remediation completed		Remediation completed	Remediation completed	15/07/2019		18/06/2020	29/06/2020				yes						Green Quarter	9 New Century Park	Manchester	M4 4EH	Pemberstone Reversions (10) Limited	Pemberstone Reversions (10) Limited	LivingCity Asset Management Limited	Lendlease	215	215	60	18	Complete	Blackley and Broughton	E14000571	E08000003	10070861738	10070861738	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Cypress Place, 9 New Century Park, M4 4EH	215	215	215	10070861738	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_MANC09	Vallea Court	Manchester	private residential	developer	Remediation completed		Remediation completed	Remediation completed	15/07/2019		18/06/2020	29/06/2020				yes						Green Quarter	1 Red Bank	Manchester	M4 4FE	Pemberstone Reversions (10) Limited	Pemberstone Reversions (10) Limited	LivingCity Asset Management Limited	Lendlease	130	130	47	17	Complete	Blackley and Broughton	E14000571	E08000003	10070862577	10070862577	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Vallea Court, 1 Red Bank, M4 4FE	130	130	130	10070862577	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_MEDW01	The Hamptons	Medway	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	18/05/2020	18/05/2020	10/02/2021	11/02/2021				not required							Pier Road	Gillingham	ME7 1FJ	Freehold Properties 42 Limited (Co. Regn. No.06420169)	Parham (Medway) Limited	Freehold Properties 42		24	24	19.6	8	Complete	Gillingham and Rainham	E14000711	E06000035	44005800	44005800	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Hamptons, Pier Road, ME7 1FJ	24	24	24	44005800	ACM only	Private	MHCLG
30/09/2025	P_MERT05	Reed House	Merton	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	31/03/2021	31/03/2021	21/10/2021	22/10/2021	01/10/2021	08/10/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE	SW19 Sanctuary	21 Dunsford Road	London	SW19 8GW	Kinleigh Folkard & Hayward	JLPPT Hold Co Ltd	Kinleigh Folkard & Hayward	Barratt	184	189	23.5	8	Complete	Wimbledon	E14001040	E09000024	48125102	48125102	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	Reed House, 21 Dunsford Road, SW19 8GW	184	189	184	48125102	ACM/BSF RAS reimbursements	Developer	GLA
30/09/2025	P_MILT0025	Travelodge Milton Keynes at The Hub	Milton Keynes	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	13/07/2020	13/07/2020	26/04/2021	23/04/2021	30/10/2020			yes							312 Midsummer Boulevard	Milton Keynes	MK9 2EA							24	8	Complete	Milton Keynes North	E14000821	E06000042		25118257	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Travelodge Milton Keynes at The Hub, 312 Midsummer Boulevard, MK9 2EA				25118257	ACM only	Private	MHCLG
30/09/2025	P_NEWC0140	The View	Newcastle upon Tyne	student	student	Remediation started		Remediation started	Remediation started	13/08/2025	01/12/2025		01/05/2026									FALSE		Barrack Road	Newcastle Upon Tyne	NE1 4SH								18	Complete	Newcastle upon Tyne Central	E14000831	E08000021		4510737518	FALSE	FALSE	FALSE	FALSE	FALSE	FALSE				The View, Barrack Road, NE1 4SH				4510737518	ACM only	Private	MHCLG
30/09/2025	P_NEWC08	Liberty Plaza North (Block A)	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	02/01/2018		19/09/2018	31/12/2019				yes							Wellington Street	Newcastle Upon Tyne	NE4 5SA	Liberty Living			George Downing Construction Ltd	31		33	12	Complete	Newcastle upon Tyne Central	E14000831	E08000021		0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Liberty Plaza North (Block A), Wellington Street, NE4 5SA	31	31		0	ACM only	Private	MHCLG
30/09/2025	P_NEWC05	Liberty Plaza North (Block B)	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	02/01/2018		19/09/2018	31/12/2019				yes							Wellington Street	Newcastle Upon Tyne	NE4 5SA	Liberty Living			George Downing Construction Ltd	31			12	Complete	Newcastle upon Tyne Central	E14000831	E08000021		0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Liberty Plaza North (Block B), Wellington Street, NE4 5SA	31	31		0	ACM only	Private	MHCLG
30/09/2025	P_NEWC07	Liberty Plaza North (Block C)	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	02/01/2018		19/09/2018	31/12/2019				yes							Wellington Street	Newcastle Upon Tyne	NE4 5SA	Liberty Living			George Downing Construction Ltd	32		24	8	Complete	Newcastle upon Tyne Central	E14000831	E08000021		0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Liberty Plaza North (Block C), Wellington Street, NE4 5SA	32	32		0	ACM only	Private	MHCLG
30/09/2025	P_NEWC10	Liberty Plaza South (Block D)	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	03/02/2018		06/09/2019	27/07/2019				yes							Wellington Street, Bath Lane	Newcastle Upon Tyne	NE4 5SN	Liberty Living			George Downing Construction Ltd	145		33	11	Complete	Newcastle upon Tyne Central	E14000831	E08000021	4510733193	4510733193	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Liberty Plaza South (Block D), Wellington Street, Bath Lane, NE4 5SN	145	145		4510733193	ACM only	Private	MHCLG
30/09/2025	P_NEWC06	Mansion Tyne	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	10/11/2018	01/11/2018	01/12/2018					complete							Howard Street	Newcastle Upon Tyne	NE1 2BW	Mansion Group	UK PBSA (Howard Street Newcastle) Limited			57			7	Complete	Newcastle upon Tyne East	E14000832	E08000021	4510735399	4510735399	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Mansion Tyne, Howard Street, NE1 2BW	57	57		4510735399	ACM only	Private	MHCLG
30/09/2025	P_NEWC01	St James Point (1-215)	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	14/10/2019		28/08/2020	28/08/2020				yes							Pitt Street	Newcastle Upon Tyne	NE4 5SU	Student Roost	PBSA 5 S.A.R.L		Buile Developments Ltd	215		30	10	Complete	Newcastle upon Tyne Central	E14000831	E08000021	4510736523	4510736523	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				St James Point (1-215), Pitt Street, NE4 5SU	215	215		4510736523	ACM only	Private	MHCLG
30/09/2025	P_NEWC02	St James Point (217 - 285)	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	14/10/2019	14/10/2019	14/12/2020	14/12/2020				yes							Pitt Street	Newcastle Upon Tyne	NE4 5AX	Student Roost	PBSA 5 S.A.R.L	Derwent Students		69		24	8	Complete	Newcastle upon Tyne Central	E14000831	E08000021	4510736523	4510736523	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				St James Point (217 - 285), Pitt Street, NE4 5AX	69	69		4510736523	ACM only	Private	MHCLG
30/09/2025	P_NEWC04	The Shield [Block C]	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	01/11/2017		01/02/2018					complete							Clarence Street	Newcastle Upon Tyne	NE2 1YN							18.2	6	Complete	Newcastle upon Tyne East	E14000832	E08000021	4510743253	4510743253	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Shield [Block C], Clarence Street, NE2 1YN				4510743253	ACM only	Private	MHCLG
30/09/2025	P_NEWC09	Verde Building A	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	01/01/2018		01/04/2018					complete							Pitt Street	Newcastle Upon Tyne	NE4 5TH	George Downng Construction Ltd			George Downing Construction Ltd	95		30	10	Complete	Newcastle upon Tyne Central	E14000831	E08000021	4510738786	4510738786	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Verde Building A, Pitt Street, NE4 5TH	95	95		4510738786	ACM only	Private	MHCLG
30/09/2025	P_NEWC03	Verde Building B	Newcastle upon Tyne	student	student	Remediation completed		Remediation completed	Remediation completed	01/01/2018		01/04/2018					complete							Pitt Street	Newcastle Upon Tyne	NE4 5TJ	George Downng Construction Ltd			George Downing Construction Ltd	145			10	Complete	Newcastle upon Tyne Central	E14000831	E08000021	4510738886	4510738886	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Verde Building B, Pitt Street, NE4 5TJ	145	145		4510738886	ACM only	Private	MHCLG
30/09/2025	P_NEWH0329	15 Fortuna House	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	02/11/2020	26/10/2020	23/12/2021	23/12/2021	12/01/2021	12/01/2021		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		Scarlet Close	London	E20 1FJ			East Village Management		46	36	24	8	Complete	West Ham	E14001032	E09000025	10090328263	10090328263	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			15 Fortuna House, Scarlet Close, E20 1FJ	36	46	46	10090328263	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_NEWH0327	Edge Apartments	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	15/12/2020	14/12/2020	29/04/2021	26/04/2021	23/04/2021	23/04/2021		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		1 Lett Road	London	E15 2HP		The Master Wardens & Commonalty of the Mystery of Freeman of the Carpentry of the City of London	Prime Property Management	Thornsett Residential Limited	64	64	25	10	Complete	West Ham	E14001032	E09000025	10008988476	10008988476	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Edge Apartments, 1 Lett Road, E15 2HP	64	64	64	10008988476	ACM only	Government	GLA
30/09/2025	P_NEWH0112	1 Kotata House	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	19/10/2020	19/10/2020	21/01/2022	28/01/2022	12/01/2021	12/01/2021		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		Ravens Walk	London	E20 1DP					56	50	31	10	Complete	West Ham	E14001032	E09000025	10090328290	10090328290	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			1 Kotata House, Ravens Walk, E20 1DP	50	56	56	10090328290	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_NEWH0109	14 Karner House	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	02/11/2020	26/10/2020	23/12/2021	23/12/2021	12/01/2021	12/01/2021		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		Logan Close	London	E20 1EZ					46	38	24	8	Complete	West Ham	E14001032	E09000025	10090328266	10090328266	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			14 Karner House, Logan Close, E20 1EZ	38	46	46	10090328266	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_NEWH04	Aphrodite Court	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	05/11/2019	13/11/2019	25/11/2021	26/11/2021	30/09/2020	30/09/2020		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		180 Stratford High Street	London	E15 2FG		Aberdeen Standard Investment	L&Q		121			10	Complete	West Ham	E14001032	E09000025	10014034978	10014034978	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Aphrodite Court, 180 Stratford High Street, E15 2FG	121	121	121	10014034978	ACM only	Government	GLA
30/09/2025	P_NEWH05	Athena Court	Newham	private residential	freeholder	Remediation started		Remediation started	Remediation started	01/05/2020	01/05/2020						yes							180 Stratford High Street	London	E15 2FD		Aberdeen Standard Investment								West Ham	E14001032	E09000025	10014034746	10014034746	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Athena Court, 180 Stratford High Street, E15 2FD				10014034746	ACM only	Private	MHCLG
30/09/2025	P_NEWH03	Donald Hunter House	Newham	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/06/2019	01/06/2019	10/03/2020	31/12/2019				yes							1 Post Office Approach	London	E7 0QQ	OMEGA LETTINGS - part of the Mears Group		Theori Ltd		80	80	29	8	Complete	West Ham	E14001032	E09000025	10008993572	10008993572	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Donald Hunter House, 1 Post Office Approach, E7 0QQ	80	80	80	10008993572	ACM only	Private	MHCLG
30/09/2025	LA00010	Ferrier Point	Newham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/03/2018	01/11/2018	31/08/2019	31/08/2019				yes	LA						FORTY ACRE LANE	London	E16 1QN	London Borough of Newham	London Borough of Newham			115	115	74	24	Complete	West Ham	E14001032	E09000025	10008996250	10008996250	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Ferrier Point, FORTY ACRE LANE, E16 1QN	115	115	115	10008996250	ACM only	Government	MHCLG
30/09/2025	P_NEWH15	ibis London ExCeL	Newham	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	17/11/2020	17/11/2020	24/09/2021	24/09/2021	20/08/2021	20/08/2021		yes							9 Western Gateway	London	E16 1AB	Accor Hotels	Accorinvest	Accorinvest				29.2	8	Complete	West Ham	E14001032	E09000025		10012838885	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				ibis London ExCeL, 9 Western Gateway, E16 1AB				10012838885	ACM only	Private	MHCLG
30/09/2025	P_NEWH0123	Mara House	Newham	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	02/11/2020	26/10/2020	23/12/2021	23/12/2021	11/01/2021	11/01/2021		yes							9 Victory Parade	London	E20 1GA		East Village Management Ltd	Savills			36	28.8	9	Complete	West Ham	E14001032	E09000025		10090328262	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Mara House, 9 Victory Parade, E20 1GA	36	36	36	10090328262	ACM only	Private	MHCLG
30/09/2025	P_NEWH16	McCabe Court 1-51 (block) - BARKINGRD000	Newham	social	social-fund	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	13/01/2020	13/01/2020	28/02/2025	28/02/2025	14/05/2021			yes	HA						99 Barking road	London	E16 4HE		One Housing Group Limited	One Housing Group	Galliford Homes	51	51	18.9	7	Complete	West Ham	E14001032	E09000025		10034510549	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			McCabe Court 1-51 (block) - BARKINGRD000, 99 Barking road, E16 4HE	51	51	51	10034510549	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_NEWH0127	Meander House	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	02/11/2020	26/10/2020	23/12/2021	23/12/2021	12/01/2021	12/01/2021		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		20 Logan Close	London	E20 1FG		East Village Management Ltd	Savills	Olympic Delivery Authority (Department of Digital, Culture, Media and Sport)	52	44	31	10	Complete	West Ham	E14001032	E09000025	10090328265	10090328265	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Meander House, 20 Logan Close, E20 1FG	44	52	52	10090328265	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	LA00014	Nicholls Point	Newham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/11/2018	01/11/2018	15/08/2019	15/08/2019				yes	LA						Park Grove	London	E15 3QU	London Borough of Newham	London Borough of Newham			56	56	41	15	Complete	West Ham	E14001032	E09000025	10008996312	10008996312	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Nicholls Point, Park Grove, E15 3QU	56	56	56	10008996312	ACM only	Government	MHCLG
30/09/2025	P_NEWH0154	Sable House	Newham	private residential	bsf	Plans in place		Plans in place	Plans in place		04/05/2026		02/07/2027											Honour Lea Avenue	London	E20 1DX						36	28.8	9	Complete	West Ham	E14001032	E09000025	10090328257	10090328257	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE	1			Sable House, Honour Lea Avenue, E20 1DX	36	36	36	10090328257	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	LA00015	Tanner Point	Newham	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/03/2018	01/11/2018	15/08/2019	15/08/2019				yes	LA						Pelly Road	London	E13 0NW	London Borough of Newham	London Borough of Newham			56	56	55	15	Complete	West Ham	E14001032	E09000025	10008996428	10008996428	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Tanner Point, Pelly Road, E13 0NW	56	56	56	10008996428	ACM only	Government	MHCLG
30/09/2025	S_NEWH0226	Tayberry House	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	19/10/2020	19/10/2020	21/01/2022	28/01/2022	12/01/2021	12/01/2021		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		Ravens Walk	London	E20 1DQ		East Village Management Ltd	Savills		55	52	28.8	9	Complete	West Ham	E14001032	E09000025	10090328291	10090328291	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Tayberry House, Ravens Walk, E20 1DQ	52	55	55	10090328291	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_NEWH0180	The Lumiere Building	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	17/05/2021	07/06/2021	27/06/2023	23/06/2023	03/02/2022	03/02/2022		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		544 Romford Road	London	E7 8AY	Chaplair	Chaplair Limited	Salter Rex		71	70	33	10	Complete	East Ham	E14000679	E09000025	10008996663	10008996663	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			The Lumiere Building, 544 Romford Road, E7 8AY	70	71	71	10008996663	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_NEWH0188	Titian Heights	Newham	private residential	bsf	Plans in place		Plans in place	Plans in place		04/05/2026		02/07/2027											12 Scarlet Close	London	E20 1FH						36	22.4	7	Complete	West Ham	E14001032	E09000025	10090328258	10090328258	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE	1			Titian Heights, 12 Scarlet Close, E20 1FH	36	36	36	10090328258	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	S_NEWH0227	ZELLER HOUSE	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	02/11/2020	26/10/2020	23/12/2021	23/12/2021	12/01/2021	12/01/2021		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		SCARLET CLOSE - Plot No 2, Block E ,House 21	Stratford	E20 1FL		East Village Management Ltd	Savills	Olympic Delivery Authority (Department of Digital, Culture, Media and Sport)	52	44	31	10	Complete	West Ham	E14001032	E09000025	10090328264	10090328264	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			ZELLER HOUSE, SCARLET CLOSE - Plot No 2, Block E ,House 21, E20 1FL	44	52	52	10090328264	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_NEWH01	Apollo Court	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	05/11/2019	11/11/2019	26/11/2021	26/11/2021	30/09/2020	30/09/2020		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE	180 Stratford	160-188 Stratford High Street	London	E15 2FF	Wgtc Nominees Limited	Aberdeen UK Property Fund	Rendall and Rittner	Inis/McFeely	476	52	34.1	8	Complete	West Ham	E14001032	E09000025	10014034925	10014034925	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Apollo Court, 160-188 Stratford High Street, E15 2FF	52	476	476	10014034925	ACM only	Government	GLA
30/09/2025	P_NEWH07	7 Calla House	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	19/10/2020	19/10/2020	21/01/2022	28/01/2022	12/01/2021	12/01/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE	East Village	Anthems Way	London	E20 1DF	Stratford Village Property Holdings 1 Limited	Stratford Village Property Holdings 1 Limited & Stratford Village Property Holdings 2 Limited	East Village Management	Olympic Delivery Authority	39	31	31	10	Complete	West Ham	E14001032	E09000025	10090328296	10090328296	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			7 Calla House, Anthems Way, E20 1DF	31	39	39	10090328296	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_NEWH09	7 Merle Mansions	Newham	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	19/10/2020	19/10/2020	21/01/2022	28/01/2022	12/01/2021	12/01/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE	East Village	Glade Walk	London	E20 1DJ	Stratford Village Property Holdings 1 Limited	Stratford Village Property Holdings 1 Limited & Stratford Village Property Holdings 2 Limited	East Village Management	Olympic Delivery Authority	45	36	31	10	Complete	West Ham	E14001032	E09000025	10090328292	10090328292	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			7 Merle Mansions, Glade Walk, E20 1DJ	36	45	45	10090328292	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_NEWH14	COLVILLE MANSIONS	Newham	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	02/11/2020	26/10/2020	23/12/2021	23/12/2021	12/01/2021	12/01/2021		Yes						East Village	12 VICTORY PARADE	London	E20 1FZ	Stratford Village Property Holdings 1 Limited	Stratford Village Property Holdings 1 Limited & Stratford Village Property Holdings 2 Limited	Savills	Olympic Delivery Authority	40	27	42			West Ham	E14001032	E09000025	10090328261	10090328261	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			COLVILLE MANSIONS, 12 VICTORY PARADE, E20 1FZ	27	40	40	10090328261	ACM /BSF crossovers only - no RAS	Private	MHCLG
30/09/2025	P_NEWH06	Maya Apartments	Newham	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	02/11/2020	26/10/2020	23/12/2021	23/12/2021	12/01/2021	12/01/2021		yes						East Village	15 Victory Parade	London	E20 1FY	Stratford Village Property Holdings 1 Limited	Stratford Village Property Holdings 1 Limited & Stratford Village Property Holdings 2 Limited	East Village Management	Olympic Delivery Authority	40	40	42	11	Complete	West Ham	E14001032	E09000025		10090328260	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Maya Apartments, 15 Victory Parade, E20 1FY	40	40	40	10090328260	ACM only	Private	MHCLG
30/09/2025	P_NORW0011	Albion Mill	Norwich	private residential	developer	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	29/01/2024	29/01/2024	16/08/2024	09/08/2024	20/03/2024	20/03/2024		not required							King Street	Norwich	NR1 2BU				PJ Livesey Group		36	7	19	Complete	Norwich South	E14000864	E07000148	10034846741	10034846741	FALSE	FALSE	FALSE	FALSE	TRUE	TRUE				Albion Mill, King Street, NR1 2BU	36	36	36	10034846741	ACM only	Private	MHCLG
30/09/2025	HA99109	Brennan Bank	Norwich	social	social-fund	Remediation completed		Remediation completed	Remediation completed	26/05/2019	31/05/2019	31/10/2019	31/10/2019				yes	HA					NR1	Geoffrey Watling Way	Norwich	NR1 1GB	Broadland Housing Association Limited	Broadland Housing Association Limited		Taylor Wimpey	54	54	18		Complete	Norwich South	E14000864	E07000148	10090481921	10090481921	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Brennan Bank, Geoffrey Watling Way, NR1 1GB	54	54	54	10090481921	ACM RAS reimbursements	Developer	MHCLG
30/09/2025	P_NORW03	Gavin Bank	Norwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	13/05/2019	13/05/2019	31/10/2019	31/10/2019				yes						NR1	Geoffrey Watling Way	Norwich	NR1 1GE	Taylor Wimpey	Taylor Wimpey UK Ltd	Norwich Residential Management Ltd	Taylor Wimpey	48	48	21.6		Complete	Norwich South	E14000864	E07000148	10090482001	10090482001	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Gavin Bank, Geoffrey Watling Way, NR1 1GE	48	48	48	10090482001	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_NORW04	Lochhead Bank	Norwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	18/02/2019	01/01/2019	21/06/2019	21/06/2019				yes						NR1	Geoffrey Watling Way	Norwich	NR1 1GF	Taylor Wimpey	Taylor Wimpey UK Ltd	Norwich Residential Management Ltd	Taylor Wimpey	24	24	21.5		Complete	Norwich South	E14000864	E07000148	10090484017	10090484017	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Lochhead Bank, Geoffrey Watling Way, NR1 1GF	24	24	24	10090484017	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_NORW02	Nethercott Bank	Norwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	15/04/2019	01/01/2019	02/08/2019	01/11/2019				yes						NR1	Geoffrey Watling Way	Norwich	NR1 1GD	Taylor Wimpey	Taylor Wimpey UK Ltd	Norwich Residential Management Ltd	Taylor Wimpey	24	24	18		Complete	Norwich South	E14000864	E07000148	10090481976	10090481976	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Nethercott Bank, Geoffrey Watling Way, NR1 1GD	24	24	24	10090481976	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_NORW01	Robinson Bank	Norwich	private residential	developer	Remediation completed		Remediation completed	Remediation completed	18/03/2019	01/01/2019	12/07/2019	01/11/2019				yes						NR1	Geoffrey Watling Way	Norwich	NR1 1GG	Taylor Wimpey	Taylor Wimpey UK Ltd	Norwich Residential Management Ltd	Taylor Wimpey	24	24	21		Complete	Norwich South	E14000864	E07000148	10090483992	10090483992	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Robinson Bank, Geoffrey Watling Way, NR1 1GG	24	24	24	10090483992	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_NOTT05	Byron House (Block 2)	Nottingham	student	student	Remediation completed		Remediation completed	Remediation completed	01/12/2017		01/09/2018	01/09/2018				yes							Hampden Street	Nottingham	NG1 4FW	UPP Ltd (private)									Nottingham East	E14000865	E06000018	10090906090	10090906090	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Byron House (Block 2), Hampden Street, NG1 4FW				10090906090	ACM only	Private	MHCLG
30/09/2025	P_NOTT06	Byron House (Block 3)	Nottingham	student	student	Remediation completed		Remediation completed	Remediation completed	01/12/2017		01/09/2018	01/09/2018				yes							Hampden Street	Nottingham	NG1 4FW	UPP Ltd (private)									Nottingham East	E14000865	E06000018	10090906090	10090906090	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Byron House (Block 3), Hampden Street, NG1 4FW				10090906090	ACM only	Private	MHCLG
30/09/2025	P_NOTT02	Byron Residence	Nottingham	student	student	Remediation completed		Remediation completed	Remediation completed	01/12/2017		01/09/2018	01/09/2018				yes							Hampden Street	Nottingham	NG1 4FW	UPP Ltd (private)						38.9	13	Complete	Nottingham East	E14000865	E06000018	10090906090	10090906090	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Byron Residence, Hampden Street, NG1 4FW				10090906090	ACM only	Private	MHCLG
30/09/2025	P_NOTT04	Global Point/Academy Heights	Nottingham	student	student	Remediation completed		Remediation completed	Remediation completed	03/12/2018	01/07/2018	07/05/2019	01/04/2019				yes							8 Bromley Place	Nottingham	NG1 6JG	Barclays Nominees (George Yard) Limited			Vinci Construction			41	14	Complete	Nottingham South	E14000867	E06000018	10090475130	10090475130	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Global Point/Academy Heights, 8 Bromley Place, NG1 6JG				10090475130	ACM only	Private	MHCLG
30/09/2025	P_NOTT01	Lace Market Studios	Nottingham	student	student	Remediation completed		Remediation completed	Remediation completed	30/11/2020	30/11/2020	22/02/2024	11/03/2024	26/02/2021	05/03/2021		yes							7 Belward Street	Nottingham	NG1 1LB	Host Student Accommodation	BAE systems 2000 Pension Plan Trustees		Colliers	113		25.6	9	Complete	Nottingham South	E14000867	E06000018	200001386368	200001386368	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Lace Market Studios, 7 Belward Street, NG1 1LB	113	113		200001386368	ACM only	Private	MHCLG
30/09/2025	P_NOTT08	The Living Quarter	Nottingham	private residential	developer	Remediation completed		Remediation completed	Remediation completed	27/10/2019		01/04/2020	01/04/2020				yes							2 St Marys Gate	Nottingham	NG1 1PF	Bildurn Properties	Bildurn Properties	Encore estates	Bildurn Properties	46	46	18.6	6	Complete	Nottingham South	E14000867	E06000018	10022952600	10022952600	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Living Quarter, 2 St Marys Gate, NG1 1PF	46	46	46	10022952600	ACM only	Private	MHCLG
30/09/2025	P_NOTT07	1-52 & 55-101 The Ice House	Nottingham	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	08/04/2019	01/04/2019	18/12/2019	11/11/2019				yes						Ice House Phase 2	Bolero Square	Nottingham	NG1 1JW	Mark Bonner, Places for People	Places For People Homes Limited		Blueroom Properties	145		27.7			Nottingham South	E14000867	E06000018	100032092954	100032092954	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				1-52 & 55-101 The Ice House, Bolero Square, NG1 1JW	145	145	145	100032092954	ACM only	Private	MHCLG
30/09/2025	P_OLDH01	Cardinal Court	Oldham	private residential	developer	Remediation completed		Remediation completed	Remediation completed	01/03/2019		07/06/2019	31/03/2019				complete							Scholes Street	Oldham	OL1 3FU	Dave Tyson	LORRAINE DOROTHY GLYNN		Construction Property UK	142				Incomplete - requires follow up	Oldham East and Saddleworth	E14000870	E08000004	422000113583	422000113583	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Cardinal Court, Scholes Street, OL1 3FU	142	142	142	422000113583	ACM only	Private	MHCLG
30/09/2025	LA11050	Evenlode Tower	Oxford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/01/2018		01/06/2018	31/10/2019				yes	LA						BLACKBIRD LEYS ROAD	Oxford	OX4 6JA		Oxford City Council			60	60	48	14		Oxford East	E14000873	E07000178	100121386534	100121386534	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Evenlode Tower, BLACKBIRD LEYS ROAD, OX4 6JA	60	60	60	100121386534	ACM only	Government	MHCLG
30/09/2025	NHS00009	John Radcliffe Hospital	Oxford	public	public	Remediation completed		Remediation completed	Remediation completed	18/11/2020	18/11/2020	03/06/2021	30/06/2021	12/02/2021	19/03/2021		yes								Oxford	OX3 9DU	Oxford University Hospitals NHS Foundation Trust	Oxford University Hospitals NHS Foundation Trust								Oxford East	E14000873	E07000178	100121298340	100121298340	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				John Radcliffe Hospital, , OX3 9DU				100121298340	ACM only	Private	MHCLG
30/09/2025	NHS00015	The Churchill Hospital	Oxford	public	public	Remediation completed		Remediation completed	Remediation completed	19/08/2019	19/08/2019	17/02/2020	17/02/2020				yes								Oxford	OX3 7LE	Oxford University Hospitals NHS Foundation Trust	Oxford University Hospitals NHS Foundation Trust								Oxford East	E14000873	E07000178		100121297787	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Churchill Hospital, , OX3 7LE				100121297787	ACM only	Private	MHCLG
30/09/2025	LA11057	Windrush Tower	Oxford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/01/2018		01/06/2018	31/10/2019				yes	LA						KNIGHTS ROAD	Oxford	OX4 6HX		Oxford City Council			60	60	48	14		Oxford East	E14000873	E07000178	100121386843	100121386843	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Windrush Tower, KNIGHTS ROAD, OX4 6HX	60	60	60	100121386843	ACM only	Government	MHCLG
30/09/2025	HA30608	Lynher House	Plymouth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/03/2019	04/03/2019	22/04/2021	30/06/2021	18/11/2020			yes	HA						22-200 JAMES STREET, MOUNT WISE	Plymouth	PL1 4HH	Plymouth Community Homes (PCH)	Plymouth Community Homes Limited			90		48		Complete	Plymouth Sutton and Devonport	E14000880	E06000026	100041230060	100041230060	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Lynher House, 22-200 JAMES STREET, MOUNT WISE, PL1 4HH	90	90	90	100041230060	ACM only	Government	MHCLG
30/09/2025	HA30609	MARLBOROUGH HOUSE	Plymouth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	28/12/2020	28/12/2020	23/12/2021	23/12/2021	09/12/2021	03/12/2021		not required	HA						GRANBY WAY	Devonport	PL1 4HG	Plymouth Community Homes Limited	Plymouth Community Homes Limited			20	121	33	13	Complete	Plymouth Sutton and Devonport	E14000880	E06000026	100041230112	100041230112	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				MARLBOROUGH HOUSE, GRANBY WAY, PL1 4HG	20	121	20	100041230112	ACM only	Government	MHCLG
30/09/2025	HA30606	Tamar House	Plymouth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/03/2019	04/03/2019	22/04/2021	30/06/2021	18/11/2019	18/11/2019		yes	HA						JAMES STREET MOUNT WISE	Plymouth	PL1 4HJ	Plymouth Community Homes (PCH)	Plymouth Community Homes Limited			90	90	48		Complete	Plymouth Sutton and Devonport	E14000880	E06000026	100041230139	100041230139	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Tamar House, JAMES STREET MOUNT WISE, PL1 4HJ	90	90	90	100041230139	ACM only	Government	MHCLG
30/09/2025	HA30607	Tavy House	Plymouth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/03/2019	04/03/2019	22/04/2021	30/06/2021	18/11/2019			yes	HA						JAMES STREET MOUNT WISE	Plymouth	PL1 4HL	Plymouth Community Homes (PCH)	Plymouth Community Homes Limited			90		48		Complete	Plymouth Sutton and Devonport	E14000880	E06000026	10000798796	10000798796	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Tavy House, JAMES STREET MOUNT WISE, PL1 4HL	90	90	90	10000798796	ACM only	Government	MHCLG
30/09/2025	P_TOWE18	New Providence Wharf	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	10/05/2021	10/05/2021	18/07/2025	11/07/2025	23/12/2021	24/12/2021		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	FALSE	New Providence Wharf	1 Fairmont Avenue	London	E14 9PA	Aaron Caffrey	LANDOR RESIDENTIAL LIMITED	Ballymore Assett Mgt Ltd	LANDOR RESIDENTIAL LIMITED	565	558	58.23	18	Complete	Poplar and Limehouse	E14000882	E09000030	6154547	6154547	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	New Providence Wharf, 1 Fairmont Avenue, E14 9PA	558	565	565	6154547	ACM/BSF RAS reimbursements	Developer	GLA
30/09/2025	LA00390	Horatia House	Portsmouth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	23/06/2017	01/12/2017	01/12/2017	28/04/2023			Vacant due for demolition	yes	LA						Meriden Road	Portsmouth	PO5 4AJ	Portsmouth LA	Portsmouth City Council			136	136	50	18	Demolished	Portsmouth South	E14000884	E06000044	1775103915	1775103915	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Horatia House, Meriden Road, PO5 4AJ	136	136		1775103915	ACM only	Government	MHCLG
30/09/2025	LA00391	Leamington House	Portsmouth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	23/06/2017	19/01/2018	17/01/2018	28/04/2023			Vacant due for demolition	yes	LA						Earlsdon Street	Portsmouth	PO5 4DA	Portsmouth LA	Portsmouth City Council			136	136	50	18	Complete	Portsmouth South	E14000884	E06000044	1775102903	1775102903	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Leamington House, Earlsdon Street, PO5 4DA	136	136		1775102903	ACM only	Government	MHCLG
30/09/2025	P_PORT01	The Tower Student Accommodation	Portsmouth	student	student	Remediation completed		Remediation completed	Remediation completed	18/03/2020	18/03/2020	23/04/2021	09/04/2021				yes							Tudor Crescent	Portsmouth	PO6 2SA	Highbury College									Portsmouth North	E14000883	E06000044	1775128657	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Tower Student Accommodation, Tudor Crescent, PO6 2SA				1775128657	ACM only	Private	MHCLG
30/09/2025	S_READ0021	Crossway Point	Reading	social	social-fund	Remediation completed		Remediation completed	Remediation completed	07/02/2020	07/02/2020	29/12/2020	29/12/2020				yes	HA						Norwood Road	Reading	RG1 3LF					98			7	Complete	Reading East	E14000889	E06000038	310067790	310067790	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Crossway Point, Norwood Road, RG1 3LF	98	98	98	310067790	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_READ01	Hanover House	Reading	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/12/2020	07/12/2020	27/05/2022	27/05/2022		30/03/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		202 Kings Road	Reading	RG1 4NN	Hanover House Residents Management Association Company Ltd	ADELAIS PROPERTIES LTD	Chaneys Chartered Surveyors	Henley Homes	82	82	25.45	8	Complete	Reading East	E14000889	E06000038	310045439	310045439	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Hanover House, 202 Kings Road, RG1 4NN	82	82	82	310045439	ACM only	Government	HE
30/09/2025	P_READ02	Queens Court	Reading	student	student	Remediation completed		Remediation completed	Remediation completed	02/07/2019		13/05/2020	24/03/2020				yes							15 Queen's Walk	Reading	RG1 7QF	Hines UK Limited	HGREIT II Reading Student Housing	CRM Students	Crowne Student Living	287		26.78		Complete	Reading East	E14000889	E06000038	310081755	310081755	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Queens Court, 15 Queen's Walk, RG1 7QF	287	287		310081755	ACM only	Private	MHCLG
30/09/2025	HA00366	St Lawrence House	Reading	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/11/2018	01/10/2018	30/08/2019	30/08/2019				yes	HA						ABBEY SQUARE	Reading	RG1 3AG	Southern Housing Group	Southern Housing Group	Southern Housing Group	PMB holdings	32	32	27	9	Complete	Reading East	E14000889	E06000038	310073537	310073537	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				St Lawrence House, ABBEY SQUARE, RG1 3AG	32	32	32	310073537	ACM only	Government	MHCLG
30/09/2025	P_REDB0012	Pioneer Point North	Redbridge	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	11/05/2020	11/05/2020	24/09/2020	24/09/2020				yes							3-5 Winston Way	Ilford	IG1 2FS						294	106.9	31	Complete	Ilford South	E14000760	E09000026	10023774739	10090502138	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				Pioneer Point North, 3-5 Winston Way, IG1 2FS	294	294	294	10023774739	ACM only	Private	MHCLG
30/09/2025	Oth10130	NOBEL HOUSE	Reigate and Banstead	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	16/05/2022	16/05/2022	05/08/2022	05/08/2022	01/07/2022	15/07/2022		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		4 QUEENSWAY	Redhill	RH1 1TX		AVON GROUND RENTS LIMITED	Y&Y Management Ltd		126	126	21		Complete	Reigate	E14000893	E07000211	68170820	68170820	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE		1		NOBEL HOUSE, 4 QUEENSWAY, RH1 1TX	126	126	126	68170820	ACM/CSS crossovers	Government	HE
30/09/2025	HA80083	Arthur Millwood Court	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	15/06/2017	24/09/2018	26/03/2021	26/03/2021	01/03/2019	01/03/2019		yes	HA						RODNEY STREET	Salford	M3 5HR	Salix Homes	Salix Homes			116	116	45	15	Complete	Salford and Eccles	E14000911	E08000006	100012888069	100012888069	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Arthur Millwood Court, RODNEY STREET, M3 5HR	116	116	116	100012888069	ACM only	Government	MHCLG
30/09/2025	HA80089	Black Friar Court	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/09/2017	12/11/2018	17/04/2019	05/04/2019				yes	HA						ST SIMON STREET	Salford	M3 7ES	Salix Homes	Salix Homes			88	88	46	15	Complete	Salford and Eccles	E14000911	E08000006	100012888154	100012888154	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Black Friar Court, ST SIMON STREET, M3 7ES	88	88	88	100012888154	ACM only	Government	MHCLG
30/09/2025	HA80085	Canon Hussey Court	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	12/06/2018	29/06/2018	26/03/2021	26/03/2021	01/01/2019	01/01/2019		yes	HA						George Street	Salford	M3 5HZ	Salix Homes	Salix Homes			115	115	45	15	Complete	Salford and Eccles	E14000911	E08000006	100012887866	100012887866	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Canon Hussey Court, George Street, M3 5HZ	115	115	115	100012887866	ACM only	Government	MHCLG
30/09/2025	CityWest04	Cawdor House	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/12/2018	01/12/2018	20/12/2019	01/11/2019				not required	HA						ENFIELD CLOSE	Manchester	M30 0QD	City West Housing Trust	City West Housing Trust Limited			58	58	30		Complete	Worsley and Eccles South	E14001054	E08000006	100012887772	100012887772	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Cawdor House, ENFIELD CLOSE, M30 0QD	58	58	58	100012887772	ACM only	Government	MHCLG
30/09/2025	CityWest12	Charter House	Salford	social	social	Remediation completed		Remediation completed	Remediation completed	06/10/2017		22/10/2019	30/04/2019				complete	HA						BARTON LANE	Manchester	M30 0HA		City West Housing Trust Limited				118			Complete	Worsley and Eccles South	E14001054	E08000006	100012887539	100012887539	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Charter House, BARTON LANE, M30 0HA	118	118	118	100012887539	ACM only	Social	MHCLG
30/09/2025	P_SALF05	City Lofts	Salford	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	18/12/2020	21/12/2020	03/09/2021	31/08/2021	28/04/2021	09/05/2021		not required		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		94 The Quays	Salford	M50 3TS	Adriatic Land	Adriatic Land	Zenith Management	David McLean Contractors	203	194	51.4	19	incomplete - requires follow up	Salford and Eccles	E14000911	E08000006	10007889372	10007889372	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		City Lofts, 94 The Quays, M50 3TS	194	203	203	10007889372	ACM/CSS crossovers	Government	HE
30/09/2025	CityWest06	College Croft	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/10/2017		01/12/2018	28/02/2018				complete	HA						Regent Street	Manchester	M30 0AN	City West Housing Trust	City West Housing Trust Limited			86	86	45		Complete	Salford and Eccles	E14000911	E08000006	10095311988	10095311988	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		College Croft, Regent Street, M30 0AN	86	86	86	10095311988	ACM/CSS crossovers	Government	MHCLG
30/09/2025	CityWest11	Craunton House	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/03/2018		01/09/2018	31/05/2018				complete	HA						ST MARYS ROAD	Manchester	M30 0AY	City West Housing Trust	City West Housing Trust Limited			85	88	45		Complete	Salford and Eccles	E14000911	E08000006	100012888144	100012888144	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Craunton House, ST MARYS ROAD, M30 0AY	85	88	85	100012888144	ACM/CSS crossovers	Government	MHCLG
30/09/2025	CityWest10	Cremer House	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017	01/06/2018	01/09/2018	30/09/2018				yes	HA						ST MARYS ROAD	Manchester	M30 0AU	City West Housing Trust	City West Housing Trust Limited			88	88	45		Complete	Salford and Eccles	E14000911	E08000006	100012888145	100012888145	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Cremer House, ST MARYS ROAD, M30 0AU	88	88	88	100012888145	ACM/CSS crossovers	Government	MHCLG
30/09/2025	CityWest02	Enfield House	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/12/2018	01/12/2018	20/12/2019	01/10/2019				not required	HA						ENFIELD CLOSE	Manchester	M30 0GD	City West Housing Trust	City West Housing Trust Limited			58	58	30		Complete	Worsley and Eccles South	E14001054	E08000006	100012887773	100012887773	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Enfield House, ENFIELD CLOSE, M30 0GD	58	58	58	100012887773	ACM only	Government	MHCLG
30/09/2025	CityWest01	Engels House	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	21/01/2020	21/01/2020	31/12/2020	30/09/2020				not required	HA						TRAFFORD ROAD	Manchester	M30 0JB	City West Housing Trust	0		Thornsett Residential Limited	58	58	30		Complete	Worsley and Eccles South	E14001054	E08000006	100012888184	100012888184	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Engels House, TRAFFORD ROAD, M30 0JB	58	58	58	100012888184	ACM only	Government	MHCLG
30/09/2025	CityWest09	Ewood House	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/03/2018	01/06/2018	01/09/2018	30/09/2018				yes	HA						ST MARYS ROAD	Manchester	M30 0BA	City West Housing Trust	City West Housing Trust Limited			88	88	45		Complete	Salford and Eccles	E14000911	E08000006	100012888146	100012888146	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Ewood House, ST MARYS ROAD, M30 0BA	88	88	88	100012888146	ACM/CSS crossovers	Government	MHCLG
30/09/2025	P_LEED0229	Lovell House	Leeds	private residential	private residential	Remediation completed		Remediation completed	Remediation completed	04/03/2024		01/08/2025	01/09/2025									FALSE		Skinner Lane	Leeds	LS7 1AR					80			8	Incomplete - requires follow up	Leeds Central	E14000777	E08000035	72571470	72571470	FALSE	FALSE	FALSE	FALSE	FALSE	FALSE	1			Lovell House, Skinner Lane, LS7 1AR	80	80	80	72571470	ACM /BSF crossovers only - no RAS	Unknown	MHCLG
30/09/2025	CityWest07	Kemball House	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/03/2018		01/09/2018	31/03/2018				complete	HA						CLARENDON ROAD	Manchester	M30 9AH	City West Housing Trust	City West Housing Trust Limited			85	84	45		Complete	Salford and Eccles	E14000911	E08000006	100012887691	100012887691	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Kemball House, CLARENDON ROAD, M30 9AH	84	85	85	100012887691	ACM/CSS crossovers	Government	MHCLG
30/09/2025	HA80095	Magnolia Court	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/12/2018	02/01/2019	13/05/2019	01/05/2019				yes	HA						CITRUS WAY	Salford	M6 5AN	Salix Homes	Salix Homes			96	95	48	17	Complete	Salford and Eccles	E14000911	E08000006	100012888382	100012888382	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Magnolia Court, CITRUS WAY, M6 5AN	95	96	96	100012888382	ACM only	Government	MHCLG
30/09/2025	CityWest03	Mees Square	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/12/2018	01/12/2018	20/12/2019	01/10/2019				not required	HA						Barton Road	Manchester	M30 7AF	City West Housing Trust	City West Housing Trust Limited			58	58	30		Complete	Worsley and Eccles South	E14001054	E08000006	10093242898	10093242898	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Mees Square, Barton Road, M30 7AF	58	58	58	10093242898	ACM only	Government	MHCLG
30/09/2025	HA80096	Mulberry Court	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2017	12/11/2018	18/04/2019	05/04/2019				yes	HA						CITRUS WAY	Salford	M6 5FR	Salix Homes	Salix Homes			96	96	48	17	Complete	Salford and Eccles	E14000911	E08000006	200000671884	200000671884	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Mulberry Court, CITRUS WAY, M6 5FR	96	96	96	200000671884	ACM only	Government	MHCLG
30/09/2025	HA80092	Newbank	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	17/09/2018	01/10/2018	15/03/2019	01/02/2019				complete	HA						BRIDGEWATER STREET	Salford	M3 7JZ	Salix Homes	Salix Homes			92	92	46	16	Complete	Salford and Eccles	E14000911	E08000006	100012887583	100012887583	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Newbank, BRIDGEWATER STREET, M3 7JZ	92	92	92	100012887583	ACM only	Government	MHCLG
30/09/2025	P_SALF03	Number One Pink Media City Uk	Salford	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	20/06/2020	20/06/2020	13/12/2021	17/12/2021	01/10/2021	30/09/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		Media City	Salford	M50 2BA	Peel Media Limited	Peel Media Limited		Land Securities Group PLC	200	65		22		Salford and Eccles	E14000911	E08000006	10024414924	10024414924	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Number One Pink Media City Uk, Media City, M50 2BA	65	200	200	10024414924	ACM RAS reimbursements	Developer	HE
30/09/2025	P_SALF06	Pioneer House	Salford	private residential	developer	Remediation completed		Remediation completed	Remediation completed	30/06/2019	30/06/2019	07/04/2020	10/10/2019				not required							1C Elmira Way	Salford	M5 3LL	Saltra Phase 2 Management Co Ltd	Abacus Land	JMB Property Management Limited	Elan Homes Residential		62	18	7	Complete	Salford and Eccles	E14000911	E08000006	10070745219	10070745219	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE		1		Pioneer House, 1C Elmira Way, M5 3LL	62	62	62	10070745219	ACM/CSS crossovers	Private	MHCLG
30/09/2025	HA80093	Riverbank	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	17/09/2018	17/09/2018	15/03/2019	01/03/2019				yes	HA						BRIDGEWATER STREET	Salford	M3 7JY	Salix Homes	Salix Homes			92	92	46	16	Complete	Salford and Eccles	E14000911	E08000006	100012887584	100012887584	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Riverbank, BRIDGEWATER STREET, M3 7JY	92	92	92	100012887584	ACM only	Government	MHCLG
30/09/2025	HA80098	Sycamore Court	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	11/02/2018	03/12/2018	30/04/2019	30/04/2019				yes	HA						CITRUS WAY	Salford	M6 5FR	Salix Homes	Salix Homes			96	96	48	17	Complete	Salford and Eccles	E14000911	E08000006	10004693067	10004693067	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Sycamore Court, CITRUS WAY, M6 5FR	96	96	96	10004693067	ACM only	Government	MHCLG
30/09/2025	P_SALF04	The Exchange	Salford	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2020	15/09/2020	26/07/2021	26/07/2021	30/06/2021	30/07/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		8 Elmira Way	Salford	M5 3NQ	Savills	Salford City Council	X1 Management Limited		140	139	34.6	10	Complete	Salford and Eccles	E14000911	E08000006	10093241368	10093241368	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				The Exchange, 8 Elmira Way, M5 3NQ	139	140	140	10093241368	ACM only	Government	HE
30/09/2025	P_SALF02	The Heart Media City Blue	Salford	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	30/10/2020	30/10/2020	29/09/2021	30/09/2021	25/06/2021	30/08/2021		yes		HE	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		Media City	Salford	M50 2TJ	Peel Media Limited	Peel Media Limited			178	41	82	26		Salford and Eccles	E14000911	E08000006	10024415125	10024415125	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	The Heart Media City Blue, Media City, M50 2TJ	41	178	178	10024415125	ACM/BSF RAS reimbursements	Developer	HE
30/09/2025	CityWest05	Wade House	Salford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/12/2018	01/11/2018	20/12/2019	01/10/2019				not required	HA						WADE CLOSE	Manchester	M30 0QE	City West Housing Trust	City West Housing Trust Limited			58	58	30		Complete	Worsley and Eccles South	E14001054	E08000006	100012888392	100012888392	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Wade House, WADE CLOSE, M30 0QE	58	58	58	100012888392	ACM only	Government	MHCLG
30/09/2025	P_SALF07	White Tower	Salford	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	01/06/2021	01/06/2021	12/08/2022	02/09/2022	07/07/2022	30/03/2022		yes							Media City	Salford	M50 2EQ		Peel Media Limited					66	18	Complete	Salford and Eccles	E14000911	E08000006	10024414909	10024414909	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				White Tower, Media City, M50 2EQ				10024414909	ACM only	Private	MHCLG
30/09/2025	LA70016	Beech Court	Salford	social	social	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	17/08/2020	17/08/2020	21/03/2025	28/03/2025	30/09/2020	14/05/2021		yes	LA					Pendleton Together	Lime Close	Salford	M6 5FJ	Salford City Council	Salford City Council			76	76	30	10	Complete	Salford and Eccles	E14000911	E08000006	100012887903	100012887903	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Beech Court, Lime Close, M6 5FJ	76	76	76	100012887903	ACM only	Social	MHCLG
30/09/2025	LA21001	Holm Court	Salford	social	social	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	17/08/2020	17/08/2020	21/03/2025	28/03/2025	30/09/2020	14/05/2021		yes	LA					Pendleton Together	Mulberry Road	Salford	M6 5FN	Salford City Council	Salford City Council			76	78	30	10	Complete	Salford and Eccles	E14000911	E08000006	10004673329	10004673329	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Holm Court, Mulberry Road, M6 5FN	76	78	76	10004673329	ACM only	Social	MHCLG
30/09/2025	LA70021	Hornbeam Court	Salford	social	social	Remediation started	remediation started - cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	17/08/2020	17/08/2020		19/12/2025	25/09/2020	15/01/2021		yes	LA					Pendleton Together	Lime Close	Salford	M6 5FT	Salford City Council	Salford City Council			44	44	36	12	Complete	Salford and Eccles	E14000911	E08000006	10004688890	10004688890	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Hornbeam Court, Lime Close, M6 5FT	44	44	44	10004688890	ACM only	Social	MHCLG
30/09/2025	LA70020	Malus Court	Salford	social	social	Remediation started	remediation started - cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	17/08/2020	17/08/2020		28/11/2025	30/09/2020	30/09/2020		yes	LA					Pendleton Together	Belvedere Road	Salford	M6 5FU	Salford City Council	Salford City Council			84	83	24	8	Complete	Salford and Eccles	E14000911	E08000006	10004692609	10004692609	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Malus Court, Belvedere Road, M6 5FU	83	84	84	10004692609	ACM only	Social	MHCLG
30/09/2025	LA70019	Plane Court	Salford	social	social	Remediation started	remediation started - cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	17/08/2020	17/08/2020		28/11/2025	30/09/2020	28/09/2020		yes	LA					Pendleton Together	Churchill Way	Salford	M6 5ER	Salford City Council	Salford City Council			84	84		7	Complete	Salford and Eccles	E14000911	E08000006	10004669796	10004669796	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Plane Court, Churchill Way, M6 5ER	84	84	84	10004669796	ACM only	Social	MHCLG
30/09/2025	LA70018	Salix Court	Salford	social	social	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	17/08/2020	17/08/2020	21/03/2025	28/03/2025	30/09/2020	28/09/2020		yes	LA					Pendleton Together	Whitebeam Close	Salford	M6 5HL	Salford City Council	Salford City Council			68	68	21	7	Complete	Salford and Eccles	E14000911	E08000006	100012888260	100012888260	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Salix Court, Whitebeam Close, M6 5HL	68	68	68	100012888260	ACM only	Social	MHCLG
30/09/2025	LA70024	Spruce Court	Salford	social	social	Remediation started	remediation started - cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	13/07/2020	13/07/2020		07/11/2025	04/09/2020			yes	LA					Pendleton Together	Belvedere Road	Salford	M6 5EN	Salford City Council	Salford City Council			178	178	69	23	Complete	Salford and Eccles	E14000911	E08000006	10004668484	10004668484	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Spruce Court, Belvedere Road, M6 5EN	178	178	178	10004668484	ACM only	Social	MHCLG
30/09/2025	LA70023	Thorn Court	Salford	social	social	Remediation started	remediation started - cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	13/07/2020	13/07/2020		24/10/2025	04/09/2020			yes	LA					Pendleton Together	Belvedere Road	Salford	M6 5EL	Salford City Council	Salford City Council			177	177	69	23	Complete	Salford and Eccles	E14000911	E08000006	10004668490	10004668490	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Thorn Court, Belvedere Road, M6 5EL	177	177	177	10004668490	ACM only	Social	MHCLG
30/09/2025	LA70022	Whitebeam Court	Salford	social	social	Remediation started	remediation started - cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	03/08/2020	03/08/2020		19/12/2025	25/09/2020	25/09/2020		yes	LA					Pendleton Together	Whitebeam Close	Salford	M6 5EU	Salford City Council	Salford City Council			44	44	36	12	Complete	Salford and Eccles	E14000911	E08000006	200000671889	200000671889	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Whitebeam Court, Whitebeam Close, M6 5EU	44	44	44	200000671889	ACM only	Social	MHCLG
30/09/2025	MR LA Sandwell 00005	Astbury Court	Sandwell	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/10/2017		01/02/2018	02/02/2018				complete	LA						HEREFORD ROAD	Oldbury	B68 0QG		Sandwell Metropolitan Borough Council			48	48	24	8	Complete	Warley	E14001016	E08000028	32080207	32080207	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Astbury Court, HEREFORD ROAD, B68 0QG	48	48	48	32080207	ACM only	Government	MHCLG
30/09/2025	MR LA Sandwell 00030	Lawrence Court	Sandwell	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/10/2017		01/02/2018	02/02/2018				complete	LA						Aldridge Road	Oldbury	B68 0HB		Sandwell Metropolitan Borough Council			48	48	24	8	Complete	Warley	E14001016	E08000028	32080111	32080111	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Lawrence Court, Aldridge Road, B68 0HB	48	48	48	32080111	ACM only	Government	MHCLG
30/09/2025	MR LA Sandwell 00032	Macauley house	Sandwell	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/10/2017		01/02/2018	02/02/2018				complete	LA						Glover Street	Oldbury	B70 6DY		Sandwell Metropolitan Borough Council			36	36	27	9	Complete	West Bromwich East	E14001029	E08000028	32109199	32109199	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Macauley house, Glover Street, B70 6DY	36	36	36	32109199	ACM only	Government	MHCLG
30/09/2025	MR LA Sandwell 00039	Neale House	Sandwell	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/10/2017		01/02/2018	02/02/2018				complete	LA						Glover Street	Oldbury	B70 6DZ		Sandwell Metropolitan Borough Council			36	36	27	9	Complete	West Bromwich East	E14001029	E08000028	32109234	32109234	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Neale House, Glover Street, B70 6DZ	36	36	36	32109234	ACM only	Government	MHCLG
30/09/2025	HA20121	Cygnet House	Sefton	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017	02/10/2017	26/03/2019	29/03/2019				yes	HA						ST JAMES DRIVE	Liverpool	L20 4EN	One Vision Housing	One Vision Housing			72	72	39	13	Complete	Bootle	E14000581	E08000014	41119962	41119962	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Cygnet House, ST JAMES DRIVE, L20 4EN	72	72	72	41119962	ACM only	Government	MHCLG
30/09/2025	HA20128	WREN HOUSE	Sefton	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017	02/10/2017	26/03/2019	29/03/2019				yes	HA						ST JAMES DRIVE	Bootle	L20 4EG	One Vision Housing	One Vision Housing			72	72	39	13	Complete	Bootle	E14000581	E08000014	41120029	41120029	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				WREN HOUSE, ST JAMES DRIVE, L20 4EG	72	72	72	41120029	ACM only	Government	MHCLG
30/09/2025	P_SHEF0084	Wards Brewery (The Brewhouse and Coopers House)	Sheffield	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	30/11/2020	30/11/2020	25/06/2021	25/06/2021	07/01/2021	04/01/2021		yes		HE	19. Practical completion - Retention Period (12m)	Applications approved: for full costs	FALSE		Eccleshall Road	Sheffield	S11 8HW		Abacus Land 4 Limited			6	68	18.9	6	Complete	Sheffield Central	E14000919	E08000019		10003576044	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Wards Brewery (The Brewhouse and Coopers House), Eccleshall Road, S11 8HW	6	68	6	10003576044	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	P_SHEF01	Allen Court - Lattimore House	Sheffield	student	student	Remediation completed		Remediation completed	Remediation completed	01/04/2018		01/08/2018	01/08/2018				complete							10 St. Georges Close	Sheffield	S3 7HB	IQSA (Hermes) Ltd	IQ Student Accommodation	Fairways Property Management				18	7		Sheffield Central	E14000919	E08000019	10022927537	10022927536	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Allen Court - Lattimore House, 10 St. Georges Close, S3 7HB				10022927537	ACM only	Private	MHCLG
30/09/2025	P_SHEF02	Atlantic One	Sheffield	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	03/02/2020		31/01/2022	28/01/2022	31/07/2020	31/07/2020		yes							16 St. George's Close	Sheffield	S3 7AP	IQSA (Hermes) Ltd	IQ Student Accommodation	Fairways Property Management			190	26	7		Sheffield Central	E14000919	E08000019	10022926516	10022926515	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Atlantic One, 16 St. George's Close, S3 7AP	190	190	190	10022926516	ACM only	Private	MHCLG
30/09/2025	P_SHEF0022	Central Quay	Sheffield	student	student	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	19/02/2024	19/02/2024	04/10/2024	04/10/2024				not required							33 Alma Street	Sheffield	S3 8SN		Straits Three (Jersey)	Unite Students				18.96	6	Complete	Sheffield Central	E14000919	E08000019		10013298686	FALSE	FALSE	FALSE	FALSE	TRUE	TRUE				Central Quay, 33 Alma Street, S3 8SN				10013298686	ACM only	Private	MHCLG
30/09/2025	P_SHEF03	COPTHORNE HOTEL	Sheffield	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	30/11/2023	30/11/2023	22/08/2024	27/12/2024			Vacant not currently occupied	yes							BRAMALL LANE	Sheffield	S2 4SU	Scarborough Development Group	Scarborough Development Group	Scarborough Development Group	Scarborough Development Group	158					Sheffield Central	E14000919	E08000019	10090222006	10090222006	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				COPTHORNE HOTEL, BRAMALL LANE, S2 4SU	158	158		10090222006	ACM only	Private	MHCLG
30/09/2025	LA80040	Hanover Tower Block	Sheffield	social	social-fund	Remediation completed		Remediation completed	Remediation completed	26/06/2017	26/06/2017	28/02/2020	28/02/2020				complete	LA						101-349 Exeter Drive	Sheffield	S3 7UB		Sheffield City Council			124		42	15	Complete	Sheffield Central	E14000919	E08000019	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Hanover Tower Block, 101-349 Exeter Drive, S3 7UB	124	124	124	0	ACM only	Government	MHCLG
30/09/2025	P_SHEF04	Metis Apartments	Sheffield	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/12/2020	07/12/2020	25/04/2022	22/04/2022	09/07/2021	09/07/2021		yes		HE	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		1 Scotland Street	Sheffield	S3 7AT	Fairways Property Management	Adriatic Land	Fairways Property Management	Metis Apartments Limited	123	118	26.1	15		Sheffield Central	E14000919	E08000019	10013162515	10013162515	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Metis Apartments, 1 Scotland Street, S3 7AT	118	123	123	10013162515	ACM only	Government	HE
30/09/2025	P_SHEF0052	Sheffield Metropolitan Hotel	Sheffield	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	06/12/2021		16/06/2023	30/06/2023	19/05/2023			not required							Blonk Street,	Sheffield	S1 2AU										Sheffield Central	E14000919	E08000019		100052079102	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				Sheffield Metropolitan Hotel, Blonk Street,, S1 2AU				100052079102	ACM only	Private	MHCLG
30/09/2025	NHS00001	Stephenson Building	Sheffield	public	public	Remediation completed		Remediation completed	Remediation completed	04/03/2019	04/03/2019	01/04/2019	30/04/2019				yes							Western Bank	Sheffield	S10 2TH	Sheffield Children's NHS Foundation Trust	Sheffield Children's NHS Foundation Trust								Sheffield Central	E14000919	E08000019	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Stephenson Building, Western Bank, S10 2TH				0	ACM only	Private	MHCLG
30/09/2025	P_SLOU0020	Mosaic	Slough	private residential	css	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	18/11/2024				28/02/2025										26 High Street	Slough	SL1 1ER						166				Slough	E14000930	E06000039	10003424484	10003424484	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE		1		Mosaic, 26 High Street, SL1 1ER	166	166	166	10003424484	ACM/CSS crossovers - transferred from BSF	Unknown	MHCLG
30/09/2025	P_SLOU05	Nova House	Slough	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	23/11/2020	23/11/2020	13/12/2024	13/12/2024	28/02/2022	28/02/2022		yes		HE	19. Practical completion - Retention Period (12m)	Applications approved: for full costs	FALSE		1, Buckingham Gardens	Slough	SL1 1AY	Slough Borough Council - Mike England (Director of Housing) - -	Ground Rent Estates 5 Ltd	Ringley	Timeless Property Services Ltd	68	68		7		Slough	E14000930	E06000039	100081261361	100081261361	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Nova House, 1, Buckingham Gardens, SL1 1AY	68	68	68	100081261361	ACM only	Government	HE
30/09/2025	P_SLOU01	Aspects Court, Block B	Slough	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/07/2019	29/07/2019	24/07/2020	31/07/2020				yes						Aspects Court	Windsor Road	Slough	SL1 2DN	Barratt	Abacus Land	Residential Management Group	Barratt	37		21.8		Complete	Slough	E14000930	E06000039	6152290	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Aspects Court, Block B, Windsor Road, SL1 2DN	37	37	37	6152290	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_SLOU04	Aspects Court, Block C	Slough	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/07/2019	29/07/2019	24/07/2020	31/07/2020				yes						Aspects Court	Windsor Road	Slough	SL1 2DN	Barratt	Abacus Land	Residential Management Group	Barratt	37		21.8			Slough	E14000930	E06000039	6648509	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Aspects Court, Block C, Windsor Road, SL1 2DN	37	37	37	6648509	ACM only	Private	MHCLG
30/09/2025	P_SLOU02	Aspects Court, Block D	Slough	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/07/2019	29/07/2019	24/07/2020	31/07/2020				yes						Aspects Court	Windsor Road	Slough	SL1 2DN	Barratt	Abacus Land	Residential Management Group	Barratt	125		24.8			Slough	E14000930	E06000039	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Aspects Court, Block D, Windsor Road, SL1 2DN	125	125	125	0	ACM only	Private	MHCLG
30/09/2025	P_SLOU03	Aspects Court, Block E	Slough	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/07/2019	29/07/2019	24/07/2020	31/07/2020				yes						Aspects Court	Windsor Road	Slough	SL1 2DN	Barratt	Abacus Land	Residential Management Group	Barratt	125		24.8			Slough	E14000930	E06000039	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Aspects Court, Block E, Windsor Road, SL1 2DN	125	125	125	0	ACM only	Private	MHCLG
30/09/2025	P_SOUT0030	Maitland House/Travelodge	Southend-on-Sea	hotel	hotel	Remediation plan unclear		Remediation plan unclear	Remediation plan unclear													FALSE		Junction of Warrior Square and Chichester Road	Southend-On-Sea	SS1 2AA		Feradene Ltd	Comer Group				40	14	Complete	Rochford and Southend East	E14000899	E06000033		10024288529	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE				Maitland House/Travelodge, Junction of Warrior Square and Chichester Road, SS1 2AA				10024288529	ACM only	Private	MHCLG
30/09/2025	P_SWAR0225	12-15 Bermondsey Square	Southwark	private residential	bsf	Remediation completed		Remediation completed	Remediation completed	11/01/2021	11/01/2021	31/10/2022	28/10/2022	21/11/2022	21/11/2022		yes							12-15 Bermondsey Square	London	SE1 3UN		British Overseas Bank Nominees Ltd	Lambert Smith Hampton			76			Complete	Bermondsey and Old Southwark	E14000553	E09000028	10013529056	10013529056	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			12-15 Bermondsey Square, 12-15 Bermondsey Square, SE1 3UN	76	76	76	10013529056	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_SWAR0242	28-30 Park Street	Southwark	private residential	private-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	11/03/2024	11/03/2024		16/10/2025	29/10/2024			yes		GLA	18. On Site Monitoring	Applications approved: for full costs	TRUE		Park Street	London	SE1 9EQ		Property Class England 2 GmbH & Co. KG				8	21.7	8	Complete	Bermondsey and Old Southwark	E14000553	E09000028	10013531967	0	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			28-30 Park Street, Park Street, SE1 9EQ	8	8	8	10013531967	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_SWARK0206	52-56 Lant Street	Southwark	private residential	private-fund	Plans in place		Plans in place	Plans in place		14/05/2026		26/02/2027				yes		GLA	16. Full Works Approved	Applications approved: for full costs	FALSE		Lant Street	London	SE1 1RF		Rockwell FC 100 Limited	Regent Property Management Limited		72	66	20	7	Complete	Bermondsey and Old Southwark	E14000553	E09000028		0	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			52-56 Lant Street, Lant Street, SE1 1RF	66	72	72	0	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_SWAR0591	BRANDON HOUSE	Southwark	private residential	developer	Remediation completed		Remediation completed	Remediation completed	20/03/2023	20/03/2023	02/06/2023	02/06/2023				not approved							10 HILARY MEWS	London	SE1 1AP		CREST NICHOLSON OPERATIONS LIMITED	CREST NICHOLSON OPERATIONS LIMITED	Crest Nicholson		88	20	7	Complete	Bermondsey and Old Southwark	E14000553	E09000028	10034867827		FALSE	FALSE	FALSE	TRUE	TRUE	TRUE			1	BRANDON HOUSE, 10 HILARY MEWS, SE1 1AP	88	88	88	10034867827	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_SWAR0211	Lock House	Southwark	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	23/05/2022	23/05/2022	19/01/2024	19/01/2024	21/07/2023	21/07/2023		Yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		Rope Street	London	SE16 7FB		Tavern Quays Developments LLP			125	41	26.5	9	Complete	Bermondsey and Old Southwark	E14000553	E09000028		10091665450	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				Lock House, Rope Street, SE16 7FB	41	125	125	10091665450	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	MR HA Hyde 00028	1-138 Bolanachi Buildings	Southwark	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/04/2018	02/04/2018	01/12/2018					yes	HA						Spa Road	London	SE16 3SG	Hyde Housing Association	Hyde Housing Association			138	129	22	7	Complete	Bermondsey and Old Southwark	E14000553	E09000028	10013530306	10013530306	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				1-138 Bolanachi Buildings, Spa Road, SE16 3SG	129	138	138	10013530306	ACM only	Government	MHCLG
30/09/2025	HA01163	1-48 CO-OPERATIVE HOUSE	Southwark	social	social	Remediation completed		Remediation completed	Remediation completed	08/04/2019	01/04/2019	30/08/2019	30/08/2019				yes	HA						249 RYE LANE	London	SE15 4UP	London and Quadrant Housing Trust	London and Quadrant Housing Trust		Barratt		122	19.8	7	Complete	Camberwell and Peckham	E14000615	E09000028	10013525324	10013525324	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			1-48 CO-OPERATIVE HOUSE, 249 RYE LANE, SE15 4UP	122	122	122	10013525324	ACM /BSF crossovers only - no RAS	Social	MHCLG
30/09/2025	HA99709	21-44 Success House	Southwark	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/01/2018	15/07/2018	01/09/2018	15/01/2019				complete	HA						Old Kent Road	London	SE1 5ZT	Peabody	Peabody Trust			24	24	24			Bermondsey and Old Southwark	E14000553	E09000028	10013529983	10013529983	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				21-44 Success House, Old Kent Road, SE1 5ZT	24	24	24	10013529983	ACM only	Government	MHCLG
30/09/2025	MR HA Notting Hill 00076	27-50 Ockham Building	Southwark	social	social-fund	Remediation completed		Remediation completed	Remediation completed	02/09/2018	01/12/2018	31/08/2019	31/08/2019				yes	HA						10 Limasol Street	London	SE16 3GE	Notting Hill Genesis	Notting Hill Genesis				24	18.1	7	Complete	Bermondsey and Old Southwark	E14000553	E09000028		10090749376	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				27-50 Ockham Building, 10 Limasol Street, SE16 3GE	24	24	24	10090749376	ACM only	Government	MHCLG
30/09/2025	P_SWARK01	AURA COURT	Southwark	private residential	developer	Remediation completed		Remediation completed	Remediation completed	07/01/2019	07/01/2019	28/02/2019					complete							163 PECKHAM RYE	Peckham	SE15 3GW	Taylor Wimpey	Taylor Wimpey UK Ltd	0	Taylor Wimpey		50	14.8	7	Complete	Camberwell and Peckham	E14000615	E09000028		10009801115	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	AURA COURT, 163 PECKHAM RYE, SE15 3GW	50	50	50	10009801115	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	HA30571	ENSIGN HOUSE	Southwark	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	23/05/2022	23/05/2022	19/01/2024	19/01/2024	21/07/2023	21/07/2023		Yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	TRUE		TAVERN QUAY, SWEDEN GATE	Southwark	SE16 7EY		Tavern Quay Developments LLP			125		26.6	9	Complete	Bermondsey and Old Southwark	E14000553	E09000028	10091665595	10091665617	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				ENSIGN HOUSE, TAVERN QUAY, SWEDEN GATE, SE16 7EY	125	125	125	10091665595	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_SWARK02	Gardens House	Southwark	student	student	Remediation completed		Remediation completed	Remediation completed			17/09/2020										FALSE		37-39 Peckham Road	London	SE5 8UB							29	10		Camberwell and Peckham	E14000615	E09000028	10093340191	10090751010	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE				Gardens House, 37-39 Peckham Road, SE5 8UB				10093340191	ACM only	Private	MHCLG
30/09/2025	NHS00010	Guys Hospital	Southwark	public	public	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	01/07/2020	01/07/2019	30/11/2023	31/05/2023	29/09/2023	28/04/2023		yes								London	SE1 9RT	Guy's and St Thomas NHS Foundation Trust	Guy's and St Thomas NHS Foundation Trust								Bermondsey and Old Southwark	E14000553	E09000028	200003376121	200003376121	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Guys Hospital, , SE1 9RT				200003376121	ACM only	Private	MHCLG
30/09/2025	HA00811_115	Marsh Court	Southwark	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/07/2018	23/07/2018	31/01/2019	31/01/2019				not required	HA						East Street	London	SE17 2FT	London and Quadrant Housing Trust	London and Quadrant Housing Trust			40	40	31	10	Incomplete - requires follow up	Camberwell and Peckham	E14000615	E09000028		10091668297	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Marsh Court, East Street, SE17 2FT	40	40	40	10091668297	ACM only	Government	MHCLG
30/09/2025	MR HA Clarion 00195	Messenger Court	Southwark	social	social-fund	Remediation completed		Remediation completed	Remediation completed	26/08/2018	25/09/2018	11/12/2019	20/09/2019				not required	HA						150 Spa Road	London	SE16 4AU	Clarion Housing Group	Clarion Housing Group			33	34	17.95	7	Complete	Bermondsey and Old Southwark	E14000553	E09000028	10090285311	10090285311	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Messenger Court, 150 Spa Road, SE16 4AU	33	34	33	10090285311	ACM only	Government	MHCLG
30/09/2025	HA99711	Success House	Southwark	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/01/2018	15/07/2018	01/09/2018	15/01/2019				complete	HA						Old Kent Road	London	SE1 5ZT	Peabody	Peabody Trust			22	22	21	7	Complete	Bermondsey and Old Southwark	E14000553	E09000028	10013529983	10013529983	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Success House, Old Kent Road, SE1 5ZT	22	22	22	10013529983	ACM only	Government	MHCLG
30/09/2025	HA00408	Kennedy Gardens Block 1	Stockton-on-Tees	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/11/2017	01/07/2017	29/08/2019	28/02/2019				yes	HA						Kennedy Gardens	Billingham	TS23 3RF		Thirteen Housing Group Limited			79	79	31	11	Complete	Stockton North	E14000970	E06000004	10009302737	10009302737	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Kennedy Gardens Block 1, Kennedy Gardens, TS23 3RF	79	79	79	10009302737	ACM only	Government	MHCLG
30/09/2025	HA00409	Kennedy Gardens Block 2	Stockton-on-Tees	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/11/2017	01/07/2017	29/08/2019	28/02/2019				yes	HA						Kennedy Gardens	Billingham	TS23 3RQ		Thirteen Housing Group Limited			79	79	31	11	Complete	Stockton North	E14000970	E06000004	10009302735	10009302735	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Kennedy Gardens Block 2, Kennedy Gardens, TS23 3RQ	79	79	79	10009302735	ACM only	Government	MHCLG
30/09/2025	HA00410	Kennedy Gardens Block 3	Stockton-on-Tees	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/11/2017	01/07/2017	29/08/2019	28/02/2019				yes	HA						Kennedy Gardens	Billingham	TS23 3RJ		Thirteen Housing Group Limited			79	79	31	11	Complete	Stockton North	E14000970	E06000004	10009302736	10009302736	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Kennedy Gardens Block 3, Kennedy Gardens, TS23 3RJ	79	79	79	10009302736	ACM only	Government	MHCLG
30/09/2025	HA00236	Church Street North	Sunderland	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017	01/04/2018	01/09/2018	30/08/2018				not required	HA						Church Street North	Sunderland	SR6 0DX	Gentoo Group	Gentoo Group			52	66	38	13	Complete	Sunderland Central	E14000982	E08000024	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Church Street North, Church Street North, SR6 0DX	52	66	52	0	ACM only	Government	MHCLG
30/09/2025	HA00235	Dame Dorothy Crescent	Sunderland	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017		01/06/2018	01/07/2018				not required	HA						Dame Dorothy Crescent	Sunderland	SR6 0EU	Gentoo Group	Gentoo Group			52	52	38	13	Complete	Sunderland Central	E14000982	E08000024	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Dame Dorothy Crescent, Dame Dorothy Crescent, SR6 0EU	52	52	52	0	ACM only	Government	MHCLG
30/09/2025	HA00234	Dock Street	Sunderland	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017	01/04/2018	01/09/2018	30/08/2018				not required	HA						Dock Street	Sunderland	SR6 0DZ	Gentoo Group	Gentoo Group			52	52	38	13	Complete	Sunderland Central	E14000982	E08000024	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Dock Street, Dock Street, SR6 0DZ	52	52	52	0	ACM only	Government	MHCLG
30/09/2025	P_SUND0006	Echo Building	Sunderland	private residential	bsf	Remediation started		Remediation started	Remediation started	03/03/2025	03/03/2025		19/12/2025		17/10/2025									West Wear Street	Sunderland	SR1 1XH						179	43.5	13		Sunderland Central	E14000982	E08000024	45021886	45021886	FALSE	FALSE	FALSE	FALSE	FALSE	TRUE	1			Echo Building, West Wear Street, SR1 1XH	179	179	179	45021886	ACM /BSF crossovers only - no RAS	Government	HE
30/09/2025	HA00231	Victor Street	Sunderland	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017		01/06/2018	01/07/2018				not required	HA						Victor Street	Sunderland	SR6 0EL	Gentoo Group	Gentoo Group			52	52	38	13	Complete	Sunderland Central	E14000982	E08000024	45139958	45139958	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Victor Street, Victor Street, SR6 0EL	52	52	52	45139958	ACM only	Government	MHCLG
30/09/2025	HA00230	Zetland Square	Sunderland	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/06/2017		01/06/2018	01/07/2018				not required	HA						Zetland Square	Sunderland	SR6 0EF	Gentoo Group	Gentoo Group			52	52	38	13	Complete	Sunderland Central	E14000982	E08000024	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Zetland Square, Zetland Square, SR6 0EF	52	52	52	0	ACM only	Government	MHCLG
30/09/2025	HA01162	17 Sutton Court Road	Sutton	social	social	Remediation completed		Remediation completed	Remediation completed	28/01/2019	01/01/2019	10/05/2019	19/04/2019				not required	HA						Sutton Court Road	Sutton	SM1 4FG	London and Quadrant Housing Trust	London and Quadrant Housing Trust				96		14	Incomplete - requires follow up	Sutton and Cheam	E14000984	E09000029		5870124943	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				17 Sutton Court Road, Sutton Court Road, SM1 4FG	96	96	96	5870124943	ACM only	Social	MHCLG
30/09/2025	LA00110	CHAUCER HOUSE	Sutton	social	social	Responded with intent		Responded with intent	Responded with intent													FALSE		CHAUCER GARDENS	Sutton	SM1 2QT		Sutton Council			96			16	Complete	Sutton and Cheam	E14000984	E09000029	5870039285	5870039285	FALSE	FALSE	FALSE	FALSE	FALSE	FALSE				CHAUCER HOUSE, CHAUCER GARDENS, SM1 2QT	96	96	96	5870039285	ACM only	Social	MHCLG
30/09/2025	P_SUTT01	Nine Sutton Court	Sutton	private residential	private-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	01/02/2021	17/02/2021		30/06/2026	20/09/2022	02/12/2022		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	TRUE		9 Sutton Court Road	London	SM1 4SZ	Developers and Managing Agents	Longharbour	Encore estates	Inspired Assett	82	82	39.2	11	Complete	Sutton and Cheam	E14000984	E09000029	5870043962	5870043962	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Nine Sutton Court, 9 Sutton Court Road, SM1 4SZ	82	82	82	5870043962	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	S_TOWE1066	39-55 Pedley Street	Tower Hamlets	social	social-fund	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	17/12/2020	17/12/2020	16/09/2021	10/09/2021	18/03/2021	09/04/2021		Complete	HA						Pedley Street	London	E1 5FQ	Spitalfields Housing Association				63	36	21	7	Complete	Bethnal Green and Bow	E14000555	E09000030	6701927	0	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				39-55 Pedley Street, Pedley Street, E1 5FQ	36	63	63	6701927	ACM only	Government	MHCLG
30/09/2025	P_TOWE1008	Levanter House	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	23/03/2020		17/07/2020	17/07/2020				yes							1 Yeo Street	Tower Hamlets	E3 3NU		Berkeley Seventy Six Ltd	Rendall and Rittner	Berkeley	29	29	29.1	9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030		6172313	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Levanter House, 1 Yeo Street, E3 3NU	29	29	29	6172313	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE1071	Royal Tower Lodge	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/03/2022	07/03/2022	14/04/2023	14/04/2023	08/07/2022	20/07/2022		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	TRUE		40 Cartright Street	Tower Hamlets	E1 8LX			Haus Block Management		50	50				Poplar and Limehouse	E14000882	E09000030	6128984	6128984	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Royal Tower Lodge, 40 Cartright Street, E1 8LX	50	50	50	6128984	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_TOWE0196	24 Wapping Wall (Capstan Court, Thorpes Yard)	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	12/02/2024	12/02/2024	28/02/2025	14/03/2025		31/07/2024		yes							Wapping Wall	Tower Hamlets	E1W 3SE		Capstan Court Freehold Ltd	Managing Estates Ltd		39	39	20.7	7	Complete	Poplar and Limehouse	E14000882	E09000030	6360744	6360744	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE			1	24 Wapping Wall (Capstan Court, Thorpes Yard), Wapping Wall, E1W 3SE	39	39	39	6360744	ACM/RAS crossover - transferred from BSF and PSCRF	Developer	MHCLG
30/09/2025	P_TOWE0255	417 Wick Lane	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	29/03/2021	29/03/2021	18/12/2023	18/12/2023	03/07/2023	03/07/2023		yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		417 Wick Lane	Tower Hamlets	E3 2JJ		Henley Homes	London Block Management	Henley Homes	90	84	31	9	Complete	Bethnal Green and Bow	E14000555	E09000030	6154511	6154511	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			417 Wick Lane, 417 Wick Lane, E3 2JJ	84	90	90	6154511	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	HA99073	Alberta Court North	Tower Hamlets	social	social-fund	Remediation completed		Remediation completed	Remediation completed	12/10/2020	12/10/2020	30/09/2022	30/09/2022	07/01/2022	21/01/2022		yes	HA						BLACKWALL WAY	London	E14 9DE	Swan Housing Association	Swan Housing Association			18	17	27	9	Complete	Poplar and Limehouse	E14000882	E09000030	6173684	6173684	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Alberta Court North, BLACKWALL WAY, E14 9DE	17	18	18	6173684	ACM only	Government	MHCLG
30/09/2025	HA99074	Alberta Court South	Tower Hamlets	social	social-fund	Remediation completed		Remediation completed	Remediation completed	17/11/2020	23/11/2020	30/09/2022	30/09/2022	07/01/2022	21/01/2022		yes	HA						BLACKWALL WAY	London	E14 9DE	Swan Housing Association	Swan Housing Association			16	15	24	8	Complete	Poplar and Limehouse	E14000882	E09000030	6173703	6173703	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Alberta Court South, BLACKWALL WAY, E14 9DE	15	16	16	6173703	ACM only	Government	MHCLG
30/09/2025	P_TOWE25	Chapter Spitalfields	Tower Hamlets	student	student	Remediation completed		Remediation completed	Remediation completed	01/03/2018		17/01/2019	01/10/2018				complete							9 Frying Pan Alley	London	E1 7HS	GS Spitalfield Unit Trust	Greystar Real Estate Partners		Nido Student Living			105	34	Incomplete - Requires follow up	Bethnal Green and Bow	E14000555	E09000030	6175772	6175772	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Chapter Spitalfields, 9 Frying Pan Alley, E1 7HS				6175772	ACM only	Private	MHCLG
30/09/2025	P_TOWE0405	Chart House	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	03/05/2021	07/03/2022	02/09/2022	26/08/2022	16/10/2020	16/10/2020		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		6 Burrells Wharf Square	Tower Hamlets	E14 3TW			Warwick Estates		80	80		9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6132133	6132133	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			Chart House, 6 Burrells Wharf Square, E14 3TW	80	80	80	6132133	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_TOWE01	Commercial Road	Tower Hamlets	private residential	private-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	07/01/2025	13/01/2025		26/06/2026				yes		GLA	18. On Site Monitoring	Applications approved: for full costs	TRUE		52-58 Commercial Road	London	E1 1AN	ROCQUEFORT PROPERTIES LIMITED	ROCQUEFORT PROPERTIES LIMITED	Sterling Estates	ROCQUEFORT PROPERTIES LIMITED	127	79	34.2	14		Bethnal Green and Bow	E14000555	E09000030	0	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Commercial Road, 52-58 Commercial Road, E1 1AN	79	127	127	0	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_TOWE20	Curve Building	Tower Hamlets	student	student	Remediation completed		Remediation completed	Remediation completed	27/04/2020	27/04/2020	13/08/2020	31/08/2020				yes							14 Fieldgate Street	London	E1 1ES	GSA	GSA	Host Students		274			9	Incomplete - Requires follow up	Bethnal Green and Bow	E14000555	E09000030	6179644	6179644	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Curve Building, 14 Fieldgate Street, E1 1ES	274	274		6179644	ACM only	Private	MHCLG
30/09/2025	HA40002	Denning Point	Tower Hamlets	social	social-fund	Remediation completed		Remediation completed	Remediation completed	25/03/2019	01/10/2019	25/06/2021	02/07/2021	26/07/2019	26/07/2019		yes	HA						33 Commercial Street	London	E1 6DH	East End Homes	East End Homes		Telford Homes		81	70	22	Complete	Bethnal Green and Bow	E14000555	E09000030	6129281	6129281	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Denning Point, 33 Commercial Street, E1 6DH	81	81	81	6129281	ACM only	Government	MHCLG
30/09/2025	HA99041	Diagoras House	Tower Hamlets	social	social-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	30/11/2020	12/10/2020		20/07/2026	04/05/2021	05/02/2021		yes	HA						POLYDAMAS CLOSE	London	E3 2ZA	Swan Housing Association	Swan Housing Association			44	44	22		Complete	Bethnal Green and Bow	E14000555	E09000030	6173994	6173994	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Diagoras House, POLYDAMAS CLOSE, E3 2ZA	44	44	44	6173994	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_TOWE0671	IBIS BUDGET WHITECHAPEL	Tower Hamlets	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	20/06/2020	20/06/2020	16/10/2020	16/10/2020				not required							100 Whitechapel Road	London	E1 1JG							31	8	Complete	Bethnal Green and Bow	E14000555	E09000030	6011531	6011531	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				IBIS BUDGET WHITECHAPEL, 100 Whitechapel Road, E1 1JG				6011531	ACM only	Private	MHCLG
30/09/2025	P_TOWE23	Iron Works	Tower Hamlets	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	09/11/2020	09/11/2020	21/04/2021	16/04/2021	03/12/2020	03/12/2020		yes							58 Dace Road	London	E3 2NX	Wallace Estates Limited	Wallace Estates Limited	PBM (Premier Block Management)	London Green Developments	79	78	26	9	Incomplete - Requires follow up	Bethnal Green and Bow	E14000555	E09000030	6358063	6358063	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Iron Works, 58 Dace Road, E3 2NX	78	79	79	6358063	ACM /BSF crossovers only - no RAS	Private	MHCLG
30/09/2025	P_TOWE21	Liberty Plaza	Tower Hamlets	student	student	Remediation completed		Remediation completed	Remediation completed	01/01/2018		12/02/2019	01/10/2018				yes							65 Leman Street	London	E1 8EU				Berkeley						Bethnal Green and Bow	E14000555	E09000030	6190961	6190961	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Liberty Plaza, 65 Leman Street, E1 8EU				6190961	ACM only	Private	MHCLG
30/09/2025	HA99075	Maple House	Tower Hamlets	social	social-fund	Remediation completed		Remediation completed	Remediation completed	17/11/2020	30/11/2020	23/08/2022	05/08/2022	23/02/2022	11/02/2022		yes	HA						BLACKWALL WAY	London	E14 9EH	Swan Housing Association	Swan Housing Association			10	8	21	6	Complete	Poplar and Limehouse	E14000882	E09000030	6173721	6173721	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Maple House, BLACKWALL WAY, E14 9EH	8	10	10	6173721	ACM only	Government	MHCLG
30/09/2025	HA99042	Milo House	Tower Hamlets	social	social-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	30/11/2020	12/10/2020		20/07/2026	04/05/2021	05/02/2021		yes	HA						POLYDAMAS CLOSE	London	E3 2YJ	Swan Housing Association	Swan Housing Association			17	17	19	6	Complete	Bethnal Green and Bow	E14000555	E09000030	6173974	6173974	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Milo House, POLYDAMAS CLOSE, E3 2YJ	17	17	17	6173974	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_TOWE0582	Parkview Apartments	Tower Hamlets	private residential	private-fund	Remediation started	cladding removed	Remediation started - cladding removed	Remediation started - cladding removed	02/12/2020	02/12/2020		30/04/2027	19/11/2021	15/11/2021		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	TRUE		Chrisp Street	London	E14 6ET		Katrin Properies Ltd.	Platinum Associates Ltd	Galliard Homes	70	68	54	19	Incomplete - requires follow up	Poplar and Limehouse	E14000882	E09000030	6167786	6167786	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Parkview Apartments, Chrisp Street, E14 6ET	68	70	70	6167786	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_TOWE07	Randall House	Tower Hamlets	private residential	developer	Remediation started		Remediation started	Remediation started	01/01/2018							complete							20, Woodall Close	London	E14 0QN	Poplar Housing And Regeneration Community Association Limited	Poplar Housing And Regeneration Community Association Limited		Folera	16	60	11.5	10	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6704629	6704629	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Randall House, 20, Woodall Close, E14 0QN	16	60	16	6704629	ACM only	Private	MHCLG
30/09/2025	P_TOWE66	Streamlight Tower	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	27/10/2020	27/10/2020	30/09/2022	30/09/2022	06/10/2021	06/10/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		9 PROVINCE SQUARE	London	E14 9DW	Swan Housing Association	Swan Housing Group		Swan Housing Group	93	93	70.72	24	Complete	Poplar and Limehouse	E14000882	E09000030	6173585	6173585	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Streamlight Tower, 9 PROVINCE SQUARE, E14 9DW	93	93	93	6173585	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_TOWE58	The Foundry	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	28/11/2022	28/11/2022	03/05/2023	05/05/2023	01/02/2023	27/01/2023		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		Foundry Court, 15 Plumbers Row	London	E1 1BX		Coal Pension Properties Limited	Y&Y Management		9	9	21	8	Complete	Bethnal Green and Bow	E14000555	E09000030	6180027	6180027	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			The Foundry, Foundry Court, 15 Plumbers Row, E1 1BX	9	9	9	6180027	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_HACK0352	Infinity Heights	Hackney	private residential	private-fund	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	21/12/2023	26/02/2024	11/08/2025	01/09/2025	29/01/2024	29/01/2024		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	TRUE		264 Kingsland Road	London	E8 4DG		Investland Ltd	Live Let Ltd			16	18.5		Complete	Hackney South and Shoreditch	E14000721	E09000012		10008339386	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			Infinity Heights, 264 Kingsland Road, E8 4DG	16	16	16	10008339386	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	HA20049	Walter Tull Court	Tower Hamlets	social	social-fund	Remediation completed		Remediation completed	Remediation completed	03/04/2019	19/04/2019	11/05/2020	11/05/2020				yes	HA						Repton Street	London	E14 7FU	Tower Hamlets Community Housing	Tower Hamlets Community Housing			60	21	20	7	Complete	Bethnal Green and Bow	E14000555	E09000030	6701307	6701307	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Walter Tull Court, Repton Street, E14 7FU	21	60	60	6701307	ACM only	Government	MHCLG
30/09/2025	P_TOWE48	Wharton house - PALMER670000	Tower Hamlets	social	social-fund	Remediation completed		Remediation completed	Remediation completed	23/07/2018	18/03/2021	26/10/2022	17/10/2022	30/09/2019	30/09/2019		yes	HA						67 Palmers road	London	E2 0FF		Barwood Ventures (Bow) Limited - soon to be One Housing group	One Housing Group	Barwood Ventures	38	38	29.7	10	Incomplete - requires follow up	Bethnal Green and Bow	E14000555	E09000030	6177295	6177295	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Wharton house - PALMER670000, 67 Palmers road, E2 0FF	38	38	38	6177295	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_TOWE0670	Wheel House	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	03/05/2021	07/03/2022	02/09/2022	26/08/2022	16/10/2020	16/10/2020		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		1 Burrells Wharf Square	Tower Hamlets	E14 3TB			Warwick Estates		77	77		9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6132128	6132128	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE	1			Wheel House, 1 Burrells Wharf Square, E14 3TB	77	77	77	6132128	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	MR HA Poplar 00002	William Cotton Place	Tower Hamlets	social	social-fund	Remediation completed		Remediation completed	Remediation completed	17/03/2019	01/04/2019	26/07/2019	15/08/2019				complete	HA						126 St. Paul's Way	London	E3 4QA	Poplar Housing And Regeneration Community Association Limited	Poplar Housing And Regeneration Community Association Limited			21	21	29	8	Incomplete - requires follow up	Poplar and Limehouse	E14000882	E09000030	6181460	6181460	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			William Cotton Place, 126 St. Paul's Way, E3 4QA	21	21	21	6181460	ACM /BSF crossovers only - no RAS	Government	MHCLG
30/09/2025	P_TOWE53	Aegean Apartments	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	12/06/2020		07/10/2020	07/10/2020				yes						Caspian Wharf	20 Seven Sea Gardens	London	E3 3GY	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	31	31	24.4	7	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6652176	6174991	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Aegean Apartments, 20 Seven Sea Gardens, E3 3GY	31	31	31	6652176	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE38	Alboran Apartments Flat 201	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	05/06/2020		07/09/2020	07/09/2020				yes						Caspian Wharf	1 Seven Sea Gardens	London	E3 3GU	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	24	24	24.6	8	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6193869	6174794	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Alboran Apartments Flat 201, 1 Seven Sea Gardens, E3 3GU	24	24	24	6193869	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE42	Ashmore House North	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	23/03/2020		19/06/2020	28/08/2020				yes						Caspian Wharf	1 Yeo Street	London	E3 3QQ	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	82	10	20	6	Complete	Poplar and Limehouse	E14000882	E09000030	6172225	6172225	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Ashmore House North, 1 Yeo Street, E3 3QQ	10	82	82	6172225	ACM only	Private	MHCLG
30/09/2025	P_TOWE39	Ashmore House South	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	23/03/2020		20/07/2020	28/08/2020				yes						Caspian Wharf	1 Yeo Street	London	E3 3FN	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	82	28	20	6	Complete	Poplar and Limehouse	E14000882	E09000030	6172241	6172241	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Ashmore House South, 1 Yeo Street, E3 3FN	28	82	82	6172241	ACM only	Private	MHCLG
30/09/2025	P_TOWE28	Atlantic Apartments	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	26/06/2020	26/06/2020	23/11/2020	23/11/2020				yes						Caspian Wharf	Caspian Wharf, Yeo Street	London	E3 3AE	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	83	82	20	6	Complete	Poplar and Limehouse	E14000882	E09000030	6652176	6652176	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Atlantic Apartments, Caspian Wharf, Yeo Street, E3 3AE	82	83	83	6652176	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE46	Ceram Court	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	10/07/2020	05/06/2020	15/12/2020	15/12/2020				yes						Caspian Wharf	10 Seven Sea Gardens	London	E3 3GW	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	77	77	40.5	12	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6174815	6174815	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Ceram Court, 10 Seven Sea Gardens, E3 3GW	77	77	77	6174815	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE31	Coulson House	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	14/04/2020		17/07/2020	17/07/2020				yes						Caspian Wharf	Caspian Wharf, Yeo Street	London	E3 3FN	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	34	4	20	6		Poplar and Limehouse	E14000882	E09000030	6172236	6172236	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Coulson House, Caspian Wharf, Yeo Street, E3 3FN	4	34	34	6172236	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE47	Gregale House	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	23/03/2020		26/06/2020	26/06/2020				yes						Caspian Wharf	18 Voysey Square	London	E3 3FY	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	37	37	29.1	9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6172343	6172343	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Gregale House, 18 Voysey Square, E3 3FY	37	37	37	6172343	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE41	Hudson House	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/07/2020	29/07/2020	19/11/2020	19/11/2020				yes						Caspian Wharf	1 Yeo Street	London	E3 3NU	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	64	61	30	9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6175063	6175063	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Hudson House, 1 Yeo Street, E3 3NU	61	64	64	6175063	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE30	Kara Court	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	10/07/2020	05/06/2020	15/12/2020	15/12/2020				yes						Caspian Wharf	15 Seven Sea Gardens	London	E3 3GX	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	96	96	40.5	12	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6701403	6174893	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Kara Court, 15 Seven Sea Gardens, E3 3GX	96	96	96	6701403	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE43	Leonard House	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	27/04/2020		19/06/2020	19/06/2020				yes						Caspian Wharf	1 Yeo Street	London	E3 3QQ	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	12	2	20	6		Poplar and Limehouse	E14000882	E09000030	6172222	6172222	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Leonard House, 1 Yeo Street, E3 3QQ	2	12	12	6172222	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE27	Maestro Apartments	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	23/03/2020		14/08/2020	28/08/2020				yes						Caspian Wharf	Caspian Wharf, Yeo Street	London	E3 3NU	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	41	41	24.6	8	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6172270	6172270	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Maestro Apartments, Caspian Wharf, Yeo Street, E3 3NU	41	41	41	6172270	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE29	Sargasso Court	Tower Hamlets	private residential	developer	Remediation completed		Remediation completed	Remediation completed	20/07/2020		19/10/2020	19/10/2020				yes						Caspian Wharf	15 Seven Sea Gardens	Tower Hamlets	E3 3LG	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	42	42	20	6	Complete	Poplar and Limehouse	E14000882	E09000030	6701402	6175020	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Sargasso Court, 15 Seven Sea Gardens, E3 3LG	42	42	42	6701402	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE03	Crown Wharf Block A	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	09/08/2021	09/08/2021	18/12/2023	15/12/2023	12/01/2023	13/01/2023		yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE	Crown Wharf	4 Roach Road	London	E3 2PF	Wallace Estates Limited	Wallace Estates Limited	PBM (Premier Block Management)	London Green Developments	125		19.56	8	BSF Application	Bethnal Green and Bow	E14000555	E09000030	6260081	6260081	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Crown Wharf Block A, 4 Roach Road, E3 2PF	125	125	125	6260081	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_TOWE02	Boston Lodge	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	20/01/2020	06/07/2020	01/07/2021	01/07/2021	04/01/2021	04/01/2021		yes						New Festival Quarter	171 Canton Street	London	E14 6FL	Bellway	Adriatic Land	Pinnacle Places	Bellway		32	21	7	Complete	Poplar and Limehouse	E14000882	E09000030	6179360	6179360	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Boston Lodge, 171 Canton Street, E14 6FL	32	32	32	6179360	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE14	Casson Apartments	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	19/12/2019	01/03/2020	25/09/2020	30/09/2020				yes						New Festival Quarter	43 Upper North Street	London	E14 6FY	Bellway	Adriatic Land	Pinnacle Places	Bellway	62	59	22.6	7	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6179567	6179567	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Casson Apartments, 43 Upper North Street, E14 6FY	59	62	62	6179567	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE05	Felix Point	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	01/08/2020	01/08/2020	17/12/2021	17/12/2021	05/02/2021	26/02/2021		yes						New Festival Quarter	5 Epstein Square	London	E14 6FX	Bellway	Adriatic Land	Pinnacle Places	Bellway	35	53	23	7	Complete	Poplar and Limehouse	E14000882	E09000030	6190280	6190280	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Felix Point, 5 Epstein Square, E14 6FX	35	53	35	6190280	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE12	Kerensky House	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	01/08/2020	01/08/2020	07/05/2021	28/05/2021	05/02/2021	26/02/2021		yes						New Festival Quarter	53 Upper North Street	London	E14 6GU	Bellway	Adriatic Land	Pinnacle Places	Bellway	175	30	23	7	Complete	Poplar and Limehouse	E14000882	E09000030	6190461	6190461	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Kerensky House, 53 Upper North Street, E14 6GU	30	175	175	6190461	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE15	Lucienne Court	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	01/08/2020	01/08/2020	07/05/2021	28/05/2021	05/02/2021	26/02/2021		yes						New Festival Quarter	72 Lindfield Street	London	E14 6GT	Bellway	Adriatic Land	Pinnacle Places	Bellway	175	60	31	9	Complete	Poplar and Limehouse	E14000882	E09000030	6190400	6190400	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Lucienne Court, 72 Lindfield Street, E14 6GT	60	175	175	6190400	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE13	Mellor House	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	01/08/2020	01/08/2020	07/05/2021	28/05/2021	05/02/2021	26/02/2021		yes						New Festival Quarter	57 Upper North Street	London	E14 6GW	Bellway	Adriatic Land	Pinnacle Places	Bellway	175	32	26	7	Complete	Poplar and Limehouse	E14000882	E09000030	6190493	6190493	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Mellor House, 57 Upper North Street, E14 6GW	32	175	175	6190493	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE11	Navis House	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	11/12/2019	30/09/2019	03/08/2020	01/08/2020				yes						New Festival Quarter	66 Lindfield Street	London	E14 6GP	Bellway	Adriatic Land	Pinnacle Places	Bellway	64	45	23	6	Complete	Poplar and Limehouse	E14000882	E09000030	6190334	6190334	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Navis House, 66 Lindfield Street, E14 6GP	45	64	64	6190334	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE06	Pasmore Court	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	20/01/2020	01/07/2020	01/07/2021	01/07/2021	04/01/2021	04/01/2021		yes						New Festival Quarter	26 New Festival Avenue	London	E14 6FW	Bellway	Adriatic Land	Pinnacle Places	Bellway	50	18	21	7	Complete	Poplar and Limehouse	E14000882	E09000030	6179545	6179545	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Pasmore Court, 26 New Festival Avenue, E14 6FW	18	50	50	6179545	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE08	Winchester House	Tower Hamlets	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	20/01/2020	01/07/2020	17/12/2021	17/12/2021	04/01/2021	04/01/2021		yes						New Festival Quarter	14 New Festival Avenue	London	E14 6FS	Bellway	Adriatic Land	Pinnacle Places	Bellway	35	35	22.5	7	Complete	Poplar and Limehouse	E14000882	E09000030	6179418	6179418	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Winchester House, 14 New Festival Avenue, E14 6FS	35	35	35	6179418	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_TOWE16	Victoria Wharf	Tower Hamlets	private residential	private-fund	Remediation started	works complete awaiting building control signoff	Works complete awaiting building control signoff	Works complete awaiting building control signoff	25/09/2023	25/09/2023	16/09/2025	01/09/2025	13/03/2025	14/03/2025		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	TRUE		2-20 Palmers Road	London	E2 0SZ	Danny Carty / Shalim Ahmed	TREASURE GLOBAL RESOURCES LIMITED	Rendall and Rittner	Kedai	100	87	33	11		Bethnal Green and Bow	E14000555	E09000030	6130484	6130484	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Victoria Wharf, 2-20 Palmers Road, E2 0SZ	87	100	100	6130484	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_TOWE62	Blenheim Apartments	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/12/2020	16/12/2020	14/01/2022	13/01/2022	10/02/2021	10/02/2021		not required		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE	St George Estate	112 Cable Street	London	E1 8NS	Clarke Hillyer	East End Homes	STG Management (London) Limited	Telford Homes	22	22	27	9	Demolished	Poplar and Limehouse	E14000882	E09000030	6193381	6193381	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Blenheim Apartments, 112 Cable Street, E1 8NS	22	22	22	6193381	ACM RAS reimbursements	Developer	GLA
30/09/2025	P_TOWE68	Chi Building	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/12/2020	16/12/2020	10/12/2021	17/12/2021	10/02/2021	10/02/2021		not required		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE	St George Estate	54 Crowder Street	London	E1 0EZ	East End Homes	East End Homes	STG Management (London) Limited	Telford Homes	29	28	33	9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6178339	6178339	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Chi Building, 54 Crowder Street, E1 0EZ	28	29	29	6178339	ACM RAS reimbursements	Developer	GLA
30/09/2025	P_TOWE10	Garamond Building	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	15/02/2021	15/02/2021	25/02/2022	18/03/2022	10/02/2021	25/03/2021		yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE	St George Estate	2 Crowder Street	London	E1 0EX	Clarke Hillyer	East End Homes	STG Management (London) Limited	Telford Homes	17	17	26.1	9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6176381	6176381	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Garamond Building, 2 Crowder Street, E1 0EX	17	17	17	6176381	ACM RAS reimbursements	Developer	GLA
30/09/2025	P_TOWE69	Orchid Apartments	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/12/2020	16/12/2020	15/12/2021	17/12/2021	10/02/2021	10/02/2021		not required		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE	St George Estate	57 Crowder Street	London	E1 0EZ	East End Homes	East End Homes	STG Management (London) Limited	Telford Homes	25	24	37.95	9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6178368	6178368	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Orchid Apartments, 57 Crowder Street, E1 0EZ	24	25	25	6178368	ACM RAS reimbursements	Developer	GLA
30/09/2025	P_TOWE67	Warwick Apartments	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/12/2020	16/12/2020	14/01/2022	13/01/2022	10/02/2021	10/02/2021		not required		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE	St George Estate	132 Cable Street	London	E1 8NU	East End Homes	East End Homes	STG Management (London) Limited	Telford Homes	17	17	35.38	9	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6193404	6193404	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Warwick Apartments, 132 Cable Street, E1 8NU	17	17	17	6193404	ACM RAS reimbursements	Developer	GLA
30/09/2025	P_TOWE09	No.1 West India Quay	Tower Hamlets	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	10/08/2020	27/07/2020	12/08/2020	28/07/2020	11/08/2020	11/08/2020		not required		GLA	16. Full Works Approved	Applications approved: for full costs	FALSE	West India Quay	22-26 Hertsmere Road	London	E14 4EF	Rendall and Rittner	Yianis group	Rendall and Rittner	West India Quay Development Company (Eastern) Limited	158	158	56.4	33	Incomplete - Requires follow up	Poplar and Limehouse	E14000882	E09000030	6153193	6193880	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				No.1 West India Quay, 22-26 Hertsmere Road, E14 4EF	158	158	158	6153193	ACM only	Government	GLA
30/09/2025	HA00045	Clifford Court	Trafford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	30/09/2019	30/09/2019	31/08/2022	31/08/2022	11/05/2020	11/05/2020		yes	HA						CHORLTON ROAD	Manchester	M15 4AS	Trafford Housing Trust	Trafford Housing Trust			87	87	46	14	Complete	Stretford and Urmston	E14000979	E08000009	200000340510	200000340510	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Clifford Court, CHORLTON ROAD, M15 4AS	87	87	87	200000340510	ACM only	Government	MHCLG
30/09/2025	HA00044	Empress Court	Trafford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	05/09/2019	05/09/2019	07/12/2021	04/12/2021	27/01/2020	27/01/2020		yes	HA						CORNBROOK PARK ROAD	Manchester	M15 4FH	Trafford Housing Trust	Trafford Housing Trust			87	87	46	14	Complete	Stretford and Urmston	E14000979	E08000009	100012893728	100012893728	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Empress Court, CORNBROOK PARK ROAD, M15 4FH	87	87	87	100012893728	ACM only	Government	MHCLG
30/09/2025	HA00046	Grafton Court	Trafford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	14/09/2020	14/09/2020	22/12/2021	14/01/2022	15/12/2020	17/12/2020		yes	HA						CHORLTON ROAD	Manchester	M15 4AQ	Trafford Housing Trust	Trafford Housing Trust			87	87	46	14	Complete	Stretford and Urmston	E14000979	E08000009	100012893721	100012893721	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Grafton Court, CHORLTON ROAD, M15 4AQ	87	87	87	100012893721	ACM only	Government	MHCLG
30/09/2025	HA00047	Pickford Court	Trafford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	14/09/2020	14/09/2020	22/12/2021	22/12/2021	10/12/2020	10/12/2020		yes	HA						Clayton Close	Manchester	M15 4BA	Trafford Housing Trust	Trafford Housing Trust			86	86	46	14	Complete	Stretford and Urmston	E14000979	E08000009	200000340703	200000340703	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Pickford Court, Clayton Close, M15 4BA	86	86	86	200000340703	ACM only	Government	MHCLG
30/09/2025	HA00051	Princess Court	Trafford	social	social-fund	Remediation completed		Remediation completed	Remediation completed	29/04/2019	29/04/2019	07/12/2021	04/12/2021	30/04/2020	30/04/2020		yes	HA						CORNBROOK PARK ROAD	Manchester	M15 4FE	Trafford Housing Trust	Trafford Housing Trust			87	87	46	14	Complete	Stretford and Urmston	E14000979	E08000009	100012893729	100012893729	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Princess Court, CORNBROOK PARK ROAD, M15 4FE	87	87	87	100012893729	ACM only	Government	MHCLG
30/09/2025	P_WALT02	Goodwood Apartments	Waltham Forest	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	01/01/2018		01/09/2018	07/11/2018				complete							91 PARADE GARDENS	London	E4 8ED	London and Quadrant Housing Trust					41		8	Complete	Chingford and Woodford Green	E14000634	E09000031	10091183825	10091183825	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Goodwood Apartments, 91 PARADE GARDENS, E4 8ED	41	41	41	10091183825	ACM only	Private	MHCLG
30/09/2025	P_WALT01	Lingfield Apartments	Waltham Forest	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	01/01/2018		01/09/2018	01/10/2018				complete							93 PARADE GARDENS	London	E4 8EB	London and Quadrant Housing Trust	L & Q Housing Association				53	19.17	7	Incomplete - requires follow up	Chingford and Woodford Green	E14000634	E09000031	10091183827	10091183827	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Lingfield Apartments, 93 PARADE GARDENS, E4 8EB	53	53	53	10091183827	ACM only	Private	MHCLG
30/09/2025	P_WAND0211	Aurora Apartments	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	04/12/2020	07/12/2020	30/04/2021	30/04/2021	15/01/2021	05/01/2021		yes							16 Buckhold Road	London	SW18 4FY		AVON GROUND RENTS LIMITED	Y & Y Management Ltd	MOUNT ANVIL		92				Putney	E14000887	E09000032		10091499769	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE				Aurora Apartments, 16 Buckhold Road, SW18 4FY	92	92	92	10091499769	ACM only	Private	MHCLG
30/09/2025	P_WAND0213	B2 Chapelier House	Wandsworth	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/12/2020	14/12/2020	23/12/2022	16/12/2022	22/04/2022	22/04/2022		yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		Eastfields Ave	London	SW18 1LR		Frasers Riverside Quarter Limited	FRASERS PROPERTY	Frasers Riverside Quarter Limited	62	62	23	7	Complete	Putney	E14000887	E09000032		10008157201	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	B2 Chapelier House, Eastfields Ave, SW18 1LR	62	62	62	10008157201	ACM/BSF RAS reimbursements	Developer	GLA
30/09/2025	S_WAND0276	Lucent House / (The Filaments)	Wandsworth	social	developer	Remediation completed		Remediation completed	Remediation completed	08/02/2021	08/02/2021	30/07/2021	05/08/2021	20/05/2021	20/05/2021		not required							11 Hardwicks Square	London	SW18 4GS						23	18	6	Complete	Putney	E14000887	E09000032		10091500587	FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Lucent House / (The Filaments), 11 Hardwicks Square, SW18 4GS	23	23	23	10091500587	ACM only	Private	MHCLG
30/09/2025	P_WAND0301	Millbrooke Court	Wandsworth	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	31/07/2023	31/07/2023	12/02/2024	12/02/2024	17/11/2023	12/02/2024		not required		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		Keswick Road	London	SW15 2RA		Laimond Properties Ltd	D&G Block Management	355 Developments Limited		73	21	7		Putney	E14000887	E09000032	100023700040		FALSE	FALSE	TRUE	TRUE	TRUE	TRUE				Millbrooke Court, Keswick Road, SW15 2RA	73	73	73	100023700040	ACM only	Government	GLA
30/09/2025	P_WAND0212	MILLINERS HOUSE	Wandsworth	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	07/12/2020	14/12/2020	23/12/2022	30/12/2022	26/04/2022	06/05/2022		yes		GLA	19. Practical Completion - Retention Period (12m)	Applications approved: for full costs	FALSE		EASTFIELDS AVENUE	London	SW18 1LR		Frasers Riverside Quarter Limited	FRASERS PROPERTY	Frasers Riverside Quarter Limited	62	54	21	7	Complete	Putney	E14000887	E09000032		10008157067	FALSE	TRUE	TRUE	TRUE	TRUE	TRUE	1		1	MILLINERS HOUSE, EASTFIELDS AVENUE, SW18 1LR	54	62	62	10008157067	ACM/BSF RAS reimbursements	Developer	GLA
30/09/2025	MR LA Wandsworth 00136	Castlemaine	Wandsworth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/04/2018	30/09/2018	02/11/2020	02/11/2020				yes	LA						Culvert Road	London	SW11 5BD	Wandsworth Council	London Borough of Wandsworth			118	114	58	21	Complete	Battersea	E14000549	E09000032	100023585995	100023585995	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Castlemaine, Culvert Road, SW11 5BD	114	118	118	100023585995	ACM only	Government	MHCLG
30/09/2025	P_WAND14	Copperlight Apartments	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	09/11/2020	09/11/2020	25/08/2021	25/08/2021	28/05/2021	28/05/2021		yes							16 Buckhold Road	London	SW18 4FY		AVON GROUND RENTS LIMITED	Y&Y Management	MOUNT ANVIL		92				Putney	E14000887	E09000032	10091499769	10091499769	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Copperlight Apartments, 16 Buckhold Road, SW18 4FY	92	92	92	10091499769	ACM only	Private	MHCLG
30/09/2025	P_WAND15	Parkside St Peters	Wandsworth	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	26/10/2020	26/10/2020	15/07/2021	02/07/2021	09/12/2020	09/12/2020		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		21 Plough Road	London	SW11 2DE		THORNSETT SOUTH LONDON LIMITED	0	THORNSETT SOUTH LONDON LIMITED	51	51	24	6	Complete	Battersea	E14000549	E09000032	10093419200	10093419200	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Parkside St Peters, 21 Plough Road, SW11 2DE	51	51	51	10093419200	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_WAND12	Sesame Apartments	Wandsworth	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	27/02/2023	27/02/2023	19/09/2025	19/09/2025	08/05/2024	31/05/2024		yes		GLA	18. On Site Monitoring	Applications approved: for full costs	FALSE		4 Holman Road	London	SW11 3PG	Adriatic Land	Adriatic Land	London Residential Management ("LRM")	Thornsett Residential Limited	80	80	22	8	Incomplete - requires follow up	Battersea	E14000549	E09000032	100023301730	100023301730	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Sesame Apartments, 4 Holman Road, SW11 3PG	80	80	80	100023301730	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	MR LA Wandsworth 00147	Sudbury House	Wandsworth	social	social-fund	Remediation completed		Remediation completed	Remediation completed	01/12/2017	13/11/2017	26/11/2020	26/11/2020				yes	LA						Wandsworth High Street	London	SW18 4LH	Wandsworth Council	London Borough of Wandsworth			132	132	75	25		Putney	E14000887	E09000032	121008079	121008079	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Sudbury House, Wandsworth High Street, SW18 4LH	132	132	132	121008079	ACM only	Government	MHCLG
30/09/2025	P_WAND08	Spinnaker House	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	22/06/2020		17/12/2020	17/12/2020				yes						Battersea Reach	Juniper Drive	London	SW18 1FR	Berkeley Homes	ST GEORGE BATTERSEA REACH LIMITED	Rendall and Rittner	Berkeley	103	103	34.2	12		Battersea	E14000549	E09000032	10024086905	10024086905	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Spinnaker House, Juniper Drive, SW18 1FR	103	103	103	10024086905	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND09	Eustace Building	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	17/08/2020	17/08/2020	07/10/2022	14/10/2022	31/03/2022	31/03/2022		yes						Chelsea Bridge Wharf	372 QUEENSTOWN ROAD	London	SW8 4PP	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	168		37	10	Complete	Battersea	E14000549	E09000032	121042097	121042097	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Eustace Building, 372 QUEENSTOWN ROAD, SW8 4PP	168	168	168	121042097	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND03	Hawker Building	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	29/06/2020	29/06/2020	18/02/2022	28/02/2022	05/03/2021	29/01/2021		yes						Chelsea Bridge Wharf	350 QUEENSTOWN ROAD	London	SW8 4AE	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	37		29	9	Complete	Battersea	E14000549	E09000032	121041683	121041683	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Hawker Building, 350 QUEENSTOWN ROAD, SW8 4AE	37	37	37	121041683	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND10	Horace Building	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	03/08/2020	03/08/2020	21/02/2022	28/02/2022	09/03/2021	26/03/2021		yes						Chelsea Bridge Wharf	364 QUEENSTOWN ROAD	London	SW8 4NH	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	28		30.7	8		Battersea	E14000549	E09000032	121041685	121041685	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Horace Building, 364 QUEENSTOWN ROAD, SW8 4NH	28	28	28	121041685	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND01	Lanson Building	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	12/06/2020	14/06/2020	11/05/2022	06/05/2022	05/03/2021	29/01/2021		yes						Chelsea Bridge Wharf	348 Queenstown Road	London	SW8 3QQ	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	158		41.4		Incomplete	Battersea	E14000549	E09000032	121041682	121041682	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Lanson Building, 348 Queenstown Road, SW8 3QQ	158	158	158	121041682	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND11	Oswald Building	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	17/08/2020	17/08/2020	07/10/2022	14/10/2022	31/03/2022	31/03/2022		yes						Chelsea Bridge Wharf	374 QUEENSTOWN ROAD	London	SW8 4NU	Berkeley Homes	Berkeley Homes	Rendall and Rittner	Berkeley	139		32.9			Battersea	E14000549	E09000032	121042184	121042184	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Oswald Building, 374 QUEENSTOWN ROAD, SW8 4NU	139	139	139	121042184	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND04	1 Eastfields Avenue	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	06/03/2019	25/02/2019	03/06/2019	01/12/2019				yes						Eastfields Avenue	Eastfields Avenue	London	SW18 1FQ	Frasers Riverside Quarter Limited	Frasers Riverside Quarter Limited		Frasers Riverside Quarter Limited	58	58	30.8			Putney	E14000887	E09000032	10090501385	10090501385	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	1 Eastfields Avenue, Eastfields Avenue, SW18 1FQ	58	58	58	10090501385	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND05	3 Eastfields Avenue	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	09/05/2019	25/02/2019	30/08/2019	01/12/2019				yes						Eastfields Avenue	Eastfields Avenue	London	SW18 1GN	Frasers Riverside Quarter Limited	Frasers Riverside Quarter Limited		Frasers Riverside Quarter Limited	81	81	45.6	13	Complete	Putney	E14000887	E09000032	10090501743	10090501743	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	3 Eastfields Avenue, Eastfields Avenue, SW18 1GN	81	81	81	10090501743	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND06	5 Eastfields Avenue	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	30/08/2019	25/02/2019	05/12/2019	01/12/2019				yes						Eastfields Avenue	Eastfields Avenue	London	SW18 1FU	Frasers Riverside Quarter Limited	Frasers Riverside Quarter Limited		Frasers Riverside Quarter Limited	55	81	56	16	Incomplete - requires follow up	Putney	E14000887	E09000032	10093417088	10093417088	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	5 Eastfields Avenue, Eastfields Avenue, SW18 1FU	55	81	55	10093417088	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WAND07	7 Eastfields Avenue	Wandsworth	private residential	developer	Remediation completed		Remediation completed	Remediation completed	05/12/2019	25/02/2019	03/03/2020	31/01/2020				yes						Eastfields Avenue	Eastfields Avenue	London	SW18 1RA	Frasers Riverside Quarter Limited	Frasers Riverside Quarter Limited	Optivo	Frasers Riverside Quarter Limited	50	18	47	13	Incomplete - requires follow up	Putney	E14000887	E09000032	10093417207	10093417207	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	7 Eastfields Avenue, Eastfields Avenue, SW18 1RA	18	50	50	10093417207	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	DfE00007	Warrington UTC	Warrington	public	public	Remediation completed		Remediation completed	Remediation completed			11/09/2019					yes							Dallam Lane	Warrington	WA2 7NG	Warrington UTC	Warrington UTC					18.9			Warrington South	E14001018	E06000007	10092996256	10092996256	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Warrington UTC, Dallam Lane, WA2 7NG				10092996256	ACM only	Private	MHCLG
30/09/2025	P_WEST13	5 Praed Street	Westminster	private residential	freeholder	Plans in place		Plans in place	Plans in place		06/04/2026		06/04/2027			Vacant not currently occupied	not required							5 Praed Street	London	W2 1NJ	Behbehani Middle East Trading Company	BEHBEHANI MIDDLE EAST GENERAL TRADING COMPANY	Bhoj Management Ltd		11	21	21.3	9	Complete	Cities of London and Westminster	E14000639	E09000033	100023476824	100023476824	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				5 Praed Street, 5 Praed Street, W2 1NJ	11	21		100023476824	ACM only	Private	MHCLG
30/09/2025	P_WEST12	60-62 St Martins Lane	Westminster	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	12/07/2021	12/07/2021	15/12/2021	14/12/2021	25/11/2021	19/11/2021		not required		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		St Martins Lane	London	WC2N 4JS	HB St Martins Pte	HB St Martins Pte	CBRE	HB St Martins Pte	2	1	18.85	6	Complete	Cities of London and Westminster	E14000639	E09000033	100023613267	100023613267	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				60-62 St Martins Lane, St Martins Lane, WC2N 4JS	1	2	2	100023613267	ACM only	Government	GLA
30/09/2025	P_WEST01	Balmoral Apartments	Westminster	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	10/08/2020	10/08/2020	11/06/2021	18/06/2021	18/12/2020	18/12/2020		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		2 Praed Street	London	W2 1JL	FREEHOLD MANAGERs (NOMINEEs) LIMITED	Freehold Managers (Nominees) Limited	Firstport	Wates Group Limited	188	185	31.4	15	Complete	Cities of London and Westminster	E14000639	E09000033	10033557493	10033557493	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	Balmoral Apartments, 2 Praed Street, W2 1JL	185	188	188	10033557493	ACM RAS reimbursements	Developer	GLA
30/09/2025	MR LA Westminster 00001	Brinklow House	Westminster	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/12/2017	22/10/2018	30/11/2020	30/11/2020				not required	LA						TORQUAY STREET	London	W2 5EN	Westminster City Council	City of Westminster Council			125	127	55	21	Complete	Westminster North	E14001036	E09000033	100023617196	100023617196	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Brinklow House, TORQUAY STREET, W2 5EN	125	127	125	100023617196	ACM only	Government	MHCLG
30/09/2025	P_WEST15	Cornwall House	Westminster	private residential	warranty claim accepted	Remediation completed		Remediation completed	Remediation completed	03/08/2020	03/08/2020	18/03/2021	26/02/2021	13/11/2020			Yes							7 Allsop Place	London	NW1 5BF	Allsop Place Management Ltd	Allsop Place Management Ltd	HML	Cromwell Land ResidentialIn administration	31	31	21.2	14		Westminster North	E14001036	E09000033	10033613322	10033613322	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Cornwall House, 7 Allsop Place, NW1 5BF	31	31	31	10033613322	ACM only	Private	MHCLG
30/09/2025	P_WEST14	Eagle Wharf	Westminster	private residential	private-fund	Remediation started		Remediation started	Remediation started	04/01/2021	15/12/2020		27/03/2026	19/01/2022	19/01/2022		not required		GLA	18. On Site Monitoring	Applications approved: for full costs	FALSE		Grosvenor Road	London	SW1V 3JS	Majorarch Limited	Majorarch Limited	LRM	Majorarch Limited	41	40	19.3	6	Complete	Cities of London and Westminster	E14000639	E09000033	10033524105	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Eagle Wharf, Grosvenor Road, SW1V 3JS	40	41	41	10033524105	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	MR LA Westminster 00002	Gaydon House	Westminster	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/12/2017	22/10/2018	30/11/2020	30/11/2020				not required	LA						BOURNE TERRACE	London	W2 5TG	Westminster City Council	City of Westminster Council			125	127	55	21	Complete	Westminster North	E14001036	E09000033	100023620205	100023620205	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Gaydon House, BOURNE TERRACE, W2 5TG	125	127	125	100023620205	ACM only	Government	MHCLG
30/09/2025	P_WEST0543	Icon Apartments	Westminster	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	16/12/2021	16/12/2021	21/02/2022	16/12/2021	21/12/2021	21/12/2021		not required		GLA	16. Full Works Approved	Applications approved: for full costs	FALSE		129 Grosvenor Road	London	SW1V 3JY		Icon Building Freehold Limited	Douglas and Gordon	London Town		13	18.6	7	Complete	Cities of London and Westminster	E14000639	E09000033	200001878111	200001878111	FALSE	FALSE	FALSE	TRUE	TRUE	TRUE				Icon Apartments, 129 Grosvenor Road, SW1V 3JY	13	13	13	200001878111	ACM only	Government	GLA
30/09/2025	MR LA Westminster 00006	Oversley House	Westminster	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/12/2017	22/10/2018	19/02/2021	01/03/2021				not required	LA						ALFRED ROAD	London	W2 5HE	Westminster City Council	City of Westminster Council			125	127	55	21	Complete	Westminster North	E14001036	E09000033	100023617462	100023617462	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Oversley House, ALFRED ROAD, W2 5HE	125	127	125	100023617462	ACM only	Government	MHCLG
30/09/2025	MR LA Westminster 00004	Polesworth House	Westminster	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/12/2017	22/10/2018	19/02/2021	01/03/2021				not required	LA						ALFRED ROAD	London	W2 5HB	Westminster City Council	City of Westminster Council			125	127	55	21	Complete	Westminster North	E14001036	E09000033	100023617463	100023617463	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Polesworth House, ALFRED ROAD, W2 5HB	125	127	125	100023617463	ACM only	Government	MHCLG
30/09/2025	MR LA Westminster 00003	Princethorpe House	Westminster	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/12/2017	22/10/2018	30/11/2020	30/11/2020				not required	LA						WOODCHESTER SQUARE	London	W2 5SU	Westminster City Council	City of Westminster Council			125	127	55	21	Complete	Westminster North	E14001036	E09000033	100023619451	100023619451	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Princethorpe House, WOODCHESTER SQUARE, W2 5SU	125	127	125	100023619451	ACM only	Government	MHCLG
30/09/2025	P_WEST11	Westminster Green	Westminster	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	19/04/2021	19/04/2021	02/12/2022	10/12/2022	02/03/2022	02/03/2022		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE		8 Dean Ryle Street	London	SW1P 4DA	Hurford Salvi Carr Property Management	Westminster Green Management Company Limited	Hurford Salvi Carr	Clementine Investment Ltd with Laing O'Rourke as the buiding contractors.	180	176	30	13	Complete	Cities of London and Westminster	E14000639	E09000033	10033525387	10033525387	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Westminster Green, 8 Dean Ryle Street, SW1P 4DA	176	180	180	10033525387	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	MR LA Westminster 00005	Wilmcote House	Westminster	social	social-fund	Remediation completed		Remediation completed	Remediation completed	04/12/2017	22/10/2018	30/11/2020	30/11/2020				not required	LA						WOODCHESTER SQUARE	London	W2 5SS	Westminster City Council	City of Westminster Council			125	127	55	21	Complete	Westminster North	E14001036	E09000033	100023619452	100023619452	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Wilmcote House, WOODCHESTER SQUARE, W2 5SS	125	127	125	100023619452	ACM only	Government	MHCLG
30/09/2025	P_WEST02	4 Merchant Square East	Westminster	private residential	freeholder	Remediation completed		Remediation completed	Remediation completed	02/07/2017		28/06/2018	01/05/2018				complete						4 Merchant Square	Merchant Square East	London	W2 1AQ	Rendall and Rittner	4 Merchant Square Residential Ltd	Rendall and Rittner	European Land Property Limited	152	148	40.2			Cities of London and Westminster	E14000639	E09000033	10033614432	10033614432	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			4 Merchant Square East, Merchant Square East, W2 1AQ	148	152	152	10033614432	ACM /BSF crossovers only - no RAS	Private	MHCLG
30/09/2025	P_WEST09	12 Hermitage Street	Westminster	private residential	developer	Remediation completed		Remediation completed	Remediation completed	18/05/2020	09/03/2020	13/10/2020	31/10/2020				Yes						NWG Exchange	Hermitage Street	London	W2 1BH	Taylor Wimpey	Amwaj Property Limited [Adriatic Land 7 Limited owns a Head Lease interest]	Savills	Taylor Wimpey	47	47	43.54	14	Complete	Cities of London and Westminster	E14000639	E09000033	10033635776	10033635776	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	12 Hermitage Street, Hermitage Street, W2 1BH	47	47	47	10033635776	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WEST08	2 Hermitage Street	Westminster	private residential	developer	Remediation completed		Remediation completed	Remediation completed	18/05/2020	09/03/2020	13/10/2020	31/10/2020				Yes						NWG Exchange	Hermitage Street	London	W2 1AR	Taylor Wimpey	Amwaj Property Limited [Adriatic Land 7 Limited owns a Head Lease interest]	Savills	Taylor Wimpey	30	27	43.54	14	Complete	Cities of London and Westminster	E14000639	E09000033	10033635671	10033635671	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	2 Hermitage Street, Hermitage Street, W2 1AR	27	30	30	10033635671	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WEST07	6 Hermitage Street	Westminster	private residential	developer	Remediation completed		Remediation completed	Remediation completed	18/05/2020	09/03/2020	13/10/2020	31/10/2020				Yes						NWG Exchange	Hermitage Street	London	W2 1BE	Taylor Wimpey	Amwaj Property Limited [Adriatic Land 7 Limited owns a Head Lease interest]	Savills	Taylor Wimpey	124	76	43.54	14	Complete	Cities of London and Westminster	E14000639	E09000033	10033635699	10033635699	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE			1	6 Hermitage Street, Hermitage Street, W2 1BE	76	124	124	10033635699	ACM/ RAS crossovers - non transfers or reimbursements	Private	MHCLG
30/09/2025	P_WEST03	Marshall Building	Westminster	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2020	03/08/2020	16/09/2022	30/09/2022	27/08/2021	28/08/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE	Paddington Walk	3 Hermitage Street	London	W2 1PB	Paddington Development Corporation	European Land	Rendall and Rittner	European Land Property Limited	78	65	33.4	15		Cities of London and Westminster	E14000639	E09000033	10033528022	10033528022	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Marshall Building, 3 Hermitage Street, W2 1PB	65	78	78	10033528022	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_WEST04	Montgomery House	Westminster	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2020	03/08/2020	05/10/2022	30/09/2022	27/08/2021	28/08/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE	Paddington Walk	135 Harrow Road	London	W2 1HG	European Land	European Land	Rendall and Rittner		77	79	33.4	15		Cities of London and Westminster	E14000639	E09000033	10033613313	10033613313	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Montgomery House, 135 Harrow Road, W2 1HG	77	79	77	10033613313	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_WEST05	Munkenbeck Building	Westminster	private residential	private-fund	Remediation completed		Remediation completed	Remediation completed	01/08/2020	03/08/2020	05/10/2022	17/12/2021	27/08/2021	28/08/2021		yes		GLA	20. Retention Payment - Application Closed	Applications approved: for full costs	FALSE	Paddington Walk	5 Hermitage Street	London	W2 1PW	Paddington Development Corporation	European Land	Rendall and Rittner	European Land Property Limited	77	87	25.9	15		Cities of London and Westminster	E14000639	E09000033	10033528123	10033528123	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE	1			Munkenbeck Building, 5 Hermitage Street, W2 1PW	77	87	77	10033528123	ACM /BSF crossovers only - no RAS	Government	GLA
30/09/2025	P_WIND02	Premier Inn Maidenhead Town Centre	Windsor and Maidenhead	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	05/03/2019	05/03/2019	01/05/2019	20/12/2019				not required							Kidwells Park Drive	Maidenhead	SL6 1RL			TowerEight				28	8	Complete	Maidenhead	E14000803	E06000040		10012333535	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn Maidenhead Town Centre, Kidwells Park Drive, SL6 1RL				10012333535	ACM only	Private	MHCLG
30/09/2025	P_WOKI01	Premier Inn Eurobet House	Woking	hotel	hotel	Remediation completed		Remediation completed	Remediation completed	20/05/2019	01/04/2019	15/01/2020	29/11/2019				yes							10-21 Church Street West	Woking	GU21 6HT	Premier Inn		TowerEight on behalf of Whitbread					8	Complete	Woking	E14001047	E07000217	10000003460	10000003460	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Premier Inn Eurobet House, 10-21 Church Street West, GU21 6HT				10000003460	ACM only	Private	MHCLG
30/09/2025	P_WOLV01	Block B - Liberty Living, Liberty Heights	Wolverhampton	student	student	Remediation completed		Remediation completed	Remediation completed	01/02/2018		01/08/2018	01/08/2018				yes							1 Culwell Street	Wolverhampton	WV10 0JT	Liberty Heights						30	10	Complete	Wolverhampton North East	E14001049	E08000031	10090011665	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Block B - Liberty Living, Liberty Heights, 1 Culwell Street, WV10 0JT				10090011665	ACM only	Private	MHCLG
30/09/2025	P_WOLV02	Block C - Liberty Living, Liberty Heights	Wolverhampton	student	student	Remediation completed		Remediation completed	Remediation completed	01/02/2018		01/08/2018	01/08/2018				yes							1 Culwell Street	Wolverhampton	WV10 0JT	Liberty Heights						24	8	Complete	Wolverhampton North East	E14001049	E08000031	10090011665	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Block C - Liberty Living, Liberty Heights, 1 Culwell Street, WV10 0JT				10090011665	ACM only	Private	MHCLG
30/09/2025	NHS00005	Heart and Lung Building	Wolverhampton	public	public	Remediation completed		Remediation completed	Remediation completed	28/01/2019		01/10/2019	01/10/2019				yes							New Cross Hospital	Wolverhampton	WV10 0QP	New Cross Hospital (Wolverhampton), RL401, WV10 0QP	New Cross Hospital (Wolverhampton)								Wolverhampton North East	E14001049	E08000031	100071556759	0	TRUE	TRUE	TRUE	TRUE	TRUE	TRUE				Heart and Lung Building, New Cross Hospital, WV10 0QP				100071556759	ACM only	Private	MHCLG

## ACM_1
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Tenure	Number of buildings this month	Number of buildings last month	Monthly change
Social sector residential	163	163	0
Private sector residential	246	246	0
Student accommodation	61	61	0
Hotels	33	33	0
Publicly-owned buildings	8	8	0
Total buildings	511	511	0

## ACM_2
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Completed Remediation	142	87%	212	86%	58	95%	29	88%	7	88%	448	88%
Works complete awaiting building control signoff	7	4%	7	3%	1	2%	0	0%	1	13%	16	3%
Remediation started - cladding removed	12	7%	8	3%	0	0%	1	3%	0	0%	21	4%
Remediation started	0	0%	10	4%	2	3%	1	3%	0	0%	13	3%
Remediation plans in place	1	1%	8	3%	0	0%	0	0%	0	0%	9	2%
Reported an intent to remediate	1	1%	0	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	2	6%	0	0%	3	1%
Total buildings	163	100%	246	100%	61	100%	33	100%	8	100%	511	100%

## ACM_3
Remediation status of buildings yet to complete ACM remediation by tenure, England, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff - Vacant	0	0	0	0	0
Remediation started - cladding removed - Vacant	0	0	0	0	0
Remediation started - Vacant	0	0	0	0	0
Remediation plans in place - Vacant	0	1	0	0	0
Reported an intent to remediate - Vacant	0	0	0	0	0
Remediation plan unclear - Vacant	0	0	0	0	0
Total vacant buildings	0	1	0	0	0

Remediation Category for occupied buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	7	7	1	0	1
Remediation started - cladding removed	12	8	0	1	0
Remediation started	0	10	2	1	0
Remediation plans in place	1	7	0	0	0
Reported an intent to remediate	1	0	0	0	0
Remediation plan unclear	0	1	0	2	0
Total occupied buildings	21	33	3	4	1

## ACM_4
ACM remediation progress by local authority, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	None	100%	100%
Barnet	6 to 10	1 to 5	Between 50% and 99%	100%
Bedford	1 to 5	None	100%	100%
Birmingham	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Bournemouth, Christchurch and Poole	1 to 5	1 to 5	Between 50% and 99%	100%
Bradford	1 to 5	None	100%	100%
Brent	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	None	100%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	100%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	100%
Hackney	11 to 20	1 to 5	Between 50% and 99%	100%
Hammersmith and Fulham	6 to 10	None	100%	100%
Haringey	6 to 10	None	100%	100%
Harrow	1 to 5	None	100%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	None	100%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Leeds	11 to 20	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	1 to 5	Between 50% and 99%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	100%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	None	100%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	None	100%	100%
Newcastle upon Tyne	11 to 20	1 to 5	Between 50% and 99%	100%
Newham	Over 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Norwich	6 to 10	1 to 5	Between 50% and 99%	100%
Nottingham	6 to 10	None	100%	100%
Oldham	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	None	100%	100%
Reading	1 to 5	None	100%	100%
Redbridge	1 to 5	None	100%	100%
Salford	Over 20	6 to 10	Between 50% and 99%	100%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	1 to 5	Between 50% and 99%	100%
Slough	6 to 10	1 to 5	Between 50% and 99%	100%
Southend-on-Sea	1 to 5	1 to 5	Less than 50%	Less than 50%
Southwark	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	6 to 10	1 to 5	Between 50% and 99%	100%
Sutton	1 to 5	1 to 5	Less than 50%	Between 50% and 99%
Tower Hamlets	Over 20	6 to 10	Between 50% and 99%	100%
Trafford	1 to 5	None	100%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	11 to 20	None	100%	100%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	None	100%	100%
Wolverhampton	1 to 5	None	100%	100%

## ACM_5
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 30 September 2025
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	38	81%	18	100%	5	100%	2	100%	0	0%	63	88%
Works complete awaiting building control signoff	3	6%	0	0%	0	0%	0	0%	0	0%	3	4%
Remediation started - cladding removed	6	13%	0	0%	0	0%	0	0%	0	0%	6	8%
Remediation started	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	18	100%	5	100%	2	100%	0	0%	72	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	72	87%	145	85%	14	93%	13	81%	0	0%	244	85%
Works complete awaiting building control signoff	4	5%	3	2%	0	0%	0	0%	1	100%	8	3%
Remediation started - cladding removed	6	7%	8	5%	0	0%	1	6%	0	0%	15	5%
Remediation started	0	0%	6	4%	1	7%	1	6%	0	0%	8	3%
Plans in place	0	0%	8	5%	0	0%	0	0%	0	0%	8	3%
Responded with intent	1	1%	0	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	1%	0	0%	1	6%	0	0%	2	1%
Total buildings	83	100%	171	100%	15	100%	16	100%	1	100%	286	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	97%	49	86%	39	95%	14	93%	7	100%	141	92%
Works complete awaiting building control signoff	0	0%	4	7%	1	2%	0	0%	0	0%	5	3%
Remediation started - cladding removed	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation started	0	0%	4	7%	1	2%	0	0%	0	0%	5	3%
Plans in place	1	3%	0	0%	0	0%	0	0%	0	0%	1	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	1	7%	0	0%	1	1%
Total buildings	33	100%	57	100%	41	100%	15	100%	7	100%	153	100%

## ACM_6
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 30 September 2025
Back to Contents
This worksheet contains four tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	136	88%	176	94%	52	100%	26	96%	7	88%	397	93%
Works complete awaiting building control signoff	6	4%	1	1%	0	0%	0	0%	1	13%	8	2%
Remediation started - cladding removed	12	8%	4	2%	0	0%	1	4%	0	0%	17	4%
Remediation started	0	0%	5	3%	0	0%	0	0%	0	0%	5	1%
Plans in place	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	154	100%	187	100%	52	100%	27	100%	8	100%	428	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	137	88%	196	92%	54	100%	28	97%	7	88%	422	92%
Works complete awaiting building control signoff	7	4%	3	1%	0	0%	0	0%	1	13%	11	2%
Remediation started - cladding removed	12	8%	5	2%	0	0%	1	3%	0	0%	18	4%
Remediation started	0	0%	6	3%	0	0%	0	0%	0	0%	6	1%
Plans in place	0	0%	2	1%	0	0%	0	0%	0	0%	2	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	156	100%	212	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	141	88%	205	91%	55	98%	29	94%	7	88%	437	91%
Works complete awaiting building control signoff	7	4%	4	2%	0	0%	0	0%	1	13%	12	2%
Remediation started - cladding removed	12	8%	7	3%	0	0%	1	3%	0	0%	20	4%
Remediation started	0	0%	7	3%	1	2%	1	3%	0	0%	9	2%
Plans in place	0	0%	3	1%	0	0%	0	0%	0	0%	3	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	160	100%	226	100%	56	100%	31	100%	8	100%	481	100%

Identified by 31 December 2022	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	141	88%	209	90%	55	98%	29	94%	7	88%	441	91%
Works complete awaiting building control signoff	7	4%	5	2%	0	0%	0	0%	1	13%	13	3%
Remediation started - cladding removed	12	8%	7	3%	0	0%	1	3%	0	0%	20	4%
Remediation started	0	0%	7	3%	1	2%	1	3%	0	0%	9	2%
Plans in place	0	0%	3	1%	0	0%	0	0%	0	0%	3	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	160	100%	232	100%	56	100%	31	100%	8	100%	487	100%

Identified by 31 December 2023	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	142	88%	209	88%	56	97%	29	94%	7	88%	443	89%
Works complete awaiting building control signoff	7	4%	6	3%	1	2%	0	0%	1	13%	15	3%
Remediation started - cladding removed	12	7%	7	3%	0	0%	1	3%	0	0%	20	4%
Remediation started	0	0%	8	3%	1	2%	1	3%	0	0%	10	2%
Plans in place	0	0%	6	3%	0	0%	0	0%	0	0%	6	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	161	100%	237	100%	58	100%	31	100%	8	100%	495	100%

Identified by 31 December 2024	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	142	88%	211	86%	58	97%	29	91%	7	88%	447	88%
Works complete awaiting building control signoff	7	4%	7	3%	1	2%	0	0%	1	13%	16	3%
Remediation started - cladding removed	12	7%	7	3%	0	0%	1	3%	0	0%	20	4%
Remediation started	0	0%	10	4%	1	2%	1	3%	0	0%	12	2%
Plans in place	1	1%	8	3%	0	0%	0	0%	0	0%	9	2%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Total buildings	162	100%	244	100%	60	100%	32	100%	8	100%	506	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	142	87%	212	86%	58	95%	29	88%	7	88%	448	88%
Works complete awaiting building control signoff	7	4%	7	3%	1	2%	0	0%	1	13%	16	3%
Remediation started - cladding removed	12	7%	8	3%	0	0%	1	3%	0	0%	21	4%
Remediation started	0	0%	10	4%	2	3%	1	3%	0	0%	13	3%
Plans in place	1	1%	8	3%	0	0%	0	0%	0	0%	9	2%
Responded with intent	1	1%	0	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	2	6%	0	0%	3	1%
Total buildings	163	100%	246	100%	61	100%	33	100%	8	100%	511	100%

## ACM_7
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed total	10,700	18,000	21,300	28,700	32,000
Remediation completed	10,100	17,600	20,700	27,600	30,800
Works complete awaiting building control signoff	600	500	600	1,100	1,200
Yet to complete remediation [note_3]	1,300	1,900	2,100	3,200	3,400
Occupied and yet to complete remediation	1,300	1,900	2,000	3,200	3,400
Total	12,000	19,900	23,400	31,900	35,400

Leasehold dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed total	3,000	18,000	21,300	21,000	24,300
Remediation completed	2,800	17,600	20,700	20,400	23,600
Works complete awaiting building control signoff	200	500	600	700	700
Yet to complete remediation [note_3]	400	1,900	2,100	2,200	2,400
Occupied and yet to complete remediation	400	1,900	2,000	2,200	2,400
Total	3,400	19,900	23,400	23,300	26,700

## ACM_8
ACM remediation progress by sources of funding, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note 4]	Not in social fund	Private: government funded / [note 5]	Private: not government funded
Remediation completed	135	7	95	117
Works complete awaiting building control signoff	4	3	5	2
Remediation started - cladding removed	5	7	8	0
Remediation started	0	0	6	4
Plans in place	0	1	6	2
Responded with intent	0	1	0	0
Remediation plan unclear	0	0	0	1
Total	144	19	120	126

## ACM_9
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	0	0
Applications approved: for pre-contract support	1	0
Full cost application submitted	0	0
Applications approved: for full costs	67	40
TOTAL	68	40

## ACM_10
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	297	235
Expenditure [note_8, note_9]	268	343

## ACM_11
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note 63]	Dec-18 / Number	Dec-19 / Number	Dec-20 / Number	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 / Number	Jun-25 / Number	Jul-25 / Number	Aug-25 / Number	Sep-25 / Number
Completed Remediation	67	135	216	289	354	357	357	357	359	360	364	367	368	369	369	388	397	399	401	401	405	406	408	411	412	415	416	416	420	423	426	427	428	432	436	437	445	448
Works complete awaiting building control signoff			33	64	53	50	51	51	51	52	51	52	54	53	53	34	28	31	32	32	30	30	29	27	30	28	28	28	26	23	20	26	26	25	21	23	17	16
Remediation started - cladding removed			48	57	35	36	36	37	38	38	38	36	35	37	38	39	37	35	33	33	33	33	32	33	31	30	31	31	29	29	31	29	29	27	28	25	23	21
Remediation started	101	123	120	39	21	21	21	21	19	18	15	15	13	13	13	15	14	15	19	21	19	18	18	17	17	17	15	17	17	18	16	12	11	11	12	12	12	13
Remediation plans in place	171	104	32	15	13	12	11	12	12	14	14	15	15	15	15	14	13	14	9	7	8	8	8	8	8	19	20	18	19	18	18	18	18	18	9	9	10	9
Reported an intent to remediate	40	78	11	15	9	9	11	10	10	7	7	5	5	3	3	1	2	1	1	1	1	1	1	1	1	1	1	1	1	1	1	0	0	0	0	1	1	1
Remediation plan unclear	58	10	2	2	2	3	3	2	1	1	1	1	2	2	4	5	5	1	1	1	2	2	2	2	4	3	3	3	2	2	3	3	4	4	5	4	3	3
Total buildings	437	450	462	481	487	488	490	490	490	490	490	491	492	492	495	496	496	496	496	496	498	498	498	499	503	513	514	514	514	514	515	515	516	517	511	511	511	511

Remediation Category [note 10]	Dec-18 / Percentage (%)	Dec-19 / Percentage (%)	Dec-20 / Percentage (%)	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)	Sep-24 / Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 / Percentage (%)	Jun-25 / Percentage (%)	Jul-25 / Percentage (%)	Aug-25 / Percentage (%)	Sep-25 / Percentage (%)
Completed Remediation	15%	30%	47%	60%	73%	73%	73%	73%	73%	73%	74%	75%	75%	75%	75%	78%	80%	80%	81%	81%	81%	82%	82%	82%	82%	81%	81%	81%	82%	82%	83%	83%	83%	84%	85%	86%	87%	88%
Works complete awaiting building control signoff			7%	13%	11%	10%	10%	10%	10%	11%	10%	11%	11%	11%	11%	7%	6%	6%	6%	6%	6%	6%	6%	5%	6%	5%	5%	5%	5%	4%	4%	5%	5%	5%	4%	5%	3%	3%
Remediation started - cladding removed			10%	12%	7%	7%	7%	8%	8%	8%	8%	7%	7%	8%	8%	8%	7%	7%	7%	7%	7%	7%	6%	7%	6%	6%	6%	6%	6%	6%	6%	6%	6%	5%	5%	5%	5%	4%
Remediation started	23%	27%	26%	8%	4%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%	3%	3%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%	4%	3%	2%	2%	2%	2%	2%	2%	2%
Remediation plans in place	39%	23%	7%	3%	3%	2%	2%	2%	2%	3%	3%	3%	3%	3%	3%	3%	3%	3%	2%	1%	2%	2%	2%	2%	2%	4%	4%	4%	4%	4%	3%	3%	3%	3%	2%	2%	2%	2%
Reported an intent to remediate	9%	17%	2%	3%	2%	2%	2%	2%	2%	1%	1%	1%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%
Remediation plan unclear	13%	2%	0%	0%	0%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	1%	0%	0%	1%	1%	1%	1%	1%	1%	1%	1%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 30 September 2025
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete
Waking Watch Relief Fund	329	468	212	320	24,700	27.3	170	105	305
Waking Watch Replacement Fund 2022	38	67	25	47	2,200	2.4	216	210	42
Waking Watch Replacement Fund 2023	272	493	194	321	18,000	32.6	372	295	195
Total [note_10]	639	1,028	431	688	44,900	62.3	259	165	542

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 30 September 2025
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_11]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	9	8	1	0	0	11%	89%	9	8	89%	3%	1.6	200,826	180,147
Bristol	3	2	1	0	0	33%	67%	3	2	67%	1%	0.1	46,256	46,256
Greater London Authority	110	65	29	16	0	26%	59%	171	111	65%	35%	8.3	74,911	64,551
Greater Manchester Combined Authority	25	20	5	0	0	20%	80%	38	33	87%	10%	2.5	75,477	76,928
Leeds	10	9	0	1	0	0%	90%	12	11	92%	3%	1.8	162,466	124,500
Liverpool	18	17	1	0	0	6%	94%	19	18	95%	6%	1.7	94,400	63,784
Newcastle	3	3	0	0	0	0%	100%	3	3	100%	1%	0.4	128,496	163,181
Sheffield	6	5	0	1	0	0%	83%	7	6	86%	2%	0.5	88,753	87,828
MHCLG (1st Tranche)	35	21	14	0	0	40%	60%	55	39	71%	12%	2.7	68,957	65,577
MHCLG (2nd Tranche)	60	27	32	1	0	53%	45%	70	34	49%	11%	3.8	112,303	81,624
MHCLG (3rd Tranche)	50	35	14	1	0	28%	70%	81	55	68%	17%	3.9	70,341	57,389
MHCLG Total	145	83	60	2	0	41%	57%	206	128	62%	40%	10.4	81,066	65,486
Total [note_10]	329	212	97	20	0	29%	64%	468	320	68%	100%	27.3	85,268	67,894

## WWRF_3
Waking Watch Replacement Fund 2022 applications, buildings and approved funding by administering authority, 30 September 2025
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_12]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	2	2	0	0	0	0%	100%	4	4	100%	9%	0.4	89,328	87,683
MHCLG	25	21	1	3	0	4%	84%	46	40	87%	85%	1.8	45,560	26,643
Greater Manchester Combined Authority	11	2	9	0	0	82%	18%	17	3	18%	6%	0.2	65,206	46,743
Leeds	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Liverpool	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Sheffield	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Total [note_10]	38	25	10	3	0	26%	66%	67	47	70%	100%	2.4	50,539	30,209

## WWRF_4
Waking Watch Replacement Fund 2023 applications, buildings and approved funding by administering authority, 30 September 2025
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
MHCLG	272	194	23	28	26	8%	71%	493	321	65%	100%	32.6	98,940	76,000
Total [Note 87]	272	194	23	28	26	8%	71%	493	321	65%	100%	32.6	98,940	76,000

## BSF_1
Remediation status of eligible buildings within BSF by tenure, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note 23][note 60]	Social sector residential (leaseholder) / Number	Social sector residential (leaseholder) / Percentage (%)	Social Sector Financial Viability / Number	Social Sector Financial Viability / Percentage (%)	Social Sector Total / Number	Social Sector Total / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Total residential Number	Total residential Percentage (%)
Remediation complete	78	63%	7	41%	85	60%	228	37%	313	41%
Remediation complete: awaiting building control sign-off	16	13%	2	12%	18	13%	109	17%	127	17%
Remediation started	26	21%	0	0%	26	18%	85	14%	111	15%
Remediation plans in place	3	2%	6	35%	9	6%	153	25%	162	21%
Intent to remediate	1	1%	2	12%	3	2%	49	8%	52	7%
Total buildings [note 10]	124	100%	17	100%	141	100%	624	100%	765	100%

## BSF_2
BSF remediation progress of eligible buildings by region, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note 23]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF / Percentage(%)	Not Started Remediation / Number	Not Started Remediation / Percentage(%)	Started Remediation / Number	Started Remediation / Percentage(%)	Completed Remediation [note_13] / Number	Completed Remediation [note_13] / Percentage(%)	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	94	12%	6	3%	8	7%	80	18%	85%	94%
London	511	67%	202	94%	74	67%	235	53%	46%	60%
East of England	15	2%	0	0%	4	4%	11	3%	73%	100%
East Midlands	13	2%	0	0%	4	4%	9	2%	69%	100%
North East	7	1%	1	0%	1	1%	5	1%	71%	86%
South East	48	6%	1	0%	1	1%	46	10%	96%	98%
South West	21	3%	0	0%	6	5%	15	3%	71%	100%
West Midlands	13	2%	1	0%	3	3%	9	2%	69%	92%
Yorkshire and The Humber	43	6%	3	1%	10	9%	30	7%	70%	93%
Total	765	100%	214	100%	111	100%	440	100%	58%	72%

## BSF_3
BSF number of eligible buildings by funding allocations, expenditure and tenure, England, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data is not available for these variables.
Table BSF_3a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF .
Funding Allocations [note_15][note_56][note_59]	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings [Note 14]	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Funding / (£ millions)
Full Applications Approved	470	1,974	5	5
Pre-Tender Support Allocations	730	304	5	2
Total [note 10]		2,278		7	114	233	2,518

Table BSF_3b: Amount of expenditure from the BSF by tenure.
Expenditure [note_43][note_44][note_59]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	801	1,756	9	7	101	190	911	1,952

## BSF_4
BSF remediation progress of eligible buildings by local authority, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.[note_23, note_24]
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_45]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF yet to be remediated / Number	Completed Remediation / Percentage(%)	Started or Completed Remediation / Percentage(%)
Adur	1-5	0	100%	100%
Ashford	1-5	0	100%	100%
Barking and Dagenham	8	1-5	38%	75%
Barnet	1-5	1-5	Less than 50%	50-99%
Barnsley	1-5	0	100%	100%
Basingstoke and Deane	1-5	1-5	Less than 50%	100%
Bexley	1-5	1-5	Less than 50%	100%
Birmingham	11	8	27%	100%
Bolton	1-5	0	100%	100%
Bournemouth, Christchurch and Poole	1-5	1-5	50-99%	100%
Bradford	1-5	1-5	50-99%	100%
Brent	19	12	37%	63%
Brighton and Hove	1-5	1-5	50-99%	100%
Bristol, City of	10	6	40%	100%
Bromley	7	1-5	43%	43%
Buckinghamshire	1-5	0	100%	100%
Calderdale	1-5	0	100%	100%
Cambridge	1-5	0	100%	100%
Camden	15	10	33%	60%
Chelmsford	1-5	0	100%	100%
City of London	1-5	1-5	Less than 50%	Less than 50%
Coventry	1-5	1-5	Less than 50%	Less than 50%
Croydon	17	12	29%	47%
Dorset	1-5	0	100%	100%
Ealing	7	1-5	29%	86%
Eastbourne	6	1-5	100%	100%
Enfield	7	1-5	43%	43%
Gateshead	1-5	1-5	50-99%	100%
Greenwich	15	11	27%	60%
Hackney	35	29	17%	60%
Hammersmith and Fulham	8	7	13%	13%
Haringey	1-5	1-5	50-99%	100%
Harrow	1-5	1-5	Less than 50%	100%
Havering	1-5	1-5	50-99%	100%
Hillingdon	8	8	0%	63%
Hounslow	15	10	33%	60%
Ipswich	1-5	1-5	50-99%	100%
Isle of Wight	1-5	0	100%	100%
Islington	21	20	5%	43%
Kensington and Chelsea	12	10	17%	92%
Kingston Upon Thames	1-5	1-5	Less than 50%	Less than 50%
Kirklees	1-5	0	100%	100%
Lambeth	18	10	44%	56%
Lancaster	1-5	0	100%	100%
Leeds	31	15	52%	90%
Leicester	1-5	1-5	Less than 50%	100%
Lewes	1-5	0	100%	100%
Lewisham	9	8	11%	44%
Liverpool	21	18	14%	81%
Luton	1-5	1-5	Less than 50%	100%
Manchester	51	22	57%	98%
Mansfield	1-5	1-5	Less than 50%	100%
Medway	1-5	0	100%	100%
Merton	7	1-5	29%	43%
Milton Keynes	1-5	1-5	50-99%	100%
Newcastle upon Tyne	1-5	1-5	50-99%	50-99%
Newham	75	46	39%	45%
North Somerset	1-5	1-5	Less than 50%	100%
North Yorkshire	1-5	0	100%	100%
Nottingham	9	1-5	78%	100%
Peterborough	1-5	0	100%	100%
Plymouth	1-5	1-5	Less than 50%	100%
Portsmouth	1-5	1-5	50-99%	100%
Preston	1-5	0	100%	100%
Reading	13	1-5	85%	92%
Redbridge	1-5	1-5	50-99%	50-99%
Richmond upon Thames	1-5	0	100%	100%
Rother	1-5	1-5	Less than 50%	100%
Salford	15	1-5	80%	100%
Sevenoaks	1-5	0	100%	100%
Sheffield	1-5	1-5	50-99%	100%
Slough	1-5	0	100%	100%
Southampton	1-5	0	100%	100%
Southend-on-Sea	1-5	0	100%	100%
Southwark	33	26	21%	55%
Stevenage	1-5	1-5	50-99%	100%
Stockport	1-5	0	100%	100%
Sunderland	1-5	1-5	Less than 50%	100%
Surrey Heath	1-5	0	100%	100%
Sutton	1-5	1-5	Less than 50%	50-99%
Swindon	1-5	1-5	Less than 50%	100%
Tower Hamlets	107	68	36%	72%
Trafford	1-5	1-5	Less than 50%	Less than 50%
Wakefield	1-5	0	100%	100%
Waltham Forest	1-5	1-5	Less than 50%	Less than 50%
Wandsworth	12	1-5	67%	92%
Watford	1-5	0	100%	100%
Westminster	24	16	33%	67%
Worcester	1-5	0	100%	100%

## BSF_5
Remediation status of eligible buildings within BSF, time series, England, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_23, note_65, note_73]	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 Number	Jun-25 Number	Jul-25 Number	Aug-25 Number	Sep-25 Number
Remediation complete	0	10	11	11	28	37	37	39	46	49	101	124	135	141	143	155	158	168	176	190	200	210	217	220	223	229	236	238	239	248	274	281	301	309	313
Remediation complete: awaiting building control sign-off	18	86	93	97	96	102	107	114	117	122	84	75	77	90	107	106	106	109	111	112	121	116	124	132	134	135	137	141	149	159	137	137	123	121	127
Remediation started	150	247	254	268	266	261	263	264	253	254	258	260	268	255	246	237	247	245	235	222	197	191	176	166	164	157	149	144	139	137	133	126	121	115	111
Remediation plans in place		322	310	297	291	289	286	278	249	236	199	203	191	198	200	200	189	174	180	152	125	130	136	139	141	143	144	146	149	143	121	118	125	165	162
Intent to remediate	813	538	540	542	535	525	532	525	285	277	326	314	303	266	251	240	234	219	209	193	158	158	156	153	147	145	147	147	148	145	107	107	104	64	52
Total buildings	981	1203	1208	1215	1216	1214	1225	1220	950	938	968	976	974	950	947	938	934	915	911	869	801	805	809	810	809	809	813	816	824	832	772	769	774	774	765

Remediation Category [note_23, note_65, note_73]	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)	Sep-24 Percentage (%)	Oct-24 Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 Percentage (%)	Jun-25 Percentage (%)	Jul-25 Percentage (%)	Aug-25 Percentage (%)	Sep-25 Percentage (%)
Remediation complete	0%	1%	1%	1%	2%	3%	3%	3%	5%	5%	10%	13%	14%	15%	15%	17%	17%	18%	19%	22%	25%	26%	27%	27%	28%	28%	29%	29%	29%	30%	35%	37%	39%	40%	41%
Remediation complete: awaiting building control sign-off	2%	7%	8%	8%	8%	8%	9%	9%	12%	13%	9%	8%	8%	9%	11%	11%	11%	12%	12%	13%	15%	14%	15%	16%	17%	17%	17%	17%	18%	19%	18%	18%	16%	16%	17%
Remediation started	15%	21%	21%	22%	22%	21%	21%	22%	27%	27%	27%	27%	28%	27%	26%	25%	26%	27%	26%	26%	25%	24%	22%	20%	20%	19%	18%	18%	17%	16%	17%	16%	16%	15%	15%
Remediation plans in place		27%	26%	24%	24%	24%	23%	23%	26%	25%	21%	21%	20%	21%	21%	21%	20%	19%	20%	17%	16%	16%	17%	17%	17%	18%	18%	18%	18%	17%	16%	15%	16%	21%	21%
Intent to remediate	83%	45%	45%	45%	44%	43%	43%	43%	30%	30%	34%	32%	31%	28%	27%	26%	25%	24%	23%	22%	20%	20%	19%	19%	18%	18%	18%	18%	18%	17%	14%	14%	13%	8%	7%
Total buildings [note_10]	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_1
Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	374	91%	261	39%	50	51%	685	58%
Works complete awaiting building control signoff	12	3%	118	18%	10	10%	140	12%
Remediation started	20	5%	93	14%	32	33%	145	12%
Remediation not started	7	2%	194	29%	6	6%	207	18%
Total [note_74]	413	100%	666	100%	98	100%	1177	100%

## Combined_2
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_42, note_77]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	546	22%	1,389	44%	1,935	35%
Remediation underway	328	13%	431	14%	759	14%
In programme	1,557	64%	1,307	42%	2,864	52%
Total	2,431	100%	3,127	100%	5,558	100%

## Combined_3
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_13, note_17, note_18, note_42, note_70, note_77]	Buildings monitored	In programme / Percentage(%)	Remediation Underway / Percentage(%)	Completed Remediation / Percentage(%)
Barking and Dagenham	51-100	58%	11%	31%
Barnet	51-100	46%	9%	46%
Basingstoke and Deane	11-50	31%	31%	38%
Bexley	11-50	53%	16%	31%
Birmingham	201-400	20%	8%	72%
Bournemouth, Christchurch and Poole	11-50	29%	37%	35%
Bradford	11-50	81%	0%	19%
Brent	51-100	52%	12%	36%
Brighton and Hove	11-50	72%	12%	16%
Bristol, City of	101-200	58%	19%	23%
Bromley	11-50	60%	13%	27%
Buckinghamshire	11-50	64%	27%	9%
Cambridge	11-50	76%	10%	14%
Camden	51-100	47%	23%	30%
Chelmsford	11-50	17%	4%	78%
Coventry	11-50	100%	0%	0%
Croydon	51-100	49%	12%	39%
Dacorum	11-50	45%	40%	15%
Dartford	11-50	26%	13%	61%
Ealing	51-100	39%	16%	45%
Eastbourne	11-50	43%	14%	43%
Elmbridge	11-50	55%	27%	18%
Enfield	11-50	75%	0%	25%
Gateshead	11-50	57%	0%	43%
Greenwich	101-200	48%	18%	34%
Hackney	201-400	65%	7%	28%
Hammersmith and Fulham	51-100	72%	5%	23%
Haringey	51-100	34%	12%	54%
Harrow	11-50	57%	9%	35%
Hastings	11-50	93%	0%	7%
Havering	11-50	46%	5%	49%
Hertsmere	11-50	35%	45%	20%
Hillingdon	11-50	64%	25%	11%
Hounslow	51-100	49%	1%	49%
Ipswich	11-50	57%	18%	25%
Islington	101-200	66%	12%	21%
Kensington and Chelsea	51-100	60%	19%	21%
Kirklees	11-50	56%	22%	22%
Lambeth	101-200	63%	12%	26%
Leeds	51-100	37%	25%	37%
Leicester	11-50	58%	6%	35%
Lewisham	101-200	60%	10%	31%
Liverpool	101-200	53%	13%	34%
Maidstone	11-50	57%	17%	26%
Manchester	201-400	45%	9%	46%
Medway	11-50	33%	7%	60%
Merton	11-50	67%	10%	24%
Milton Keynes	11-50	52%	33%	15%
Newcastle upon Tyne	51-100	40%	11%	49%
Newham	101-200	42%	22%	36%
North Somerset	11-50	62%	24%	14%
Norwich	11-50	48%	3%	48%
Nottingham	11-50	50%	10%	40%
Plymouth	11-50	50%	9%	41%
Portsmouth	51-100	19%	33%	48%
Reading	11-50	41%	9%	50%
Redbridge	11-50	74%	0%	26%
Richmond upon Thames	11-50	19%	19%	63%
Salford	51-100	25%	26%	49%
Sheffield	11-50	53%	8%	39%
Slough	11-50	52%	7%	41%
Solihull	11-50	70%	0%	30%
Southampton	101-200	54%	14%	32%
Southwark	201-400	58%	5%	37%
Stevenage	11-50	75%	13%	13%
Stockport	11-50	89%	5%	5%
Stoke-on-Trent	11-50	64%	21%	14%
Sunderland	11-50	43%	7%	50%
Sutton	11-50	32%	21%	47%
Tower Hamlets	over 400	50%	18%	32%
Trafford	11-50	63%	6%	31%
Waltham Forest	51-100	58%	11%	31%
Wandsworth	101-200	57%	14%	30%
Watford	11-50	54%	23%	23%
West Berkshire	11-50	55%	0%	45%
West Northamptonshire	11-50	46%	8%	46%
Westminster	51-100	44%	7%	49%
Woking	11-50	39%	57%	4%
Wolverhampton	11-50	75%	0%	25%

## Combined_4
Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings [note_10, note_13, note_17, note_18, note_42, note_77]	Estimated dwellings in 11-18m buildings	Estimated dwellings in 18m+ buildings	Estimated Total dwellings
Remediation complete (including those awaiting building control signoff)	17,000	96,000	113,000
Remediation underway	11,000	36,000	47,000
In programme	46,000	86,000	133,000
Total	74,000	218,000	292,000

## Combined_5
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by tenure, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_42, note_77]	Private / Number	Private / Percentage (%)	Social / Number	Social / Percentage (%)	Other [note 57] / Number	Other / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	794	30%	1046	37%	95	94%	1,935	35%
Remediation underway	484	18%	271	10%	4	4%	759	14%
In programme	1,355	51%	1,507	53%	2	2%	2,864	52%
Total	2,633	100%	2,824	100%	101	100%	5,558	100%

## Combined_6
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, time series, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_13,note_16, note_17, note_18, note_42, note_64, note_77]	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 / Number	Jun-25 / Number	Jul-25 / Number	Aug-25 / Number	Sep-25 / Number
Remediation complete (including those awaiting building control signoff)	448	456	461	477	492	499	508	523	535	544	703	777	797	815	863	976	991	1,088	1,332	1,350	1,392	1,412	1,436	1,463	1,472	1,482	1,619	1,637	1,652	1,754	1,767	1,780	1,927	1,935
Remediation underway	301	308	322	321	317	319	320	308	304	311	809	826	811	871	952	992	984	978	969	949	985	1,000	983	934	931	928	809	822	825	728	723	722	750	759
In programme	853	844	834	820	806	806	791	519	501	509	2,285	2,221	2,231	2,286	2,277	2,361	2,361	2,308	2,312	2,331	2,394	2,409	2,415	2,601	2,608	2,615	2,586	2,572	2,575	2,694	2,700	2,712	2,877	2,864
Total	1,602	1,608	1,617	1,618	1,615	1,624	1,619	1,350	1,340	1,364	3,797	3,824	3,839	3,972	4,092	4,329	4,336	4,374	4,613	4,630	4,771	4,821	4,834	4,998	5,011	5,025	5,014	5,031	5,052	5,176	5,190	5,214	5,554	5,558

Remediation Category [note_13, note_16, note_17, note_18, note_42, note_64]	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)	Sep-24 / Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 / Percentage (%)	Jun-25 / Percentage (%)	Jul-25 / Percentage (%)	Aug-25 / Percentage (%)	Sep-25 / Percentage (%)
Remediation complete (including those awaiting building control signoff)	28%	28%	29%	29%	30%	31%	31%	39%	40%	40%	19%	20%	21%	21%	21%	23%	23%	25%	29%	29%	29%	29%	30%	29%	29%	29%	32%	33%	33%	34%	34%	34%	35%	35%
Remediation underway	19%	19%	20%	20%	20%	20%	20%	23%	23%	23%	21%	22%	21%	22%	23%	23%	23%	22%	21%	20%	21%	21%	20%	19%	19%	18%	16%	16%	16%	14%	14%	14%	14%	14%
In programme	53%	52%	52%	51%	50%	50%	49%	38%	37%	37%	60%	58%	58%	58%	56%	55%	54%	53%	50%	50%	50%	50%	50%	52%	52%	52%	52%	51%	51%	52%	52%	52%	52%	52%
Total	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_7
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by region, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_13, note_16, note_17, note_18, note_42, note_77]	Total buildings monitored / Number	Total buildings monitored / Percentage(%)	In programme / Number	In programme / Percentage(%)	Remediation underway / Number	Remediation underway / Percentage(%)	Remediation complete (including those awaiting building control signoff) / Number	Remediation complete (including those awaiting building control signoff) / Percentage(%)	Buildings monitored that have completed Remediation / Percentage (%)	Buildings monitored that have started or completed remediation / Percentage (%)
North West	530	10%	251	9%	69	9%	210	11%	40%	53%
London	3,129	56%	1,697	59%	385	51%	1,047	54%	33%	46%
East of England	286	5%	151	5%	51	7%	84	4%	29%	47%
East Midlands	107	2%	58	2%	14	2%	35	2%	33%	46%
North East	94	2%	40	1%	8	1%	46	2%	49%	57%
South East	642	12%	318	11%	116	15%	208	11%	32%	50%
South West	288	5%	154	5%	61	8%	73	4%	25%	47%
West Midlands	297	5%	108	4%	21	3%	168	9%	57%	64%
Yorkshire and The Humber	185	3%	87	3%	34	4%	64	3%	35%	53%
Total	5,558	100%	2,864	100%	759	100%	1,935	100%	35%	48%

## Combined_8
Remediation progress for unique buildings being remediated or mitigated as part of a government funded scheme, 11 metres and over in height, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_77, note_78]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	49	9%	812	56%	861	43%
Remediation underway	95	18%	180	12%	275	14%
In programme	397	73%	458	32%	855	43%
Total	541	100%	1,450	100%	1,991	100%

## CSS_1
Application status of buildings within the CSS, England, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Pre - eligible buildings [note_47, note_48]	Number	Percentage (%)
Pre - application	1818	67%
Live application	890	33%
Total pre-eligible buildings	2,708	100%

Eligible buildings [note_13]	Number	Percentage (%)
Works not started	667	80%
Works started	114	14%
Works completed	55	7%
Total eligible buildings	836	100%

## CSS_2
CSS remediation progress by region, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_48, note_13]	Eligible Buildings in the CSS / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible CSS buildings that have started or completed remediation / Percentage (%)
North West	122	101	16	5	4%	17%
London	369	283	52	34	9%	23%
East of England	59	49	8	2	3%	17%
East Midlands	33	26	6	1	3%	21%
North East	15	12	3	0	0%	20%
South East	84	66	11	7	8%	21%
South West	75	65	8	2	3%	13%
West Midlands	23	22	1	0	0%	4%
Yorkshire and The Humber	52	42	7	3	6%	19%
Northern Ireland	4	1	2	1	25%	75%
Total	836	667	114	55	7%	20%

## CSS_3
CSS remediation progress by height, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48, note_13]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)
Remediation complete	49	9%	6	2%
Remediation started	95	18%	19	6%
In programme	397	73%	270	92%
Total buildings	541	100%	295	100%

## CSS_4
CSS remediation progress by tenure, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48, note_13]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	26	8%	29	6%
Remediation started	33	11%	81	15%
In programme	251	81%	416	79%
Total buildings	310	100%	526	100%

## CSS_5
CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Table CSS_5a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the CSS
Funding Allocations	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Funding / (£ millions)
Works Package Approved	170	681.7	49	59.8	741.5
Pre-Tender Support Allocations	483	148.9	148	46.2	195.1
Total [note 10]	503	830.6	187	106.0	936.6

Table CSS_5b: Amount of expenditure from the CSS by tenure
Expenditure [note_44]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	487	244.0	180	83.1	667	327.1

## CSS_6
CSS remediation progress, time series, England, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings unless otherwise stated or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_48, note_13]	Oct-23 Number	Nov-23 Number	Dec-23 Number	Jan-24 Number	Feb-24 Number	Mar-24 Number	Apr-24 Number	May-24 Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 Number	Jan-25 Number	Feb-25 Number	Mar-25 Number	Apr-25 Number	May-25 Number	Jun-25 Number	Jul-25 Number	Aug-25 Number	Sep-25 Number
Remediation complete	0	0	0	0	0	0	0	0	0	0	0	0	14	16	17	20	24	31	33	38	43	49	53	55
Remediation started	0	0	0	0	1	2	2	2	6	8	10	22	17	30	36	45	56	82	85	85	87	93	102	114
In programme	48	75	104	127	151	168	199	222	282	371	395	410	429	446	472	491	510	504	538	609	623	640	651	667
Total buildings	48	75	104	127	152	170	201	224	288	379	405	432	460	492	525	556	590	617	656	732	753	782	806	836

Remediation Category [note_48, note_13]	Oct-23 Percentage (%)	Nov-23 Percentage (%)	Dec-23 Percentage (%)	Jan-24 Percentage (%)	Feb-24 Percentage (%)	Mar-24 Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)	Sep-24 Percentage (%)	Oct-24 Percentage (%)	Nov-24 / Percentage (%)	Dec-24 Percentage (%)	Jan-25 Percentage (%)	Feb-25 Percentage (%)	Mar-25 Percentage (%)	Apr-25 Percentage (%)	May-25 Percentage (%)	Jun-25 Percentage (%)	Jul-25 Percentage (%)	Aug-25 Percentage (%)	Sep-25 Percentage (%)
Remediation complete	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	3%	3%	3%	4%	4%	5%	5%	5%	6%	6%	7%	7%
Remediation started	0%	0%	0%	0%	1%	1%	1%	1%	2%	2%	2%	5%	4%	6%	7%	8%	9%	13%	13%	12%	12%	12%	13%	14%
In programme	100%	100%	100%	100%	99%	99%	99%	99%	98%	98%	98%	95%	93%	91%	90%	88%	86%	82%	82%	83%	83%	82%	81%	80%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Developer_1
Remediation status of buildings requiring works under the developer remediation contract by height group, England, 30 September 2025
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - All Defect Types [Note 25, Note 26, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	205	17%	233	21%	438	18%
Remediation complete - awaiting building control sign-off	42	3%	57	5%	99	4%
Remediation started	195	16%	302	27%	497	21%
Remediation not Started - Plans in Place	198	16%	180	16%	378	16%
Remediation not Started - No Plans in Place	601	48%	364	32%	965	41%
Total	1241	100%	1136	100%	2,377	100%

Remediation Category - Cladding Defects [Note 25, Note 26, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	162	19%	216	23%	378	21%
Remediation complete - awaiting building control sign-off	30	4%	55	6%	85	5%
Remediation started	143	17%	258	28%	401	23%
Remediation not Started - Plans in Place	156	19%	167	18%	323	18%
Remediation not Started - No Plans in Place	351	42%	225	24%	576	33%
Total	842	100%	921	100%	1,763	100%

Remediation Category - Self-reported Information, All Defect Types [Note 25, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	202	16%	173	17%	375	17%
Remediation complete - awaiting building control sign-off	42	3%	43	4%	85	4%
Remediation started	192	16%	269	27%	461	21%
Remediation not Started - Plans in Place	198	16%	179	18%	377	17%
Remediation not Started - No Plans in Place	597	48%	351	35%	948	42%
Total	1231	100%	1015	100%	2,246	100%

Remediation Category - BSF Transfers [Note 25, Note 26, Note 29, Note 61]	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	44	10%
Remediation complete - awaiting building control sign-off	14	3%
Remediation started	133	30%
Remediation not Started - Plans in Place	106	24%
Remediation not Started - No Plans in Place	79	18%
No life-critical fire-safety defects reported	69	16%
Total buildings	445	100%

## Developer_2
Estimated cost of buildings requiring works under the developer remediation contract by height, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for estimated cost of buildings identified as requiring works under the Developer Remediation Contract in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Cost Category [Note 29, Note 33]	11-18m / (£ millions)	18m+ / (£ millions)	Total / (£ millions)
Total estimated cost of works	1,409	3,256	4,664

## Developer_3
Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note 29]	Number of buildings developed or refurbished by the developer covered by the contract	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme) [Note 28]	Number of buildings found to require remediation, which will be remediated by the developer directly [Note 31]	Number of buildings without a determination [Note 32]	Number of buildings where no remediation is required	Number of buildings with no reported defects under clauses 5.4d(i) or 5.4d(ii) of the developer remediation contract	Percentage of buildings for which the developer has determined whether remediation is required
Total (all developers)	4655	4538	2246	366	1806	120	92%
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	60	51	30	21	0	0	59%
Ballymore Limited	85	69	13	0	17	39	100%
Barratt Redrow PLC	836	821	500	195	126	0	76%
Bellway PLC	437	420	355	0	65	0	100%
The Berkeley Group Holdings PLC	821	810	72	14	724	0	98%
Bewley Group Limited	9	7	3	1	3	0	86%
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	16	16	4	0	12	0	100%
Cala Group (Holdings) Limited	22	22	20	0	2	0	100%
Canary Wharf Group PLC	13	13	0	4	9	0	69%
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	8	8	0	0	8	0	100%
Crest Nicholson Holdings PLC	293	292	268	2	22	0	99%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	21	21	19	0	2	0	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	121	121	66	0	48	7	100%
Frasers Property (UK) Ltd	16	11	5	3	3	0	73%
Galliard Group Limited	101	101	29	7	65	0	93%
MJ Gleeson PLC	17	16	13	3	0	0	81%
Grosvenor Developments Limited	21	21	12	1	0	8	95%
Hill Holdings Limited	90	90	25	14	2	49	84%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	7	7	5	0	2	0	100%
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	42	39	9	27	3	0	31%
Lendlease Europe Holdings Limited	89	88	42	0	46	0	100%
Pegasus Homes (formerly Lifestory Group)	18	18	1	0	17	0	100%
London Square Development (Holdings) Limited	40	40	39	0	1	0	100%
Miller Homes Limited	39	39	31	0	4	4	100%
Morris Homes Group Limited	6	6	2	0	4	0	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	120	113	23	0	90	0	100%
Persimmon Public Limited Company	71	70	56	0	13	1	100%
Regal Holdco Limited (parent company for Regal London)	16	16	4	0	12	0	100%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	25	22	16	0	6	0	100%
Sorbon Group Limited (parent company for Shanly Homes)	26	26	20	0	6	0	100%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	13	10	6	0	0	4	100%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	439	431	224	59	148	0	86%
Telford Homes Limited	144	143	91	1	51	0	99%
Tilia Homes Limited	8	8	8	0	0	0	100%
Vistry Group PLC	300	294	135	3	156	0	99%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	88	87	27	0	60	0	100%
McCarthy & Stone Limited	62	62	12	2	48	0	97%
Seven Capital PLC	21	21	19	0	0	2	100%
Wates Group Limited	24	23	11	3	9	0	87%
Watkin Jones PLC	14	14	7	6	1	0	57%
Bouygues (UK) Limited	35	31	18	0	13	0	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	21	20	6	0	8	6	100%

## Developer_4
Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Remediation Status
		Buildings being remediated by the developer directly where remediation has...
		…not yet started		... started or completed		... started		...completed, awaiting building control sign-off		...completed
Developer [Note 25, Note 29]	Number of buildings found to require remediation, which will be remediated by the developer directly [Note 31]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total (all developers)	2246	1325	59%	921	41%	461	21%	85	4%	375	17%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	30	27	90%	3	10%	1	3%	0	0%	2	7%
Ballymore Limited	13	2	15%	11	85%	0	0%	0	0%	11	85%
Barratt Redrow PLC	500	371	74%	129	26%	44	9%	45	9%	40	8%
Bellway PLC	355	231	65%	124	35%	81	23%	0	0%	43	12%
The Berkeley Group Holdings PLC	72	23	32%	49	68%	8	11%	0	0%	41	57%
Bewley Group Limited	3	0	0%	3	100%	2	67%	0	0%	1	33%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	4	2	50%	2	50%	2	50%	0	0%	0	0%
Cala Group (Holdings) Limited	20	9	45%	11	55%	7	35%	0	0%	4	20%
Canary Wharf Group PLC	0	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	268	148	55%	120	45%	115	43%	4	1%	1	0%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	19	1	5%	18	95%	18	95%	0	0%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	66	25	38%	41	62%	8	12%	0	0%	33	50%
Frasers Property (UK) Ltd	5	0	0%	5	100%	0	0%	1	20%	4	80%
Galliard Group Limited	29	13	45%	16	55%	0	0%	0	0%	16	55%
MJ Gleeson PLC	13	8	62%	5	38%	3	23%	0	0%	2	15%
Grosvenor Developments Limited	12	4	33%	8	67%	7	58%	0	0%	1	8%
Hill Holdings Limited	25	12	48%	13	52%	2	8%	0	0%	11	44%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	5	3	60%	2	40%	0	0%	2	40%	0	0%
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	9	3	33%	6	67%	2	22%	0	0%	4	44%
Lendlease Europe Holdings Limited	42	31	74%	11	26%	8	19%	0	0%	3	7%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%	0	0%	0	0%
London Square Development (Holdings) Limited	39	0	0%	39	100%	39	100%	0	0%	0	0%
Miller Homes Limited	31	11	35%	20	65%	8	26%	5	16%	7	23%
Morris Homes Group Limited	2	0	0%	2	100%	1	50%	0	0%	1	50%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	23	9	39%	14	61%	2	9%	1	4%	11	48%
Persimmon Public Limited Company	56	24	43%	32	57%	24	43%	0	0%	8	14%
Regal Holdco Limited (parent company for Regal London)	4	3	75%	1	25%	0	0%	0	0%	1	25%
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	16	1	6%	15	94%	1	6%	0	0%	14	88%
Sorbon Group Limited (parent company for Shanly Homes)	20	8	40%	12	60%	6	30%	0	0%	6	30%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	6	4	67%	2	33%	0	0%	0	0%	2	33%
Story Homes Limited	-	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	224	135	60%	89	40%	28	13%	10	4%	51	23%
Telford Homes Limited	91	90	99%	1	1%	1	1%	0	0%	0	0%
Tilia Homes Limited	8	1	13%	7	88%	7	88%	0	0%	0	0%
Vistry Group PLC	135	79	59%	56	41%	10	7%	15	11%	31	23%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	27	1	4%	26	96%	20	74%	0	0%	6	22%
McCarthy & Stone Limited	12	0	0%	12	100%	3	25%	2	17%	7	58%
Seven Capital PLC	19	19	100%	0	0%	0	0%	0	0%	0	0%
Wates Group Limited	11	4	36%	7	64%	1	9%	0	0%	6	55%
Watkin Jones PLC	7	7	100%	0	0%	0	0%	0	0%	0	0%
Bouygues (UK) Limited	18	11	61%	7	39%	1	6%	0	0%	6	33%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	6	4	67%	2	33%	1	17%	0	0%	1	17%

## Developer_5
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings that require remediation by the developer which have not yet started, with a start date…

		…within the next 12 months		…after the next 12 months		…start date unclear
Developer [Note 27, Note 29]	Number of buildings being remediated by the developer directly where remediation has not started	Number	Percentage‎	Number	Percentage	Number	Percentage
Total (all developers)	1325	558	42%	172	13%	595	45%
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	27	0	0%	0	0%	27	100%
Ballymore Limited	2	2	100%	0	0%	0	0%
Barratt Redrow PLC	371	183	49%	100	27%	88	24%
Bellway PLC	231	54	23%	5	2%	172	74%
The Berkeley Group Holdings PLC	23	22	96%	1	4%	0	0%
Bewley Group Limited	0	0	-	0	-	0	-
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	2	0	0%	0	0%	2	100%
Cala Group (Holdings) Limited	9	6	67%	0	0%	3	33%
Canary Wharf Group PLC	0	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-
Crest Nicholson Holdings PLC	148	15	10%	0	0%	133	90%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	1	0	0%	1	100%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	25	22	88%	1	4%	2	8%
Frasers Property (UK) Ltd	0	0	-	0	-	0	-
Galliard Group Limited	13	8	62%	4	31%	1	8%
MJ Gleeson PLC	8	7	88%	0	0%	1	13%
Grosvenor Developments Limited	4	4	100%	0	0%	0	0%
Hill Holdings Limited	12	10	83%	0	0%	2	17%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0%	0	0%	3	100%
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	3	0	0%	0	0%	3	100%
Lendlease Europe Holdings Limited	31	17	55%	2	6%	12	39%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%
London Square Development (Holdings) Limited	0	0	-	0	-	0	-
Miller Homes Limited	11	8	73%	0	0%	3	27%
Morris Homes Group Limited	0	0	-	0	-	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	9	2	22%	0	0%	7	78%
Persimmon Public Limited Company	24	24	100%	0	0%	0	0%
Regal Holdco Limited (parent company for Regal London)	3	0	0%	0	0%	3	100%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	1	1	100%	0	0%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	8	1	13%	0	0%	7	88%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0%	0	0%	4	100%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	135	80	59%	46	34%	9	7%
Telford Homes Limited	90	38	42%	7	8%	45	50%
Tilia Homes Limited	1	0	0%	0	0%	1	100%
Vistry Group PLC	79	37	47%	3	4%	39	49%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	1	0	0%	0	0%	1	100%
McCarthy & Stone Limited	0	0	-	0	-	0	-
Seven Capital PLC	19	5	26%	0	0%	14	74%
Wates Group Limited	4	4	100%	0	0%	0	0%
Watkin Jones PLC	7	4	57%	2	29%	1	14%
Bouygues (UK) Limited	11	0	0%	0	0%	11	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	3	75%	0	0%	1	25%

## Developer_6
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which have not yet started, start profiles by financial year...

Developer [Note 27, Note 29]	Number of buildings being remediated by the developer directly where remediation has not started	2024-2025	2025-2026	2026-2027	2027-2028	2028-29	2029-30	.. no start date provided
Total (all developers)	1325	17	459	286	22	15	3	523
Abbey Developments Limited	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	27	0	1	0	0	0	0	26
Ballymore Limited	2	0	1	1	0	0	0	0
Barratt Redrow PLC	371	0	97	181	5	0	0	88
Bellway PLC	231	0	30	28	1	0	0	172
The Berkeley Group Holdings PLC	23	0	16	7	0	0	0	0
Bewley Group Limited	0	0	0	0	0	0	0	0
Bloor Investments Limited	-	-	-	-	-	-	-	-
The British Land Company PLC	2	0	0	0	0	0	0	2
Cala Group (Holdings) Limited	9	0	9	0	0	0	0	0
Canary Wharf Group PLC	0	0	0	0	0	0	0	0
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	148	13	21	0	0	0	0	114
Croudace Homes Group Limited	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	1	0	0	0	1	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-
Fairview Holdings Limited	25	1	18	5	0	0	0	1
Frasers Property (UK) Ltd	0	0	0	0	0	0	0	0
Galliard Group Limited	13	0	9	2	2	0	0	0
MJ Gleeson PLC	8	0	7	0	0	0	0	1
Grosvenor Developments Limited	4	0	4	0	0	0	0	0
Hill Holdings Limited	12	0	10	0	0	0	0	2
Hopkins Home Group Limited	-	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0	0	0	0	0	3
Keepmoat Limited	-	-	-	-	-	-	-	-
Land Securities Group PLC	3	0	0	0	0	0	0	3
Lendlease Europe Holdings Limited	31	0	26	4	0	0	0	1
Pegasus Homes (formerly Lifestory Group)	1	0	1	0	0	0	0	0
London Square Development (Holdings) Limited	0	0	0	0	0	0	0	0
Miller Homes Limited	11	0	11	0	0	0	0	0
Morris Homes Group Limited	0	0	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	9	0	1	1	0	0	0	7
Persimmon Public Limited Company	24	0	24	0	0	0	0	0
Regal Holdco Limited (parent company for Regal London)	3	0	0	0	0	0	0	3
Rowland Group Limited	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	1	0	1	0	0	0	0	0
Sorbon Group Limited (parent company for Shanly Homes)	8	0	6	0	0	0	0	2
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0	0	0	0	0	4
Story Homes Limited	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	135	0	66	29	13	15	3	9
Telford Homes Limited	90	2	35	17	0	0	0	36
Tilia Homes Limited	1	0	0	0	0	0	0	1
Vistry Group PLC	79	1	48	9	0	0	0	21
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-
Weston Group PLC	1	0	1	0	0	0	0	0
McCarthy & Stone Limited	0	0	0	0	0	0	0	0
Seven Capital PLC	19	0	5	0	0	0	0	14
Wates Group Limited	4	0	4	0	0	0	0	0
Watkin Jones PLC	7	0	4	2	0	0	0	1
Bouygues (UK) Limited	11	0	0	0	0	0	0	11
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	0	3	0	0	0	0	1

## Developer_7
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings that require remediation by the developer which have not yet completed, with a completion date…
		…within the next 12 months		…after the next 12 months		…completion date unclear
Developer [Note 29, Note 55]	Number of buildings being remediated by the developer directly where remediation has not yet completed	Number	Percentage‎	Number	Percentage	Number2	Pecentage
Total (all developers)	1786	344	19%	750	42%	692	39%
Abbey Developments Limited	0	0	-	0	-	0	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	28	0	0%	0	0%	28	100%
Ballymore Limited	2	0	0%	2	100%	0	0%
Barratt Redrow PLC	415	37	9%	283	68%	95	23%
Bellway PLC	312	22	7%	88	28%	202	65%
The Berkeley Group Holdings PLC	31	12	39%	12	39%	7	23%
Bewley Group Limited	2	0	0%	0	0%	2	100%
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	4	0	0%	0	0%	4	100%
Cala Group (Holdings) Limited	16	10	63%	2	13%	4	25%
Canary Wharf Group PLC	0	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-
Crest Nicholson Holdings PLC	263	64	24%	43	16%	156	59%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	19	3	16%	16	84%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	33	13	39%	14	42%	6	18%
Frasers Property (UK) Ltd	0	0	-	0	-	0	-
Galliard Group Limited	13	3	23%	10	77%	0	0%
MJ Gleeson PLC	11	9	82%	0	0%	2	18%
Grosvenor Developments Limited	11	2	18%	4	36%	5	45%
Hill Holdings Limited	14	8	57%	3	21%	3	21%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0%	0	0%	3	100%
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	5	0	0%	0	0%	5	100%
Lendlease Europe Holdings Limited	39	18	46%	18	46%	3	8%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%
London Square Development (Holdings) Limited	39	39	100%	0	0%	0	0%
Miller Homes Limited	19	4	21%	5	26%	10	53%
Morris Homes Group Limited	1	1	100%	0	0%	0	0%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	11	0	0%	2	18%	9	82%
Persimmon Public Limited Company	48	15	31%	32	67%	1	2%
Regal Holdco Limited (parent company for Regal London)	3	0	0%	0	0%	3	100%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	1	50%	1	50%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	14	11	79%	0	0%	3	21%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0%	0	0%	4	100%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	163	24	15%	126	77%	13	8%
Telford Homes Limited	91	6	7%	47	52%	38	42%
Tilia Homes Limited	8	2	25%	1	13%	5	63%
Vistry Group PLC	89	26	29%	38	43%	25	28%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	21	1	5%	0	0%	20	95%
McCarthy & Stone Limited	3	0	0%	0	0%	3	100%
Seven Capital PLC	19	1	5%	0	0%	18	95%
Wates Group Limited	5	4	80%	0	0%	1	20%
Watkin Jones PLC	7	3	43%	3	43%	1	14%
Bouygues (UK) Limited	12	1	8%	0	0%	11	92%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	5	3	60%	0	0%	2	40%

## Developer_8
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which have not yet completed, completion profiles by financial year...					Buildings which have not yet completed, with...

Developer [Note 29, Note 55]	Number of buildings being remediated by the developer directly where remediation has not yet completed	2024-2025	2025-2026	2026-2027	2027-2028	2028-2029	2029-2030	.. no completiondate provided	... completion date prior to 2024-2025
Total (all developers)	1786	37	284	431	335	81	6	602	10
Abbey Developments Limited	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	28	0	1	0	0	0	0	26	1
Ballymore Limited	2	0	0	0	2	0	0	0	0
Barratt Redrow PLC	415	2	23	122	146	29	0	93	0
Bellway PLC	312	5	24	35	42	14	1	186	5
The Berkeley Group Holdings PLC	31	3	6	15	0	3	0	4	0
Bewley Group Limited	2	0	2	0	0	0	0	0	0
Bloor Investments Limited	-	-	-	-	-	-	-	-	-
The British Land Company PLC	4	0	0	0	0	0	0	4	0
Cala Group (Holdings) Limited	16	0	13	3	0	0	0	0	0
Canary Wharf Group PLC	0	0	0	0	0	0	0	0	0
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	263	9	50	55	9	0	0	138	2
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	19	0	1	5	8	5	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	33	3	12	17	0	0	0	1	0
Frasers Property (UK) Ltd	0	0	0	0	0	0	0	0	0
Galliard Group Limited	13	0	2	3	6	2	0	0	0
MJ Gleeson PLC	11	1	8	1	0	0	0	1	0
Grosvenor Developments Limited	11	0	0	6	0	0	0	5	0
Hill Holdings Limited	14	0	4	7	0	0	0	3	0
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0	0	0	0	0	3	0
Keepmoat Limited	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	5	0	0	0	0	0	0	5	0
Lendlease Europe Holdings Limited	39	0	14	18	6	0	0	1	0
Pegasus Homes (formerly Lifestory Group)	1	0	1	0	0	0	0	0	0
London Square Development (Holdings) Limited	39	0	39	0	0	0	0	0	0
Miller Homes Limited	19	3	5	5	1	0	0	5	0
Morris Homes Group Limited	1	0	1	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	11	0	0	1	1	0	0	9	0
Persimmon Public Limited Company	48	0	8	29	11	0	0	0	0
Regal Holdco Limited (parent company for Regal London)	3	0	0	0	0	0	0	3	0
Rowland Group Limited	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	0	0	2	0	0	0	0	0
Sorbon Group Limited (parent company for Shanly Homes)	14	1	11	0	0	0	0	2	0
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0	0	0	0	0	4	0
Story Homes Limited	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	163	0	14	58	48	28	5	10	0
Telford Homes Limited	91	0	3	16	34	0	0	38	0
Tilia Homes Limited	8	0	4	1	0	0	0	3	0
Vistry Group PLC	89	0	20	26	19	0	0	24	0
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-
Weston Group PLC	21	9	10	1	0	0	0	1	0
McCarthy & Stone Limited	3	1	0	0	0	0	0	0	2
Seven Capital PLC	19	0	0	1	0	0	0	18	0
Wates Group Limited	5	0	1	3	0	0	0	1	0
Watkin Jones PLC	7	0	3	1	2	0	0	1	0
Bouygues (UK) Limited	12	0	1	0	0	0	0	11	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	5	0	3	0	0	0	0	2	0

## Developer_9
Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Buildings where the developer or 'responsible entity' has engaged with the leaseholders, freeholders, residents, occupiers and other users regarding works for buildings being remediated directly by the developer, excluding completed buildings, by...					Number of buildings being remediated by the developers, excluding completed buildings	Sum of communication
	... the Responsible Entity		... directly		... directly and by the Responsible Entity		... unconfirmed how
Developer [Note 29]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total (all developers)	1042	58%	57	3%	152	9%	124	7%	1786	77%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0%	0	0%	0	0%	15	54%	28	54%
Ballymore Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Barratt Redrow PLC	164	40%	14	3%	11	3%	108	26%	415	72%
Bellway PLC	303	97%	1	0%	0	0%	0	0%	312	97%
The Berkeley Group Holdings PLC	27	87%	0	0%	4	13%	0	0%	31	100%
Bewley Group Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	2	50%	0	0%	0	0%	0	0%	4	50%
Cala Group (Holdings) Limited	16	100%	0	0%	0	0%	0	0%	16	100%
Canary Wharf Group PLC	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	118	45%	0	0%	0	0%	1	0%	263	45%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	0	0%	19	100%	0	0%	19	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	2	6%	2	6%	29	88%	0	0%	33	100%
Frasers Property (UK) Ltd	0	-	0	-	0	-	0	-	0	-
Galliard Group Limited	11	85%	0	0%	2	15%	0	0%	13	100%
MJ Gleeson PLC	6	55%	2	18%	3	27%	0	0%	11	100%
Grosvenor Developments Limited	0	0%	6	55%	5	45%	0	0%	11	100%
Hill Holdings Limited	3	21%	0	0%	4	29%	0	0%	14	50%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	3	100%	0	0%	0	0%	0	0%	3	100%
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	0	0%	0	0%	0	0%	0	0%	5	0%
Lendlease Europe Holdings Limited	0	0%	0	0%	0	0%	0	0%	39	0%
Pegasus Homes (formerly Lifestory Group)	0	0%	1	100%	0	0%	0	0%	1	100%
London Square Development (Holdings) Limited	39	100%	0	0%	0	0%	0	0%	39	100%
Miller Homes Limited	4	21%	0	0%	15	79%	0	0%	19	100%
Morris Homes Group Limited	0	0%	0	0%	1	100%	0	0%	1	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	7	64%	0	0%	2	18%	0	0%	11	82%
Persimmon Public Limited Company	48	100%	0	0%	0	0%	0	0%	48	100%
Regal Holdco Limited (parent company for Regal London)	0	0%	0	0%	0	0%	0	0%	3	0%
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Sorbon Group Limited (parent company for Shanly Homes)	0	0%	0	0%	14	100%	0	0%	14	100%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	0	0%	0	0%	0	0%	0	0%	4	0%
Story Homes Limited	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	163	100%	0	0%	0	0%	0	0%	163	100%
Telford Homes Limited	63	69%	0	0%	28	31%	0	0%	91	100%
Tilia Homes Limited	2	25%	5	63%	0	0%	0	0%	8	88%
Vistry Group PLC	42	47%	21	24%	4	4%	0	0%	89	75%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	0	0%	0	0%	1	5%	0	0%	21	5%
McCarthy & Stone Limited	0	0%	0	0%	0	0%	0	0%	3	0%
Seven Capital PLC	3	16%	0	0%	8	42%	0	0%	19	58%
Wates Group Limited	0	0%	4	80%	1	20%	0	0%	5	100%
Watkin Jones PLC	7	100%	0	0%	0	0%	0	0%	7	100%
Bouygues (UK) Limited	1	8%	0	0%	1	8%	0	0%	12	17%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	40%	1	20%	0	0%	0	0%	5	60%

## Developer_10
Remediation status of buildings requiring works under the developer remediation contract, time series, England, 30 September 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category - All Defect Types [Note 25, Note 26, Note 29, Note 66]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)	Oct-24 Number	Oct-24 Percentage (%)	Jan-25 Number	Jan-25 Percentage (%)	Apr-25 Number	Apr-25 Percentage (%)	Jul-25 Number	Jul-25 Percentage (%)
Remediation complete	262	19%	307	20%	362	23%	410	25%	439	25%	501	27%	516	25%	537	23%
Remediation started	211	16%	317	21%	365	23%	359	22%	411	24%	456	25%	481	24%	497	21%
Remediation not Started - Plans in Place	506	38%	512	34%	371	24%	455	28%	430	25%	370	20%	372	18%	378	16%
Remediation not Started - No Plans in Place	366	27%	364	24%	471	30%	402	25%	466	27%	517	28%	656	32%	965	41%
Total buildings	1345	100%	1500	100%	1569	100%	1626	100%	1746	100%	1844	100%	2025	100%	2377	100%

Remediation Category - Cladding Defects [Note 25, Note 26, Note 29, Note 66]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)	Oct-24 Number	Oct-24 Percentage (%)	Jan-25 Number	Jan-25 Percentage (%)	Apr-25 Number	Apr-25 Percentage (%)	Jul-25 Number	Jul-25 Percentage (%)
Remediation complete	245	19%	284	20%	340	24%	381	26%	397	26%	441	30%	448	29%	463	26%
Remediation started	200	16%	303	22%	337	24%	334	23%	393	26%	348	24%	376	25%	401	23%
Remediation not Started - Plans in Place	476	37%	481	34%	345	24%	418	29%	390	25%	322	22%	325	21%	323	18%
Remediation not Started - No Plans in Place	352	28%	335	24%	406	28%	316	22%	356	23%	340	23%	377	25%	576	33%
Total buildings	1273	100%	1403	100%	1428	100%	1449	100%	1536	100%	1451	100%	1526	100%	1763	100%

## Developer_11
Estimated number of determinations, starts and completions made each quarter for buildings under the developer remediation contract, by height group, England, 31 July 2025 [Note 86]
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Buildings where the Developer is directly responsible for Remediation and a Determination was made... [Note 28] [Note 84]	...Before 31 January 2024 [Note 83]	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025
Total	2500	268	213	207	259	253	472

Buildings (by height) currently found to require Remediation and will be Remediated by the Developer directly, where works started… [Note 31] [Note 85]	...Before 31 July 2023	...Between 1 August 2023 and 31 October 2023	...Between 1 November 2023 and 31 January 2024	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025
11-18m	109	43	70	36	15	56	68	24	15
18m+	171	65	65	59	13	29	41	16	26
Total	280	108	135	95	28	85	109	40	41

Buildings (by height) currently found to require Remediation and will be Remediated by the Developer directly, where works completed… [Note 31] [Note 85]	...Before 31 July 2023	...Between 1 August 2023 and 31 October 2023	...Between 1 November 2023 and 31 January 2024	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025
11-18m	56	25	26	32	7	22	48	7	21
18m+	74	48	9	21	23	7	15	11	8
Total	130	73	35	53	30	29	63	18	29

## Developer_12
Developer by developer update against RAP Joint Plan targets, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note 29]	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme)	Number of buildings for which the developer has determined whether works are required	Percentage of buildings for which the developer has determined whether works are required	Number of buildings where an exception request has been accepted against the July 2025 joint plan target [Note 95]	Estimated percentage of buildings for which the developer has determined whether works are required (excluding buildings for which an exception request has been accepted)
All Developers	4538	4172	92%	55	93%
Joint Plan Signatories [Note 94]	4271	3969	93%	55	94%
Other Developers (Other Developers)	267	203	76%	0	76%

Developer - Joint Plan Signatories [Note 94]	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme)	Number of buildings for which the developer has determined whether works are required	Percentage of buildings for which the developer has determined whether works are required	Number of buildings where an exception request has been accepted against the July 2025 joint plan target [Note 95]	Estimated percentage of buildings for which the developer has determined whether works are required (excluding buildings for which an exception request has been accepted)
Total - (Joint Plan signatories)	4271	3969	93%	55	94%
Ballymore Limited	69	69	100%	0	100%
Barratt Redrow PLC	821	626	76%	0	76%
Bellway PLC	420	420	100%	0	100%
Bewley Group Limited	7	6	86%	0	86%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	10	10	100%	0	100%
Cala Group (Holdings) Limited	22	22	100%	0	100%
Canary Wharf Group PLC	13	9	69%	4	100%
Crest Nicholson Holdings PLC	292	290	99%	2	100%
Dandara Living Holdings Limited	21	21	100%	0	100%
Fairview Holdings Limited	121	121	100%	0	100%
Grosvenor Developments Limited	21	20	95%	0	95%
Hill Holdings Limited	90	76	84%	14	100%
Jelson Holdings Limited	7	7	100%	0	100%
Lendlease Europe Holdings Limited	88	88	100%	0	100%
London Square Development (Holdings) Limited	40	40	100%	0	100%
McCarthy & Stone Limited	62	60	97%	0	97%
Miller Homes Limited	39	39	100%	0	100%
MJ Gleeson PLC	16	13	81%	0	81%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	113	113	100%	0	100%
Morris Homes Group Limited	6	6	100%	0	100%
Pegasus Homes (formerly Lifestory Group)	18	18	100%	0	100%
Persimmon Public Limited Company	70	70	100%	0	100%
Regal Holdco Limited (parent company for Regal London)	16	16	100%	0	100%
Rydon Group Holdings Limited	22	22	100%	0	100%
Seven Capital PLC	21	21	100%	0	100%
Sorbon Group Limited (parent company for Shanly Homes)	26	26	100%	0	100%
Taylor Wimpey PLC	431	372	86%	19	90%
Telford Homes Limited	143	142	99%	1	100%
The Berkeley Group Holdings PLC	810	796	98%	10	100%
The British Land Company PLC	16	16	100%	0	100%
Tilia Homes Limited	8	8	100%	0	100%
Vistry Group PLC	294	291	99%	2	100%
Wates Group Limited	23	20	87%	3	100%
Weston Group PLC	87	87	100%	0	100%
Other (combined total for all developers with 5 or fewer buildings each: Bloor, CG Fry, Hopkins, Keepmoat Homes)	8	8	100%	0	100%

## Social_1
Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - Social Buildings with Unsafe Cladding [Note 34] [Note 35] [Note 37] [Note 58] [Note 91] [Note 92]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete [Note 54]	374	26%	678	44%	1052	36%
Remediation complete - Awaiting building control sign-off	10	1%	37	2%	47	2%
Remediation started	147	10%	137	9%	284	10%
Remediation works planned	545	39%	446	29%	991	34%
Remediation plans unclear from survey	336	24%	243	16%	579	20%
Total buildings [Note 36]	1,412	100%	1,541	100%	2,953	100%

Social Buildings with Unsafe Cladding identified since June 2017, as reported by Social Housing Providers [Note 34] [Note 35] [Note 37] [Note 67] [Note 91] [Note 92]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete - Prior to the most recent assessment	281	21%	604	41%	885	31%
Remediation complete - Since the most recent assessment [Note 54]	78	6%	79	5%	157	6%
Remediation started	138	10%	127	9%	265	9%
Remediation works planned	539	41%	441	30%	980	35%
Remediation plans unclear from survey	294	22%	229	15%	523	19%
Total buildings	1,330	100%	1,480	100%	2,810	100%

Remediation Category - Social Buildings with Unsafe Cladding at the Time of their Most Recent Assessment, as reported by Social Housing Providers [Note 34] [Note 35] [Note 37] [Note 62] [Note 91] [Note 92]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete [Note 54]	68	6%	43	5%	111	6%
Remediation complete - Awaiting building control sign-off	10	1%	36	4%	46	2%
Remediation started	138	13%	127	14%	265	14%
Remediation works planned	539	51%	441	50%	980	51%
Remediation plans unclear from survey	294	28%	229	26%	523	27%
Total buildings	1,049	100%	876	100%	1,925	100%

## Social_2
Provider by provider breakdown of buildings, by assessment status, England, 30 June 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey as of 30 June 2025
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51] [Note 91]	Total number of buildings over 11 metres	Progress with assessments
		Of the total number of buildings over 11m, buildings that…
		…have had a recent works assessment [Note 52]		…have not had a recent works assessment
		Number	Percentage	Number	Percentage‎
Total	17140	16978	99%	17	0%
A2Dominion Housing Group Limited	174	174	100%	0	0%
Abri Group Limited	39	39	100%	0	0%
Accent Group Limited	7	7	100%	0	0%
Acis Group Limited	21	21	100%	0	0%
Agudas Israel Housing Association Limited	19	19	100%	0	0%
Anchor Hanover Group	37	37	100%	0	0%
Ashford Borough Council	19	19	100%	0	0%
Ashton Pioneer Homes Limited	10	10	100%	0	0%
Aster Group Limited	42	42	100%	0	0%
B3 Living Limited	12	12	100%	0	0%
Beyond Housing Limited	10	10	100%	0	0%
Birkenhead Forum Housing Association Limited	9	9	100%	0	0%
Birmingham City Council	205	205	100%	0	0%
Bolton at Home Limited	10	10	100%	0	0%
Bournemouth, Christchurch and Poole Council	15	15	100%	0	0%
bpha Limited	27	27	100%	0	0%
Bridgwater Young Men’s Christian Association	6	6	100%	0	0%
Brighter Places	11	11	100%	0	0%
Brighton and Hove City Council	81	-	-	-	-
Bristol City Council	93	93	100%	0	0%
Broadland Housing Association Limited	10	10	100%	0	0%
Bromford Flagship Limited	24	24	100%	0	0%
Cambridge City Council	21	21	100%	0	0%
Central Bedfordshire Council	9	9	100%	0	0%
Christian Action (Enfield) Housing Association Limited	13	13	100%	0	0%
Citizen Housing Group Limited	60	60	100%	0	0%
City of Doncaster Council	9	9	100%	0	0%
City of London Corporation	26	26	100%	0	0%
City of Westminster Council	410	410	100%	0	0%
Clarion Housing Group Limited	554	554	100%	0	0%
Curo Group (Albion) Limited	147	147	100%	0	0%
Dacorum Borough Council	17	17	100%	0	0%
Dudley Metropolitan Borough Council	49	49	100%	0	0%
East End Homes Limited	44	44	100%	0	0%
Ekaya Housing Association Limited	9	9	100%	0	0%
Estuary Housing Association Limited	19	19	100%	0	0%
Exeter City Council	7	7	100%	0	0%
Fairhazel Co-operative Limited	12	12	100%	0	0%
First Choice Homes Oldham Limited	8	8	100%	0	0%
ForHousing Limited	26	26	100%	0	0%
Gateshead Metropolitan Borough Council	23	23	100%	0	0%
Gateway Housing Association Limited	23	23	100%	0	0%
Gentoo Group Limited	32	32	100%	0	0%
Gloucester City Homes Limited	6	6	100%	0	0%
Golding Homes Limited	8	8	100%	0	0%
Gosport Borough Council	6	6	100%	0	0%
Gravesham Borough Council	7	7	100%	0	0%
Great Places Housing Group Limited	17	17	100%	0	0%
GreenSquareAccord Limited	16	16	100%	0	0%
Haringey London Borough Council	95	95	100%	0	0%
Harlow District Council	18	18	100%	0	0%
Hastoe Housing Association Limited	6	6	100%	0	0%
Heart of Medway Housing Association Limited	8	8	100%	0	0%
Hexagon Housing Association Limited	21	21	100%	0	0%
HFL Homes Limited	7	7	100%	0	0%
Hightown Housing Association Limited	20	20	100%	0	0%
Home Group Limited	73	73	100%	0	0%
Housing 21	19	19	100%	0	0%
Housing For Women	20	20	100%	0	0%
Hyde Housing Association Limited	236	236	100%	0	0%
Incommunities Limited	32	32	100%	0	0%
Irwell Valley Housing Association Limited	13	13	100%	0	0%
Islington and Shoreditch Housing Association Limited	44	44	100%	0	0%
Jigsaw Homes Group Limited	19	19	100%	0	0%
Karbon Homes Limited	35	35	100%	0	0%
Karibu Community Homes Limited	8	8	100%	0	0%
Kingston upon Hull City Council	26	26	100%	0	0%
Kirklees Metropolitan Borough Council	21	21	100%	0	0%
Lambeth and Southwark Housing Association Limited	11	11	100%	0	0%
Leeds City Council	131	131	100%	0	0%
Legal & General Affordable Homes (AR) LLP	6	6	100%	0	0%
Legal & General Affordable Homes Limited	6	6	100%	0	0%
Legal and General Affordable Homes (Development 3) Limited	6	6	100%	0	0%
Leicester City Council	11	11	100%	0	0%
LiveWest Homes Limited	66	66	100%	0	0%
Livv Housing Group	9	9	100%	0	0%
London & Quadrant Housing Trust	713	713	100%	0	0%
London Borough of Barking and Dagenham	76	76	100%	0	0%
London Borough of Barnet	48	48	100%	0	0%
London Borough of Brent	64	-	-	-	-
London Borough of Camden Council	952	952	100%	0	0%
London Borough of Croydon	66	66	100%	0	0%
London Borough of Ealing	48	48	100%	0	0%
London Borough of Enfield	66	66	100%	0	0%
London Borough of Hackney	462	462	100%	0	0%
London Borough of Hammersmith and Fulham	231	231	100%	0	0%
London Borough of Havering Council	23	23	100%	0	0%
London Borough of Hillingdon	13	13	100%	0	0%
London Borough of Hounslow	63	63	100%	0	0%
London Borough of Islington	386	386	100%	0	0%
London Borough of Lambeth	389	389	100%	0	0%
London Borough of Lewisham	159	159	100%	0	0%
London Borough of Newham	91	91	100%	0	0%
London Borough of Redbridge	22	22	100%	0	0%
London Borough of Sutton	60	60	100%	0	0%
London Borough of Tower Hamlets	326	326	100%	0	0%
London Borough of Waltham Forest	65	64	98%	1	2%
London Borough of Wandsworth	363	363	100%	0	0%
Look Ahead Care and Support Limited	8	8	100%	0	0%
Luton Borough Council	15	6	40%	9	60%
Magenta Living	11	11	100%	0	0%
Manchester City Council	42	42	100%	0	0%
Metropolitan Housing Trust Limited	258	258	100%	0	0%
Midland Heart Limited	17	17	100%	0	0%
Moat Homes Limited	26	26	100%	0	0%
New Foundations Housing Association Limited	6	6	100%	0	0%
Newark and Sherwood District Council	6	6	100%	0	0%
Newcastle City Council	54	54	100%	0	0%
Newlon Housing Trust	85	85	100%	0	0%
North Devon Homes	6	6	100%	0	0%
North London Muslim Housing Association Limited	12	12	100%	0	0%
Norwich City Council	25	25	100%	0	0%
Notting Hill Genesis	955	955	100%	0	0%
Nottingham City Council	24	24	100%	0	0%
Nottingham Community Housing Association Limited	13	13	100%	0	0%
Octavia Housing	115	115	100%	0	0%
One Manchester Limited	25	25	100%	0	0%
One Vision Housing Limited	8	8	100%	0	0%
Onward Group Limited	49	49	100%	0	0%
Orbit Group Limited	81	81	100%	0	0%
Oxford City Council	8	8	100%	0	0%
P3 Housing Limited	33	33	100%	0	0%
Paradigm Housing Group Limited	24	24	100%	0	0%
Paragon Asra Housing Limited	84	84	100%	0	0%
Peabody Trust	1239	1239	100%	0	0%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	15	100%	0	0%
Places for People Group Limited	195	195	100%	0	0%
Platform Housing Group Limited	16	16	100%	0	0%
Plus Dane Housing Limited	10	10	100%	0	0%
Plymouth Community Homes Limited	55	55	100%	0	0%
Poplar Housing And Regeneration Community Association Limited	118	118	100%	0	0%
Portsmouth City Council	55	55	100%	0	0%
Providence Row Housing Association	11	11	100%	0	0%
Raven Housing Trust Limited	13	13	100%	0	0%
Reading Borough Council	18	18	100%	0	0%
Regenda Limited	18	18	100%	0	0%
Richmond Housing Partnership Limited	43	43	100%	0	0%
Rochdale Boroughwide Housing Limited	14	14	100%	0	0%
Rooftop Housing Group Limited	6	6	100%	0	0%
Royal Borough of Greenwich	193	193	100%	0	0%
Royal Borough of Kensington and Chelsea	208	207	100%	1	0%
Royal Borough of Kingston Upon Thames	34	34	100%	0	0%
Salix Homes Limited	20	20	100%	0	0%
Salvation Army Housing Association	14	14	100%	0	0%
Sanctuary Housing Association	424	424	100%	0	0%
Sandwell Metropolitan Borough Council	55	55	100%	0	0%
Seymour Housing Co-operative Limited	8	8	100%	0	0%
Sheffield City Council	359	359	100%	0	0%
Soho Housing Association Limited	46	46	100%	0	0%
Solihull Metropolitan Borough Council	37	37	100%	0	0%
Southampton City Council	196	196	100%	0	0%
Southend on Sea City Council	18	18	100%	0	0%
Southern Housing	550	550	100%	0	0%
Southwark Council	852	851	100%	1	0%
Southway Housing Trust (Manchester) Limited	6	6	100%	0	0%
Sovereign Network Group	300	295	98%	5	2%
Spitalfields Housing Association Limited	11	11	100%	0	0%
St Mungo Community Housing Association	20	20	100%	0	0%
Stevenage Borough Council	12	12	100%	0	0%
Stockport Homes Limited	30	30	100%	0	0%
Stoke on Trent City Council	18	18	100%	0	0%
Stonewater Limited	33	33	100%	0	0%
Swindon Borough Council	8	8	100%	0	0%
Tamworth Borough Council	7	7	100%	0	0%
Teign Housing	8	8	100%	0	0%
Thanet District Council	10	10	100%	0	0%
The ExtraCare Charitable Trust	10	10	100%	0	0%
The Guinness Partnership Limited	313	313	100%	0	0%
The Housing Plus Group Limited	13	13	100%	0	0%
The Industrial Dwellings Society (1885) Limited	35	35	100%	0	0%
The Riverside Group Limited	301	301	100%	0	0%
Thirteen Housing Group Limited	15	15	100%	0	0%
Thrive Homes Limited	6	6	100%	0	0%
Thurrock Council	18	18	100%	0	0%
Together Housing Group Limited	45	45	100%	0	0%
Torus62 Limited	6	6	100%	0	0%
Trident Housing Association Limited	12	12	100%	0	0%
Vico Homes Limited	19	19	100%	0	0%
Vivid Housing Limited	54	54	100%	0	0%
Walsall Housing Group Limited	20	20	100%	0	0%
Wandle Housing Association Limited	40	40	100%	0	0%
Warwick District Council	9	9	100%	0	0%
Watford Community Housing Trust	11	11	100%	0	0%
Watmos Community Homes	35	35	100%	0	0%
West Hampstead Housing Co-operative Limited	11	11	100%	0	0%
West Northamptonshire Council	14	14	100%	0	0%
Wigan Council	7	7	100%	0	0%
Winchester City Council	9	9	100%	0	0%
Woking Borough Council	25	25	100%	0	0%
Wolverhampton City Council	52	52	100%	0	0%
Women’s Pioneer Housing Limited	63	63	100%	0	0%
Worthing Homes Limited	6	6	100%	0	0%
Wythenshawe Community Housing Group Limited	12	12	100%	0	0%
YMCA St Paul’s Group	6	6	100%	0	0%
Yorkshire Housing Limited	14	14	100%	0	0%
Your Housing Group Limited	24	24	100%	0	0%
Zebra Housing Association Limited	8	8	100%	0	0%
Other RPs	522	522	100%	0	0%

## Social_3
Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 June 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey as of 30 June 2025
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51] [Note 91]	Total number of buildings over 11 metres	Number of buildings identified as having EWS life-critical fire-safety defects since June 2017 [Note_35] [Note_67]	% buildings identified as having EWS life-critical fire-safety defects since June 2017	Number of buildings assessed as having EWS life-critical fire-safety defects at the time of their most recent assessment [Note_35] [Note_52] [Note_62]	% buildings assessed as having EWS life-critical fire-safety defects at the time of their most recent assessment
Total	17,140	2,810	16%	1,925	11%
A2Dominion Housing Group Limited	174	44	25%	24	14%
Abri Group Limited	39	5	13%	2	5%
Accent Group Limited	7	3	43%	1	14%
Acis Group Limited	21	1	5%	1	5%
Agudas Israel Housing Association Limited	19	1	5%	1	5%
Anchor Hanover Group	37	10	27%	10	27%
Ashford Borough Council	19	0	0%	0	0%
Ashton Pioneer Homes Limited	10	0	0%	0	0%
Aster Group Limited	42	8	19%	4	10%
B3 Living Limited	12	5	42%	5	42%
Beyond Housing Limited	10	0	0%	0	0%
Birkenhead Forum Housing Association Limited	9	0	0%	0	0%
Birmingham City Council	205	140	68%	16	8%
Bolton at Home Limited	10	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	15	2	13%	0	0%
bpha Limited	27	5	19%	2	7%
Bridgwater Young Men’s Christian Association	6	0	0%	0	0%
Brighter Places	11	0	0%	0	0%
Brighton and Hove City Council	81	-	-	-	-
Bristol City Council	93	44	47%	44	47%
Broadland Housing Association Limited	10	2	20%	1	10%
Bromford Flagship Limited	24	2	8%	2	8%
Cambridge City Council	21	3	14%	3	14%
Central Bedfordshire Council	9	1	11%	1	11%
Christian Action (Enfield) Housing Association Limited	13	3	23%	3	23%
Citizen Housing Group Limited	60	2	3%	2	3%
City of Doncaster Council	9	9	100%	9	100%
City of London Corporation	26	0	0%	0	0%
City of Westminster Council	410	8	2%	2	0%
Clarion Housing Group Limited	554	115	21%	65	12%
Curo Group (Albion) Limited	147	0	0%	0	0%
Dacorum Borough Council	17	4	24%	4	24%
Dudley Metropolitan Borough Council	49	0	0%	0	0%
East End Homes Limited	44	8	18%	6	14%
Ekaya Housing Association Limited	9	0	0%	0	0%
Estuary Housing Association Limited	19	2	11%	0	0%
Exeter City Council	7	0	0%	0	0%
Fairhazel Co-operative Limited	12	0	0%	0	0%
First Choice Homes Oldham Limited	8	2	25%	0	0%
ForHousing Limited	26	11	42%	5	19%
Gateshead Metropolitan Borough Council	23	1	4%	0	0%
Gateway Housing Association Limited	23	1	4%	1	4%
Gentoo Group Limited	32	11	34%	5	16%
Gloucester City Homes Limited	6	0	0%	0	0%
Golding Homes Limited	8	3	38%	3	38%
Gosport Borough Council	6	0	0%	0	0%
Gravesham Borough Council	7	0	0%	0	0%
Great Places Housing Group Limited	17	6	35%	6	35%
GreenSquareAccord Limited	16	9	56%	9	56%
Haringey London Borough Council	95	49	52%	20	21%
Harlow District Council	18	2	11%	0	0%
Hastoe Housing Association Limited	6	3	50%	3	50%
Heart of Medway Housing Association Limited	8	5	63%	0	0%
Hexagon Housing Association Limited	21	19	90%	19	90%
HFL Homes Limited	7	0	0%	0	0%
Hightown Housing Association Limited	20	2	10%	1	5%
Home Group Limited	73	25	34%	19	26%
Housing 21	19	0	0%	0	0%
Housing For Women	20	0	0%	0	0%
Hyde Housing Association Limited	236	82	35%	43	18%
Incommunities Limited	32	11	34%	11	34%
Irwell Valley Housing Association Limited	13	6	46%	5	38%
Islington and Shoreditch Housing Association Limited	44	14	32%	7	16%
Jigsaw Homes Group Limited	19	14	74%	6	32%
Karbon Homes Limited	35	18	51%	18	51%
Karibu Community Homes Limited	8	1	13%	0	0%
Kingston upon Hull City Council	26	0	0%	0	0%
Kirklees Metropolitan Borough Council	21	15	71%	14	67%
Lambeth and Southwark Housing Association Limited	11	0	0%	0	0%
Leeds City Council	131	0	0%	0	0%
Legal & General Affordable Homes (AR) LLP	6	0	0%	0	0%
Legal & General Affordable Homes Limited	6	0	0%	0	0%
Legal and General Affordable Homes (Development 3) Limited	6	0	0%	0	0%
Leicester City Council	11	0	0%	0	0%
LiveWest Homes Limited	66	7	11%	6	9%
Livv Housing Group	9	0	0%	0	0%
London & Quadrant Housing Trust	713	80	11%	57	8%
London Borough of Barking and Dagenham	76	2	3%	2	3%
London Borough of Barnet	48	13	27%	7	15%
London Borough of Brent	64	-	-	-	-
London Borough of Camden Council	952	12	1%	5	1%
London Borough of Croydon	66	0	0%	0	0%
London Borough of Ealing	48	2	4%	2	4%
London Borough of Enfield	66	0	0%	0	0%
London Borough of Hackney	462	75	16%	73	16%
London Borough of Hammersmith and Fulham	231	7	3%	7	3%
London Borough of Havering Council	23	1	4%	1	4%
London Borough of Hillingdon	13	1	8%	0	0%
London Borough of Hounslow	63	1	2%	0	0%
London Borough of Islington	386	3	1%	1	0%
London Borough of Lambeth	389	7	2%	4	1%
London Borough of Lewisham	159	34	21%	26	16%
London Borough of Newham	91	43	47%	32	35%
London Borough of Redbridge	22	0	0%	0	0%
London Borough of Sutton	60	1	2%	1	2%
London Borough of Tower Hamlets	326	34	10%	30	9%
London Borough of Waltham Forest	65	30	46%	20	31%
London Borough of Wandsworth	363	2	1%	2	1%
Look Ahead Care and Support Limited	8	4	50%	3	38%
Luton Borough Council	15	0	0%	0	0%
Magenta Living	11	3	27%	0	0%
Manchester City Council	42	21	50%	16	38%
Metropolitan Housing Trust Limited	258	114	44%	106	41%
Midland Heart Limited	17	1	6%	0	0%
Moat Homes Limited	26	5	19%	4	15%
New Foundations Housing Association Limited	6	0	0%	0	0%
Newark and Sherwood District Council	6	0	0%	0	0%
Newcastle City Council	54	0	0%	0	0%
Newlon Housing Trust	85	52	61%	47	55%
North Devon Homes	6	0	0%	0	0%
North London Muslim Housing Association Limited	12	8	67%	8	67%
Norwich City Council	25	2	8%	2	8%
Notting Hill Genesis	955	116	12%	49	5%
Nottingham City Council	24	0	0%	0	0%
Nottingham Community Housing Association Limited	13	1	8%	0	0%
Octavia Housing	115	24	21%	23	20%
One Manchester Limited	25	16	64%	0	0%
One Vision Housing Limited	8	2	25%	0	0%
Onward Group Limited	49	19	39%	15	31%
Orbit Group Limited	81	28	35%	27	33%
Oxford City Council	8	0	0%	0	0%
P3 Housing Limited	33	0	0%	0	0%
Paradigm Housing Group Limited	24	1	4%	0	0%
Paragon Asra Housing Limited	84	21	25%	19	23%
Peabody Trust	1,239	196	16%	165	13%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	4	27%	4	27%
Places for People Group Limited	195	46	24%	20	10%
Platform Housing Group Limited	16	2	13%	2	13%
Plus Dane Housing Limited	10	3	30%	3	30%
Plymouth Community Homes Limited	55	4	7%	0	0%
Poplar Housing And Regeneration Community Association Limited	118	31	26%	7	6%
Portsmouth City Council	55	22	40%	4	7%
Providence Row Housing Association	11	1	9%	0	0%
Raven Housing Trust Limited	13	0	0%	0	0%
Reading Borough Council	18	3	17%	3	17%
Regenda Limited	18	4	22%	1	6%
Richmond Housing Partnership Limited	43	18	42%	16	37%
Rochdale Boroughwide Housing Limited	14	9	64%	9	64%
Rooftop Housing Group Limited	6	1	17%	1	17%
Royal Borough of Greenwich	193	10	5%	10	5%
Royal Borough of Kensington and Chelsea	208	9	4%	8	4%
Royal Borough of Kingston Upon Thames	34	0	0%	0	0%
Salix Homes Limited	20	8	40%	0	0%
Salvation Army Housing Association	14	1	7%	0	0%
Sanctuary Housing Association	424	87	21%	68	16%
Sandwell Metropolitan Borough Council	55	4	7%	0	0%
Seymour Housing Co-operative Limited	8	0	0%	0	0%
Sheffield City Council	359	1	0%	0	0%
Soho Housing Association Limited	46	0	0%	0	0%
Solihull Metropolitan Borough Council	37	16	43%	11	30%
Southampton City Council	196	83	42%	83	42%
Southend on Sea City Council	18	0	0%	0	0%
Southern Housing	550	170	31%	150	27%
Southwark Council	852	128	15%	59	7%
Southway Housing Trust (Manchester) Limited	6	0	0%	0	0%
Sovereign Network Group	300	102	34%	53	18%
Spitalfields Housing Association Limited	11	4	36%	4	36%
St Mungo Community Housing Association	20	1	5%	1	5%
Stevenage Borough Council	12	5	42%	5	42%
Stockport Homes Limited	30	15	50%	15	50%
Stoke on Trent City Council	18	12	67%	12	67%
Stonewater Limited	33	7	21%	6	18%
Swindon Borough Council	8	0	0%	0	0%
Tamworth Borough Council	7	0	0%	0	0%
Teign Housing	8	1	13%	1	13%
Thanet District Council	10	5	50%	5	50%
The ExtraCare Charitable Trust	10	1	10%	0	0%
The Guinness Partnership Limited	313	26	8%	17	5%
The Housing Plus Group Limited	13	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	35	0	0%	0	0%
The Riverside Group Limited	301	91	30%	91	30%
Thirteen Housing Group Limited	15	0	0%	0	0%
Thrive Homes Limited	6	0	0%	0	0%
Thurrock Council	18	0	0%	0	0%
Together Housing Group Limited	45	14	31%	0	0%
Torus62 Limited	6	0	0%	0	0%
Trident Housing Association Limited	12	0	0%	0	0%
Vico Homes Limited	19	4	21%	4	21%
Vivid Housing Limited	54	9	17%	1	2%
Walsall Housing Group Limited	20	0	0%	0	0%
Wandle Housing Association Limited	40	14	35%	14	35%
Warwick District Council	9	5	56%	5	56%
Watford Community Housing Trust	11	0	0%	0	0%
Watmos Community Homes	35	0	0%	0	0%
West Hampstead Housing Co-operative Limited	11	0	0%	0	0%
West Northamptonshire Council	14	8	57%	2	14%
Wigan Council	7	0	0%	0	0%
Winchester City Council	9	0	0%	0	0%
Woking Borough Council	25	14	56%	14	56%
Wolverhampton City Council	52	9	17%	9	17%
Women’s Pioneer Housing Limited	63	0	0%	0	0%
Worthing Homes Limited	6	2	33%	1	17%
Wythenshawe Community Housing Group Limited	12	7	58%	0	0%
YMCA St Paul’s Group	6	1	17%	1	17%
Yorkshire Housing Limited	14	0	0%	0	0%
Your Housing Group Limited	24	11	46%	10	42%
Zebra Housing Association Limited	8	0	0%	0	0%
Other RPs	522	51	10%	32	6%

## Social_4
Provider by provider breakdown of buildings, by remediation status, England, 30 June 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey as of 30 June 2025
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51] [Note 91]	Number of buildings with EWS life-critical fire safety defects since June 2017	Remediation Status
		Number and proportion of buildings identified as having EWS life-critical fire-safety defects [Note 35] [Note 67] since June 2017, where remediation...
		…plans are unclear from survey		…works are planned		…has started		... has completed since the most recent works assessment [Note 54]		... has completed prior to the most recent works assessment
		Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total	2,810	523	19%	980	35%	265	9%	157	6%	885	31%
A2Dominion Housing Group Limited	44	1	2%	15	34%	8	18%	0	0%	20	45%
Abri Group Limited	5	0	0%	2	40%	0	0%	0	0%	3	60%
Accent Group Limited	3	0	0%	1	33%	0	0%	0	0%	2	67%
Acis Group Limited	1	0	0%	1	100%	0	0%	0	0%	0	0%
Agudas Israel Housing Association Limited	1	0	0%	1	100%	0	0%	0	0%	0	0%
Anchor Hanover Group	10	0	0%	10	100%	0	0%	0	0%	0	0%
Ashford Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Ashton Pioneer Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Aster Group Limited	8	1	13%	2	25%	1	13%	0	0%	4	50%
B3 Living Limited	5	4	80%	1	20%	0	0%	0	0%	0	0%
Beyond Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Birkenhead Forum Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Birmingham City Council	140	0	0%	1	1%	4	3%	11	8%	124	89%
Bolton at Home Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	2	0	0%	0	0%	0	0%	0	0%	2	100%
bpha Limited	5	2	40%	0	0%	0	0%	0	0%	3	60%
Bridgwater Young Men’s Christian Association	0	0	0%	0	0%	0	0%	0	0%	0	0%
Brighter Places	0	0	0%	0	0%	0	0%	0	0%	0	0%
Brighton and Hove City Council	-	-	-	-	-	-	-	-	-	-	-
Bristol City Council	44	5	11%	28	64%	1	2%	10	23%	0	0%
Broadland Housing Association Limited	2	1	50%	0	0%	0	0%	0	0%	1	50%
Bromford Flagship Limited	2	0	0%	1	50%	1	50%	0	0%	0	0%
Cambridge City Council	3	2	67%	1	33%	0	0%	0	0%	0	0%
Central Bedfordshire Council	1	0	0%	1	100%	0	0%	0	0%	0	0%
Christian Action (Enfield) Housing Association Limited	3	0	0%	3	100%	0	0%	0	0%	0	0%
Citizen Housing Group Limited	2	0	0%	2	100%	0	0%	0	0%	0	0%
City of Doncaster Council	9	4	44%	0	0%	4	44%	1	11%	0	0%
City of London Corporation	0	0	0%	0	0%	0	0%	0	0%	0	0%
City of Westminster Council	8	0	0%	2	25%	0	0%	0	0%	6	75%
Clarion Housing Group Limited	115	17	15%	25	22%	19	17%	4	3%	50	43%
Curo Group (Albion) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Dacorum Borough Council	4	2	50%	0	0%	2	50%	0	0%	0	0%
Dudley Metropolitan Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
East End Homes Limited	8	2	25%	3	38%	0	0%	1	13%	2	25%
Ekaya Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Estuary Housing Association Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
Exeter City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Fairhazel Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
First Choice Homes Oldham Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
ForHousing Limited	11	4	36%	1	9%	0	0%	0	0%	6	55%
Gateshead Metropolitan Borough Council	1	0	0%	0	0%	0	0%	0	0%	1	100%
Gateway Housing Association Limited	1	0	0%	1	100%	0	0%	0	0%	0	0%
Gentoo Group Limited	11	3	27%	1	9%	0	0%	1	9%	6	55%
Gloucester City Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Golding Homes Limited	3	1	33%	0	0%	2	67%	0	0%	0	0%
Gosport Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Gravesham Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Great Places Housing Group Limited	6	1	17%	5	83%	0	0%	0	0%	0	0%
GreenSquareAccord Limited	9	0	0%	9	100%	0	0%	0	0%	0	0%
Haringey London Borough Council	49	0	0%	20	41%	0	0%	0	0%	29	59%
Harlow District Council	2	0	0%	0	0%	0	0%	0	0%	2	100%
Hastoe Housing Association Limited	3	0	0%	2	67%	1	33%	0	0%	0	0%
Heart of Medway Housing Association Limited	5	0	0%	0	0%	0	0%	0	0%	5	100%
Hexagon Housing Association Limited	19	14	74%	3	16%	1	5%	1	5%	0	0%
HFL Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Hightown Housing Association Limited	2	0	0%	1	50%	0	0%	0	0%	1	50%
Home Group Limited	25	0	0%	8	32%	9	36%	2	8%	6	24%
Housing 21	0	0	0%	0	0%	0	0%	0	0%	0	0%
Housing For Women	0	0	0%	0	0%	0	0%	0	0%	0	0%
Hyde Housing Association Limited	82	0	0%	26	32%	5	6%	12	15%	39	48%
Incommunities Limited	11	11	100%	0	0%	0	0%	0	0%	0	0%
Irwell Valley Housing Association Limited	6	1	17%	0	0%	4	67%	0	0%	1	17%
Islington and Shoreditch Housing Association Limited	14	1	7%	5	36%	1	7%	0	0%	7	50%
Jigsaw Homes Group Limited	14	3	21%	2	14%	0	0%	1	7%	8	57%
Karbon Homes Limited	18	0	0%	17	94%	0	0%	1	6%	0	0%
Karibu Community Homes Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Kingston upon Hull City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Kirklees Metropolitan Borough Council	15	10	67%	2	13%	2	13%	0	0%	1	7%
Lambeth and Southwark Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Leeds City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Legal & General Affordable Homes (AR) LLP	0	0	0%	0	0%	0	0%	0	0%	0	0%
Legal & General Affordable Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Legal and General Affordable Homes (Development 3) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Leicester City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
LiveWest Homes Limited	7	6	86%	0	0%	0	0%	0	0%	1	14%
Livv Housing Group	0	0	0%	0	0%	0	0%	0	0%	0	0%
London & Quadrant Housing Trust	80	21	26%	4	5%	5	6%	27	34%	23	29%
London Borough of Barking and Dagenham	2	2	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Barnet	13	0	0%	7	54%	0	0%	0	0%	6	46%
London Borough of Brent	-	-	-	-	-	-	-	-	-	-	-
London Borough of Camden Council	12	0	0%	4	33%	1	8%	0	0%	7	58%
London Borough of Croydon	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Ealing	2	2	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Enfield	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hackney	75	71	95%	1	1%	1	1%	0	0%	2	3%
London Borough of Hammersmith and Fulham	7	0	0%	4	57%	3	43%	0	0%	0	0%
London Borough of Havering Council	1	0	0%	1	100%	0	0%	0	0%	0	0%
London Borough of Hillingdon	1	0	0%	0	0%	0	0%	0	0%	1	100%
London Borough of Hounslow	1	0	0%	0	0%	0	0%	0	0%	1	100%
London Borough of Islington	3	1	33%	0	0%	0	0%	0	0%	2	67%
London Borough of Lambeth	7	0	0%	4	57%	0	0%	0	0%	3	43%
London Borough of Lewisham	34	0	0%	26	76%	0	0%	0	0%	8	24%
London Borough of Newham	43	3	7%	9	21%	19	44%	1	2%	11	26%
London Borough of Redbridge	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Sutton	1	1	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Tower Hamlets	34	1	3%	27	79%	2	6%	0	0%	4	12%
London Borough of Waltham Forest	30	14	47%	0	0%	6	20%	0	0%	10	33%
London Borough of Wandsworth	2	0	0%	2	100%	0	0%	0	0%	0	0%
Look Ahead Care and Support Limited	4	3	75%	0	0%	0	0%	0	0%	1	25%
Luton Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Magenta Living	3	0	0%	0	0%	0	0%	0	0%	3	100%
Manchester City Council	21	3	14%	12	57%	1	5%	0	0%	5	24%
Metropolitan Housing Trust Limited	114	92	81%	0	0%	14	12%	0	0%	8	7%
Midland Heart Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Moat Homes Limited	5	0	0%	2	40%	1	20%	1	20%	1	20%
New Foundations Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newark and Sherwood District Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newcastle City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newlon Housing Trust	52	0	0%	42	81%	5	10%	0	0%	5	10%
North Devon Homes	0	0	0%	0	0%	0	0%	0	0%	0	0%
North London Muslim Housing Association Limited	8	0	0%	8	100%	0	0%	0	0%	0	0%
Norwich City Council	2	0	0%	2	100%	0	0%	0	0%	0	0%
Notting Hill Genesis	116	0	0%	45	39%	4	3%	0	0%	67	58%
Nottingham City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Nottingham Community Housing Association Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Octavia Housing	24	7	29%	16	67%	0	0%	0	0%	1	4%
One Manchester Limited	16	0	0%	0	0%	0	0%	0	0%	16	100%
One Vision Housing Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
Onward Group Limited	19	0	0%	15	79%	0	0%	0	0%	4	21%
Orbit Group Limited	28	16	57%	1	4%	10	36%	0	0%	1	4%
Oxford City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
P3 Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Paradigm Housing Group Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Paragon Asra Housing Limited	21	0	0%	16	76%	3	14%	0	0%	2	10%
Peabody Trust	196	62	32%	79	40%	13	7%	11	6%	31	16%
Phoenix Community Housing Association (Bellingham and Downham) Limited	4	0	0%	2	50%	2	50%	0	0%	0	0%
Places for People Group Limited	46	10	22%	8	17%	2	4%	0	0%	26	57%
Platform Housing Group Limited	2	0	0%	1	50%	1	50%	0	0%	0	0%
Plus Dane Housing Limited	3	1	33%	2	67%	0	0%	0	0%	0	0%
Plymouth Community Homes Limited	4	0	0%	0	0%	0	0%	0	0%	4	100%
Poplar Housing And Regeneration Community Association Limited	31	0	0%	5	16%	2	6%	0	0%	24	77%
Portsmouth City Council	22	0	0%	4	18%	0	0%	0	0%	18	82%
Providence Row Housing Association	1	0	0%	0	0%	0	0%	0	0%	1	100%
Raven Housing Trust Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Reading Borough Council	3	0	0%	3	100%	0	0%	0	0%	0	0%
Regenda Limited	4	0	0%	0	0%	1	25%	0	0%	3	75%
Richmond Housing Partnership Limited	18	0	0%	4	22%	3	17%	9	50%	2	11%
Rochdale Boroughwide Housing Limited	9	9	100%	0	0%	0	0%	0	0%	0	0%
Rooftop Housing Group Limited	1	1	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Greenwich	10	10	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Kensington and Chelsea	9	1	11%	3	33%	0	0%	4	44%	1	11%
Royal Borough of Kingston Upon Thames	0	0	0%	0	0%	0	0%	0	0%	0	0%
Salix Homes Limited	8	0	0%	0	0%	0	0%	0	0%	8	100%
Salvation Army Housing Association	1	0	0%	0	0%	0	0%	0	0%	1	100%
Sanctuary Housing Association	87	1	1%	60	69%	7	8%	0	0%	19	22%
Sandwell Metropolitan Borough Council	4	0	0%	0	0%	0	0%	0	0%	4	100%
Seymour Housing Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Sheffield City Council	1	0	0%	0	0%	0	0%	0	0%	1	100%
Soho Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Solihull Metropolitan Borough Council	16	0	0%	11	69%	0	0%	0	0%	5	31%
Southampton City Council	83	0	0%	46	55%	6	7%	31	37%	0	0%
Southend on Sea City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Southern Housing	170	0	0%	142	84%	8	5%	0	0%	20	12%
Southwark Council	128	45	35%	12	9%	1	1%	1	1%	69	54%
Southway Housing Trust (Manchester) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Sovereign Network Group	102	0	0%	34	33%	19	19%	0	0%	49	48%
Spitalfields Housing Association Limited	4	4	100%	0	0%	0	0%	0	0%	0	0%
St Mungo Community Housing Association	1	0	0%	0	0%	1	100%	0	0%	0	0%
Stevenage Borough Council	5	0	0%	5	100%	0	0%	0	0%	0	0%
Stockport Homes Limited	15	15	100%	0	0%	0	0%	0	0%	0	0%
Stoke on Trent City Council	12	7	58%	0	0%	3	25%	2	17%	0	0%
Stonewater Limited	7	2	29%	3	43%	0	0%	1	14%	1	14%
Swindon Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Tamworth Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Teign Housing	1	0	0%	1	100%	0	0%	0	0%	0	0%
Thanet District Council	5	0	0%	5	100%	0	0%	0	0%	0	0%
The ExtraCare Charitable Trust	1	0	0%	0	0%	0	0%	0	0%	1	100%
The Guinness Partnership Limited	26	4	15%	6	23%	5	19%	2	8%	9	35%
The Housing Plus Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
The Riverside Group Limited	91	0	0%	46	51%	25	27%	20	22%	0	0%
Thirteen Housing Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Thrive Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Thurrock Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Together Housing Group Limited	14	0	0%	0	0%	0	0%	0	0%	14	100%
Torus62 Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Trident Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Vico Homes Limited	4	0	0%	2	50%	2	50%	0	0%	0	0%
Vivid Housing Limited	9	1	11%	0	0%	0	0%	0	0%	8	89%
Walsall Housing Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Wandle Housing Association Limited	14	2	14%	8	57%	4	29%	0	0%	0	0%
Warwick District Council	5	0	0%	5	100%	0	0%	0	0%	0	0%
Watford Community Housing Trust	0	0	0%	0	0%	0	0%	0	0%	0	0%
Watmos Community Homes	0	0	0%	0	0%	0	0%	0	0%	0	0%
West Hampstead Housing Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
West Northamptonshire Council	8	0	0%	2	25%	0	0%	0	0%	6	75%
Wigan Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Winchester City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Woking Borough Council	14	0	0%	0	0%	14	100%	0	0%	0	0%
Wolverhampton City Council	9	0	0%	9	100%	0	0%	0	0%	0	0%
Women’s Pioneer Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Worthing Homes Limited	2	0	0%	1	50%	0	0%	0	0%	1	50%
Wythenshawe Community Housing Group Limited	7	0	0%	0	0%	0	0%	0	0%	7	100%
YMCA St Paul’s Group	1	0	0%	1	100%	0	0%	0	0%	0	0%
Yorkshire Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Your Housing Group Limited	11	5	45%	5	45%	0	0%	0	0%	1	9%
Zebra Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Other RPs	51	10	20%	14	27%	6	12%	2	4%	19	37%

## Social_5
Remediation status of buildings with cladding defects monitored under the social housing surveys, time series, England, 31 August 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [Note 34] [Note 35] [Note 69]	Aug-23 / Number	Aug-23 / Percentage (%)	Dec-23 / Number	Dec-23 / Percentage (%)	Mar-24 [Note 68] / Number	Mar-24 [Note 68] / Percentage (%)	Jun-24 / Number	Jun-24 / Percentage (%)	Sep-24 / Number	Sep-24 / Percentage (%)	Dec-24 / Number	Dec-24 / Percentage (%)	Mar-25 / Number	Mar-25 / Percentage (%)	Jun-25 [Note 92] / Number	Jun-25 [Note 92] / Percentage (%)
Remediation complete [Note 37] [Note 54]	106	7%	204	10%	661	27%	703	28%	728	28%	857	32%	953	34%	1,099	37%
Remediation started [Note 72]	394	25%	525	27%	544	23%	565	23%	448	18%	370	14%	273	10%	286	10%
Remediation works planned	591	37%	658	34%	717	30%	699	28%	845	33%	990	36%	997	36%	991	34%
Remediation plans unclear from survey	510	32%	559	29%	488	20%	540	22%	585	21%	496	18%	571	20%	577	20%
Work is not required	7	0%	6	0%	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	1,608	100%	1,952	100%	2,410	100%	2,507	100%	2,606	100%	2,713	100%	2,794	100%	2,953	100%

## Enforcement_1
Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 19 September 2025
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [note 19] [note 76].

Local Authority [note 2]	BSF or CSS only (non-ACM cladding only) / Number / Previous month	BSF or CSS only (non-ACM cladding only) / Number / Current month	ACM cladding only / Number / Previous month	ACM cladding only / Number / Current month	Both ACM and non-ACM cladding in either the BSF or CSS / Number / Previous month	Both ACM and non-ACM cladding in either the BSF or CSS / Number / Current month	Not in any remediation fund (non-ACM cladding only) / Number / Previous month	Not in any remediation fund (non-ACM cladding only) / Number / Current month	Total / Number / Previous month	Total / Number / Current month
Barking and Dagenham	1	1	0	0	0	0	5	5	6	6
Barnet	3	3	3	3	1	1	3	3	10	10
Birmingham	4	4	1	1	0	0	11	12	16	17
Bournemouth, Christchurch and Poole	2	2	2	2	0	0	1	1	5	5
Bradford	0	0	1	1	0	0	0	0	1	1
Brent	0	0	2	2	0	0	0	0	2	2
Brighton and Hove	0	0	0	0	0	0	0	0	0	0
Bristol, City of	6	6	1	1	0	0	9	9	16	16
Bromley	0	0	0	0	0	0	0	0	0	0
Calderdale	0	0	0	0	0	0	0	0	0	0
Camden	16	16	1	1	0	0	28	28	45	45
City of London	3	3	0	0	0	0	8	8	11	11
Croydon	3	4	0	0	1	1	1	1	5	6
Dacorum	0	0	0	0	0	0	1	1	1	1
Ealing	2	2	1	1	1	1	0	1	4	5
Gateshead	0	0	0	0	0	0	0	0	0	0
Greenwich	4	4	0	0	0	0	6	7	10	11
Hackney	5	5	2	2	2	2	5	6	14	15
Hammersmith and Fulham	12	12	1	1	2	2	80	80	95	95
Haringey	0	0	0	0	0	0	0	0	0	0
Harrow	0	0	0	0	0	0	0	0	0	0
Hillingdon	3	3	1	1	0	0	10	10	14	14
Hounslow	0	0	0	0	0	0	1	1	1	1
Ipswich	0	0	0	0	0	0	0	0	0	0
Islington	3	3	0	0	0	0	6	7	9	10
Kensington and Chelsea	0	0	0	0	0	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0	0	0	0	0	0
Kirklees	0	0	0	0	0	0	0	0	0	0
Lambeth	2	2	2	2	0	0	0	0	4	4
Leeds	0	0	0	0	0	0	0	0	0	0
Leicester	0	0	0	0	0	0	0	0	0	0
Lewisham	0	0	0	0	0	0	0	0	0	0
Liverpool	4	4	2	2	3	3	2	2	11	11
Maidstone	0	0	0	0	0	0	0	0	0	0
Manchester	0	0	0	0	0	0	0	0	0	0
Medway	0	0	1	1	0	0	0	0	1	1
Merton	0	0	0	0	0	0	0	0	0	0
Milton Keynes	1	1	0	0	0	0	5	5	6	6
Newcastle upon Tyne	6	6	0	0	0	0	10	11	16	17
Newham	18	18	1	1	1	1	19	30	39	50
North Somerset	0	0	0	0	0	0	0	0	0	0
Norwich	0	0	0	0	0	0	0	0	0	0
Nottingham	3	3	1	1	0	0	1	1	5	5
Plymouth	3	3	0	0	0	0	3	3	6	6
Portsmouth	0	0	1	1	0	0	4	4	5	5
Reading	3	3	1	1	0	0	1	1	5	5
Redbridge	3	3	0	0	0	0	3	4	6	7
Salford	1	1	0	0	0	0	0	0	1	1
Sheffield	1	1	0	0	0	0	0	0	1	1
Slough	0	0	0	0	0	0	0	0	0	0
Southampton	3	3	0	0	0	0	0	0	3	3
Southwark	30	30	3	3	3	3	24	25	60	61
Sunderland	1	2	0	0	0	0	0	0	1	2
Sutton	0	0	0	0	1	1	0	0	1	1
Thanet	0	0	0	0	0	0	0	0	0	0
Tower Hamlets	25	26	8	8	5	5	32	32	70	71
Trafford	0	0	0	0	0	0	0	0	0	0
Waltham Forest	1	1	0	0	0	0	1	1	2	2
Wandsworth	1	1	2	2	1	1	0	0	4	4
Westminster	32	32	4	4	6	6	74	76	116	118
Windsor and Maidenhead	0	0	0	0	0	0	0	0	0	0
Others	16	17	0	0	2	2	31	36	49	55
Total	221	225	42	42	29	29	385	411	677	707

## Enforcement_2
Category rating of buildings inspected by local authorities, England, 19 September 2025
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [note 2]	Inspections with the building rated Category 1 [note 20] [note 68] / Number	Inspections with the building rated Category 2 [note 20] [note 68] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	3	3	0	6
Barnet	6	4	0	10
Birmingham	2	14	1	17
Bournemouth, Christchurch and Poole	5	0	0	5
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	13	3	16
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	3	39	3	45
City of London	7	3	1	11
Croydon	2	4	0	6
Dacorum	0	1	0	1
Ealing	2	3	0	5
Gateshead	0	0	0	0
Greenwich	3	4	4	11
Hackney	8	4	3	15
Hammersmith and Fulham	0	91	4	95
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	3	5	6	14
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	2	6	2	10
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	3	7	1	11
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	1	5	6
Newcastle upon Tyne	1	13	3	17
Newham	13	23	14	50
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	0	5	0	5
Plymouth	2	4	0	6
Portsmouth	0	2	3	5
Reading	0	5	0	5
Redbridge	3	3	1	7
Salford	0	1	0	1
Sheffield	0	0	1	1
Slough	0	0	0	0
Southampton	1	0	2	3
Southwark	29	29	3	61
Sunderland	1	1	0	2
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	13	43	15	71
Trafford	0	0	0	0
Waltham Forest	0	2	0	2
Wandsworth	1	3	0	4
Westminster	6	111	1	118
Windsor and Maidenhead	0	0	0	0
Others	13	31	11	55
Total	138	482	87	707

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 19 September 2025
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [note 2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number	Improvement notice appeals / Number
Barking and Dagenham	2	0	0	2	0
Barnet	9	0	0	9	3
Birmingham	14	0	0	14	1
Bournemouth, Christchurch and Poole	3	0	0	3	3
Bradford	1	0	0	1	1
Brent	0	0	0	0	0
Brighton and Hove	0	0	0	0	0
Bristol, City of	0	0	0	0	0
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	15	3	0	18	4
City of London	4	0	0	4	0
Croydon	1	0	0	1	0
Dacorum	1	0	0	1	0
Ealing	2	0	0	2	0
Gateshead	0	0	0	0	0
Greenwich	6	1	0	7	0
Hackney	11	1	0	12	0
Hammersmith and Fulham	0	6	0	6	0
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	5	1	0	6	3
Hounslow	1	0	0	1	0
Ipswich	0	0	0	0	0
Islington	5	1	0	6	2
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	4	0	0	4	0
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	6	0	0	6	1
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	1	0	0	1	1
Merton	0	0	0	0	0
Milton Keynes	1	0	0	1	0
Newcastle upon Tyne	3	4	0	7	0
Newham	36	3	0	39	13
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	3	0	0	3	0
Plymouth	3	3	0	6	1
Portsmouth	1	0	0	1	0
Reading	0	0	0	0	0
Redbridge	4	1	0	5	1
Salford	0	0	0	0	0
Sheffield	0	0	0	0	0
Slough	0	0	0	0	0
Southampton	1	0	0	1	1
Southwark	34	4	0	38	10
Sunderland	1	0	0	1	0
Sutton	1	0	0	1	0
Thanet	0	0	0	0	0
Tower Hamlets	18	22	0	40	2
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	1	1
Wandsworth	1	0	0	1	0
Westminster	1	20	1	22	1
Windsor and Maidenhead	0	0	0	0	0
Others	19	1	0	20	7
Total	219	71	1	291	56

## Enforcement_4
Number of inspections by local authorities supported by the Joint Inspection Team, England, 19 September 2025
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team [note 76].
Local Authority [note_2]	Inspections supported by the Joint Inspection Team [note 21] / Number	Inspections supported by the Joint Inspection Team [note 21] / Number	Buildings inspected with support from the Joint Inspection Team [note 75] / Number	Buildings inspected with support from the Joint Inspection Team [note 75] / Number
	Previous month	Current month	Previous month	Current month
Barking and Dagenham	2	2	2	2
Barnet	3	3	3	3
Birmingham	14	15	13	14
Bournemouth, Christchurch and Poole	2	2	2	2
Bradford	0	0	0	0
Brent	2	2	2	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	6	6	6	6
City of London	1	1	1	1
Croydon	5	6	5	6
Dacorum	0	0	0	0
Ealing	4	5	4	5
Gateshead	0	0	0	0
Greenwich	11	12	10	11
Hackney	11	12	11	12
Hammersmith and Fulham	3	3	2	2
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	1	1	1	1
Hounslow	1	1	1	1
Ipswich	0	0	0	0
Islington	3	3	3	3
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	2	2
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	9	9	9	9
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	0	0	0	0
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	2	2	2
Newham	28	28	28	28
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	3	3	3	3
Plymouth	1	1	1	1
Portsmouth	3	3	3	3
Reading	0	0	0	0
Redbridge	3	4	3	4
Salford	1	1	1	1
Sheffield	1	1	1	1
Slough	0	0	0	0
Southampton	3	3	3	3
Southwark	4	5	4	5
Sunderland	0	1	0	1
Sutton	1	1	1	1
Thanet	0	0	0	0
Tower Hamlets	21	22	21	22
Trafford	0	0	0	0
Waltham Forest	2	2	2	2
Wandsworth	4	4	4	4
Westminster	3	3	3	3
Windsor and Maidenhead	0	0	0	0
Others	8	10	8	10
Total	168	179	165	176

## JIT_1
Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for the number of Joint Inspection Team training sessions attended by local authority officers. [Note 71]
Local Authority [note_22]	Intro to Fire Safety (Level 1) Total attendees 2024 [note 89] / Number	Intermediate Fire Safety (Level 2) Total attendees 2024 [note 89] / Number	Intro to Fire Safety (Level 1) Total attendees 2025 [note 89] / Number	Intermediate Fire Safety (Level 2) Total attendees 2025 [note 89] / Number	Intro to Fire Safety (Level 1) Total attendees [note 90] / Number	Intermediate Fire Safety (Level 2) Total attendees [note 90] / Number
Barking and Dagenham	0	2	0	1	0	3
Barnet	0	3	0	0	4	6
Birmingham	0	3	0	0	10	21
Bournemouth, Christchurch and Poole	0	0	0	1	10	6
Bradford	0	0	0	2	24	7
Brent	0	0	0	0	1	4
Brighton and Hove	0	0	0	0	0	12
Bristol, City of	0	0	0	0	10	8
Bromley	0	0	0	0	3	0
Calderdale	0	0	0	0	3	1
Camden	0	1	0	3	16	20
City of London	0	0	0	0	8	5
Croydon	0	3	0	2	26	10
Dacorum	0	0	0	0	4	3
Ealing	0	6	0	1	10	7
Gateshead	0	0	0	0	6	3
Greenwich	0	1	0	2	2	12
Hackney	0	9	0	3	18	16
Hammersmith and Fulham	0	6	0	0	20	16
Haringey	0	0	0	0	4	2
Harrow	0	2	0	0	1	2
Hillingdon	0	1	0	0	3	2
Hounslow	0	1	0	0	4	4
Ipswich	0	0	0	0	0	0
Islington	0	3	0	1	11	10
Kensington and Chelsea	0	0	0	0	0	1
Kingston upon Thames	0	0	0	0	3	0
Kirklees	0	0	0	1	2	2
Lambeth	0	7	0	1	16	16
Leeds	0	0	0	3	6	5
Leicester	0	0	0	0	0	0
Lewisham	0	0	0	0	5	3
Liverpool	0	0	0	0	32	15
Maidstone	0	0	0	0	0	0
Manchester	0	2	0	0	8	7
Merton	0	5	0	2	6	7
Medway	0	0	0	3	12	8
Milton Keynes	0	0	0	0	6	7
Newcastle upon Tyne	0	0	0	0	6	5
Newham	0	2	0	3	10	10
North Somerset	0	0	0	0	8	5
Norwich	0	0	0	0	11	7
Nottingham	0	27	0	0	34	43
Plymouth	0	0	0	0	3	3
Portsmouth	0	0	0	3	2	17
Richmond and Wandsworth	0	0	0	1	8	11
Reading	0	2	0	0	15	5
Redbridge	0	1	0	0	4	3
Salford	0	0	0	0	11	7
Sheffield	0	1	0	3	0	4
Slough	0	0	0	3	5	10
Southampton	0	0	0	0	1	1
Southwark	0	1	0	0	7	1
Sunderland	0	0	0	0	3	5
Sutton	0	0	0	0	2	0
Thanet	0	1	0	0	2	2
Tower Hamlets	0	8	0	3	9	16
Trafford	0	0	0	0	7	3
Waltham Forest	0	3	0	2	6	9
Westminster	0	5	0	1	17	12
Windsor and Maidenhead	0	1	0	0	8	5
Others	0	31	0	20	414	266
Total	0	138	0	65	887	701

## Estimated_1
Estimates of the number of residential buildings, containing dwellings, that have or had unsafe cladding requiring work, 11 metres and over in height, England, January 2025
Back to Contents
This worksheet contains two tables. Figures are for number of 11m+ buildings, containing dwellings, estimated to have unsafe cladding, and the percentage of the 11m+ residential buildings stock, containing dwellings, that relates to.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height [Note_10, Note_77, Note_79, Note_80, Note_81, Note_82]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	2,900	5,800
18m+	2,900	3,200
Total 11m+	5,900	9,000

Building height	Estimated prevalence of unsafe cladding in residential buildings 11 metres and over (low) / Percentage (%)	Estimated prevalence of unsafe cladding in residential buildings 11 metres and over (high) / Percentage (%)
11-18m	8%	10%
18m+	24%	27%
Total 11m+	12%	13%

## Estimated_2
Estimates of the number of residential buildings, that have or had unsafe cladding requiring work, expected to be remediated or mitigated as part of a government remediation programme, 11 metres and over in height, England, January 2025
Back to Contents
This worksheet contains one table. All figures are for number of 11m+ residential buildings with unsafe cladding estimated to be remediated or mitigated as part of the department's five remediation programmes (ACM programme, BSF, CSS, developer-led remediation, and social housing remediation).
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height [Note_10, Note_77, Note_79, Note_81, Note_82]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	2,800	5,400
18m+	3,000	3,200
Total 11m+	5,700	8,600

## Estimated_3
Estimated proportion of buildings with unsafe cladding expected to be remediated or mitigated in a government remediation programme that are currently monitored in a government remediation programme, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for proportion of 11m+ residential buildings with unsafe cladding estimated to be remediated or mitigated as part of the department's five remediation programmes (ACM programme, BSF, CSS, developer-led remediation, and social housing remediation), that are currently monitored in a government remediation programme.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Building height [Note_77, Note_79, Note_81]	Estimated percentage of buildings 11 metres and over with unsafe cladding that are monitored by MHCLG (low estimate) / Percentage (%)	Estimated percentage of buildings 11 metres and over with unsafe cladding that are monitored by MHCLG (high estimate) / Percentage (%)
11-18m	88%	45%
18m+	106%	98%
Total 11m+	97%	65%

## Estimated_4
Estimates of the number of residential buildings, that have or had unsafe cladding requiring remediation or mitigation work, expected to be remediated or mitigated as part of a government funded scheme, based on January 2025 eligibility criteria, 11 metres and over in height, England, January 2025
Back to Contents
This worksheet contains one table. All figures are for number of 11m+ residential buildings estimated to be remediated in a government funded scheme (ACM programme, BSF, CSS).
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height [Note_77, Note_78, Note_79, Note_81, Note_88]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	800	3,700
18m+	1,500	1,600
Total 11m+	2,300	5,300