TERMS OF REFERENCE / Reconnecting Growth and Jobs: Mapping Constraints, Opportunities, and Reforms for Inclusive Job Creation in Kenya / November 2025

1. BACKGROUND

1.1 About the Evidence Fund
The Foreign, Commonwealth & Development Office (FCDO) wants accessible high-quality research, evaluation and evidence products which target policy, country-specific and regional priorities and are available for use by FCDO and the international development sector. FCDO’s Research and Evidence Directorate (RED) has as its mission to develop and deliver new technologies and innovations that can help solve development challenges, test high potential interventions, and support the delivery of His Majesty’s Government (HMG) objectives. The Evidence Fund is a co-ordinated effort to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant, and manage research and evaluation contracting.
1.2 Details on the Research Context and Evidence Gaps
Kenya has experienced sustained economic growth over the past decade, with GDP expanding by KSh 1.2 trillion in 2024 and projected to grow by 4.8 percent in 2025[1]. However, this growth has not translated into proportional job creation. According to the 2025 Economic Survey by the Kenya National Bureau of Statistics (KNBS), the number of new jobs declined from 848,100 in 2023 to 782,300 in 2024, marking the slowest rate since the COVID-19 pandemic. Most new jobs are informal, and real wages continue to fall.
[1] Kenya and the IMF
This disconnect between economic growth and employment creation presents a critical policy challenge. It undermines poverty reduction, weakens social cohesion, and threatens Kenya’s ability to harness its demographic dividend. While previous studies[2],[3] have explored some of the underlying causes including skills mismatches and structural constraints, evidence remains fragmented and sector specific. There is limited integrated analysis across labour demand, labour supply, informality, and policy implementation. Although World Bank reports provide valuable macro-level insights, they do not offer the granular, context-specific evidence needed to design actionable reform pathways or sector strategies tailored to Kenya’s labour market realities.
[2] Kenya : Capturing Skills Requirements and Assessing Skills Gaps in the Modern Economy
[3] Kenya Labour Market Profile – 2024/2025
High-growth sectors such as ICT and digital services, light manufacturing, tourism, agro-processing, and renewable energy offer opportunities to accelerate formal and productive employment, particularly for youth, women, and rural populations. However, labour market rigidities, weak institutional capacity, and gaps in skills alignment constrain these opportunities. In light of this, a comprehensive and policy-focused labour market assessment is needed to diagnose binding constraints and identify actionable reforms that reconnect economic growth with equitable job creation by exploring how Kenya’s labour market dynamics, skills development systems, and institutional frameworks can be better aligned with high-growth sectors.

2. OBJECTIVES AND SCOPE OF WORK

2.1. Objectives
Why FCDO wants to undertake this study:
This study will generate actionable evidence to inform policy and programming under the Growth pillar of the 2025–2030 Kenya–UK Strategic Partnership and the Kenya Country Business Plan (CBP). It will strengthen the UK’s role as a trusted partner by providing the Government of Kenya (GoK) with insights to guide reforms in labour market regulation, skills development, and private sector job creation. The research also supports FCDO’s priorities on economic growth and science & technology (S&T) by building the evidence base for high-impact interventions in skills, green industrialisation, and business environment reforms.
Intended outcomes at policy, programme, and project level:
- Policy level: Inform labour market and skills policies, regulatory reforms, and institutional strengthening to reduce frictions and improve inclusivity.
- Programme level: Shape FCDO’s economic development portfolio, including future investments in skills development, SME productivity, and sector-specific job creation strategies.
- Project level: Enable targeted interventions in high-growth sectors (ICT/digital, manufacturing, health, tourism, renewable energy) that integrate vulnerable groups such as youth, women, and rural populations.
Specific Objectives:
1. Diagnose labour market dynamics and frictions by producing a comprehensive analysis of structural features, informality, wage/productivity trends, and institutional constraints.
2. Map skills demand and supply alignment through sectoral skills foresight and employer–education interface analysis, focusing on ICT, manufacturing, agro-processing, and digital economy.
3. Assess policy and institutional effectiveness and recommend at least five priority reforms (regulatory, fiscal, skills, incentives) with clear implementation considerations.
4. Identify sector-specific opportunities and barriers and propose actionable strategies for at least three high-growth sectors to boost formal job creation and inclusion.
Primary beneficiaries and use of deliverables:
- Government of Kenya: Evidence-based recommendations for labour market reforms and skills alignment.
- FCDO Kenya: Inputs for CBP programming and policy influencing.
- Development partners and private sector: Sector insights and reform priorities to guide investment and collaboration.
Limitations and sensitivities:
Findings may challenge prevailing narratives or expose politically sensitive issues. To mitigate reputational risks, the Supplier must ensure robust stakeholder engagement, transparent methods, and rigorous quality assurance.
Plans for uptake and dissemination: The Supplier will design and deliver uptake activities, including validation workshops and tailored briefs. A Research Uptake Strategy will be prepared by the supplier at inception, mapping audiences, decisions to influence, and communication channels. At least one validation workshop will be organised to present findings and recommendations.
2.2 Scope
- Geography: Kenya (country-wide), with disaggregation by county where possible.
  Population: Working-age population with emphasis on inclusion (youth and women).
- Sectors: Priority focus on ICT and digital economy, manufacturing, agro-processing, construction, hospitality and tourism, renewable energy, and other sectors where evidence suggests high employment multipliers.
- Data: Secondary data (e.g., national surveys, administrative datasets, and existing national reports) and primary qualitative data; limited primary quantitative data collection may be proposed if justified and feasible within timelines and budget.
- Duration: 6 months, starting December 2025 and concluding by May 2026.
2.3 Research/Evaluation Questions
Overarching Research Question: How can the constraints in Kenya’s labour market (skills mismatches, labour market rigidities, policy implementation) and opportunities in high-growth sectors be systematically addressed to inform the design of inclusive, evidence-based interventions that reconnect economic growth with equitable employment creation?
Sub-Research Questions/Objectives:
Diagnose Labour Market Dynamics, Rigidities and Frictions
- What are the structural features, evolving trends and institutional constraints shaping Kenya’s labour market, including informality, sectoral distribution (formal and informal), gender and youth participation, wage and productivity patterns?
- How do institutional and market frictions such as wage-setting mechanisms, job search inefficiencies and skills mismatches shape employment outcomes and impede inclusive job creation/growth in high-productivity sectors?
Address Skills Mismatches with Labour Supply
- How can Kenya’s education and training systems, including TVET and higher education, be better aligned with labour market needs and to improve access and outcomes for women, youth, and persons with disabilities??
- What are the skills demands for high-growth sectors such as ICT, manufacturing, and the digital economy and how are they aligned with TVET/higher education pathways?
- Where do employer–training linkages work well, and where do they fail?
Improve Policy Implementation and Effectiveness
- Which policy and institutional reforms (regulatory, fiscal, skills, incentive) have the highest potential to increase formal, productive employment and inclusion?
- What are their fiscal, political economy, and implementation considerations?
Tackle Sector-Specific Gaps
- What are the opportunities and barriers in Kenya’s high-growth sectors such as ICT and fintech, health, agro-processing, manufacturing, tourism, and renewable energy?
- What targeted, sector-specific interventions (public or crowding-in private) could unlock formal job creation, especially for youth, women, and rural populations?
All research questions should, to the extent possible, apply a gender equality and social inclusion lens.
2.4 Research/Evaluation Methodology
This is a formative, policy‑oriented mixed methods research that will generate decision‑ready evidence to guide programmes and reforms. It will include a process evaluation of current policy and institutional arrangements and a light‑touch impact inference using quasi‑experimental and counterfactual techniques with secondary data where appropriate. The Supplier should apply an inclusion lens in data choices, analyses, and results interpretation.
Analytical Framework Linked to Objectives
Objective	Data Sources	Methods	Outputs
O1/Q1: / Diagnose structural features, dynamics, and frictions	KNBS Labour Force Surveys, Economic Surveys, enterprise/establishment data, administrative datasets	Descriptive and inferential statistics on participation, employment, wages, and productivity with disaggregation by sex, age, and region where feasible. / Measures of informality and transitions between labour statuses using panel data methods or synthetic panels if feasible. / Decomposition of employment and wage changes quantitatively using shift‑share, growth‑employment elasticities, where applicable. / Simple job transition matrices to characterise frictions in job search and matching.	Quantified labour market profile with indicators and visuals
O2/Q2: Skills Demand & Supply Alignment / (Map skills demand and alignment with higher learning institutions/ TVET pathways)	Employer KIIs, firm FGDs, job postings data (if available), TVET and higher learning institutions curricula and tracer data	Sectoral skills foresight based on employer interviews and expert elicitation. / Curriculum and competency mapping between priority occupations and TVET/HLI programmes using a standard skills taxonomy. / Rapid tracer approaches where feasible to test alignment and graduate outcomes.	Skills gap matrix; employer–education interface analysis; actionable alignment recommendations
O3/Q3: / Assess regulatory and institutional performance and prioritise reforms	Labour laws/regulations, policy documents, budget data, KIIs with ministries and agencies and private sector leaders.	Regulatory stocktake focused on labour market rules that influence hiring, wages, mobility, and formality. / Implementation analysis to identify delivery bottlenecks across national and county levels. / Political economy analysis to understand interests, coalitions, and feasibility. / Contribution Analysis to assess how plausible reform pathways could contribute to outcomes in employment and inclusion.	Prioritised list of at least five feasible reforms with implementation steps
O4/Q4: Sector Deep-Dives / (Identify opportunities and barriers in high-growth sectors)	Sector reports, value chain data, enterprise surveys, investor and private sector dialogues	Sector value chain mapping with attention to firm size distribution and constraints to scaling. / Light enterprise soundings and investor dialogues to validate constraints and opportunities. / Estimation of potential job creation under alternative scenarios using sector employment multipliers or growth‑employment elasticities from national accounts and survey data.	Sector-specific strategies for at least three sectors with actionable interventions

2.5 Theory of Change
If high-quality, integrated evidence on labour market constraints and sectoral opportunities is produced, and co-created with policy counterparts and stakeholders (Inputs/Activities), then FCDO and GoK can collaboratively prioritize feasible reforms and programmes (Outputs), which increases alignment of skills systems, reduces frictions, and improves the business environment (Outcomes), leading to higher rates of formal, productive, and inclusive employment (Impact).
2.6 Required Skills
- Labor Economist (Team Lead): 10+ years in labor market diagnostics in LMICs; strong quantitative skills and policy advisory experience.
- Quantitative Analyst/Econometrician: Expertise in microdata analysis, survey methods, and modelling; proficiency in R/Python/Stata; reproducible research.
- Qualitative Researcher: Experience in KIIs/FGDs, labor institutions, and political economy analysis in Kenya/East Africa.
- Policy & Institutional Reform Expert: Track record in regulatory analysis, skills systems, and employment policy design.
- Experience working on Kenyan policy issues: Deep understanding of context, stakeholders, and subnational dynamics.

3. PROJECT MANAGEMENT ARRANGEMENTS

The Supplier will design, implement and manage the study, including data collection and analysis, stakeholder engagement, and reporting. FCDO will provide strategic oversight. The Fund Manager (PwC/Integrity) will manage the commercial contract and support quality assurance as required. The Supplier will propose a detailed workplan, risk register, stakeholder map, and communications & uptake plan at inception. Regular (bi-monthly) progress check-ins with FCDO counterparts are expected. The Supplier will maintain a single point of contact and a day-to-day project manager.

4. ADMINISTRATIVE ARRANGEMENT

The study would be supported through The Evidence Fund, an FCDO programme intended to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2023, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions f or research and evaluation projects and conduct due diligence assessments on prospective sub – contracted Research Pool providers, where relevant.
The Foreign, Commonwealth & Development Of f ice (FCDO) is the sole contracting authority for all projects funded through the Evidence Fund. The FCDO holds full responsibility for issuing contracts and managing all contract and project management activities throughout the lifecycle of each project. The Fund Manager’s role is limited to pre-contracting activities and does not extend to contract execution or post-award management

5. TIMEFRAME, EXPECTED DELIVERABLES, AND OVERALL BUDGET

The study should be completed in a maximum period of 6 months, starting January 2026.
The budget for the study should not exceed £100,000, excluding UK VAT and inclusive of all other relevant added Government taxes.
The deliverables and timelines/milestones expected of the Supplier are as follows:
Milestone	Description	Milestone Payments (% of Overall Budget)	Delivery By
1. Kick-Off /Inception Meeting	Inception meeting to agree on implementation and requirements of the inception report
2. Delivery of the Inception Report	Delivery of the report includes refined methodology and theory of change, workplan, stakeholder map, risk register, and data mapping and access plan. Annexes (e.g. ethics/data management) can be separate. / (15–20 pages)	15%	End of Month 1 (Jan 2026)
2.Stakeholder Engagement & Uptake Plan	Detailed communications and research uptake strategy, including audience mapping and engagement calendar. / (8–10 pages)	10%	Mid Month 2 (Feb 2026)
Draft Diagnostic Report	Full draft report covering labour market analysis, skills mapping, policy/institutional review, and sector deep-dives; includes preliminary recommendations. Technical annexes (e.g. data tables, code summaries) can be separate. / (40–50 pages)	25%	End of Month 4 (April 2026)
3.Validation Workshop(s)	Findings validation sessions with GoK, FCDO, private sector, and partners; workshop summary and revision log. / 5-7 pages: Workshop proceedings, feedback log, and summary of revisions.	20%	Month 5 (May 2026)
4.Final Report & Knowledge Products	Final diagnostic report including executive summary (40–60 pages); 2 policy briefs (briefs (4–6 pages each); slide deck (~15 slides); infographic pack; cleaned datasets and documented code where feasible, Quality assured by independent QA.	25%	End of Month 6 (June 2026)
5.Close-out & Handover	Close-out report; handover meeting; response-to-comments matrix.	5%	End of Month 6 (June 2026)

6. QUALITY ASSURANCE MECHANISMS

Peer review/Quality Assurance Required
Peer review/ quality assurance completed in-house by FCDO	✓
Peer review/ quality assurance arranged by the research provider as part of their contract	✓
Independent peer review independently carried out, through a contract with the Fund Manager
Further EqUALS review for all evaluation products

7. COMPETENCIES

It is expected that the core team delivering this work will have the requisite technical and contextual experience in the collation, interpretation, synthesis, and communication of the research findings and recommendations.

8. SUBMISSIONS

The Supplier is required to submit all outputs in accordance with the expectations and page limits set out in sections 4 above.

9. MANAGEMENT ARRANGEMENTS

The Supplier will design and manage this research study, including drawing together the findings for reporting.
This project will be administered by a FDCO EARIH lead adviser.
The Supplier will quality-assure all outputs before submission to the EARIH lead adviser. The Supplier will be required to comply with FCDO reporting requirements. The Supplier will be responsible for alerting the EARIH lead adviser as early as possible of any emerging issues and risks, to ensure that the project is staying on track.
All deliverables will need to be reviewed and approved by the FCDO technical steering group; however, the Supplier is encouraged to embed their own internal mechanisms for quality assurance.
The Supplier will be required to review and outline how they plan to manage any potential conflicts of interest identified during proposal development.
The Supplier will be required to attend several meetings during all phases of the work, comprising largely of virtual meetings.

10. BIDDING PROCESS

Technical and financial proposals should be sent as two separate files to ke_evidencefundeastafrica@pwc.com by 16 January 2026 (23:59 EAT). Since these will be assessed independently of each other, they should, in no case, be combined or cross-referenced.
The instructions for submitting the tender and details on scoring methodology and evaluation criteria are detailed in ITT Volume 1. The application forms f or submitting the technical proposal (sent as a clearly titled PDF file) are detailed in ITT Volume 3 and ITT Volume 4 provides the Pro Formas f or the commercial proposal.

11. DUTY OF CARE ARRANGEMENTS

Technical and financial proposals should be sent as two separate files to ke_evidencefundeastafrica@pwc.com by 16 January 2026 (23:59 EAT). Since these will be assessed independently of each other, they should, in no case, be combined or cross-referenced.
The instructions for submitting the tender and details on scoring methodology and evaluation criteria are detailed in ITT Volume 1. The application forms f or submitting the technical proposal (sent as a clearly titled PDF file) are detailed in ITT Volume 3 and ITT Volume 4 provides the Pro Formas f or the commercial proposal.

12. DUTY OF CARE ARRANGEMENTS

The Supplier should set out duty of care arrangements for any country visits or field-based activities.

13. ETHICAL CONSIDERATIONS, DATA PROTECTION, AND SAFEGUARDING

The Supplier will adhere to recognised research ethics, including informed consent, confidentiality, and the right to withdraw. Inclusion principles should guide sampling and analysis (gender, youth, disability). Personal data (if any) must be minimised and processed in compliance with applicable data protection laws and FCDO requirements. A Data Management Plan will be submitted at inception, covering storage, access control, anonymisation, and sharing protocols.

14. GENERAL DATA PROTECTION REGULATIONS (GDPR)

Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Section 15: Interpretation, the clause on Data Protection Laws in Volume 6: Pro Forma Contract of the ITT Application Pack.4

15. RISK MANAGEMENT

The Supplier should identify and actively manage risks that could affect delivery, quality, or uptake of the study. The Supplier must remain alert to these risks and propose additional mitigation measures in the inception report. A risk register should be maintained and updated throughout the assignment. Key anticipated risks include:
Risk	Description	Some mitigation measures
Reputational Risk	Findings may be politically sensitive or challenge prevailing narratives, potentially creating tension with stakeholders or attracting public scrutiny.	Ensure robust stakeholder engagement throughout the research process; apply transparent and rigorous methods; communicate limitations clearly; embed independent quality assurance and peer review.
Timely Data Access	Delays in accessing official datasets (e.g., KNBS labour force microdata, administrative records) could affect timelines and analytical depth.	Engage data custodians early; secure data-sharing agreements during inception; maintain a contingency plan for alternative data sources; document data lineage and assumptions transparently.
Uptake Risk	Findings may not be used if they are not aligned with policy windows or stakeholder priorities.	Develop and implement a Research Uptake Strategy; organise validation and co-creation workshops; tailor outputs to decision-makers; align recommendations with CBP, UK-GoK Strategic Partnership, and GoK reform agendas.
Operational Constraints	Fieldwork disruptions due to logistical, security, or political factors.	Use flexible modalities (remote KIIs, virtual workshops); apply robust duty-of-care protocols; build contingency time into the workplan.

16. FCDO RESEARCH GUIDANCE DOCUMENTS

Annex 1: Guidance on Communication and Research Uptake Strategy
Stakeholder Mapping and Research Uptake Strategy
	Key communications and research uptake considerations
Audience mapping	Which organisations are the main intended audiences for the research? Who are the key decision-makers in the policy area and are they involved and aware of the research (and how are they involved in the research design and intent)? Are there other actors who may use findings or are involved in this policy area? / Within FCDO – which teams and departments are involved?
Knowledge requirements of stakeholders	What are the evidence gaps that actors are interested in? Are there key statistics or data that can define the research? What new evidence does the research offer to both strategic planning and informing programming?
Decisions to be influenced	What are the key programming decisions that the research will influence – both for FCDO policy teams and country offices? Will the research support decision-making among other actors? E.g., multilateral, and bilateral donors, non-government organisations, regional governments? What decisions are those?
What are the outputs?	Largely defined by the ToR, but what outputs will be produced? I.e., will there be supporting infographics, summary briefs, or single case studies in order to land the research more effectively/efficiently with particular audiences? How do these map to particular stakeholders?
How will outputs be communicated?	How will various audiences be kept abreast or informed about the research? Will different audiences require different communications? What will be the balance of different dissemination techniques: i.e., seminars, emails, social media, meetings, slide decks, use of the internet or published documentation?
Relevance of research products	The communications plan (and research products) should be iterative and reflect research needs from all stakeholders. Considering responses to the points outlined above, how will the research be designed, produced, and disseminated to meet these needs?
How will research impact be measured?	What methods and indicators can be used to measure or assess how useful the research is? I.e., to what extent has it been used and by which audiences, what are the outcomes of the research, and what impact has it had on policy making and programming?