## Front_Sheet
Construction Framework 2025 Handbook - Appendix A - Process Timelines
Process timelines for the framework procurement routes to support Framework Users and Contractors

## Document_Control
Construction Framework 2025 Handbook - Appendix A - Process Timelines
Document Summary
Version History
Date | Editor | Version | Status | Reason for change
2025-03-27 | DJK | P01 | Final | Final for PSQ
2025-06-19 | DJK | P02 | Final | Final for ITT
2025-08-06 | DJK | P03 | Final | Updates following clarifications
2025-12-01 | DJK | P04 | Final | Framework Live Issue. SCDP stage references added. Minor drafting amendments.
2025-12-29 | NP | P05 | Final | Updated for accessibility requirements

## Engagement_Based_Route EBSR
Design and Build Competition Timeline
Engagement Based Selection Route (EBSR)
High Value Band D&B Competition (BATCHES AND SINGLE PROJECTS) | SCDP Stage | Stage 1: Pre-Feasibility | Stage 2: Feasibility | Stage 3: Choose Contractor | [21 empty] | Stage 4: Design, Planning & Contract Development | [30 empty] | Stage 5: Construction | Stage 6: Post Practical Completion & Use
| Approx. RIBA Stage | RIBA Stage 0 (Strategic Definition) | RIBA 1 Preparation and Briefing (Feasibility Study) | RIBA Stage 2 (Concept Design) |  |  |  |  | RIBA Stage 2 (Concept Design) | [16 empty] | RIBA Stage 3 (Spatial Coordination) | [9 empty] | RIBA Stage 4 (Technical Design) | [20 empty] | RIBA Stage 5 (Manufacturing and Construction) | RIBA Stage 6 (Handover and Post-Handover) | RIBA Stage 7 (In Use)
| Framework Stage |  | Feasibility Study (c31 Weeks) | Expression of Interest (EoI) (4 Weeks minimum) |  |  |  | PITT to Contract Close: 44 to 47 Weeks Framework Users to draft realistic programmes based on project-specifics | Mini-Competition (c16 Weeks) | [16 empty] | Design Development (3 weeks) |  |  | Planning Submission Development (4 Weeks) |  |  |  | Planning Application Submission (3 Weeks) |  |  | Planning Determination (15 to 18 Weeks) | [17 empty] | Contract Finalisation (3 Weeks) |  |  | Construction | Handover and Rectification Period | In Use
[9 empty] | Preliminary Invitation to Tender (PITT) (3 Weeks) |  |  |  | Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS | [7 empty] | Evaluation and Appointment (5 Weeks) | [14 empty] | Contractor's Proposals (8 to 10 Weeks) | [9 empty] | Contractor's Proposals Review (7 to 8 Weeks)
| Week |  | Week -35 to -5 | Week -4 | Week -3 | Week -2 | Week -1 |  | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47
| Stage Summary | Framework User agrees Business Case and Strategic Brief | Framework User prepares the Scheme to end of RIBA Stage 1 – including a Feasibility Study and costed control option Indicative information will be published on the Pipeline for a minimum period of 4 weeks prior to EoI. DfE Touchpoint A - Options Appraisal DfE Touchpoint B - Feasibility Study | Framework User gives minimum of four weeks notice to DfE Framework Team who provide at least four weeks notice to Panel Members Framework User issues Feasibility Study / Employer's Requirements / design information via DfE Framework Team A Bidders Day will be held within the first two weeks of the EoI / Pipeline period. All Panel Members within the Lot will be invited Panel Members return Expression of Interest feedback to DfE Framework Team |  |  |  |  | Preliminary Invitation to Tender (PITT) (3 Weeks) Week 0: Issue of PITT; Preliminary Invitation to Tender (PITT) (3 Weeks) Week 1: PITT Response submitted; Preliminary Invitation to Tender (PITT) (3 Weeks) Week 2: PITT evaluation and shortlisting; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 4: CEM 0; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 5: CEM 1; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 6: CEDD Period; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 7: CEM 2; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 8: CEM 3; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 9: CEDD Period; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 11: Submission; Evaluation and Appointment (5 Weeks) Week 12: Evaluation and Appointment of Selected Panel Member (SPM) under a Pre Construction Services Agreement (PCSA) DfE Touchpoint C - ITT (CA); Evaluation and Appointment (5 Weeks) Week 15: Engrossment of PCSA; Evaluation and Appointment (5 Weeks) Week 17: CEM 4; Evaluation and Appointment (5 Weeks) Week 18: CEM 5; Evaluation and Appointment (5 Weeks) Week 19: CEM 6; Evaluation and Appointment (5 Weeks) Week 20: Planning submission development period; review of draft submission documents (including cost plan) via a pre-agreed plan of document reviews (to be set out by the Selected Panel Member as part of their ITT submission); leading to final submission of the planning pack in week 23 for approval (subject to any changes made by the Project Team). It is expected the Planning Public Consultation/Information Event will take place during this period; Evaluation and Appointment (5 Weeks) Week 23: Stage 3 submission including draft Planning Pack; Evaluation and Appointment (5 Weeks) Week 24: Review and confirm acceptance of submission of planning application; Contractor's Proposals (8 to 10 Weeks) Week 27: Time allocation subject to expected planning determination period As per Exchange Information Requirements SPM sessions to continue to evolve decisions / design (including resolving RDD matters); Contractor's Proposals Review (7 to 8 Weeks) Week 37: CPs Submitted; Contractor's Proposals Review (7 to 8 Weeks) Week 38: Time allocation subject to expected planning determination period Clarifications process run in parallel leading to approval of Contract Contractor's Proposals (CPs) Gaps calls to run in parallel leading to drafting of Contract Schedules Update CPs to reflect planning decisions Conclusion of Contract Schedules DfE Touchpoint E - Procurement (RIBA4); Contractor's Proposals Review (7 to 8 Weeks) Week 45: Finalisation, agreement and signature of contract following planning permission
[9 empty] | At conclusion of the EoI period, and on the date advised by the DfE Framework Team, the Framework User invites Panel Members to compete for the Scheme by issuing a Preliminary Invitation to Tender (PITT) The PITT states the maximum number of Panel Members be invited to the next stage – either one or two If part of a Batch, the PITT for the Sample Scheme will include named Future Schools |  |  |  | Design Competition / Client Engagement Meetings (CEMs): A project initiation (CEM 0) meeting will be held at the commencement of the ITT period. The purpose of this session is for the Panel Member to review and confirm the Project Brief with the Project Team. Note: There must be at least 5 working days between the announcement of the shortlisted bidders and CEM 0 Thereafter, CEMs will be held leading to an ITT submission of concept design strategies and responses to quality questions (expected to be 3 number CEMs). Additional CEMs can be included at the discretion of the Project Team Periods for client engagement Stage 2 design development (CEDD Period) have been allowed after CEM 1 and CEM 3. These periods can be moved at the discretion of the Project Team prior to ITT commencing, noting that a minimum of 10 working days must be allowed between CEM3 / the final CEM and submission of the ITT reponse DfE Touchpoint C - ITT (DA) | [12 empty] | Client Engagement Meetings (CEMs) leading to production of the RIBA Stage 3 Deliverables (circa 3 number further CEMs) leading to approval to proceed to planning | [5 empty] | - Stage 3 Information Exchange as set out in DEIR IE301 - The contents of the planning application - Cost Plan - Programme and Phasing Plans - Risk Register | Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission DfE Touchpoint D - Procurement (RIBA 3 Pre-Planning)
| Key Documents |  | Feasibility Study (and associated appendices) | Scheme Notification Form |  |  |  |  | Preliminary Invitation to Tender (PITT) (3 Weeks) Week 0: Information to be provided at PITT by Framework User - PITT Letter - Evaluation Criteria - Draft Invitation to Tender (ITT) - Feasibility Study - Employer's Requirements Information to be submitted by Bidders - Responses to Questions set - Framework Pricing Schedule - Completed and signed Forms and Certificates; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 5: Information to be provided at ITT by Framework User - ITT Letter and ITT document - Evaluation Criteria - Employer's Requirements - PCSA (+ draft Contract) - Future Schools Notice and Agreement (if applicable) Information to be submitted by Bidders - Responses to Questions set - Design and Construction Information Deliverables - Framework Pricing Schedule - Completed and signed Forms and Certificates - Completed PCSA Gaps List; Evaluation and Appointment (5 Weeks) Week 12: Information to be issued by Framework User - Successful Bidder Letter - Unsuccessful Bidder Letter - PCSA for execution Information to be provided by SPM - PCSA (signed); Evaluation and Appointment (5 Weeks) Week 17: Information to be provided by Framework User - n/a Information to be provided by SPM - Design Development information as required to support CEM process; Evaluation and Appointment (5 Weeks) Week 20: Information to be provided by Framework User - n/a Information to be provided by SPM - Planning Submission (IE301); Evaluation and Appointment (5 Weeks) Week 24: Information to be provided by Framework User - Clarifications - Approval to submit Planning Information to be provided by SPM - Clarification responses - Final Planning Submission - Remaining Stage 3 Deliverables (IE311); Contractor's Proposals (8 to 10 Weeks) Week 27: Information to be provided by Framework User - Stage 3 submission clarifications - Stage 3 Approval (by week 30) Information to be provided by SPM - Contractor's Proposals; Contractor's Proposals Review (7 to 8 Weeks) Week 37: Info to be provided by SPM - Contractor's Proposals (final); Contractor's Proposals Review (7 to 8 Weeks) Week 38: Information to be provided by Framework User - Employer's Requirements - Gaps List - Draft Contract - Contract Schedules - Clarifications Information to be provided by SPM - Contractor's Proposals (final) - Contract Schedules - Clarification responses
| IM Information Exchange Code | IE001 | IE101 / IE102 / IE201 | IE202 |  |  |  |  | Preliminary Invitation to Tender (PITT) (3 Weeks) Week 0: IE211 / IE212 / IE213; Invitation to Tender (ITT) (8 Weeks) max 2 BIDDERS Week 5: IE214; Evaluation and Appointment (5 Weeks) Week 12: IE241; Evaluation and Appointment (5 Weeks) Week 20: IE301; Evaluation and Appointment (5 Weeks) Week 24: IE311; Contractor's Proposals Review (7 to 8 Weeks) Week 37: IE401 | IE501 / IE511 / IE521 | IE601 / IE611

## Selection_Based_Route SBSR
Design and Build Competition Timeline
Submission Based Selection Route (SBSR)
High and Low Value Band Two Stage D&B | SCDP Stage | Stage 1: Pre-Feasibility | Stage 2: Feasibility | Stage 3: Choose Contractor | [13 empty] | Stage 4: Design, Planning & Contract Development | [37 empty] | Stage 5: Construction | Stage 6: Post Practical Completion & Use
| Approx. RIBA Stage | RIBA Stage 0 (Strategic Definition) | RIBA 1 Preparation and Briefing (Feasibility Study) | RIBA Stage 2 (Concept Design) |  |  |  |  | RIBA Stage 2 (Concept Design) | [14 empty] | RIBA Stage 3 (Spatial Coordination) | [10 empty] | RIBA Stage 4 (Technical Design) | [20 empty] | RIBA Stage 5 (Manufacturing and Construction) | RIBA Stage 6 (Handover and Post-Handover) | RIBA Stage 7 (In Use)
| Framework Stage |  | Feasibility Study (c31 Weeks) | Expression of Interest (EoI) (4 Weeks minimum) |  |  |  | EOI to Contract Close: 43 to 47 Weeks Framework Users to draft realistic programmes based on project-specifics | Mini-Competition (8 Weeks) | [8 empty] | Design Development (c9 Weeks) | [8 empty] | Planning Submission Development (5 Weeks) |  |  |  |  | Planning Application Submission (3 Weeks) |  |  | Planning Determination (15 to 18 Weeks) | [17 empty] | Contract Finalisation (3 Weeks) |  |  | Construction | Handover and Rectification Period | In Use
[9 empty] | Invitation to Tender (ITT) (3 Weeks) |  |  |  | Evaluation and Appointment (5 Weeks) | [21 empty] | Contractor's Proposals (8 to 10 Weeks) | [9 empty] | Contractor's Proposals Review (7 to 8 Weeks)
| Week |  | Week -35 to -5 | Week -4 | Week -3 | Week -2 | Week -1 |  | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46
| Stage Summary | Framework User agrees Business Case and Strategic Brief | Framework User prepares the Scheme to end of RIBA Stage 1 – including a Feasibility Study and costed control option Indicative information will be published on the Pipeline for a minimum period of 4 weeks prior to EoI. Alternate option: Framework User has the option to develop the Scheme to end of RIBA Stage 2 or 3 DfE Touchpoint A - Options Appraisal DfE Touchpoint B - Feasibility Study | Framework User gives minimum of four weeks notice to DfE Framework Team who provide at least four weeks notice to Panel Members Framework User issues Feasibility Study / Employer's Requirements / design information via DfE Framework Team A Bidders Day will be held within the first two weeks of the EoI period. All Panel Members within the Lot will be invited Panel Members return Expression of Interest feedback to DfE Framework Team |  |  |  |  | Invitation to Tender (ITT) (3 Weeks) Week 0: At conclusion of the EoI period, and on the date advised by the DfE Framework Team, the Framework User invites Panel Members to compete for the Scheme by issuing an Invitation to Tender (ITT) - week 0 represents issue of ITT Alternate option: This period may need to be extended to reflect the quantity of design information Panel Members must review; Evaluation and Appointment (5 Weeks) Week 4: Evaluation and Appointment of Selected Panel Member (SPM) under a Pre Construction Services Agreement (PCSA) DfE Touchpoint C - ITT (CA); Evaluation and Appointment (5 Weeks) Week 7: Engrossment of PCSA; Evaluation and Appointment (5 Weeks) Week 9: CEM 0; Evaluation and Appointment (5 Weeks) Week 10: CEM 1; Evaluation and Appointment (5 Weeks) Week 11: CEDD Period; Evaluation and Appointment (5 Weeks) Week 12: CEM 2; Evaluation and Appointment (5 Weeks) Week 13: CEM 3; Evaluation and Appointment (5 Weeks) Week 14: CEDD Period; Evaluation and Appointment (5 Weeks) Week 15: CEM 4; Evaluation and Appointment (5 Weeks) Week 16: CEM 5; Evaluation and Appointment (5 Weeks) Week 17: CEM 6; Evaluation and Appointment (5 Weeks) Week 18: Planning submission development period; review of draft submission documents (including cost plan) via a pre-agreed plan of document reviews (to be set out by the Selected Panel Member as part of their ITT submission); leading to final submission of the planning pack in week 22 for approval (subject to any changes made by the Project Team) It is expected the Planning Public Consultation/Information Event will take place during this period; Evaluation and Appointment (5 Weeks) Week 22: Stage 3 submission including draft Planning Pack; Evaluation and Appointment (5 Weeks) Week 23: Review and confirm acceptance of submission of planning application; Contractor's Proposals (8 to 10 Weeks) Week 26: Time allocation subject to expected planning determination period As per Exchange Information Requirements SPM sessions to continue to evolve decision (including resolving RDD matters); Contractor's Proposals Review (7 to 8 Weeks) Week 36: CPs Submitted; Contractor's Proposals Review (7 to 8 Weeks) Week 37: Time allocation subject to expected planning determination period Clarifications process run in parallel leading to approval of Contract Contractor's Proposals (CPs) Gaps calls to run in parallel leading to drafting of Contract Schedules Update CPs to reflect planning decisions Conclusion of Contract Schedules DfE Touchpoint E - Procurement (RIBA4); Contractor's Proposals Review (7 to 8 Weeks) Week 44: Finalisation, agreement and signature of contract following planning permission
[18 empty] | A project initiation (CEM 0) meeting will be held at the commencement of the Design Development period. The purpose of this session is for the Selected Panel Member to review and confirm the Project Brief with the Project Team. Note: There must be at least 5 working days between the announcement of the shortlisted bidders and CEM 0 Thereafter, Client Engagement Meetings (CEMs) leading to production of the RIBA Stage 2 / Stage 3 Deliverables (circa 6 number further CEMs) leading to approval to proceed to planning. Additional CEMs can be included at the discretion of the Project Team Periods for client engagement Stage 2 design development (CEDD Period) have been allowed after CEM 1 and CEM 3. These periods can be moved at the discretion of the Project Team prior to ITT commencing, noting that a minimum of 10 working days must be allowed between CEM3 / the final CEM and submission of the ITT reponse DfE Touchpoint C - ITT (DA) | [12 empty] | - Stage 3 Information Exchange as set out in DEIR IE301 - The contents of the planning application - Cost Plan - Programme and Phasing Plans - Risk Register | Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission DfE Touchpoint D - Procurement (RIBA 3 Pre-Planning)
| Key Documents |  | Feasibility Study (and associated appendices) | Scheme Notification Form |  |  |  |  | Invitation to Tender (ITT) (3 Weeks) Week 0: Information to be provided at ITT by Framework User - ITT Letter and ITT document - Evaluation Criteria - Feasibility Study - Employer's Requirements - PCSA (+ draft Contract) Information to be submitted by Bidders - Responses to Questions set - Framework Pricing Schedule - Completed and signed Forms and Certificates - Completed PCSA Gaps List; Evaluation and Appointment (5 Weeks) Week 4: Information to be provided by Framework User - Successful Bidder Letter - Unsuccessful Bidder Letter - PCSA for execution Information to be provided by SPM - PCSA (signed); Evaluation and Appointment (5 Weeks) Week 15: Information to be provided - n/a Information to be provided by SPM - Design Development information as required to support CEM process - Planning Submission (IE301); Evaluation and Appointment (5 Weeks) Week 23: Information to be provided by Framework User - Clarifications - Approval to submit Planning Information to be provided by SPM - Clarification responses - Final Planning Submission - Remaining Stage 3 Deliverables (IE311); Contractor's Proposals (8 to 10 Weeks) Week 26: Information to be provided by Framework User - Stage 3 submission clarifications - Stage 3 Approval (by week 29) Information to be provided by SPM - Contractor's Proposals; Contractor's Proposals Review (7 to 8 Weeks) Week 36: Info to be provided by SPM - Contractor's Proposals (final); Contractor's Proposals Review (7 to 8 Weeks) Week 37: Information to be provided by Framework User - Employer's Requirements - Gaps List - Draft Contract - Contract Schedules - Clarifications Information to be provided by SPM - Contractor's Proposals (final) - Contract Schedules - Clarification responses
| IM Information Exchange Code | IE001 | IE101 / IE102 / IE201 | IE202 |  |  |  |  | Invitation to Tender (ITT) (3 Weeks) Week 0: IE221 / IE222; Evaluation and Appointment (5 Weeks) Week 4: IE241; Evaluation and Appointment (5 Weeks) Week 15: IE301; Evaluation and Appointment (5 Weeks) Week 23: IE311; Contractor's Proposals Review (7 to 8 Weeks) Week 36: IE401 | IE501 / IE511 / IE521 | IE601 / IE611

## DA_&_Future-ISP_No_ESI
Design and Build Competition Timeline
Direct Allocation and Future Schemes - No Early Supplier Involvement
DIRECT ALLOCATION AND FUTURE SCHOOLS PROCESS - NO EARLY SUPPLIER INVOLVEMENT (ALL BANDS) | SCDP Stage | Stage 1: Pre-Feasibility | Stage 2: Feasibility | Stage 3: Choose Contractor | [13 empty] | Stage 4: Design, Planning & Contract Development | [37 empty] | Stage 5: Construction | Stage 6: Post Practical Completion & Use
| Approx. RIBA Stage | RIBA Stage 0 (Strategic Definition) | RIBA 1 Preparation and Briefing (Feasibility Study) | RIBA Stage 2 (Concept Design) |  |  |  |  | RIBA Stage 2 (Concept Design) | [14 empty] | RIBA Stage 3 (Spatial Coordination) | [10 empty] | RIBA Stage 4 (Technical Design) | [20 empty] | RIBA Stage 5 (Manufacturing and Construction) | RIBA Stage 6 (Handover and Post-Handover) | RIBA Stage 7 (In Use)
| Framework Stage |  | Feasibility Study (c31 Weeks) | Expression of Interest (EoI) / Pipeline (4 Weeks minimum) |  |  |  | EOI to Contract Close: 43 to 47 Weeks Framework Users to draft realistic programmes based on project-specifics | Future School ISP (8 Weeks) | [8 empty] | Design Development (c9 Weeks) | [8 empty] | Planning Submission Development (5 Weeks) |  |  |  |  | Planning Application Submission (3 Weeks) |  |  | Planning Determination (15 to 18 Weeks) | [17 empty] | Contract Finalisation (3 Weeks) |  |  | Construction | Handover and Rectification Period | In Use
[9 empty] | Invitation to Submit Proposal (ISP) (3 Weeks) |  |  |  | Evaluation and Appointment (5 Weeks) | [21 empty] | Contractor's Proposals (8 to 10 Weeks) | [9 empty] | Contractor's Proposals Review (7 to 8 Weeks)
| Week |  | Week -35 to -5 | Week -4 | Week -3 | Week -2 | Week -1 |  | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46
| Stage Summary | Framework User agrees Business Case and Strategic Brief | Framework User prepares the Scheme to end of RIBA Stage 1 – including a Feasibility Study and costed control option Indicative information will be published on the Pipeline for a minimum period of 4 weeks prior to EoI. Alternate option: Framework User has the option to develop the Scheme to end of RIBA Stage 2 or 3 DfE Touchpoint A - Options Appraisal DfE Touchpoint B - Feasibility Study | Framework User gives minimum of four weeks notice to DfE Framework Team who provide at least four weeks notice to Panel Members Framework User issues Feasibility Study / Employer's Requirements / design information via DfE Framework Team A Bidders Day will be held within the first two weeks of the EoI period. All Panel Members within the Lot will be invited Panel Members return Expression of Interest feedback to DfE Framework Team |  |  |  |  | Invitation to Submit Proposal (ISP) (3 Weeks) Week 0: At conclusion of the EoI period, and on the date advised by the DfE Framework Team, the Framework User invites Panel Members to compete for the Scheme by issuing an Invitation to Submit Proposal (ISP) - week 0 represents issue of ISP Alternate option: This period may need to be extended to reflect the quantity of design information Panel Members must review; Evaluation and Appointment (5 Weeks) Week 4: Evaluation and Appointment of Selected Panel Member (SPM) under a Pre Construction Services Agreement (PCSA) DfE Touchpoint C - ITT (CA); Evaluation and Appointment (5 Weeks) Week 7: Engrossment of PCSA; Evaluation and Appointment (5 Weeks) Week 9: CEM 0; Evaluation and Appointment (5 Weeks) Week 10: CEM 1; Evaluation and Appointment (5 Weeks) Week 11: CEDD Period; Evaluation and Appointment (5 Weeks) Week 12: CEM 2; Evaluation and Appointment (5 Weeks) Week 13: CEM 3; Evaluation and Appointment (5 Weeks) Week 14: CEDD Period; Evaluation and Appointment (5 Weeks) Week 15: CEM 4; Evaluation and Appointment (5 Weeks) Week 16: CEM 5; Evaluation and Appointment (5 Weeks) Week 17: CEM 6; Evaluation and Appointment (5 Weeks) Week 18: Planning submission development period; review of draft submission documents (including cost plan) via a pre-agreed plan of document reviews (to be set out by the Selected Panel Member as part of their ISP submission); leading to final submission of the planning pack in week 22 for approval (subject to any changes made by the Project Team) It is expected the Planning Public Consultation/Information Event will take place during this period; Evaluation and Appointment (5 Weeks) Week 22: Stage 3 submission including draft Planning Pack; Evaluation and Appointment (5 Weeks) Week 23: Review and confirm acceptance of submission of planning application; Contractor's Proposals (8 to 10 Weeks) Week 26: Time allocation subject to expected planning determination period As per Exchange Information Requirements SPM sessions to continue to evolve decision (including resolving RDD matters); Contractor's Proposals Review (7 to 8 Weeks) Week 36: CPs Submitted; Contractor's Proposals Review (7 to 8 Weeks) Week 37: Time allocation subject to expected planning determination period Clarifications process run in parallel leading to approval of Contract Contractor's Proposals (CPs) Gaps calls to run in parallel leading to drafting of Contract Schedules Update CPs to reflect planning decisions Conclusion of Contract Schedules DfE Touchpoint E - Procurement (RIBA4); Contractor's Proposals Review (7 to 8 Weeks) Week 44: Finalisation, agreement and signature of contract following planning permission
[18 empty] | A project initiation (CEM 0) meeting will be held at the commencement of the Design Development period. The purpose of this session is for the Selected Panel Member to review and confirm the Project Brief with the Project Team. Note: There must be at least 5 working days between the announcement of the shortlisted bidders and CEM 0 Thereafter, Client Engagement Meetings (CEMs) leading to production of the RIBA Stage 2 / Stage 3 Deliverables (circa 6 number further CEMs) leading to approval to proceed to planning. Additional CEMs can be included at the discretion of the Project Team Periods for client engagement Stage 2 design development (CEDD Period) have been allowed after CEM 1 and CEM 3. These periods can be moved at the discretion of the Project Team prior to ITT commencing, noting that a minimum of 10 working days must be allowed between CEM3 / the final CEM and submission of the ITT reponse DfE Touchpoint C - ITT (DA) | [12 empty] | - Stage 3 Information Exchange as set out in DEIR IE301 - The contents of the planning application - Cost Plan - Programme and Phasing Plans - Risk Register | Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission DfE Touchpoint D - Procurement (RIBA 3 Pre-Planning)
| Key Documents |  | Feasibility Study (and associated appendices) | Scheme Notification Form |  |  |  |  | Invitation to Submit Proposal (ISP) (3 Weeks) Week 0: Information to be provided at ISP by Framework User - ISP Letter and ISP document - Evaluation Criteria - Feasibility Study - Employer's Requirements - PCSA (+ draft Contract) Information to be submitted by Bidders - Responses to Questions set - Framework Pricing Schedule - Completed and signed Forms and Certificates - Completed PCSA Gaps List; Evaluation and Appointment (5 Weeks) Week 4: Information to be provided by Framework User - Successful Bidder Letter - Unsuccessful Bidder Letter - PCSA for execution Information to be provided by SPM - PCSA (signed); Evaluation and Appointment (5 Weeks) Week 15: Information to be provided - n/a Information to be provided by SPM - Design Development information as required to support CEM process - Planning Submission (IE301); Evaluation and Appointment (5 Weeks) Week 23: Information to be provided by Framework User - Clarifications - Approval to submit Planning Information to be provided by SPM - Clarification responses - Final Planning Submission - Remaining Stage 3 Deliverables (IE311); Contractor's Proposals (8 to 10 Weeks) Week 26: Information to be provided by Framework User - Stage 3 submission clarifications - Stage 3 Approval (by week 29) Information to be provided by SPM - Contractor's Proposals; Contractor's Proposals Review (7 to 8 Weeks) Week 36: Info to be provided by SPM - Contractor's Proposals (final); Contractor's Proposals Review (7 to 8 Weeks) Week 37: Information to be provided by Framework User - Employer's Requirements - Gaps List - Draft Contract - Contract Schedules - Clarifications Information to be provided by SPM - Contractor's Proposals (final) - Contract Schedules - Clarification responses
| IM Information Exchange Code | IE001 | IE101 / IE102 / IE201 | IE202 |  |  |  |  | Invitation to Submit Proposal (ISP) (3 Weeks) Week 0: IE231 / IE232; Evaluation and Appointment (5 Weeks) Week 4: IE241; Evaluation and Appointment (5 Weeks) Week 15: IE301; Evaluation and Appointment (5 Weeks) Week 23: IE311; Contractor's Proposals Review (7 to 8 Weeks) Week 36: IE401 | IE501 / IE511 / IE521 | IE601 / IE611

## DA_&_Future-ISP_with_ESI
Design and Build Competition Timeline
Direct Allocation and Future Schemes - with Early Supplier Involvement
DIRECT ALLOCATION AND FUTURE SCHOOLS PROCESS - WITH EARLY SUPPLIER ENGAGEMENT (ALL BANDS) | SCDP Stage | Stage 1: Pre-Feasibility | Stage 2: Feasibility | [8 empty] | Stage 3: Choose Contractor |  |  |  |  | Stage 4: Design, Planning & Contract Development | [37 empty] | Stage 5: Construction | Stage 6: Post Practical Completion & Use
| Approx. RIBA Stage | RIBA Stage 0 (Strategic Definition) | RIBA Stage 1 (Preparation and Briefing) | [8 empty] | RIBA Stage 2 (Concept Design) | [10 empty] | RIBA Stage 3 (Spatial Coordination) | [10 empty] | RIBA Stage 4 (Technical Design) | [20 empty] | RIBA Stage 5 (Manufacturing and Construction) | RIBA Stage 6 (Handover and Post-Handover) | RIBA Stage 7 (In Use)
| Framework Stage | Pre-Feasibility (c 3 weeks) | Feasibility 1.1 Project Strategy (c 10 weeks) | ESI Pipeline Notice | Feasibility 1.2 Project Options Appraisal (c 6 weeks) | PCSA | PCSA to Contract Close: 53 weeks Framework Users to draft realistic programmes based on project-specifics | Feasibility 2.0 Project Brief Development (c 12 weeks) | Approve Feasibility 2.0 (3wks) |  |  | Future School ISP (4 wks) |  |  |  |  | Design Development (c9 Weeks) | [8 empty] | Planning Submission Development (5 Weeks) |  |  |  |  | Planning Application Submission (3 Weeks) |  |  | Planning Determination (15 to 18 Weeks) | [17 empty] | Contract Finalisation (3 Weeks) |  |  | Construction | Handover and Rectification Period | In Use
[12 empty] | Invitation to Submit Proposal (ISP) |  |  | Evaluation and Appointment (2 Weeks) | [18 empty] | Contractor's Proposals (8 to 10 Weeks) | [9 empty] | CPs Review (7 to 8 Weeks)
| Week | Weeks -34 to -32 | Weeks -31 to -22 | 1 week prior to conclusion of 1.1 | Weeks -21 to -16 | 2-3 weeks after 1.2 commences |  | Weeks -15 to -4 | Week -3 | Week -2 | Week -1 | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42
| Stage Summary | Framework User agrees Business Case and Strategic Brief - confirms the ownership boundary (red line) and PAN for school | Technical Advisor (TA) gathers factual and desktop information about the site, and prepares the Project Strategy Report Aim of this stage is to produce agreed project scope and block assessment table Framework User issues Strategic Outline Case and ESI decision taken |  | TA gathers RIBA Stage 1 options and cost plan and undertakes an options appraisal to select the preferred option. Aim of this stage is to confirm the control option. Selected Panel Member (SPM) provides review and comment on proposed development options to support selection of control option. DfE Touchpoint A - Options Appraisal | Contractor submits ESI documentation for acceptance. Contractor appointment confirmed. Sign PCSA for RIBA 2 Concept Design Consultative Services |  | Selected Panel Member (SPM) supports the development of the concept control option design to RIBA Stage 2 including programme, phasing plans, pre application consultation, stats enquiries, building services strategy, and assessment of project level risks Framework User collates the Feasibility Study and prepares a control option cost plan Weekly Project Team meetings including the Selected Panel Member to review scheme development, surveys results, abnormals and costs DfE Touchpoint B - Feasibility Study | Week -3: Framework User review and approval of Feasibility 2.0 leading to approval to proceed; Invitation to Submit Proposal (ISP) Week 0: Invitation to Submit Proposal (ISP) and response (two weeks, or as agreed with Panel Member) - week 0 represents issue of ISP Alternate Option: This period may need to be extended to reflect the quantity of design information Contractors must review; Evaluation and Appointment (2 Weeks) Week 3: Evaluation and Appointment of Selected Panel Member (SPM) DfE Touchpoint C - ITT (CA); Evaluation and Appointment (2 Weeks) Week 4: Notice to proceed issued for PCSA Services covering RIBA Stages 3&4; Evaluation and Appointment (2 Weeks) Week 5: CEM 0; Evaluation and Appointment (2 Weeks) Week 6: CEM 1; Evaluation and Appointment (2 Weeks) Week 7: CEDD Period; Evaluation and Appointment (2 Weeks) Week 8: CEM 2; Evaluation and Appointment (2 Weeks) Week 9: CEM 3; Evaluation and Appointment (2 Weeks) Week 10: CEDD Period; Evaluation and Appointment (2 Weeks) Week 11: CEM 4; Evaluation and Appointment (2 Weeks) Week 12: CEM 5; Evaluation and Appointment (2 Weeks) Week 13: CEM 6; Evaluation and Appointment (2 Weeks) Week 14: Planning submission development period; review of draft submission documents (including cost plan) via a pre-agreed plan of document reviews (to be set out by the Selected Panel Member as part of their ISP submission); leading to final submission of the planning pack in week 18 for approval (subject to any changes made by the Project Team) It is expected the Planning Public Consultation/Information Event will take place during this period; Evaluation and Appointment (2 Weeks) Week 18: Stage 3 submission including draft Planning Pack; Evaluation and Appointment (2 Weeks) Week 19: Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission DfE Touchpoint D - Procurement (RIBA 3 Pre-Planning); Contractor's Proposals (8 to 10 Weeks) Week 22: Time allocation subject to expected planning determination period As per Exchange Information Requirements SPM sessions to continue to evolve decision (including resolving RDD matters); CPs Review (7 to 8 Weeks) Week 32: CPs Submitted; CPs Review (7 to 8 Weeks) Week 33: Time allocation subject to expected planning determination period Clarifications process run in parallel leading to approval of Contract Contractor's Proposals (CPs) Gaps calls to run in parallel leading to drafting of Contract Schedules Update CPs to reflect planning decisions Conclusion of Contract Schedules DfE Touchpoint E - Procurement (RIBA4); CPs Review (7 to 8 Weeks) Week 40: Finalisation, agreement and signature of contract following planning permission
[17 empty] | A project initiation (CEM 0) meeting will be held at the commencement of the Design Development period. The purpose of this session is for the Selected Panel Member to review and confirm the Project Brief with the Project Team and end user Thereafter, Client Engagement Meetings (CEMs) leading to production of the RIBA Stage 2 / Stage 3 Information Deliverables (circa 6 number further CEMs) leading to approval to proceed to planning. Additional CEMs can be included at the discretion of the Project Team Periods for client engagement Stage 2 design development (CEDD Period) have been allowed after CEM 1 and CEM 3. These periods can be moved at the discretion of the Project Team prior to Design Development commencing, noting that a minimum of 10 working days must be allowed between CEM3 / the final CEM and submission of the Design Development documents. DfE Touchpoint C - ITT (DA) | [12 empty] | - Stage 3 Information Exchange as set out in DEIR IE301 - The contents of the planning application - Cost Plan - Programme and Phasing Plans - Risk Register
| Key Documents |  | Feasibility Study (and associated appendices) PCSA | [5 empty] | Invitation to Submit Proposal (ISP) Week 0: Information to be provided at ISP by Framework User - ISP Letter and ISP document - Evaluation Criteria - Feasibility Study - Employer's Requirements - PCSA (+ draft Contract) Information to be submitted by Bidders - Responses to Questions set - Framework Pricing Schedule - Completed and signed Forms and Certificates - Completed PCSA Gaps List; Evaluation and Appointment (2 Weeks) Week 11: Information to be provided - n/a Information to be provided by SPM - Design Development information as required to support CEM process - Planning Submission (IE301); Evaluation and Appointment (2 Weeks) Week 19: Information to be provided by Framework User - Clarifications - Approval to submit Planning Information to be provided by SPM - Clarification responses - Final Planning Submission - Remaining Stage 3 Deliverables (IE311); Contractor's Proposals (8 to 10 Weeks) Week 22: Information to be provided by Framework User - Stage 3 submission clarifications - Stage 3 Approval (by week 25) Information to be provided by SPM - Contractor's Proposals; CPs Review (7 to 8 Weeks) Week 32: Info to be provided by SPM - Contractor's Proposals (final); CPs Review (7 to 8 Weeks) Week 33: Information to be provided by Framework User - Employer's Requirements - Gaps List - Draft Contract - Contract Schedules - Clarifications Information to be provided by SPM - Contractor's Proposals (final) - Contract Schedules - Clarification responses
| IM Information Exchange Code | IE001 | IE101 |  | IE102 |  |  |  | Week -3: IE201 / IE202; Invitation to Submit Proposal (ISP) Week 0: IE231 / IE232; Evaluation and Appointment (2 Weeks) Week 3: IE241; Evaluation and Appointment (2 Weeks) Week 11: IE301; Evaluation and Appointment (2 Weeks) Week 19: IE 311; CPs Review (7 to 8 Weeks) Week 32: IE401 | IE501 / IE511 / IE521 | IE601 / IE611