## Cover
Building Safety Remediation Data Release, England: 31 October 2025
Back to Contents
Background
This publication provides data on 1) the remediation progress across MHCLG’s Building Safety Remediation portfolio, covering buildings in the ACM programme, Building Safety Fund, Cladding Safety Scheme, developer remediation contract and reported by registered providers of social housing, 2) Progress with remediation of high-rise (18 metres and over in height) residential buildings (including student accommodation and hotels) and publicly owned buildings with ACM cladding systems unlikely to meet Building Regulations in the ACM programme, 3) the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund, 4) progress with remediation of high-rise residential buildings with non-ACM cladding systems assessed as eligible for funding from the Building Safety Fund , 5) Progress with the applications for and remediation of medium-rise (11 – 18 metres in height) residential buildings in England and high-rise residential buildings outside of London with non-ACM cladding systems in the Cladding Safety Scheme, 6) progress of remediation of residential buildings 11 metres and over in height with life-safety defects under the developer remediation contract, 7) progress of remediation of residential buildings 11 metres and over in height with unsafe cladding reported by registered providers of social housing, 8) enforcement action taken by local authorities against 11m+ residential buildings with cladding defects under the Housing Act 2004.
Tables on the ACM programme, BSF, CSS, developer remediation contract and social housing surveys include buildings which can be in multiple schemes or data collections so counting across tables can result in double counting. Tab Combined_2 provides an overall summary of all remediation progress, without double counting.
Publication dates
The data tables in this spreadsheet were originally published on 20 November 2025.
The next publication is scheduled for December 2025.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
We are committed to improving and broadening this data release further in the months ahead and would welcome feedback both on the content of this data release and what could be further done in the future.
BuildingSafetyData2@communities.gov.uk
NewsDesk@communities.gov.uk
Date published: 20 November 2025

## Table_of_Contents
Building Safety Remediation Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 October 2025
ACM_2	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 October 2025
ACM_3	Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 October 2025
ACM_4	ACM remediation progress by local authority, England, 31 October 2025
ACM_5	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 October 2025
ACM_6	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 October 2025
ACM_7	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 31 October 2025
ACM_8	ACM remediation progress by sources of funding, England, 31 October 2025
ACM_9	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 October 2025
ACM_10	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 October 2025
ACM_11	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 31 October 2025
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 October 2025
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 October 2025
WWRF_3	Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 October 2025
BSF_1	Remediation status of eligible buildings within BSF by tenure, England, 31 October 2025
BSF_2	BSF remediation progress of eligible buildings by region, England, 31 October 2025
BSF_3	BSF number of eligible buildings with funding approved and expenditure amounts by tenure, England, 31 October 2025
BSF_4	BSF remediation progress of eligible buildings by local authority, England, 31 October 2025
BSF_5	Remediation status of eligible buildings within BSF, time series, England, 31 October 2025
Combined_1	Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 October 2025
Combined_2	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 October 2025
Combined_3	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 31 October 2025
Combined_4	Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 31 October 2025
Combined_5	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by tenure, 31 October 2025
Combined_6	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, time series, 31 October 2025
Combined_7	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by region, 31 October 2025
Combined_8	Remediation progress for unique buildings being remediated or mitigated as part of a government funded scheme, 11 metres and over in height, England, 31 October 2025
CSS_1	Application status of buildings within the CSS, England, 31 October 2025
CSS_2	CSS remediation progress by region, England, 31 October 2025
CSS_3	CSS remediation progress by height, England, 31 October 2025
CSS_4	CSS remediation progress by tenure, England, 31 October 2025
CSS_5	CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 31 October 2025
CSS_6	CSS remediation progress, time series, England, 31 October 2025
Social_1	Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 31 October 2025
Social_2	Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 June 2025
Social_3	Provider by provider breakdown of buildings, by assessment status, England, 30 June 2025
Social_4	Provider by provider breakdown of buildings, by remediation status, England, 30 June 2025
Social_5	Remediation status of buildings with cladding defects monitored under the social housing surveys, time series, England, 31 August 2025
Developer_1	Remediation status of buildings covered by the developer remediation contracts by height group, England, 31 October 2025
Developer_2	Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 October 2025
Developer_3	Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 July 2025
Developer_4	Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 July 2025
Developer_5	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 July 2025
Developer_6	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 July 2025
Developer_7	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 July 2025
Developer_8	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 July 2025
Developer_9	Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 July 2025
Developer_10	Remediation status of buildings requiring works under the developer remediation contract, time series, England, 31 August 2025
Developer_11	Estimated number of determinations, starts and completions made each quarter for buildings under the developer remediation contract, by height group, England, 31 July 2025
Developer_12	Developer by developer update against RAP Joint Plan targets, 31 July 2025
Enforcement_1	Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 20 October 2025
Enforcement_2	Building inspections conducted by local authorities, England, 20 October 2025
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 20 October 2025
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 20 October 2025
JIT_1	Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 October 2025
Estimated_1	Estimates of the number of residential buildings, containing dwellings, that have or had unsafe cladding requiring work, 11 metres and over in height, England, January 2025
Estimated_2	Estimates of the number of residential buildings, that have or had unsafe cladding requiring work, expected to be remediated or mitigated as part of a government remediation programme, 11 metres and over in height, England, January 2025
Estimated_3	Estimated proportion of buildings with unsafe cladding expected to be remediated or mitigated in a government remediation programme that are currently monitored in a government remediation programme, 31 October 2025
Estimated_4	Estimates of the number of residential buildings, that have or had unsafe cladding requiring remediation or mitigation work, expected to be remediated or mitigated as part of a government funded scheme, based on January 2025 eligibility criteria, 11 metres and over in height, England, January 2025

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in table ACM_1 and ACM_2.	ACM_3
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_4, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to complete remediation works on-site	ACM_7
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_8
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period. 16 private sector buildings are receving government funding from the Building Safety Fund or Cladding Safety Scheme, so do not appear in the totals in table ACM_9, but do in ACM_8.	ACM_8, ACM_9
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_10
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_10
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_10
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_10
[note 10]	Total figures may not sum due to rounding.	ACM_11, WWRF_1, WWRF_2, WWRF_3, BSF_1, BSF_2, BSF_3, BSF_5, Combined_4, Estimated_1, Estimated_2
[note 11]	The first tranche of the Waking Watch Relief Fund was administered by eight local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Relief Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_2
[note 12]	The Waking Watch Replacement Fund was administered by five local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Replacement Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_3
[note 13]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2, CSS_1, CSS_2, CSS_3, CSS_4, CSS_6, Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8
[note 14]	Private sector and social sector financial viability buildings can receive pre-tender support allocation in addition to their full applications funding, but not all buildings receive this therefore these numbers cannot be added together to directly give a total.	BSF_3
[note 15]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_3
[note 16]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1
[note 17]	Buildings can be in multiple schemes and data collections. These tables show the unique number of buildings across the schemes without double counting buildings where they are in multiple schemes. The total here will be lower than the summed total number of buildings reported in each scheme.	Combined_1, Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8
[note 18]	Where buildings are in multiple programmes, a combined remediation stage is first assigned for buildings in more than one of the ACM programme, BSF and CSS. 'In programme' is assigned for buildings that are eligible for but have not started works in any programme, or on one type of cladding (ACM or non-ACM). 'Remediation Underway' is assigned for buildings where work has started on remediation in at least one programme, or on one type of cladding. 'Remediation complete' is assigned for buildings that have completed remediation on site in all programmes or on all types of cladding. / For further overlaps, remediation stages are assigned from programmes in priority order: ACM, BSF, CSS (or a combined stage across these programmes), developer returns, social housing returns.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8
[note 19]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 20]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 21]	The Government-funded Joint Inspection Team, hosted by the Local Government Association, carries out building inspections on behalf of local authorities and provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4
[note 22]	The number of training sessions for Wandsworth and Richmond are combined as Merton, Wandsworth and Richmond operate a joint service where Merton officers attend training on behalf of Richmond and Wandsworth.	JIT_1
[note 23]	Buildings confirmed by delivery partners to be transferred to developers or the Cladding Safety Scheme have been withdrawn from the Building Safety Fund, which has led to a decrease in the number of eligible buildings in the Fund. The number of eligible buildings may continue to decrease as more buildings are confirmed as developer or CSS transfers out of the fund.	BSF_1, BSF_2, BSF_4, BSF_5
[note 24]	The Building Safety Fund first opened to registrations from June to July 2020 receiving registrations from 3,488 buildings. In July 2022 the Building Safety Fund reopened to new applications; this remains open to new applications from buildings in London over 18 metres in height (high-rise buildings outside of London can apply for remediation via the Cladding Safety Scheme). Buildings from both application periods are now combined as one Building Safety Fund, so numbers include both application periods. It is possible for a building to submit a new application to the fund after having completed remediation if it originally applied in 2020, therefore buildings could be double counted. As of the latest reporting period one building had undertaken remediation work from both application periods, so is double counted.	BSF_1, BSF_2, BSF_3, BSF_4, BSF_5
[note 25]	Some buildings have an unknown remediation status reported by the developer. These have been interpreted as ‘Remediation not started – no plans in place’. Furthermore, some buildings have an unknown defect type. These are interpreted as cladding related defects.	Developer_1, Developer_4, Developer_10
[note 26]	The buildings reported in this table as requiring remediation are estimated by MHCLG using information provided by developers in their data return and other data available within the department. In this table, a building is defined as requiring works under the developer remediation contract if it is either self-reported by the developer as requiring (or having previously required) remedial works; is an eligible building in the BSF or ACM and the developer has agreed to re-imburse the funds; has had money paid out by the BSF or ACM; or has a self-reported work status of either: works completed, works started, or works not started but plans in place. / They therefore differ from other published tables which reference only to the number of 'self-reported' buildings requiring works.	Developer_1, Developer_10
[note 27]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which the developer is remediating directly (please see note 28). The tables shows the number of buildings which have not yet started works; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Plans under Development' or where no status was provided. The table shows the estimated or actual start date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet started remediation work, but have an estimated or actual start date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_5, Developer_6
[note 28]	This represents buildings that developers are solely responsible for. These exclude buildings that are being remediated solely under a government remediation scheme, for which the developer will reimburse taxpayers. However, some buildings being remediated under a government remediation scheme will be included if other relevant fire safety defects have been found, which were not eligible for a government remediation scheme and which the developer is remediating themselves.	Developer_3
[note 29]	The tables report data for 53 developers who have signed the Developer Remediation Contract. Data for one developer who has gone into administration is not included in this release. / Where tables show the breakdown of data for each developer, there are 12 developers with 5 or fewer builidings who have been supressed to avoid inadvertently identifying buildings with life-critical fire safety defects. They are grouped in the category 'Other (combined total for all developers with five or fewer buildings each'. This includes: Abbey Developments, Allison Homes, Bloor, CG Fry, Courdace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata and William Davis. These developers will be represented in the data with a dash (-) in tables	Developer_1, / Developer_2, / Developer_3, Developer_4, Developer_5, Developer_6, Developer_7, Developer_8, Developer_9, Developer_10
[note 31]	This represents buildings which have been found to require remediation, for which the developer is directly responsible for the works. It excludes buildings being remediated solely under a government remediation scheme, for which the developer will reimburse taxpayers (see Note 28), as the developer cannot influence the pace of remediation on these buildings. However, some buildings being remediated under a government remediation scheme will be included if other relevant fire safety defects have been found, which were not eligible for a government remediation scheme and which the developer is remediating themselves.	Developer_3, Developer_4
[note 32]	The data here is comprised of of buildings where the response to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?’ was either left blank or reported as ‘Don’t Know – no assessment made’, ‘Don’t Know’ or ‘No – Declaration 5.4B.	Developer_3
[note 33]	The total estimated cost of remediation is based on the actual or estimated cost of remediating EWS and non-EWS defects, as reported by developers, and an assumed average where a cost has not been reported (averages are based on the developer-reported costs, by height).	Developer_2
[Note 34]	Data is taken from a building level survey issued to Registered Providers of Social Housing on their 11 metre plus buildings and is correct as at 30 June 2025. / Landlords were asked to respond to the survey for buildings in which they are the responsible entity. A 'Responsible Entity' is the organisation that has the legal obligation or right to carry out the remediation works. The Responsible Entity may be the building’s freeholder or head leaseholder, registered provider of social housing or a management company or Right To Manage (RTM) company that has primary responsibility for the repair of the property. / As a result, buildings within the survey may comprise of mixed tenure dwellings e.g., private leasehold and social rented dwellings, however remedial works will fall under the responsibility of the responding landlord. / Furthermore, landlords were asked to provide information on any life critical fire safety (LCFS) defects, which the survey defined as defects, shrinkages, faults or other failings in a building that give rise to fire safety risks. These are identified by: / 1) a Fire Risk Appraisal of External Wall construction (FRAEW) undertaken in accordance with PAS 9980 that assesses the external wall construction or cladding as not “medium - tolerable” (or better); or / 2) a fire risk assessment (FRA) that assesses the relevant parts of the building as high risk or medium risk or equivalent according to industry standards.	Social_1; Social_5
[Note 35]	A building with EWS 'cladding defects' is defined as a building which has at least one Life-critical Fire-safety defect relating to an External Wall System (EWS) cladding defect. These buildings may also include non-cladding associated defects.	Social_1; Social_2; Social_3; Social_4; Social_5
[Note 36]	The number of buildings identified as 'Remediation complete' may not match the number of social buildings being reported and complete under the BSF, ACM, CSS or developer contract due to the following: / 1) Non-responses to building level survey issued to Registered Providers of Social Housing - a small number or landlords did not respond to the survey, which means some buildings remediated through other remediation schemes may not be captured. / 2) Differences in how buildings are reported in the building level survey issued to Registered Providers of Social Housing - some buildings which have already completed remediation via other schemes have been reported as having no Life-Critical Fire-Safety defects in the survey, as the latest fire safety assessment has concluded that the the building is safe. Subsequently, the landlord has reported that no defects are present in the survey and have left the remediation category blank.	Social_1
[Note 37]	The data here includes buildings in the building level survey issued to Registered Providers of Social Housing, which may have also applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract. These are not excluded from the Social Housing Sector Management Information tables (Social_1).	Social_1
[note 38]	The total number of social high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 2 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 39]	The total number of social high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 1 building that falls under the developer remediation contract.	ACM_8
[note 40]	The total number of private high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 21 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 41]	The total number of private high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 68 buildings that fall under the developer remediation contract.	ACM_8
[note 42]	Data for the ACM, BSF and CSS are updated monthly. Developer data and data reported by Registered Providers of social housing are updated quarterly.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7
[note 43]	The number of buildings associated with particular expenditures paid out may also include buildings where a full reimbursement of funding has taken place, including those where required under the developer contract.	BSF_3
[note 44]	Buildings receive expenditure funding in stages and therefore these figures should not be used to calculate the average expenditure paid out to each building.	BSF_3, CSS_5
[note 45]	In this table where a local authority has 5 or fewer eligible BSF buildings, the numbers provided are banded. In all other cases the numbers are provided. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	BSF_4
[note 47]	Three buildings with live applications to the CSS are in Northern Ireland, the remainder are in England.	CSS_1
[note 48]	Four eligible buildings in the CSS are in Northern Ireland, the remainder are in England.	CSS_1, CSS_2, CSS_3, CSS_4
[Note 50]	The data in this table is derived from the building level survey which has been submitted by Registered Providers of Social Housing on their 11 metre plus buildings and is correct as at 30 September 2024. It covers buildings in England over 11m which contain at least 1 unit of social housing for which the social housing provider is the Responsible Entity. / Some buildings in this table may have applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract.	Social_2; Social_3; Social_4
[Note 51]	Registered social housing providers who have five or fewer 11m+ buildings (which may or may not require EWS life-critical fire-safety works) have been grouped together in the ‘Other RPs’ row in the data table, in order to avoid inadvertently identifying individual buildings with EWS life-critical fire-safety defects.	Social_2; Social_3; Social_4
[Note 52]	A building works assessments should comply with the requirements of the Fire Safety Order, for example a Fire Risk Assessment or Fire Risk Appraisal of External Walls assessment (FRAEW).	Social_2; Social_3
[Note 54]	Buildings reported as having completed remediation in the building level survey may require reassessment to confirm the building is now safe.	Social_1; Social_4
[Note 55]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which the developer is remediating directly (please see note 28). The tables shows the number of buildings which have not yet completed remediation; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Remediation Started' or where a remediation status was not provided. The table shows the estimated or actual completion date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet completed remediation work, but have an estimated or actual completion date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_7, / Developer_8
[Note 56]	Funding allocations of Full Applications Approved has reduced from previously published figures. This is the result of a data reconciliation exercise, where buildings transferring from the BSF to the Responsible Actors Scheme and Cladding Safety Scheme have had their BSF funding allocation removed.	BSF_3
[Note 57]	The 'Other' tenure includes buildings that are recorded in the ACM programme as student, hotel or public buildings.	Combined_5
[Note 58]	The estimates in this table include buildings which are: / a) reported in the latest survey (as at 30 June 2025) as having unsafe cladding at the time of their most recent assessment; / b) reported in the latest survey (as at 30 June 2025) as having unsafe cladding found since June 2017 but prior to the most recent survey, which have since been remediated; / c) being monitored under another government programme (BSF, ACM, CSS or RAS) due to having unsafe cladding.	Social_1
[Note 59]	Until May 2024, private sector funding allocations and expenditures included buildings which have successful social sector financial viability claims. This is because both private sector and social sector financial viability buildings receive full government funding, whereas those in the social sector receive partial funding dependant on the number of eligible leaseholders who pay a service charge. For full details please refer to the accompanying technical note.	[BSF_3]
[Note 60]	Until the May 2024 data release, social sector buildings with a successful financial viability claim were included in the "Private" figures due to them receiving funding for all work, rather than a percentage based on the number of leaseholders that pay a service charge. These buildings are now split out into the "social sector financially viability" category. Further details on the difference between these can be found in the accompanying technical note.	[BSF_1]
[Note 61]	This table depicts the number of buildings that are estimated to require works which have transferred from the Building Safety Fund (BSF). This figure is based on the developer's dataset definition of a building and differs to the number reported by the BSF because of difference in building definitions.	Developer_1
[Note 62]	The estimates in this table include buildings which are reported in the latest survey (as at 30 June 2025) as having unsafe cladding at the time of their most recent works assessment. They do not include buildings which are reported in the latest survey (30 June 2025) as having unsafe cladding found since June 2017, which have since been remediated. / They also do not include buildings that were identified through other government programmes (BSF, ACM, CSS or RAS) which have not been reported by social housing providers as having unsafe cladding.	Social_1; Social 2; Social_3; Social 4
[Note 63]	The December 2018 and December 2019 ACM remediation progress figures did not include the breakdowns for 'remediation started - cladding removed' and 'works complete awaiting building control signoff'. Those buildings which had started remediation and removed unsafe cladding are included in the 'remediation started' category, and those that were awaiting building control sign off may have been included in the 'completed remediation' category	ACM_11
[Note 64]	Up to October 2023 combined remediation progress in the Building Safety Fund (BSF) and ACM programme is shown. Between June 2023 and September 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers. From October 2023 onwards combined remediation progress is shown across the BSF, ACM programme, Cladding Safety Scheme, developer remediation contract and as reported by registered providers of social housing.	Combined_6
[Note 65]	Between June 2023 and July 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers.	BSF_5
[Note 66]	This table is updated quarterly with the latest data and therefore may not align with monthly figures where the programme data is updated.	Developer_10
[Note 67]	The estimates in this table include buildings which are reported in the latest survey (as at 30 June 2025) as having unsafe cladding: / a) at the time of their most recent assessment. / b) found since June 2017 but prior to the most recent survey, which have since been remediated. / The estimates in this table do not include buildings that were identified through other government programmes (BSF, ACM, CSS or RAS) which have not been reported by social housing providers as having unsafe cladding.	Social_1; Social 2; Social 4
[Note 68]	In previous Building Safety Remediation releases, this table was known as 'Building inspections conducted by local authorities'. As of the August 2024 release, this table reports the category assigned from the most recent building inspection.	Enforcement_2
[Note 69]	The Mar-24 and Jun-24 estimates are not comparable to previous quarters due to a change in methodology in reporting social housing sector remediation. Since Mar-24, the estimates include buildings which have been reported by Registered Providers to have completed remediation since June 2017 but prior to the most recent assessment. They also include social buildings the department has identified in other remediation programmes as having unsafe cladding and are also being monitored in those programmes.	Social_5
[Note 70]	This table excludes local authorities with fewer than 10 11m+ buildings monitored with unsafe cladding. These disclosure control measures are in place to prevent the identification of one or more buildings with unsafe cladding in these areas.	Combined_3
[Note 71]	As of the November 2024 data release, there is only one column covering Level 2 training. This is a sum of the data from Level 2 Part 1 and Level 2 Part 2. To make comparisons with previous JIT training data, the values in columns C and D should be totalled. When training is delivered as Level 1 and Level 2 in the same session, the training is recorded only in the Level 2 column.	JIT_1
[Note 72]	The reported number of buildings to have started or completed remediation works has fallen between August 2024 data release and November 2024 data release mainly due to data revisions from some Registered Providers of social housing following the addition of more detailed questions on start and completion dates.	Social_5
[Note 73]	The figures from before December 2022 for BSF remediation progress did not distinguish between 'Remediation plans in place' and 'Intent to remediate'; they were recorded as 'Remediation not yet started.' Therefore, before December 2022, buildings that would have been categorised as 'Remediation not yet started' are now classified as 'Intent to remediate.'	BSF_5
[Note 74]	It is possible for a building to submit 2 applications to the Building Safety Fund after having completed remediation if it originally applied in 2020, to avoid duplication on a portfolio level these buildings are combined into 1 entry. This means that the total of Non-ACM cladding only in the BSF and Both ACM and non-ACM cladding in the BSF won't match the total number of BSF buildings seen in the BSF tables. As of 30 June 2025 one building had undertaken remediation work from both application periods.	Combined_1
[Note 75]	The number of buildings inspected with support from the Joint Inspection Team may not match the overall number of inspections carried out with their support, as some buildings may have been inspected more than once.	Enforcement_4
[Note 76]	The numbers of notices, inspections etc. may decrease as a result of revisions submitted.	Enforcement_1, Enforcement_4
[Note 77]	These figures exclude CSS buildings in Northern Ireland.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8, Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 78]	A government funded scheme includes the ACM programme (including buildings not receiving government funding), the BSF and the CSS.	Combined_8, Estimated_4
[Note 79]	These figures represent MHCLG's best estimates of the number of 11m+ residential buildings that have or had unsafe cladding, in England, as at January 2025. The estimates of 11-18m buildings with unsafe cladding replace estimates first published in 2022. New estimates use the recently released Ordnance Survey National Geographic Database (OS NGD) data, alongside the original sample survey used in 2021. The estimates of 18m+ buildings with unsafe cladding use known building numbers as at July 2024, alongside individual assumptions of further buildings to be identified in different categories. Full methodology is available in the Technical Note.	Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 80]	The estimate of the number of 11-18m buildings in England used to calculate the prevalence of unsafe cladding is an updated estimate, replacing the original estimates first published in 2021. Further information is available in the Technical Note.	Estimated_1
[Note 81]	These figures include buildings which have already undergone remediation or mitigation of unsafe cladding.	Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 82]	The estimates in Estimated_2 differ from the estimates in Estimated_1 as Estimated_2 includes 18m+ hotels, student accommodation or public buildings identified with unsafe ACM cladding, because these buildings are remediated through the ACM programme. At the time the estimate was made there were 98 of these buildings. These are excluded from Estimated_1 because the buildings do not contain dwellings. The estimated number of 11m+ buildings which are assumed to be remediated privately, outside of one of the department’s remediation programmes, are included in Estimated_1 but excluded from the Estimated_2.	Estimated_1, Estimated_2
[Note 83]	MHCLG have collected quarterly data returns from developers since 31 July 2023. However, it is not possible to show a breakdown of determinations made between 31 July 2023 and 31 January 2024 due to an amendment which was made to the question used to track determinations in January 2024. Determinations are based on the survey question 'Does this building require works, or has it previously been identified with defects, as per the contract?' Prior to January 2024 the response options for this question were 'Yes', 'No' and 'Don't Know', however as the response 'No' comprised a combination of buildings which had received a qualifying assessment and buildings which hadn't, it was not possible to accurately identify buildings which had recieved a determination on whether remedial works are required. Therefore, in January 2024 the options were amended to 'No - as shown by assessment', 'Yes - as shown by assessment', 'Don't Know - no assessment made' and 'Don't Know - further assessment required'. This enables developers to more accurately report on whether a determination has been made for each building.	Developer_11
[Note 84]	Determinations are based on a developers response to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?'. To estimate the quarterly number of buildings where determinations were made, MHCLG uses the most recent quarterly returns submitted by developers. Buildings reported with a determination in the most recent quarterly return are compared against previous returns and categorised based on the earliest quarterly return in which they were reported to have had a determination, providing they continue to be reported as determined in subsequent quarters. If a determination alternates across returns, the most recent reported data return is used. See the Technical Note for further information.	Developer_11
[Note 85]	To estimate the number of buildings where works were started or works were completed in each quarter, MHCLG have used the most recent quarterly returns submitted by developers. Using developer responses to the question 'Status of Works', buildings reported as Started or Completed in the most recent quarterly return are compared against previous returns and categorised based on the earliest quarterly return in which they were reported to have started or completed works, providing they continue to be reported as started or completed in subsequent quarters. If the response to 'Status of Works' alternates across returns, the most recent reported data return is used. / In January 2025, as part of data validation improvements, an additional response of 'Yes - the building previously required works which are now fixed' was added to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?'. For buildings where the 'Status of Works' has changed from not started/blank to using this new response in consecutive quarters, the start and completion dates reported by developers are used to categorise the quarter in which they started or completed. For buildings where valid dates were not reported by developers, it is assumed that they had started and completed works before 31 July 2023; the first point at which developers submitted data to MHCLG." See the Technical Note for further information.	Developer_11
[Note 86]	The statistics in these tables are experimental and as such will be subject to methodology refinements as more data becomes available. See the Technical Note for further information.	Developer_11
[Note 87]	The total is the same as the row above since there is only one Administering Authority for the 2023 Replacement Fund	WWRF_4
[Note 88]	Figures in this table are based on funding eligibility criteria as at January 2025.	Estimated_4
[Note 89]	Running total of training for the year to date (or total for that year if not current year)	JIT_1
[Note 90]	Total attendees on training for all the years we have received data. May not be a sum of the individual years' data.	JIT_1
[Note 91]	Two providers – London Borough of Brent and Brighton and Hove City Council – reported they were not able to confidently provide further information on their 11m+ buildings as of 30 June 2025 while they were undertaking a review of their data. As a result, this data release includes only their total number of 11m+ buildings which they confirmed as at 30 June 2025. No information is included for the assessment status, presence of life-critical fire safety defects related to the external wall system or remediation status of their buildings. MHCLG and RSH are working with these two providers to support their reviews and future data submission.	Social_1; Social_2; Social_3; Social_4; Social_5
[Note 92]	The Jun-25 estimates are not comparable to previous quarters due to two social housing providers - London Borough of Brent and Brighton and Hove City Council - reporting that they were not able to confidently provide information on whether their 11m+ buildings have life-critical fire safety defects related to the EWS.These two social housing providers previously jointly reported 43 11m+ buildings with life-critical fire safety defects related to the EWS (which are included in the Mar-25 estimates).	Social_1; Social_5
[Note 93]	Two providers – London Borough of Brent and Brighton and Hove City Council – reported they were not able to confidently provide further information on their 11m+ buildings as at 30 June 2025 while they were undertaking a review of their data. As a result, this data release includes only their total number of 11m+ buildings, which they confirmed as at 30 June 2025. No information is included for the assessment status, presence of life-critical fire safety defects related to the external wall system or remediation status of their buildings. London Borough of Brent and Brighton and Hove City Council's figures are included in the total number of 11m+ buildings to calculate the percentage of 11+m buildings which have had or have not had a recent building works assessments (social_2) and to calculate the percentage of 11+m buildings which have been assessed and identified life-critical fire safety defects related to the EWS since June 2017 or in their most recent building works assessment (social_3).	Social_2; Social_3; Social_4
[Note 94]	Following publication of the public inquiry report into the Grenfell Tower Fire, the Prime Minister made clear that unsafe buildings must be remediated more quickly. The joint plan was published alongside the government’s broader Remediation Acceleration Plan. 39 developers have signed up to the Joint Plan, where they have committed to making every effort to achieve several stretch targets: / • Finish assessing all their buildings to determine which require works by end July 2025 / • Start or complete remedial works on 80% of their buildings by end July 2026 / • Start or complete remedial works on all their buildings by end July 2027 / • Resolve extant cost-recovery negotiations with social housing providers by end July 2025	Developer_12
[Note 95]	Under the joint plan, developers committed to complete determinations for all buildings for which they are responsible under the contract by end July 2025, and to provide evidence to MHCLG in any cases where a building missed the stretch target for reasons outside the developer’s control. MHCLG committed to consider any such evidence and take it into account when reporting on developer progress. This column shows the number of buildings where a reasonable exception has been requested by a developer and accepted by MHCLG. / To calculate the estimated percentage of buildings that would have a determination if buildings with exceptions are accounted for, the 'number of buildings where an exception request has been accepted' is subtracted from the 'number of contract buildings where the developer is directly responsible for remediation' and this is used as the denominator. The 'number of buildings for which the developer has determined whether works are required' is used as the numerator	Developer_12

## ACM_1
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Tenure	Number of buildings this month	Number of buildings last month	Monthly change
Social sector residential	162	163	-1
Private sector residential	250	246	4
Student accommodation	61	61	0
Hotels	32	33	-1
Publicly-owned buildings	8	8	0
Total buildings	513	511	2

## ACM_2
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Completed Remediation	142	88%	214	86%	58	95%	29	91%	7	88%	450	88%
Works complete awaiting building control signoff	7	4%	8	3%	1	2%	0	0%	1	13%	17	3%
Remediation started - cladding removed	12	7%	7	3%	0	0%	1	3%	0	0%	20	4%
Remediation started	0	0%	8	3%	2	3%	1	3%	0	0%	11	2%
Remediation plans in place	1	1%	8	3%	0	0%	0	0%	0	0%	9	2%
Reported an intent to remediate	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Remediation plan unclear	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Total buildings	162	100%	250	100%	61	100%	32	100%	8	100%	513	100%

## ACM_3
Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff - Vacant	0	0	0	0	0
Remediation started - cladding removed - Vacant	0	0	0	0	0
Remediation started - Vacant	0	0	0	0	0
Remediation plans in place - Vacant	0	1	0	0	0
Reported an intent to remediate - Vacant	0	0	0	0	0
Remediation plan unclear - Vacant	0	0	0	0	0
Total vacant buildings	0	1	0	0	0

Remediation Category for occupied buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	7	8	1	0	1
Remediation started - cladding removed	12	7	0	1	0
Remediation started	0	8	2	1	0
Remediation plans in place	1	7	0	0	0
Reported an intent to remediate	0	4	0	0	0
Remediation plan unclear	0	1	0	1	0
Total occupied buildings	20	35	3	3	1

## ACM_4
ACM remediation progress by local authority, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	None	100%	100%
Barnet	6 to 10	1 to 5	Between 50% and 99%	100%
Bedford	1 to 5	None	100%	100%
Birmingham	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Bournemouth, Christchurch and Poole	1 to 5	1 to 5	Between 50% and 99%	100%
Bradford	1 to 5	None	100%	100%
Brent	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	None	100%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	100%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	100%
Hackney	11 to 20	1 to 5	Between 50% and 99%	100%
Hammersmith and Fulham	6 to 10	None	100%	100%
Haringey	6 to 10	None	100%	100%
Harrow	1 to 5	None	100%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	None	100%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Leeds	11 to 20	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	1 to 5	Between 50% and 99%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	None	100%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	None	100%	100%
Newcastle upon Tyne	11 to 20	1 to 5	Between 50% and 99%	100%
Newham	Over 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Norwich	6 to 10	1 to 5	Between 50% and 99%	100%
Nottingham	6 to 10	None	100%	100%
Oldham	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	None	100%	100%
Reading	1 to 5	None	100%	100%
Redbridge	1 to 5	None	100%	100%
Salford	Over 20	11 to 20	Between 50% and 99%	Between 50% and 99%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	1 to 5	Between 50% and 99%	100%
Slough	6 to 10	1 to 5	Between 50% and 99%	100%
Southwark	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	6 to 10	1 to 5	Between 50% and 99%	100%
Sutton	1 to 5	1 to 5	Between 50% and 99%	100%
Tower Hamlets	Over 20	6 to 10	Between 50% and 99%	100%
Trafford	1 to 5	None	100%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	Over 20	1 to 5	Between 50% and 99%	100%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	None	100%	100%
Wolverhampton	1 to 5	None	100%	100%

## ACM_5
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 October 2025
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	38	81%	18	90%	5	100%	2	100%	0	0%	63	85%
Works complete awaiting building control signoff	3	6%	0	0%	0	0%	0	0%	0	0%	3	4%
Remediation started - cladding removed	6	13%	0	0%	0	0%	0	0%	0	0%	6	8%
Remediation started	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	2	10%	0	0%	0	0%	0	0%	2	3%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	20	100%	5	100%	2	100%	0	0%	74	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	72	88%	147	86%	14	93%	13	81%	0	0%	246	86%
Works complete awaiting building control signoff	4	5%	5	3%	0	0%	0	0%	1	100%	10	4%
Remediation started - cladding removed	6	7%	5	3%	0	0%	1	6%	0	0%	12	4%
Remediation started	0	0%	5	3%	1	7%	1	6%	0	0%	7	2%
Plans in place	0	0%	8	5%	0	0%	0	0%	0	0%	8	3%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	1%	0	0%	1	6%	0	0%	2	1%
Total buildings	82	100%	171	100%	15	100%	16	100%	1	100%	285	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	97%	49	83%	39	95%	14	100%	7	100%	141	92%
Works complete awaiting building control signoff	0	0%	3	5%	1	2%	0	0%	0	0%	4	3%
Remediation started - cladding removed	0	0%	2	3%	0	0%	0	0%	0	0%	2	1%
Remediation started	0	0%	3	5%	1	2%	0	0%	0	0%	4	3%
Plans in place	1	3%	0	0%	0	0%	0	0%	0	0%	1	1%
Responded with intent	0	0%	2	3%	0	0%	0	0%	0	0%	2	1%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	33	100%	59	100%	41	100%	14	100%	7	100%	154	100%

## ACM_6
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 October 2025
Back to Contents
This worksheet contains four tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	136	88%	178	95%	52	100%	26	96%	7	88%	399	93%
Works complete awaiting building control signoff	6	4%	1	1%	0	0%	0	0%	1	13%	8	2%
Remediation started - cladding removed	12	8%	3	2%	0	0%	1	4%	0	0%	16	4%
Remediation started	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Plans in place	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	154	100%	187	100%	52	100%	27	100%	8	100%	428	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	137	88%	198	93%	54	100%	28	97%	7	88%	424	92%
Works complete awaiting building control signoff	7	4%	3	1%	0	0%	0	0%	1	13%	11	2%
Remediation started - cladding removed	12	8%	4	2%	0	0%	1	3%	0	0%	17	4%
Remediation started	0	0%	5	2%	0	0%	0	0%	0	0%	5	1%
Plans in place	0	0%	2	1%	0	0%	0	0%	0	0%	2	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	156	100%	212	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	141	88%	207	92%	55	98%	29	94%	7	88%	439	91%
Works complete awaiting building control signoff	7	4%	5	2%	0	0%	0	0%	1	13%	13	3%
Remediation started - cladding removed	12	8%	5	2%	0	0%	1	3%	0	0%	18	4%
Remediation started	0	0%	6	3%	1	2%	1	3%	0	0%	8	2%
Plans in place	0	0%	3	1%	0	0%	0	0%	0	0%	3	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	160	100%	226	100%	56	100%	31	100%	8	100%	481	100%

Identified by 31 December 2022	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	141	88%	211	91%	55	98%	29	94%	7	88%	443	91%
Works complete awaiting building control signoff	7	4%	6	3%	0	0%	0	0%	1	13%	14	3%
Remediation started - cladding removed	12	8%	5	2%	0	0%	1	3%	0	0%	18	4%
Remediation started	0	0%	6	3%	1	2%	1	3%	0	0%	8	2%
Plans in place	0	0%	3	1%	0	0%	0	0%	0	0%	3	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	160	100%	232	100%	56	100%	31	100%	8	100%	487	100%

Identified by 31 December 2023	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	142	88%	211	89%	56	97%	29	94%	7	88%	445	90%
Works complete awaiting building control signoff	7	4%	7	3%	1	2%	0	0%	1	13%	16	3%
Remediation started - cladding removed	12	7%	5	2%	0	0%	1	3%	0	0%	18	4%
Remediation started	0	0%	7	3%	1	2%	1	3%	0	0%	9	2%
Plans in place	0	0%	6	3%	0	0%	0	0%	0	0%	6	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	161	100%	237	100%	58	100%	31	100%	8	100%	495	100%

Identified by 31 December 2024	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	142	88%	213	87%	58	97%	29	94%	7	88%	449	89%
Works complete awaiting building control signoff	7	4%	7	3%	1	2%	0	0%	1	13%	16	3%
Remediation started - cladding removed	12	7%	7	3%	0	0%	1	3%	0	0%	20	4%
Remediation started	0	0%	8	3%	1	2%	1	3%	0	0%	10	2%
Plans in place	1	1%	8	3%	0	0%	0	0%	0	0%	9	2%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	162	100%	244	100%	60	100%	31	100%	8	100%	505	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	142	88%	214	86%	58	95%	29	91%	7	88%	450	88%
Works complete awaiting building control signoff	7	4%	8	3%	1	2%	0	0%	1	13%	17	3%
Remediation started - cladding removed	12	7%	7	3%	0	0%	1	3%	0	0%	20	4%
Remediation started	0	0%	8	3%	2	3%	1	3%	0	0%	11	2%
Plans in place	1	1%	8	3%	0	0%	0	0%	0	0%	9	2%
Responded with intent	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Remediation plan unclear	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Total buildings	162	100%	250	100%	61	100%	32	100%	8	100%	513	100%

## ACM_7
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed total	10,700	18,100	21,300	28,800	32,000
Remediation completed	10,100	17,600	20,800	27,700	30,900
Works complete awaiting building control signoff	600	400	500	1,100	1,100
Yet to complete remediation [note_3]	1,200	2,100	2,300	3,400	3,500
Occupied and yet to complete remediation	1,200	2,100	2,300	3,400	3,500
Total	11,900	20,200	23,700	32,100	35,600

Leasehold dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed total	3,000	18,100	21,300	21,100	24,300
Remediation completed	2,800	17,600	20,800	20,500	23,700
Works complete awaiting building control signoff	200	400	500	600	700
Yet to complete remediation [note_3]	300	2,100	2,300	2,500	2,700
Occupied and yet to complete remediation	300	2,100	2,300	2,500	2,700
Total	3,300	20,200	23,700	23,500	27,000

## ACM_8
ACM remediation progress by sources of funding, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note 4]	Not in social fund	Private: government funded / [note 5]	Private: not government funded
Remediation completed	135	7	96	118
Works complete awaiting building control signoff	4	3	6	2
Remediation started - cladding removed	5	7	7	0
Remediation started	0	0	5	3
Plans in place	0	1	6	2
Responded with intent	0	0	4	0
Remediation plan unclear	0	0	0	1
Total	144	18	124	126

## ACM_9
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	0	0
Applications approved: for pre-contract support	1	0
Full cost application submitted	0	0
Applications approved: for full costs	67	40
TOTAL	68	40

## ACM_10
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	297	235
Expenditure [note_8, note_9]	268	345

## ACM_11
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note 63]	Dec-18 / Number	Dec-19 / Number	Dec-20 / Number	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 / Number	Jun-25 / Number	Jul-25 / Number	Aug-25 / Number	Sep-25 / Number	Oct-25 / Number
Completed Remediation	67	135	216	289	354	357	357	357	359	360	364	367	368	369	369	388	397	399	401	401	405	406	408	411	412	415	416	416	420	423	426	427	428	432	436	437	445	448	450
Works complete awaiting building control signoff			33	64	53	50	51	51	51	52	51	52	54	53	53	34	28	31	32	32	30	30	29	27	30	28	28	28	26	23	20	26	26	25	21	23	17	16	17
Remediation started - cladding removed			48	57	35	36	36	37	38	38	38	36	35	37	38	39	37	35	33	33	33	33	32	33	31	30	31	31	29	29	31	29	29	27	28	25	23	21	20
Remediation started	101	123	120	39	21	21	21	21	19	18	15	15	13	13	13	15	14	15	19	21	19	18	18	17	17	17	15	17	17	18	16	12	11	11	12	12	12	13	11
Remediation plans in place	171	104	32	15	13	12	11	12	12	14	14	15	15	15	15	14	13	14	9	7	8	8	8	8	8	19	20	18	19	18	18	18	18	18	9	9	10	9	9
Reported an intent to remediate	40	78	11	15	9	9	11	10	10	7	7	5	5	3	3	1	2	1	1	1	1	1	1	1	1	1	1	1	1	1	1	0	0	0	0	1	1	1	4
Remediation plan unclear	58	10	2	2	2	3	3	2	1	1	1	1	2	2	4	5	5	1	1	1	2	2	2	2	4	3	3	3	2	2	3	3	4	4	5	4	3	3	2
Total buildings	437	450	462	481	487	488	490	490	490	490	490	491	492	492	495	496	496	496	496	496	498	498	498	499	503	513	514	514	514	514	515	515	516	517	511	511	511	511	513

Remediation Category [note 10]	Dec-18 / Percentage (%)	Dec-19 / Percentage (%)	Dec-20 / Percentage (%)	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)	Sep-24 / Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 / Percentage (%)	Jun-25 / Percentage (%)	Jul-25 / Percentage (%)	Aug-25 / Percentage (%)	Sep-25 / Percentage (%)	Oct-25 / Percentage (%)
Completed Remediation	15%	30%	47%	60%	73%	73%	73%	73%	73%	73%	74%	75%	75%	75%	75%	78%	80%	80%	81%	81%	81%	82%	82%	82%	82%	81%	81%	81%	82%	82%	83%	83%	83%	84%	85%	86%	87%	88%	88%
Works complete awaiting building control signoff			7%	13%	11%	10%	10%	10%	10%	11%	10%	11%	11%	11%	11%	7%	6%	6%	6%	6%	6%	6%	6%	5%	6%	5%	5%	5%	5%	4%	4%	5%	5%	5%	4%	5%	3%	3%	3%
Remediation started - cladding removed			10%	12%	7%	7%	7%	8%	8%	8%	8%	7%	7%	8%	8%	8%	7%	7%	7%	7%	7%	7%	6%	7%	6%	6%	6%	6%	6%	6%	6%	6%	6%	5%	5%	5%	5%	4%	4%
Remediation started	23%	27%	26%	8%	4%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%	3%	3%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%	4%	3%	2%	2%	2%	2%	2%	2%	2%	2%
Remediation plans in place	39%	23%	7%	3%	3%	2%	2%	2%	2%	3%	3%	3%	3%	3%	3%	3%	3%	3%	2%	1%	2%	2%	2%	2%	2%	4%	4%	4%	4%	4%	3%	3%	3%	3%	2%	2%	2%	2%	2%
Reported an intent to remediate	9%	17%	2%	3%	2%	2%	2%	2%	2%	1%	1%	1%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	1%
Remediation plan unclear	13%	2%	0%	0%	0%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	1%	0%	0%	1%	1%	1%	1%	1%	1%	1%	1%	0%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 October 2025
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete
Waking Watch Relief Fund	329	468	212	320	24,700	27.3	170	105	305
Waking Watch Replacement Fund 2022	38	67	25	47	2,200	2.4	216	210	42
Waking Watch Replacement Fund 2023	285	525	205	340	18,900	33.4	373	295	216
Total [note_10]	652	1,060	442	707	45,800	63.1	262	167	563

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 October 2025
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_11]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	9	8	1	0	0	11%	89%	9	8	89%	3%	1.6	200,826	180,147
Bristol	3	2	1	0	0	33%	67%	3	2	67%	1%	0.1	46,256	46,256
Greater London Authority	110	65	29	16	0	26%	59%	171	111	65%	35%	8.3	74,911	64,551
Greater Manchester Combined Authority	25	20	5	0	0	20%	80%	38	33	87%	10%	2.5	75,477	76,928
Leeds	10	9	0	1	0	0%	90%	12	11	92%	3%	1.8	162,466	124,500
Liverpool	18	17	1	0	0	6%	94%	19	18	95%	6%	1.7	94,400	63,784
Newcastle	3	3	0	0	0	0%	100%	3	3	100%	1%	0.4	128,496	163,181
Sheffield	6	5	0	1	0	0%	83%	7	6	86%	2%	0.5	88,753	87,828
MHCLG (1st Tranche)	35	21	14	0	0	40%	60%	55	39	71%	12%	2.7	68,957	65,577
MHCLG (2nd Tranche)	60	27	32	1	0	53%	45%	70	34	49%	11%	3.8	112,303	81,624
MHCLG (3rd Tranche)	50	35	14	1	0	28%	70%	81	55	68%	17%	3.9	70,341	57,389
MHCLG Total	145	83	60	2	0	41%	57%	206	128	62%	40%	10.4	81,066	65,486
Total [note_10]	329	212	97	20	0	29%	64%	468	320	68%	100%	27.3	85,268	67,894

## WWRF_3
Waking Watch Replacement Fund 2022 applications, buildings and approved funding by administering authority, 31 October 2025
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_12]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	2	2	0	0	0	0%	100%	4	4	100%	9%	0.4	89,328	87,683
MHCLG	25	21	1	3	0	4%	84%	46	40	87%	85%	1.8	45,560	26,643
Greater Manchester Combined Authority	11	2	9	0	0	82%	18%	17	3	18%	6%	0.2	65,206	46,743
Leeds	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Liverpool	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Sheffield	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Total [note_10]	38	25	10	3	0	26%	66%	67	47	70%	100%	2.4	50,539	30,209

## WWRF_4
Waking Watch Replacement Fund 2023 applications, buildings and approved funding by administering authority, 31 October 2025
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
MHCLG	285	205	25	28	26	9%	72%	525	340	65%	100%	33.4	96,890	75,980
Total [Note 87]	285	205	25	28	26	9%	72%	525	340	65%	100%	33.4	96,890	75,980

## BSF_1
Remediation status of eligible buildings within BSF by tenure, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note 23][note 60]	Social sector residential (leaseholder) / Number	Social sector residential (leaseholder) / Percentage (%)	Social Sector Financial Viability / Number	Social Sector Financial Viability / Percentage (%)	Social Sector Total / Number	Social Sector Total / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Total residential Number	Total residential Percentage (%)
Remediation complete	80	65%	7	41%	87	62%	234	41%	321	45%
Remediation complete: awaiting building control sign-off	17	14%	2	12%	19	14%	104	18%	123	17%
Remediation started	22	18%	0	0%	22	16%	85	15%	107	15%
Remediation plans in place	3	2%	6	35%	9	6%	125	22%	134	19%
Intent to remediate	1	1%	2	12%	3	2%	20	4%	23	3%
Total buildings [note 10]	123	100%	17	100%	140	100%	568	100%	708	100%

## BSF_2
BSF remediation progress of eligible buildings by region, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note 23]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF / Percentage(%)	Not Started Remediation / Number	Not Started Remediation / Percentage(%)	Started Remediation / Number	Started Remediation / Percentage(%)	Completed Remediation [note_13] / Number	Completed Remediation [note_13] / Percentage(%)	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	95	13%	6	4%	8	7%	81	18%	85%	94%
London	454	64%	146	93%	68	64%	240	54%	53%	68%
East of England	15	2%	0	0%	4	4%	11	2%	73%	100%
East Midlands	13	2%	0	0%	4	4%	9	2%	69%	100%
North East	7	1%	1	1%	2	2%	4	1%	57%	86%
South East	48	7%	0	0%	2	2%	46	10%	96%	100%
South West	21	3%	0	0%	6	6%	15	3%	71%	100%
West Midlands	13	2%	1	1%	3	3%	9	2%	69%	92%
Yorkshire and The Humber	42	6%	3	2%	10	9%	29	7%	69%	93%
Total	708	100%	157	100%	107	100%	444	100%	63%	78%

## BSF_3
BSF number of eligible buildings by funding allocations, expenditure and tenure, England, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data is not available for these variables.
Table BSF_3a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF .
Funding Allocations [note_15][note_56][note_59]	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings [Note 14]	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Funding / (£ millions)
Full Applications Approved	470	1,984	5	5
Pre-Tender Support Allocations	730	304	5	2
Total [note 10]		2,288		7	114	233	2,529

Table BSF_3b: Amount of expenditure from the BSF by tenure.
Expenditure [note_43][note_44][note_59]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	803	1,772	9	7	101	190	913	1,968

## BSF_4
BSF remediation progress of eligible buildings by local authority, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.[note_23, note_24]
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_45]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF yet to be remediated / Number	Completed Remediation / Percentage(%)	Started or Completed Remediation / Percentage(%)
Adur	1-5	0	100%	100%
Ashford	1-5	0	100%	100%
Barking and Dagenham	7	1-5	43%	86%
Basingstoke and Deane	1-5	1-5	Less than 50%	100%
Barnet	1-5	1-5	50-99%	50-99%
Barnsley	1-5	0	100%	100%
Bexley	1-5	1-5	Less than 50%	100%
Birmingham	11	7	36%	100%
Bolton	1-5	0	100%	100%
Bournemouth, Christchurch and Poole	1-5	1-5	50-99%	100%
Bradford	1-5	0	100%	100%
Brent	19	12	37%	63%
Brighton and Hove	1-5	1-5	50-99%	100%
Bristol, City of	10	6	40%	100%
Bromley	6	1-5	50%	50%
Buckinghamshire	1-5	0	100%	100%
Calderdale	1-5	0	100%	100%
Cambridge	1-5	0	100%	100%
Camden	13	8	38%	69%
Chelmsford	1-5	0	100%	100%
Coventry	1-5	1-5	Less than 50%	Less than 50%
Croydon	14	9	36%	57%
Dorset	1-5	0	100%	100%
Ealing	7	1-5	29%	86%
Eastbourne	6	1-5	100%	100%
Enfield	7	1-5	43%	43%
Gateshead	1-5	1-5	50-99%	100%
Greenwich	14	10	29%	64%
Hackney	27	20	26%	78%
Hammersmith and Fulham	8	7	13%	13%
Haringey	1-5	1-5	50-99%	100%
Harrow	1-5	1-5	Less than 50%	100%
Havering	1-5	1-5	50-99%	100%
Hillingdon	8	8	0%	63%
Hounslow	13	10	23%	54%
Ipswich	1-5	1-5	50-99%	100%
Isle of Wight	1-5	0	100%	100%
Islington	18	17	6%	50%
Kensington and Chelsea	11	9	18%	100%
Kirklees	1-5	0	100%	100%
Lambeth	17	8	53%	59%
Lancaster	1-5	0	100%	100%
Leeds	31	15	52%	90%
Leicester	1-5	1-5	Less than 50%	100%
Lewes	1-5	0	100%	100%
Lewisham	7	1-5	57%	57%
Liverpool	21	18	14%	81%
Luton	1-5	1-5	Less than 50%	100%
Manchester	52	21	60%	98%
Mansfield	1-5	1-5	Less than 50%	100%
Medway	1-5	0	100%	100%
Merton	1-5	1-5	50-99%	100%
Milton Keynes	1-5	1-5	50-99%	100%
Newcastle upon Tyne	1-5	1-5	50-99%	50-99%
Newham	69	40	42%	49%
North Somerset	1-5	1-5	Less than 50%	100%
North Yorkshire	1-5	0	100%	100%
Nottingham	9	1-5	78%	100%
Peterborough	1-5	0	100%	100%
Plymouth	1-5	1-5	Less than 50%	100%
Portsmouth	1-5	1-5	50-99%	100%
Preston	1-5	0	100%	100%
Reading	13	1-5	85%	100%
Redbridge	1-5	1-5	50-99%	50-99%
Richmond upon Thames	1-5	0	100%	100%
Rother	1-5	1-5	Less than 50%	100%
Salford	15	1-5	80%	100%
Sevenoaks	1-5	0	100%	100%
Sheffield	1-5	1-5	50-99%	100%
Slough	1-5	0	100%	100%
Southampton	1-5	0	100%	100%
Southend-on-Sea	1-5	0	100%	100%
Southwark	28	19	32%	64%
Stevenage	1-5	1-5	50-99%	100%
Stockport	1-5	0	100%	100%
Sunderland	1-5	1-5	Less than 50%	100%
Surrey Heath	1-5	0	100%	100%
Sutton	1-5	1-5	Less than 50%	50-99%
Swindon	1-5	1-5	Less than 50%	100%
Tower Hamlets	100	61	39%	78%
Trafford	1-5	1-5	Less than 50%	Less than 50%
Wakefield	1-5	0	100%	100%
Wandsworth	12	1-5	67%	92%
Watford	1-5	0	100%	100%
Westminster	19	11	42%	84%
Worcester	1-5	0	100%	100%

## BSF_5
Remediation status of eligible buildings within BSF, time series, England, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_23, note_65, note_73]	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 Number	Jun-25 Number	Jul-25 Number	Aug-25 Number	Sep-25 Number	Oct-25 Number
Remediation complete	0	10	11	11	28	37	37	39	46	49	101	124	135	141	143	155	158	168	176	190	200	210	217	220	223	229	236	238	239	248	274	281	301	309	313	321
Remediation complete: awaiting building control sign-off	18	86	93	97	96	102	107	114	117	122	84	75	77	90	107	106	106	109	111	112	121	116	124	132	134	135	137	141	149	159	137	137	123	121	127	123
Remediation started	150	247	254	268	266	261	263	264	253	254	258	260	268	255	246	237	247	245	235	222	197	191	176	166	164	157	149	144	139	137	133	126	121	115	111	107
Remediation plans in place		322	310	297	291	289	286	278	249	236	199	203	191	198	200	200	189	174	180	152	125	130	136	139	141	143	144	146	149	143	121	118	125	165	162	134
Intent to remediate	813	538	540	542	535	525	532	525	285	277	326	314	303	266	251	240	234	219	209	193	158	158	156	153	147	145	147	147	148	145	107	107	104	64	52	23
Total buildings	981	1203	1208	1215	1216	1214	1225	1220	950	938	968	976	974	950	947	938	934	915	911	869	801	805	809	810	809	809	813	816	824	832	772	769	774	774	765	708

Remediation Category [note_23, note_65, note_73]	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)	Sep-24 Percentage (%)	Oct-24 Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 Percentage (%)	Jun-25 Percentage (%)	Jul-25 Percentage (%)	Aug-25 Percentage (%)	Sep-25 Percentage (%)	Oct-25 Percentage (%)
Remediation complete	0%	1%	1%	1%	2%	3%	3%	3%	5%	5%	10%	13%	14%	15%	15%	17%	17%	18%	19%	22%	25%	26%	27%	27%	28%	28%	29%	29%	29%	30%	35%	37%	39%	40%	41%	45%
Remediation complete: awaiting building control sign-off	2%	7%	8%	8%	8%	8%	9%	9%	12%	13%	9%	8%	8%	9%	11%	11%	11%	12%	12%	13%	15%	14%	15%	16%	17%	17%	17%	17%	18%	19%	18%	18%	16%	16%	17%	17%
Remediation started	15%	21%	21%	22%	22%	21%	21%	22%	27%	27%	27%	27%	28%	27%	26%	25%	26%	27%	26%	26%	25%	24%	22%	20%	20%	19%	18%	18%	17%	16%	17%	16%	16%	15%	15%	15%
Remediation plans in place		27%	26%	24%	24%	24%	23%	23%	26%	25%	21%	21%	20%	21%	21%	21%	20%	19%	20%	17%	16%	16%	17%	17%	17%	18%	18%	18%	18%	17%	16%	15%	16%	21%	21%	19%
Intent to remediate	83%	45%	45%	45%	44%	43%	43%	43%	30%	30%	34%	32%	31%	28%	27%	26%	25%	24%	23%	22%	20%	20%	19%	19%	18%	18%	18%	18%	18%	17%	14%	14%	13%	8%	7%	3%
Total buildings [note_10]	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_1
Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	379	90%	268	44%	50	53%	697	62%
Works complete awaiting building control signoff	12	3%	114	19%	11	12%	137	12%
Remediation started	19	5%	91	15%	27	29%	137	12%
Remediation not started	9	2%	140	23%	6	6%	155	14%
Total [note_74]	419	100%	613	100%	94	100%	1126	100%

## Combined_2
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_42, note_77]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	550	22%	1,396	45%	1,946	35%
Remediation underway	334	14%	425	14%	759	14%
In programme	1,561	64%	1,304	42%	2,865	51%
Total	2,445	100%	3,125	100%	5,570	100%

## Combined_3
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_13, note_17, note_18, note_42, note_70, note_77]	Buildings monitored	In programme / Percentage(%)	Remediation Underway / Percentage(%)	Completed Remediation / Percentage(%)
Barking and Dagenham	51-100	58%	11%	31%
Barnet	51-100	46%	8%	47%
Basingstoke and Deane	11-50	31%	31%	38%
Bexley	11-50	53%	16%	31%
Birmingham	201-400	20%	8%	72%
Bournemouth, Christchurch and Poole	11-50	29%	37%	35%
Bradford	11-50	81%	0%	19%
Brent	51-100	53%	12%	35%
Brighton and Hove	51-100	73%	12%	16%
Bristol, City of	101-200	58%	18%	24%
Bromley	11-50	65%	12%	24%
Buckinghamshire	11-50	64%	27%	9%
Cambridge	11-50	76%	10%	14%
Camden	51-100	48%	22%	30%
Chelmsford	11-50	19%	5%	76%
Coventry	11-50	100%	0%	0%
Croydon	51-100	49%	12%	39%
Dacorum	11-50	45%	40%	15%
Dartford	11-50	23%	14%	64%
Ealing	51-100	39%	14%	46%
Eastbourne	11-50	43%	14%	43%
Elmbridge	11-50	55%	27%	18%
Enfield	11-50	75%	0%	25%
Gateshead	11-50	57%	0%	43%
Greenwich	101-200	48%	18%	34%
Hackney	201-400	65%	7%	28%
Hammersmith and Fulham	51-100	72%	5%	23%
Haringey	51-100	34%	12%	54%
Harrow	11-50	57%	9%	35%
Hastings	11-50	93%	0%	7%
Havering	11-50	47%	5%	47%
Hertsmere	11-50	35%	45%	20%
Hillingdon	11-50	64%	25%	11%
Hounslow	51-100	49%	2%	48%
Ipswich	11-50	54%	21%	25%
Islington	101-200	66%	13%	21%
Kensington and Chelsea	51-100	60%	19%	21%
Kirklees	11-50	56%	22%	22%
Lambeth	101-200	63%	12%	26%
Leeds	51-100	37%	25%	37%
Leicester	11-50	58%	6%	35%
Lewisham	101-200	60%	7%	33%
Liverpool	101-200	53%	14%	33%
Maidstone	11-50	57%	17%	26%
Manchester	201-400	45%	9%	46%
Medway	11-50	33%	7%	60%
Merton	11-50	59%	12%	29%
Milton Keynes	11-50	52%	33%	15%
Newcastle upon Tyne	51-100	40%	13%	47%
Newham	101-200	41%	20%	38%
North Somerset	11-50	62%	24%	14%
Norwich	11-50	48%	3%	48%
Nottingham	11-50	50%	10%	40%
Plymouth	11-50	47%	12%	41%
Portsmouth	51-100	20%	33%	47%
Reading	11-50	38%	13%	50%
Redbridge	11-50	74%	0%	26%
Richmond upon Thames	11-50	24%	18%	59%
Salford	51-100	23%	29%	49%
Sheffield	11-50	53%	8%	39%
Slough	11-50	52%	7%	41%
Solihull	11-50	70%	0%	30%
Southampton	101-200	54%	14%	32%
Southwark	201-400	59%	5%	37%
Stevenage	11-50	75%	6%	19%
Stockport	11-50	89%	5%	5%
Stoke-on-Trent	11-50	64%	21%	14%
Sunderland	11-50	43%	7%	50%
Sutton	11-50	32%	21%	47%
Tower Hamlets	Over 400	49%	18%	32%
Trafford	11-50	63%	6%	31%
Waltham Forest	51-100	60%	10%	30%
Wandsworth	101-200	59%	11%	30%
Watford	11-50	54%	23%	23%
West Berkshire	11-50	55%	0%	45%
West Northamptonshire	11-50	46%	8%	46%
Westminster	51-100	44%	7%	49%
Woking	11-50	39%	57%	4%
Wolverhampton	11-50	75%	0%	25%

## Combined_4
Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings [note_10, note_13, note_17, note_18, note_42, note_77]	Estimated dwellings in 11-18m buildings	Estimated dwellings in 18m+ buildings	Estimated Total dwellings
Remediation complete (including those awaiting building control signoff)	17,000	97,000	114,000
Remediation underway	11,000	35,000	46,000
In programme	46,000	86,000	132,000
Total	75,000	218,000	292,000

## Combined_5
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by tenure, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_42, note_77]	Private / Number	Private / Percentage (%)	Social / Number	Social / Percentage (%)	Other [note 57] / Number	Other / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	803	30%	1048	37%	95	95%	1,946	35%
Remediation underway	487	18%	268	9%	4	4%	759	14%
In programme	1,352	51%	1,512	53%	1	1%	2,865	51%
Total	2,642	100%	2,828	100%	100	100%	5,570	100%

## Combined_6
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, time series, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_13,note_16, note_17, note_18, note_42, note_64, note_77]	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 / Number	Jun-25 / Number	Jul-25 / Number	Aug-25 / Number	Sep-25 / Number	Oct-25 / Number
Remediation complete (including those awaiting building control signoff)	448	456	461	477	492	499	508	523	535	544	703	777	797	815	863	976	991	1,088	1,332	1,350	1,392	1,412	1,436	1,463	1,472	1,482	1,619	1,637	1,652	1,754	1,767	1,780	1,927	1,935	1,946
Remediation underway	301	308	322	321	317	319	320	308	304	311	809	826	811	871	952	992	984	978	969	949	985	1,000	983	934	931	928	809	822	825	728	723	722	750	759	759
In programme	853	844	834	820	806	806	791	519	501	509	2,285	2,221	2,231	2,286	2,277	2,361	2,361	2,308	2,312	2,331	2,394	2,409	2,415	2,601	2,608	2,615	2,586	2,572	2,575	2,694	2,700	2,712	2,877	2,864	2,865
Total	1,602	1,608	1,617	1,618	1,615	1,624	1,619	1,350	1,340	1,364	3,797	3,824	3,839	3,972	4,092	4,329	4,336	4,374	4,613	4,630	4,771	4,821	4,834	4,998	5,011	5,025	5,014	5,031	5,052	5,176	5,190	5,214	5,554	5,558	5,570

Remediation Category [note_13, note_16, note_17, note_18, note_42, note_64]	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)	Sep-24 / Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 / Percentage (%)	Jun-25 / Percentage (%)	Jul-25 / Percentage (%)	Aug-25 / Percentage (%)	Sep-25 / Percentage (%)	Oct-25 / Percentage (%)
Remediation complete (including those awaiting building control signoff)	28%	28%	29%	29%	30%	31%	31%	39%	40%	40%	19%	20%	21%	21%	21%	23%	23%	25%	29%	29%	29%	29%	30%	29%	29%	29%	32%	33%	33%	34%	34%	34%	35%	35%	35%
Remediation underway	19%	19%	20%	20%	20%	20%	20%	23%	23%	23%	21%	22%	21%	22%	23%	23%	23%	22%	21%	20%	21%	21%	20%	19%	19%	18%	16%	16%	16%	14%	14%	14%	14%	14%	14%
In programme	53%	52%	52%	51%	50%	50%	49%	38%	37%	37%	60%	58%	58%	58%	56%	55%	54%	53%	50%	50%	50%	50%	50%	52%	52%	52%	52%	51%	51%	52%	52%	52%	52%	52%	51%
Total	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_7
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by region, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_13, note_16, note_17, note_18, note_42, note_77]	Total buildings monitored / Number	Total buildings monitored / Percentage(%)	In programme / Number	In programme / Percentage(%)	Remediation underway / Number	Remediation underway / Percentage(%)	Remediation complete (including those awaiting building control signoff) / Number	Remediation complete (including those awaiting building control signoff) / Percentage(%)	Buildings monitored that have completed Remediation / Percentage (%)	Buildings monitored that have started or completed remediation / Percentage (%)
North West	531	10%	248	9%	73	10%	210	11%	40%	53%
London	3,142	56%	1,705	60%	378	50%	1,059	54%	34%	46%
East of England	283	5%	149	5%	51	7%	83	4%	29%	47%
East Midlands	107	2%	58	2%	14	2%	35	2%	33%	46%
North East	94	2%	40	1%	9	1%	45	2%	48%	57%
South East	643	12%	317	11%	118	16%	208	11%	32%	51%
South West	288	5%	153	5%	61	8%	74	4%	26%	47%
West Midlands	297	5%	108	4%	21	3%	168	9%	57%	64%
Yorkshire and The Humber	185	3%	87	3%	34	4%	64	3%	35%	53%
Total	5,570	100%	2,865	100%	759	100%	1,946	100%	35%	49%

## Combined_8
Remediation progress for unique buildings being remediated or mitigated as part of a government funded scheme, 11 metres and over in height, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_77, note_78]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	54	10%	819	56%	873	43%
Remediation underway	101	18%	174	12%	275	14%
In programme	403	72%	458	32%	861	43%
Total	558	100%	1,451	100%	2,009	100%

## CSS_1
Application status of buildings within the CSS, England, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Pre - eligible buildings [note_47, note_48]	Number	Percentage (%)
Pre - application	1571	56%
Live application	1216	44%
Total pre-eligible buildings	2,787	100%

Eligible buildings [note_13]	Number	Percentage (%)
Works not started	732	80%
Works started	120	13%
Works completed	60	7%
Total eligible buildings	912	100%

## CSS_2
CSS remediation progress by region, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_48, note_13]	Eligible Buildings in the CSS / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible CSS buildings that have started or completed remediation / Percentage (%)
North West	124	99	20	5	4%	20%
London	438	348	53	37	8%	21%
East of England	60	49	8	3	5%	18%
East Midlands	35	28	6	1	3%	20%
North East	15	12	3	0	0%	20%
South East	86	67	12	7	8%	22%
South West	75	64	8	3	4%	15%
West Midlands	23	22	1	0	0%	4%
Yorkshire and The Humber	52	42	7	3	6%	19%
Northern Ireland	4	1	2	1	25%	75%
Total	912	732	120	60	7%	20%

## CSS_3
CSS remediation progress by height, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48, note_13]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)
Remediation complete	54	10%	6	2%
Remediation started	101	18%	19	5%
In programme	405	72%	327	93%
Total buildings	560	100%	352	100%

## CSS_4
CSS remediation progress by tenure, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48, note_13]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	26	8%	34	6%
Remediation started	34	11%	86	15%
In programme	262	81%	470	80%
Total buildings	322	100%	590	100%

## CSS_5
CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Table CSS_5a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the CSS
Funding Allocations	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Funding / (£ millions)
Works Package Approved	178	702.0	52	63.3	765.3
Pre-Tender Support Allocations	497	154.9	156	48.2	203.1
Total [note 10]	517	856.9	198	111.5	968.4

Table CSS_5b: Amount of expenditure from the CSS by tenure
Expenditure [note_44]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	501	266.3	189	85.9	690	352.3

## CSS_6
CSS remediation progress, time series, England, 31 October 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings unless otherwise stated or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_48, note_13]	Oct-23 Number	Nov-23 Number	Dec-23 Number	Jan-24 Number	Feb-24 Number	Mar-24 Number	Apr-24 Number	May-24 Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 Number	Jan-25 Number	Feb-25 Number	Mar-25 Number	Apr-25 Number	May-25 Number	Jun-25 Number	Jul-25 Number	Aug-25 Number	Sep-25 Number	Oct-25 Number
Remediation complete	0	0	0	0	0	0	0	0	0	0	0	0	14	16	17	20	24	31	33	38	43	49	53	55	60
Remediation started	0	0	0	0	1	2	2	2	6	8	10	22	17	30	36	45	56	82	85	85	87	93	102	114	120
In programme	48	75	104	127	151	168	199	222	282	371	395	410	429	446	472	491	510	504	538	609	623	640	651	667	732
Total buildings	48	75	104	127	152	170	201	224	288	379	405	432	460	492	525	556	590	617	656	732	753	782	806	836	912

Remediation Category [note_48, note_13]	Oct-23 Percentage (%)	Nov-23 Percentage (%)	Dec-23 Percentage (%)	Jan-24 Percentage (%)	Feb-24 Percentage (%)	Mar-24 Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)	Sep-24 Percentage (%)	Oct-24 Percentage (%)	Nov-24 / Percentage (%)	Dec-24 Percentage (%)	Jan-25 Percentage (%)	Feb-25 Percentage (%)	Mar-25 Percentage (%)	Apr-25 Percentage (%)	May-25 Percentage (%)	Jun-25 Percentage (%)	Jul-25 Percentage (%)	Aug-25 Percentage (%)	Sep-25 Percentage (%)	Oct-25 Percentage (%)
Remediation complete	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	3%	3%	3%	4%	4%	5%	5%	5%	6%	6%	7%	7%	7%
Remediation started	0%	0%	0%	0%	1%	1%	1%	1%	2%	2%	2%	5%	4%	6%	7%	8%	9%	13%	13%	12%	12%	12%	13%	14%	13%
In programme	100%	100%	100%	100%	99%	99%	99%	99%	98%	98%	98%	95%	93%	91%	90%	88%	86%	82%	82%	83%	83%	82%	81%	80%	80%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Developer_1
Remediation status of buildings requiring works under the developer remediation contract by height group, England, 30 September 2025
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - All Defect Types [Note 25, Note 26, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	205	17%	233	21%	438	18%
Remediation complete - awaiting building control sign-off	42	3%	57	5%	99	4%
Remediation started	195	16%	302	27%	497	21%
Remediation not Started - Plans in Place	198	16%	180	16%	378	16%
Remediation not Started - No Plans in Place	602	48%	364	32%	966	41%
Total	1242	100%	1136	100%	2,378	100%

Remediation Category - Cladding Defects [Note 25, Note 26, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	162	19%	216	23%	378	21%
Remediation complete - awaiting building control sign-off	30	4%	55	6%	85	5%
Remediation started	143	17%	258	28%	401	23%
Remediation not Started - Plans in Place	156	19%	167	18%	323	18%
Remediation not Started - No Plans in Place	352	42%	225	24%	577	33%
Total	843	100%	921	100%	1,764	100%

Remediation Category - Self-reported Information, All Defect Types [Note 25, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	202	16%	173	17%	375	17%
Remediation complete - awaiting building control sign-off	42	3%	43	4%	85	4%
Remediation started	192	16%	269	27%	461	21%
Remediation not Started - Plans in Place	198	16%	179	18%	377	17%
Remediation not Started - No Plans in Place	597	48%	351	35%	948	42%
Total	1231	100%	1015	100%	2,246	100%

Remediation Category - BSF Transfers [Note 25, Note 26, Note 29, Note 61]	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	44	10%
Remediation complete - awaiting building control sign-off	16	4%
Remediation started	133	30%
Remediation not Started - Plans in Place	106	24%
Remediation not Started - No Plans in Place	80	18%
No life-critical fire-safety defects reported	69	15%
Total buildings	448	100%

## Developer_2
Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for estimated cost of buildings identified as requiring works under the Developer Remediation Contract in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Cost Category [Note 29, Note 33]	11-18m / (£ millions)	18m+ / (£ millions)	Total / (£ millions)
Total estimated cost of works	1,410	3,241	4,651

## Developer_3
Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note 29]	Number of buildings developed or refurbished by the developer covered by the contract	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme) [Note 28]	Number of buildings found to require remediation, which will be remediated by the developer directly [Note 31]	Number of buildings without a determination [Note 32]	Number of buildings where no remediation is required	Number of buildings with no reported defects under clauses 5.4d(i) or 5.4d(ii) of the developer remediation contract	Percentage of buildings for which the developer has determined whether remediation is required
Total (all developers)	4655	4538	2246	366	1806	120	92%
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	60	51	30	21	0	0	59%
Ballymore Limited	85	69	13	0	17	39	100%
Barratt Redrow PLC	836	821	500	195	126	0	76%
Bellway PLC	437	420	355	0	65	0	100%
The Berkeley Group Holdings PLC	821	810	72	14	724	0	98%
Bewley Group Limited	9	7	3	1	3	0	86%
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	16	16	4	0	12	0	100%
Cala Group (Holdings) Limited	22	22	20	0	2	0	100%
Canary Wharf Group PLC	13	13	0	4	9	0	69%
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	8	8	0	0	8	0	100%
Crest Nicholson Holdings PLC	293	292	268	2	22	0	99%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	21	21	19	0	2	0	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	121	121	66	0	48	7	100%
Frasers Property (UK) Ltd	16	11	5	3	3	0	73%
Galliard Group Limited	101	101	29	7	65	0	93%
MJ Gleeson PLC	17	16	13	3	0	0	81%
Grosvenor Developments Limited	21	21	12	1	0	8	95%
Hill Holdings Limited	90	90	25	14	2	49	84%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	7	7	5	0	2	0	100%
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	42	39	9	27	3	0	31%
Lendlease Europe Holdings Limited	89	88	42	0	46	0	100%
Pegasus Homes (formerly Lifestory Group)	18	18	1	0	17	0	100%
London Square Development (Holdings) Limited	40	40	39	0	1	0	100%
Miller Homes Limited	39	39	31	0	4	4	100%
Morris Homes Group Limited	6	6	2	0	4	0	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	120	113	23	0	90	0	100%
Persimmon Public Limited Company	71	70	56	0	13	1	100%
Regal Holdco Limited (parent company for Regal London)	16	16	4	0	12	0	100%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	25	22	16	0	6	0	100%
Sorbon Group Limited (parent company for Shanly Homes)	26	26	20	0	6	0	100%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	13	10	6	0	0	4	100%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	439	431	224	59	148	0	86%
Telford Homes Limited	144	143	91	1	51	0	99%
Tilia Homes Limited	8	8	8	0	0	0	100%
Vistry Group PLC	300	294	135	3	156	0	99%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	88	87	27	0	60	0	100%
McCarthy & Stone Limited	62	62	12	2	48	0	97%
Seven Capital PLC	21	21	19	0	0	2	100%
Wates Group Limited	24	23	11	3	9	0	87%
Watkin Jones PLC	14	14	7	6	1	0	57%
Bouygues (UK) Limited	35	31	18	0	13	0	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	21	20	6	0	8	6	100%

## Developer_4
Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Remediation Status
		Buildings being remediated by the developer directly where remediation has...
		…not yet started		... started or completed		... started		...completed, awaiting building control sign-off		...completed
Developer [Note 25, Note 29]	Number of buildings found to require remediation, which will be remediated by the developer directly [Note 31]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total (all developers)	2246	1325	59%	921	41%	461	21%	85	4%	375	17%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	30	27	90%	3	10%	1	3%	0	0%	2	7%
Ballymore Limited	13	2	15%	11	85%	0	0%	0	0%	11	85%
Barratt Redrow PLC	500	371	74%	129	26%	44	9%	45	9%	40	8%
Bellway PLC	355	231	65%	124	35%	81	23%	0	0%	43	12%
The Berkeley Group Holdings PLC	72	23	32%	49	68%	8	11%	0	0%	41	57%
Bewley Group Limited	3	0	0%	3	100%	2	67%	0	0%	1	33%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	4	2	50%	2	50%	2	50%	0	0%	0	0%
Cala Group (Holdings) Limited	20	9	45%	11	55%	7	35%	0	0%	4	20%
Canary Wharf Group PLC	0	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	268	148	55%	120	45%	115	43%	4	1%	1	0%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	19	1	5%	18	95%	18	95%	0	0%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	66	25	38%	41	62%	8	12%	0	0%	33	50%
Frasers Property (UK) Ltd	5	0	0%	5	100%	0	0%	1	20%	4	80%
Galliard Group Limited	29	13	45%	16	55%	0	0%	0	0%	16	55%
MJ Gleeson PLC	13	8	62%	5	38%	3	23%	0	0%	2	15%
Grosvenor Developments Limited	12	4	33%	8	67%	7	58%	0	0%	1	8%
Hill Holdings Limited	25	12	48%	13	52%	2	8%	0	0%	11	44%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	5	3	60%	2	40%	0	0%	2	40%	0	0%
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	9	3	33%	6	67%	2	22%	0	0%	4	44%
Lendlease Europe Holdings Limited	42	31	74%	11	26%	8	19%	0	0%	3	7%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%	0	0%	0	0%
London Square Development (Holdings) Limited	39	0	0%	39	100%	39	100%	0	0%	0	0%
Miller Homes Limited	31	11	35%	20	65%	8	26%	5	16%	7	23%
Morris Homes Group Limited	2	0	0%	2	100%	1	50%	0	0%	1	50%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	23	9	39%	14	61%	2	9%	1	4%	11	48%
Persimmon Public Limited Company	56	24	43%	32	57%	24	43%	0	0%	8	14%
Regal Holdco Limited (parent company for Regal London)	4	3	75%	1	25%	0	0%	0	0%	1	25%
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	16	1	6%	15	94%	1	6%	0	0%	14	88%
Sorbon Group Limited (parent company for Shanly Homes)	20	8	40%	12	60%	6	30%	0	0%	6	30%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	6	4	67%	2	33%	0	0%	0	0%	2	33%
Story Homes Limited	-	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	224	135	60%	89	40%	28	13%	10	4%	51	23%
Telford Homes Limited	91	90	99%	1	1%	1	1%	0	0%	0	0%
Tilia Homes Limited	8	1	13%	7	88%	7	88%	0	0%	0	0%
Vistry Group PLC	135	79	59%	56	41%	10	7%	15	11%	31	23%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	27	1	4%	26	96%	20	74%	0	0%	6	22%
McCarthy & Stone Limited	12	0	0%	12	100%	3	25%	2	17%	7	58%
Seven Capital PLC	19	19	100%	0	0%	0	0%	0	0%	0	0%
Wates Group Limited	11	4	36%	7	64%	1	9%	0	0%	6	55%
Watkin Jones PLC	7	7	100%	0	0%	0	0%	0	0%	0	0%
Bouygues (UK) Limited	18	11	61%	7	39%	1	6%	0	0%	6	33%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	6	4	67%	2	33%	1	17%	0	0%	1	17%

## Developer_5
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings that require remediation by the developer which have not yet started, with a start date…

		…within the next 12 months		…after the next 12 months		…start date unclear
Developer [Note 27, Note 29]	Number of buildings being remediated by the developer directly where remediation has not started	Number	Percentage‎	Number	Percentage	Number	Percentage
Total (all developers)	1325	558	42%	172	13%	595	45%
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	27	0	0%	0	0%	27	100%
Ballymore Limited	2	2	100%	0	0%	0	0%
Barratt Redrow PLC	371	183	49%	100	27%	88	24%
Bellway PLC	231	54	23%	5	2%	172	74%
The Berkeley Group Holdings PLC	23	22	96%	1	4%	0	0%
Bewley Group Limited	0	0	-	0	-	0	-
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	2	0	0%	0	0%	2	100%
Cala Group (Holdings) Limited	9	6	67%	0	0%	3	33%
Canary Wharf Group PLC	0	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-
Crest Nicholson Holdings PLC	148	15	10%	0	0%	133	90%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	1	0	0%	1	100%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	25	22	88%	1	4%	2	8%
Frasers Property (UK) Ltd	0	0	-	0	-	0	-
Galliard Group Limited	13	8	62%	4	31%	1	8%
MJ Gleeson PLC	8	7	88%	0	0%	1	13%
Grosvenor Developments Limited	4	4	100%	0	0%	0	0%
Hill Holdings Limited	12	10	83%	0	0%	2	17%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0%	0	0%	3	100%
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	3	0	0%	0	0%	3	100%
Lendlease Europe Holdings Limited	31	17	55%	2	6%	12	39%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%
London Square Development (Holdings) Limited	0	0	-	0	-	0	-
Miller Homes Limited	11	8	73%	0	0%	3	27%
Morris Homes Group Limited	0	0	-	0	-	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	9	2	22%	0	0%	7	78%
Persimmon Public Limited Company	24	24	100%	0	0%	0	0%
Regal Holdco Limited (parent company for Regal London)	3	0	0%	0	0%	3	100%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	1	1	100%	0	0%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	8	1	13%	0	0%	7	88%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0%	0	0%	4	100%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	135	80	59%	46	34%	9	7%
Telford Homes Limited	90	38	42%	7	8%	45	50%
Tilia Homes Limited	1	0	0%	0	0%	1	100%
Vistry Group PLC	79	37	47%	3	4%	39	49%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	1	0	0%	0	0%	1	100%
McCarthy & Stone Limited	0	0	-	0	-	0	-
Seven Capital PLC	19	5	26%	0	0%	14	74%
Wates Group Limited	4	4	100%	0	0%	0	0%
Watkin Jones PLC	7	4	57%	2	29%	1	14%
Bouygues (UK) Limited	11	0	0%	0	0%	11	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	3	75%	0	0%	1	25%

## Developer_6
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which have not yet started, start profiles by financial year...

Developer [Note 27, Note 29]	Number of buildings being remediated by the developer directly where remediation has not started	2024-2025	2025-2026	2026-2027	2027-2028	2028-29	2029-30	.. no start date provided
Total (all developers)	1325	17	459	286	22	15	3	523
Abbey Developments Limited	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	27	0	1	0	0	0	0	26
Ballymore Limited	2	0	1	1	0	0	0	0
Barratt Redrow PLC	371	0	97	181	5	0	0	88
Bellway PLC	231	0	30	28	1	0	0	172
The Berkeley Group Holdings PLC	23	0	16	7	0	0	0	0
Bewley Group Limited	0	0	0	0	0	0	0	0
Bloor Investments Limited	-	-	-	-	-	-	-	-
The British Land Company PLC	2	0	0	0	0	0	0	2
Cala Group (Holdings) Limited	9	0	9	0	0	0	0	0
Canary Wharf Group PLC	0	0	0	0	0	0	0	0
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	148	13	21	0	0	0	0	114
Croudace Homes Group Limited	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	1	0	0	0	1	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-
Fairview Holdings Limited	25	1	18	5	0	0	0	1
Frasers Property (UK) Ltd	0	0	0	0	0	0	0	0
Galliard Group Limited	13	0	9	2	2	0	0	0
MJ Gleeson PLC	8	0	7	0	0	0	0	1
Grosvenor Developments Limited	4	0	4	0	0	0	0	0
Hill Holdings Limited	12	0	10	0	0	0	0	2
Hopkins Home Group Limited	-	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0	0	0	0	0	3
Keepmoat Limited	-	-	-	-	-	-	-	-
Land Securities Group PLC	3	0	0	0	0	0	0	3
Lendlease Europe Holdings Limited	31	0	26	4	0	0	0	1
Pegasus Homes (formerly Lifestory Group)	1	0	1	0	0	0	0	0
London Square Development (Holdings) Limited	0	0	0	0	0	0	0	0
Miller Homes Limited	11	0	11	0	0	0	0	0
Morris Homes Group Limited	0	0	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	9	0	1	1	0	0	0	7
Persimmon Public Limited Company	24	0	24	0	0	0	0	0
Regal Holdco Limited (parent company for Regal London)	3	0	0	0	0	0	0	3
Rowland Group Limited	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	1	0	1	0	0	0	0	0
Sorbon Group Limited (parent company for Shanly Homes)	8	0	6	0	0	0	0	2
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0	0	0	0	0	4
Story Homes Limited	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	135	0	66	29	13	15	3	9
Telford Homes Limited	90	2	35	17	0	0	0	36
Tilia Homes Limited	1	0	0	0	0	0	0	1
Vistry Group PLC	79	1	48	9	0	0	0	21
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-
Weston Group PLC	1	0	1	0	0	0	0	0
McCarthy & Stone Limited	0	0	0	0	0	0	0	0
Seven Capital PLC	19	0	5	0	0	0	0	14
Wates Group Limited	4	0	4	0	0	0	0	0
Watkin Jones PLC	7	0	4	2	0	0	0	1
Bouygues (UK) Limited	11	0	0	0	0	0	0	11
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	0	3	0	0	0	0	1

## Developer_7
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings that require remediation by the developer which have not yet completed, with a completion date…
		…within the next 12 months		…after the next 12 months		…completion date unclear
Developer [Note 29, Note 55]	Number of buildings being remediated by the developer directly where remediation has not yet completed	Number	Percentage‎	Number	Percentage	Number2	Pecentage
Total (all developers)	1786	344	19%	750	42%	692	39%
Abbey Developments Limited	0	0	-	0	-	0	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	28	0	0%	0	0%	28	100%
Ballymore Limited	2	0	0%	2	100%	0	0%
Barratt Redrow PLC	415	37	9%	283	68%	95	23%
Bellway PLC	312	22	7%	88	28%	202	65%
The Berkeley Group Holdings PLC	31	12	39%	12	39%	7	23%
Bewley Group Limited	2	0	0%	0	0%	2	100%
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	4	0	0%	0	0%	4	100%
Cala Group (Holdings) Limited	16	10	63%	2	13%	4	25%
Canary Wharf Group PLC	0	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-
Crest Nicholson Holdings PLC	263	64	24%	43	16%	156	59%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	19	3	16%	16	84%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	33	13	39%	14	42%	6	18%
Frasers Property (UK) Ltd	0	0	-	0	-	0	-
Galliard Group Limited	13	3	23%	10	77%	0	0%
MJ Gleeson PLC	11	9	82%	0	0%	2	18%
Grosvenor Developments Limited	11	2	18%	4	36%	5	45%
Hill Holdings Limited	14	8	57%	3	21%	3	21%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0%	0	0%	3	100%
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	5	0	0%	0	0%	5	100%
Lendlease Europe Holdings Limited	39	18	46%	18	46%	3	8%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%
London Square Development (Holdings) Limited	39	39	100%	0	0%	0	0%
Miller Homes Limited	19	4	21%	5	26%	10	53%
Morris Homes Group Limited	1	1	100%	0	0%	0	0%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	11	0	0%	2	18%	9	82%
Persimmon Public Limited Company	48	15	31%	32	67%	1	2%
Regal Holdco Limited (parent company for Regal London)	3	0	0%	0	0%	3	100%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	1	50%	1	50%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	14	11	79%	0	0%	3	21%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0%	0	0%	4	100%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	163	24	15%	126	77%	13	8%
Telford Homes Limited	91	6	7%	47	52%	38	42%
Tilia Homes Limited	8	2	25%	1	13%	5	63%
Vistry Group PLC	89	26	29%	38	43%	25	28%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	21	1	5%	0	0%	20	95%
McCarthy & Stone Limited	3	0	0%	0	0%	3	100%
Seven Capital PLC	19	1	5%	0	0%	18	95%
Wates Group Limited	5	4	80%	0	0%	1	20%
Watkin Jones PLC	7	3	43%	3	43%	1	14%
Bouygues (UK) Limited	12	1	8%	0	0%	11	92%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	5	3	60%	0	0%	2	40%

## Developer_8
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which have not yet completed, completion profiles by financial year...					Buildings which have not yet completed, with...

Developer [Note 29, Note 55]	Number of buildings being remediated by the developer directly where remediation has not yet completed	2024-2025	2025-2026	2026-2027	2027-2028	2028-2029	2029-2030	.. no completiondate provided	... completion date prior to 2024-2025
Total (all developers)	1786	37	284	431	335	81	6	602	10
Abbey Developments Limited	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	28	0	1	0	0	0	0	26	1
Ballymore Limited	2	0	0	0	2	0	0	0	0
Barratt Redrow PLC	415	2	23	122	146	29	0	93	0
Bellway PLC	312	5	24	35	42	14	1	186	5
The Berkeley Group Holdings PLC	31	3	6	15	0	3	0	4	0
Bewley Group Limited	2	0	2	0	0	0	0	0	0
Bloor Investments Limited	-	-	-	-	-	-	-	-	-
The British Land Company PLC	4	0	0	0	0	0	0	4	0
Cala Group (Holdings) Limited	16	0	13	3	0	0	0	0	0
Canary Wharf Group PLC	0	0	0	0	0	0	0	0	0
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	263	9	50	55	9	0	0	138	2
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	19	0	1	5	8	5	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	33	3	12	17	0	0	0	1	0
Frasers Property (UK) Ltd	0	0	0	0	0	0	0	0	0
Galliard Group Limited	13	0	2	3	6	2	0	0	0
MJ Gleeson PLC	11	1	8	1	0	0	0	1	0
Grosvenor Developments Limited	11	0	0	6	0	0	0	5	0
Hill Holdings Limited	14	0	4	7	0	0	0	3	0
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0	0	0	0	0	3	0
Keepmoat Limited	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	5	0	0	0	0	0	0	5	0
Lendlease Europe Holdings Limited	39	0	14	18	6	0	0	1	0
Pegasus Homes (formerly Lifestory Group)	1	0	1	0	0	0	0	0	0
London Square Development (Holdings) Limited	39	0	39	0	0	0	0	0	0
Miller Homes Limited	19	3	5	5	1	0	0	5	0
Morris Homes Group Limited	1	0	1	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	11	0	0	1	1	0	0	9	0
Persimmon Public Limited Company	48	0	8	29	11	0	0	0	0
Regal Holdco Limited (parent company for Regal London)	3	0	0	0	0	0	0	3	0
Rowland Group Limited	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	0	0	2	0	0	0	0	0
Sorbon Group Limited (parent company for Shanly Homes)	14	1	11	0	0	0	0	2	0
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0	0	0	0	0	4	0
Story Homes Limited	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	163	0	14	58	48	28	5	10	0
Telford Homes Limited	91	0	3	16	34	0	0	38	0
Tilia Homes Limited	8	0	4	1	0	0	0	3	0
Vistry Group PLC	89	0	20	26	19	0	0	24	0
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-
Weston Group PLC	21	9	10	1	0	0	0	1	0
McCarthy & Stone Limited	3	1	0	0	0	0	0	0	2
Seven Capital PLC	19	0	0	1	0	0	0	18	0
Wates Group Limited	5	0	1	3	0	0	0	1	0
Watkin Jones PLC	7	0	3	1	2	0	0	1	0
Bouygues (UK) Limited	12	0	1	0	0	0	0	11	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	5	0	3	0	0	0	0	2	0

## Developer_9
Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Buildings where the developer or 'responsible entity' has engaged with the leaseholders, freeholders, residents, occupiers and other users regarding works for buildings being remediated directly by the developer, excluding completed buildings, by...					Number of buildings being remediated by the developers, excluding completed buildings	Sum of communication
	... the Responsible Entity		... directly		... directly and by the Responsible Entity		... unconfirmed how
Developer [Note 29]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total (all developers)	1042	58%	57	3%	152	9%	124	7%	1786	77%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0%	0	0%	0	0%	15	54%	28	54%
Ballymore Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Barratt Redrow PLC	164	40%	14	3%	11	3%	108	26%	415	72%
Bellway PLC	303	97%	1	0%	0	0%	0	0%	312	97%
The Berkeley Group Holdings PLC	27	87%	0	0%	4	13%	0	0%	31	100%
Bewley Group Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	2	50%	0	0%	0	0%	0	0%	4	50%
Cala Group (Holdings) Limited	16	100%	0	0%	0	0%	0	0%	16	100%
Canary Wharf Group PLC	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	118	45%	0	0%	0	0%	1	0%	263	45%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	0	0%	19	100%	0	0%	19	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	2	6%	2	6%	29	88%	0	0%	33	100%
Frasers Property (UK) Ltd	0	-	0	-	0	-	0	-	0	-
Galliard Group Limited	11	85%	0	0%	2	15%	0	0%	13	100%
MJ Gleeson PLC	6	55%	2	18%	3	27%	0	0%	11	100%
Grosvenor Developments Limited	0	0%	6	55%	5	45%	0	0%	11	100%
Hill Holdings Limited	3	21%	0	0%	4	29%	0	0%	14	50%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	3	100%	0	0%	0	0%	0	0%	3	100%
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	0	0%	0	0%	0	0%	0	0%	5	0%
Lendlease Europe Holdings Limited	0	0%	0	0%	0	0%	0	0%	39	0%
Pegasus Homes (formerly Lifestory Group)	0	0%	1	100%	0	0%	0	0%	1	100%
London Square Development (Holdings) Limited	39	100%	0	0%	0	0%	0	0%	39	100%
Miller Homes Limited	4	21%	0	0%	15	79%	0	0%	19	100%
Morris Homes Group Limited	0	0%	0	0%	1	100%	0	0%	1	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	7	64%	0	0%	2	18%	0	0%	11	82%
Persimmon Public Limited Company	48	100%	0	0%	0	0%	0	0%	48	100%
Regal Holdco Limited (parent company for Regal London)	0	0%	0	0%	0	0%	0	0%	3	0%
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Sorbon Group Limited (parent company for Shanly Homes)	0	0%	0	0%	14	100%	0	0%	14	100%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	0	0%	0	0%	0	0%	0	0%	4	0%
Story Homes Limited	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	163	100%	0	0%	0	0%	0	0%	163	100%
Telford Homes Limited	63	69%	0	0%	28	31%	0	0%	91	100%
Tilia Homes Limited	2	25%	5	63%	0	0%	0	0%	8	88%
Vistry Group PLC	42	47%	21	24%	4	4%	0	0%	89	75%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	0	0%	0	0%	1	5%	0	0%	21	5%
McCarthy & Stone Limited	0	0%	0	0%	0	0%	0	0%	3	0%
Seven Capital PLC	3	16%	0	0%	8	42%	0	0%	19	58%
Wates Group Limited	0	0%	4	80%	1	20%	0	0%	5	100%
Watkin Jones PLC	7	100%	0	0%	0	0%	0	0%	7	100%
Bouygues (UK) Limited	1	8%	0	0%	1	8%	0	0%	12	17%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	40%	1	20%	0	0%	0	0%	5	60%

## Developer_10
Remediation status of buildings requiring works under the developer remediation contract, time series, England, 31 August 2025
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category - All Defect Types [Note 25, Note 26, Note 29, Note 66]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)	Oct-24 Number	Oct-24 Percentage (%)	Jan-25 Number	Jan-25 Percentage (%)	Apr-25 Number	Apr-25 Percentage (%)	Jul-25 Number	Jul-25 Percentage (%)
Remediation complete	262	19%	307	20%	362	23%	410	25%	439	25%	501	27%	516	25%	537	23%
Remediation started	211	16%	317	21%	365	23%	359	22%	411	24%	456	25%	481	24%	497	21%
Remediation not Started - Plans in Place	506	38%	512	34%	371	24%	455	28%	430	25%	370	20%	372	18%	378	16%
Remediation not Started - No Plans in Place	366	27%	364	24%	471	30%	402	25%	466	27%	517	28%	656	32%	965	41%
Total buildings	1345	100%	1500	100%	1569	100%	1626	100%	1746	100%	1844	100%	2025	100%	2377	100%

Remediation Category - Cladding Defects [Note 25, Note 26, Note 29, Note 66]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)	Oct-24 Number	Oct-24 Percentage (%)	Jan-25 Number	Jan-25 Percentage (%)	Apr-25 Number	Apr-25 Percentage (%)	Jul-25 Number	Jul-25 Percentage (%)
Remediation complete	245	19%	284	20%	340	24%	381	26%	397	26%	441	30%	448	29%	463	26%
Remediation started	200	16%	303	22%	337	24%	334	23%	393	26%	348	24%	376	25%	401	23%
Remediation not Started - Plans in Place	476	37%	481	34%	345	24%	418	29%	390	25%	322	22%	325	21%	323	18%
Remediation not Started - No Plans in Place	352	28%	335	24%	406	28%	316	22%	356	23%	340	23%	377	25%	576	33%
Total buildings	1273	100%	1403	100%	1428	100%	1449	100%	1536	100%	1451	100%	1526	100%	1763	100%

## Developer_11
Estimated number of determinations, starts and completions made each quarter for buildings under the developer remediation contract, by height group, England, 31 July 2025 [Note 86]
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Buildings where the Developer is directly responsible for Remediation and a Determination was made... [Note 28] [Note 84]	...Before 31 January 2024 [Note 83]	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025
Total	2500	268	213	207	259	253	472

Buildings (by height) currently found to require Remediation and will be Remediated by the Developer directly, where works started… [Note 31] [Note 85]	...Before 31 July 2023	...Between 1 August 2023 and 31 October 2023	...Between 1 November 2023 and 31 January 2024	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025
11-18m	109	43	70	36	15	56	68	24	15
18m+	171	65	65	59	13	29	41	16	26
Total	280	108	135	95	28	85	109	40	41

Buildings (by height) currently found to require Remediation and will be Remediated by the Developer directly, where works completed… [Note 31] [Note 85]	...Before 31 July 2023	...Between 1 August 2023 and 31 October 2023	...Between 1 November 2023 and 31 January 2024	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025
11-18m	56	25	26	32	7	22	48	7	21
18m+	74	48	9	21	23	7	15	11	8
Total	130	73	35	53	30	29	63	18	29

## Developer_12
Developer by developer update against RAP Joint Plan targets, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note 29]	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme)	Number of buildings for which the developer has determined whether works are required	Percentage of buildings for which the developer has determined whether works are required	Number of buildings where an exception request has been accepted against the July 2025 joint plan target [Note 95]	Estimated percentage of buildings for which the developer has determined whether works are required (excluding buildings for which an exception request has been accepted)
All Developers	4538	4172	92%	55	93%
Joint Plan Signatories [Note 94]	4271	3969	93%	55	94%
Other Developers (Other Developers)	267	203	76%	0	76%

Developer - Joint Plan Signatories [Note 94]	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme)	Number of buildings for which the developer has determined whether works are required	Percentage of buildings for which the developer has determined whether works are required	Number of buildings where an exception request has been accepted against the July 2025 joint plan target [Note 95]	Estimated percentage of buildings for which the developer has determined whether works are required (excluding buildings for which an exception request has been accepted)
Total - (Joint Plan signatories)	4271	3969	93%	55	94%
Ballymore Limited	69	69	100%	0	100%
Barratt Redrow PLC	821	626	76%	0	76%
Bellway PLC	420	420	100%	0	100%
Bewley Group Limited	7	6	86%	0	86%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	10	10	100%	0	100%
Cala Group (Holdings) Limited	22	22	100%	0	100%
Canary Wharf Group PLC	13	9	69%	4	100%
Crest Nicholson Holdings PLC	292	290	99%	2	100%
Dandara Living Holdings Limited	21	21	100%	0	100%
Fairview Holdings Limited	121	121	100%	0	100%
Grosvenor Developments Limited	21	20	95%	0	95%
Hill Holdings Limited	90	76	84%	14	100%
Jelson Holdings Limited	7	7	100%	0	100%
Lendlease Europe Holdings Limited	88	88	100%	0	100%
London Square Development (Holdings) Limited	40	40	100%	0	100%
McCarthy & Stone Limited	62	60	97%	0	97%
Miller Homes Limited	39	39	100%	0	100%
MJ Gleeson PLC	16	13	81%	0	81%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	113	113	100%	0	100%
Morris Homes Group Limited	6	6	100%	0	100%
Pegasus Homes (formerly Lifestory Group)	18	18	100%	0	100%
Persimmon Public Limited Company	70	70	100%	0	100%
Regal Holdco Limited (parent company for Regal London)	16	16	100%	0	100%
Rydon Group Holdings Limited	22	22	100%	0	100%
Seven Capital PLC	21	21	100%	0	100%
Sorbon Group Limited (parent company for Shanly Homes)	26	26	100%	0	100%
Taylor Wimpey PLC	431	372	86%	19	90%
Telford Homes Limited	143	142	99%	1	100%
The Berkeley Group Holdings PLC	810	796	98%	10	100%
The British Land Company PLC	16	16	100%	0	100%
Tilia Homes Limited	8	8	100%	0	100%
Vistry Group PLC	294	291	99%	2	100%
Wates Group Limited	23	20	87%	3	100%
Weston Group PLC	87	87	100%	0	100%
Other (combined total for all developers with 5 or fewer buildings each: Bloor, CG Fry, Hopkins, Keepmoat Homes)	8	8	100%	0	100%

## Social_1
Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - Social Buildings with Unsafe Cladding [Note 34] [Note 35] [Note 37] [Note 58] [Note 91] [Note 92]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete [Note 54]	374	26%	679	44%	1053	36%
Remediation complete - Awaiting building control sign-off	10	1%	36	2%	46	2%
Remediation started	147	10%	137	9%	284	10%
Remediation works planned	539	38%	441	29%	980	33%
Remediation plans unclear from survey	345	24%	250	16%	595	20%
Total buildings [Note 36]	1,415	100%	1,543	100%	2,958	100%

Social Buildings with Unsafe Cladding identified since June 2017, as reported by Social Housing Providers [Note 34] [Note 35] [Note 37] [Note 67] [Note 91] [Note 92]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete - Prior to the most recent assessment	281	21%	604	41%	885	31%
Remediation complete - Since the most recent assessment [Note 54]	78	6%	79	5%	157	6%
Remediation started	138	10%	127	9%	265	9%
Remediation works planned	539	41%	441	30%	980	35%
Remediation plans unclear from survey	294	22%	229	15%	523	19%
Total buildings	1,330	100%	1,480	100%	2,810	100%

Remediation Category - Social Buildings with Unsafe Cladding at the Time of their Most Recent Assessment, as reported by Social Housing Providers [Note 34] [Note 35] [Note 37] [Note 62] [Note 91] [Note 92]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete [Note 54]	68	6%	43	5%	111	6%
Remediation complete - Awaiting building control sign-off	10	1%	36	4%	46	2%
Remediation started	138	13%	127	14%	265	14%
Remediation works planned	539	51%	441	50%	980	51%
Remediation plans unclear from survey	294	28%	229	26%	523	27%
Total buildings	1,049	100%	876	100%	1,925	100%

## Social_2
Provider by provider breakdown of buildings, by assessment status, England, 30 June 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey as of 30 June 2025
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51] [Note 91]	Total number of buildings over 11 metres	Progress with assessments
		Of the total number of buildings over 11m, buildings that…
		…have had a recent works assessment [Note 52]		…have not had a recent works assessment
		Number	Percentage	Number	Percentage‎
Total	17140	16978	99%	17	0%
A2Dominion Housing Group Limited	174	174	100%	0	0%
Abri Group Limited	39	39	100%	0	0%
Accent Group Limited	7	7	100%	0	0%
Acis Group Limited	21	21	100%	0	0%
Agudas Israel Housing Association Limited	19	19	100%	0	0%
Anchor Hanover Group	37	37	100%	0	0%
Ashford Borough Council	19	19	100%	0	0%
Ashton Pioneer Homes Limited	10	10	100%	0	0%
Aster Group Limited	42	42	100%	0	0%
B3 Living Limited	12	12	100%	0	0%
Beyond Housing Limited	10	10	100%	0	0%
Birkenhead Forum Housing Association Limited	9	9	100%	0	0%
Birmingham City Council	205	205	100%	0	0%
Bolton at Home Limited	10	10	100%	0	0%
Bournemouth, Christchurch and Poole Council	15	15	100%	0	0%
bpha Limited	27	27	100%	0	0%
Bridgwater Young Men’s Christian Association	6	6	100%	0	0%
Brighter Places	11	11	100%	0	0%
Brighton and Hove City Council	81	-	-	-	-
Bristol City Council	93	93	100%	0	0%
Broadland Housing Association Limited	10	10	100%	0	0%
Bromford Flagship Limited	24	24	100%	0	0%
Cambridge City Council	21	21	100%	0	0%
Central Bedfordshire Council	9	9	100%	0	0%
Christian Action (Enfield) Housing Association Limited	13	13	100%	0	0%
Citizen Housing Group Limited	60	60	100%	0	0%
City of Doncaster Council	9	9	100%	0	0%
City of London Corporation	26	26	100%	0	0%
City of Westminster Council	410	410	100%	0	0%
Clarion Housing Group Limited	554	554	100%	0	0%
Curo Group (Albion) Limited	147	147	100%	0	0%
Dacorum Borough Council	17	17	100%	0	0%
Dudley Metropolitan Borough Council	49	49	100%	0	0%
East End Homes Limited	44	44	100%	0	0%
Ekaya Housing Association Limited	9	9	100%	0	0%
Estuary Housing Association Limited	19	19	100%	0	0%
Exeter City Council	7	7	100%	0	0%
Fairhazel Co-operative Limited	12	12	100%	0	0%
First Choice Homes Oldham Limited	8	8	100%	0	0%
ForHousing Limited	26	26	100%	0	0%
Gateshead Metropolitan Borough Council	23	23	100%	0	0%
Gateway Housing Association Limited	23	23	100%	0	0%
Gentoo Group Limited	32	32	100%	0	0%
Gloucester City Homes Limited	6	6	100%	0	0%
Golding Homes Limited	8	8	100%	0	0%
Gosport Borough Council	6	6	100%	0	0%
Gravesham Borough Council	7	7	100%	0	0%
Great Places Housing Group Limited	17	17	100%	0	0%
GreenSquareAccord Limited	16	16	100%	0	0%
Haringey London Borough Council	95	95	100%	0	0%
Harlow District Council	18	18	100%	0	0%
Hastoe Housing Association Limited	6	6	100%	0	0%
Heart of Medway Housing Association Limited	8	8	100%	0	0%
Hexagon Housing Association Limited	21	21	100%	0	0%
HFL Homes Limited	7	7	100%	0	0%
Hightown Housing Association Limited	20	20	100%	0	0%
Home Group Limited	73	73	100%	0	0%
Housing 21	19	19	100%	0	0%
Housing For Women	20	20	100%	0	0%
Hyde Housing Association Limited	236	236	100%	0	0%
Incommunities Limited	32	32	100%	0	0%
Irwell Valley Housing Association Limited	13	13	100%	0	0%
Islington and Shoreditch Housing Association Limited	44	44	100%	0	0%
Jigsaw Homes Group Limited	19	19	100%	0	0%
Karbon Homes Limited	35	35	100%	0	0%
Karibu Community Homes Limited	8	8	100%	0	0%
Kingston upon Hull City Council	26	26	100%	0	0%
Kirklees Metropolitan Borough Council	21	21	100%	0	0%
Lambeth and Southwark Housing Association Limited	11	11	100%	0	0%
Leeds City Council	131	131	100%	0	0%
Legal & General Affordable Homes (AR) LLP	6	6	100%	0	0%
Legal & General Affordable Homes Limited	6	6	100%	0	0%
Legal and General Affordable Homes (Development 3) Limited	6	6	100%	0	0%
Leicester City Council	11	11	100%	0	0%
LiveWest Homes Limited	66	66	100%	0	0%
Livv Housing Group	9	9	100%	0	0%
London & Quadrant Housing Trust	713	713	100%	0	0%
London Borough of Barking and Dagenham	76	76	100%	0	0%
London Borough of Barnet	48	48	100%	0	0%
London Borough of Brent	64	-	-	-	-
London Borough of Camden Council	952	952	100%	0	0%
London Borough of Croydon	66	66	100%	0	0%
London Borough of Ealing	48	48	100%	0	0%
London Borough of Enfield	66	66	100%	0	0%
London Borough of Hackney	462	462	100%	0	0%
London Borough of Hammersmith and Fulham	231	231	100%	0	0%
London Borough of Havering Council	23	23	100%	0	0%
London Borough of Hillingdon	13	13	100%	0	0%
London Borough of Hounslow	63	63	100%	0	0%
London Borough of Islington	386	386	100%	0	0%
London Borough of Lambeth	389	389	100%	0	0%
London Borough of Lewisham	159	159	100%	0	0%
London Borough of Newham	91	91	100%	0	0%
London Borough of Redbridge	22	22	100%	0	0%
London Borough of Sutton	60	60	100%	0	0%
London Borough of Tower Hamlets	326	326	100%	0	0%
London Borough of Waltham Forest	65	64	98%	1	2%
London Borough of Wandsworth	363	363	100%	0	0%
Look Ahead Care and Support Limited	8	8	100%	0	0%
Luton Borough Council	15	6	40%	9	60%
Magenta Living	11	11	100%	0	0%
Manchester City Council	42	42	100%	0	0%
Metropolitan Housing Trust Limited	258	258	100%	0	0%
Midland Heart Limited	17	17	100%	0	0%
Moat Homes Limited	26	26	100%	0	0%
New Foundations Housing Association Limited	6	6	100%	0	0%
Newark and Sherwood District Council	6	6	100%	0	0%
Newcastle City Council	54	54	100%	0	0%
Newlon Housing Trust	85	85	100%	0	0%
North Devon Homes	6	6	100%	0	0%
North London Muslim Housing Association Limited	12	12	100%	0	0%
Norwich City Council	25	25	100%	0	0%
Notting Hill Genesis	955	955	100%	0	0%
Nottingham City Council	24	24	100%	0	0%
Nottingham Community Housing Association Limited	13	13	100%	0	0%
Octavia Housing	115	115	100%	0	0%
One Manchester Limited	25	25	100%	0	0%
One Vision Housing Limited	8	8	100%	0	0%
Onward Group Limited	49	49	100%	0	0%
Orbit Group Limited	81	81	100%	0	0%
Oxford City Council	8	8	100%	0	0%
P3 Housing Limited	33	33	100%	0	0%
Paradigm Housing Group Limited	24	24	100%	0	0%
Paragon Asra Housing Limited	84	84	100%	0	0%
Peabody Trust	1239	1239	100%	0	0%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	15	100%	0	0%
Places for People Group Limited	195	195	100%	0	0%
Platform Housing Group Limited	16	16	100%	0	0%
Plus Dane Housing Limited	10	10	100%	0	0%
Plymouth Community Homes Limited	55	55	100%	0	0%
Poplar Housing And Regeneration Community Association Limited	118	118	100%	0	0%
Portsmouth City Council	55	55	100%	0	0%
Providence Row Housing Association	11	11	100%	0	0%
Raven Housing Trust Limited	13	13	100%	0	0%
Reading Borough Council	18	18	100%	0	0%
Regenda Limited	18	18	100%	0	0%
Richmond Housing Partnership Limited	43	43	100%	0	0%
Rochdale Boroughwide Housing Limited	14	14	100%	0	0%
Rooftop Housing Group Limited	6	6	100%	0	0%
Royal Borough of Greenwich	193	193	100%	0	0%
Royal Borough of Kensington and Chelsea	208	207	100%	1	0%
Royal Borough of Kingston Upon Thames	34	34	100%	0	0%
Salix Homes Limited	20	20	100%	0	0%
Salvation Army Housing Association	14	14	100%	0	0%
Sanctuary Housing Association	424	424	100%	0	0%
Sandwell Metropolitan Borough Council	55	55	100%	0	0%
Seymour Housing Co-operative Limited	8	8	100%	0	0%
Sheffield City Council	359	359	100%	0	0%
Soho Housing Association Limited	46	46	100%	0	0%
Solihull Metropolitan Borough Council	37	37	100%	0	0%
Southampton City Council	196	196	100%	0	0%
Southend on Sea City Council	18	18	100%	0	0%
Southern Housing	550	550	100%	0	0%
Southwark Council	852	851	100%	1	0%
Southway Housing Trust (Manchester) Limited	6	6	100%	0	0%
Sovereign Network Group	300	295	98%	5	2%
Spitalfields Housing Association Limited	11	11	100%	0	0%
St Mungo Community Housing Association	20	20	100%	0	0%
Stevenage Borough Council	12	12	100%	0	0%
Stockport Homes Limited	30	30	100%	0	0%
Stoke on Trent City Council	18	18	100%	0	0%
Stonewater Limited	33	33	100%	0	0%
Swindon Borough Council	8	8	100%	0	0%
Tamworth Borough Council	7	7	100%	0	0%
Teign Housing	8	8	100%	0	0%
Thanet District Council	10	10	100%	0	0%
The ExtraCare Charitable Trust	10	10	100%	0	0%
The Guinness Partnership Limited	313	313	100%	0	0%
The Housing Plus Group Limited	13	13	100%	0	0%
The Industrial Dwellings Society (1885) Limited	35	35	100%	0	0%
The Riverside Group Limited	301	301	100%	0	0%
Thirteen Housing Group Limited	15	15	100%	0	0%
Thrive Homes Limited	6	6	100%	0	0%
Thurrock Council	18	18	100%	0	0%
Together Housing Group Limited	45	45	100%	0	0%
Torus62 Limited	6	6	100%	0	0%
Trident Housing Association Limited	12	12	100%	0	0%
Vico Homes Limited	19	19	100%	0	0%
Vivid Housing Limited	54	54	100%	0	0%
Walsall Housing Group Limited	20	20	100%	0	0%
Wandle Housing Association Limited	40	40	100%	0	0%
Warwick District Council	9	9	100%	0	0%
Watford Community Housing Trust	11	11	100%	0	0%
Watmos Community Homes	35	35	100%	0	0%
West Hampstead Housing Co-operative Limited	11	11	100%	0	0%
West Northamptonshire Council	14	14	100%	0	0%
Wigan Council	7	7	100%	0	0%
Winchester City Council	9	9	100%	0	0%
Woking Borough Council	25	25	100%	0	0%
Wolverhampton City Council	52	52	100%	0	0%
Women’s Pioneer Housing Limited	63	63	100%	0	0%
Worthing Homes Limited	6	6	100%	0	0%
Wythenshawe Community Housing Group Limited	12	12	100%	0	0%
YMCA St Paul’s Group	6	6	100%	0	0%
Yorkshire Housing Limited	14	14	100%	0	0%
Your Housing Group Limited	24	24	100%	0	0%
Zebra Housing Association Limited	8	8	100%	0	0%
Other RPs	522	522	100%	0	0%

## Social_3
Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 June 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey as of 30 June 2025
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51] [Note 91]	Total number of buildings over 11 metres	Number of buildings identified as having EWS life-critical fire-safety defects since June 2017 [Note_35] [Note_67]	% buildings identified as having EWS life-critical fire-safety defects since June 2017	Number of buildings assessed as having EWS life-critical fire-safety defects at the time of their most recent assessment [Note_35] [Note_52] [Note_62]	% buildings assessed as having EWS life-critical fire-safety defects at the time of their most recent assessment
Total	17,140	2,810	16%	1,925	11%
A2Dominion Housing Group Limited	174	44	25%	24	14%
Abri Group Limited	39	5	13%	2	5%
Accent Group Limited	7	3	43%	1	14%
Acis Group Limited	21	1	5%	1	5%
Agudas Israel Housing Association Limited	19	1	5%	1	5%
Anchor Hanover Group	37	10	27%	10	27%
Ashford Borough Council	19	0	0%	0	0%
Ashton Pioneer Homes Limited	10	0	0%	0	0%
Aster Group Limited	42	8	19%	4	10%
B3 Living Limited	12	5	42%	5	42%
Beyond Housing Limited	10	0	0%	0	0%
Birkenhead Forum Housing Association Limited	9	0	0%	0	0%
Birmingham City Council	205	140	68%	16	8%
Bolton at Home Limited	10	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	15	2	13%	0	0%
bpha Limited	27	5	19%	2	7%
Bridgwater Young Men’s Christian Association	6	0	0%	0	0%
Brighter Places	11	0	0%	0	0%
Brighton and Hove City Council	81	-	-	-	-
Bristol City Council	93	44	47%	44	47%
Broadland Housing Association Limited	10	2	20%	1	10%
Bromford Flagship Limited	24	2	8%	2	8%
Cambridge City Council	21	3	14%	3	14%
Central Bedfordshire Council	9	1	11%	1	11%
Christian Action (Enfield) Housing Association Limited	13	3	23%	3	23%
Citizen Housing Group Limited	60	2	3%	2	3%
City of Doncaster Council	9	9	100%	9	100%
City of London Corporation	26	0	0%	0	0%
City of Westminster Council	410	8	2%	2	0%
Clarion Housing Group Limited	554	115	21%	65	12%
Curo Group (Albion) Limited	147	0	0%	0	0%
Dacorum Borough Council	17	4	24%	4	24%
Dudley Metropolitan Borough Council	49	0	0%	0	0%
East End Homes Limited	44	8	18%	6	14%
Ekaya Housing Association Limited	9	0	0%	0	0%
Estuary Housing Association Limited	19	2	11%	0	0%
Exeter City Council	7	0	0%	0	0%
Fairhazel Co-operative Limited	12	0	0%	0	0%
First Choice Homes Oldham Limited	8	2	25%	0	0%
ForHousing Limited	26	11	42%	5	19%
Gateshead Metropolitan Borough Council	23	1	4%	0	0%
Gateway Housing Association Limited	23	1	4%	1	4%
Gentoo Group Limited	32	11	34%	5	16%
Gloucester City Homes Limited	6	0	0%	0	0%
Golding Homes Limited	8	3	38%	3	38%
Gosport Borough Council	6	0	0%	0	0%
Gravesham Borough Council	7	0	0%	0	0%
Great Places Housing Group Limited	17	6	35%	6	35%
GreenSquareAccord Limited	16	9	56%	9	56%
Haringey London Borough Council	95	49	52%	20	21%
Harlow District Council	18	2	11%	0	0%
Hastoe Housing Association Limited	6	3	50%	3	50%
Heart of Medway Housing Association Limited	8	5	63%	0	0%
Hexagon Housing Association Limited	21	19	90%	19	90%
HFL Homes Limited	7	0	0%	0	0%
Hightown Housing Association Limited	20	2	10%	1	5%
Home Group Limited	73	25	34%	19	26%
Housing 21	19	0	0%	0	0%
Housing For Women	20	0	0%	0	0%
Hyde Housing Association Limited	236	82	35%	43	18%
Incommunities Limited	32	11	34%	11	34%
Irwell Valley Housing Association Limited	13	6	46%	5	38%
Islington and Shoreditch Housing Association Limited	44	14	32%	7	16%
Jigsaw Homes Group Limited	19	14	74%	6	32%
Karbon Homes Limited	35	18	51%	18	51%
Karibu Community Homes Limited	8	1	13%	0	0%
Kingston upon Hull City Council	26	0	0%	0	0%
Kirklees Metropolitan Borough Council	21	15	71%	14	67%
Lambeth and Southwark Housing Association Limited	11	0	0%	0	0%
Leeds City Council	131	0	0%	0	0%
Legal & General Affordable Homes (AR) LLP	6	0	0%	0	0%
Legal & General Affordable Homes Limited	6	0	0%	0	0%
Legal and General Affordable Homes (Development 3) Limited	6	0	0%	0	0%
Leicester City Council	11	0	0%	0	0%
LiveWest Homes Limited	66	7	11%	6	9%
Livv Housing Group	9	0	0%	0	0%
London & Quadrant Housing Trust	713	80	11%	57	8%
London Borough of Barking and Dagenham	76	2	3%	2	3%
London Borough of Barnet	48	13	27%	7	15%
London Borough of Brent	64	-	-	-	-
London Borough of Camden Council	952	12	1%	5	1%
London Borough of Croydon	66	0	0%	0	0%
London Borough of Ealing	48	2	4%	2	4%
London Borough of Enfield	66	0	0%	0	0%
London Borough of Hackney	462	75	16%	73	16%
London Borough of Hammersmith and Fulham	231	7	3%	7	3%
London Borough of Havering Council	23	1	4%	1	4%
London Borough of Hillingdon	13	1	8%	0	0%
London Borough of Hounslow	63	1	2%	0	0%
London Borough of Islington	386	3	1%	1	0%
London Borough of Lambeth	389	7	2%	4	1%
London Borough of Lewisham	159	34	21%	26	16%
London Borough of Newham	91	43	47%	32	35%
London Borough of Redbridge	22	0	0%	0	0%
London Borough of Sutton	60	1	2%	1	2%
London Borough of Tower Hamlets	326	34	10%	30	9%
London Borough of Waltham Forest	65	30	46%	20	31%
London Borough of Wandsworth	363	2	1%	2	1%
Look Ahead Care and Support Limited	8	4	50%	3	38%
Luton Borough Council	15	0	0%	0	0%
Magenta Living	11	3	27%	0	0%
Manchester City Council	42	21	50%	16	38%
Metropolitan Housing Trust Limited	258	114	44%	106	41%
Midland Heart Limited	17	1	6%	0	0%
Moat Homes Limited	26	5	19%	4	15%
New Foundations Housing Association Limited	6	0	0%	0	0%
Newark and Sherwood District Council	6	0	0%	0	0%
Newcastle City Council	54	0	0%	0	0%
Newlon Housing Trust	85	52	61%	47	55%
North Devon Homes	6	0	0%	0	0%
North London Muslim Housing Association Limited	12	8	67%	8	67%
Norwich City Council	25	2	8%	2	8%
Notting Hill Genesis	955	116	12%	49	5%
Nottingham City Council	24	0	0%	0	0%
Nottingham Community Housing Association Limited	13	1	8%	0	0%
Octavia Housing	115	24	21%	23	20%
One Manchester Limited	25	16	64%	0	0%
One Vision Housing Limited	8	2	25%	0	0%
Onward Group Limited	49	19	39%	15	31%
Orbit Group Limited	81	28	35%	27	33%
Oxford City Council	8	0	0%	0	0%
P3 Housing Limited	33	0	0%	0	0%
Paradigm Housing Group Limited	24	1	4%	0	0%
Paragon Asra Housing Limited	84	21	25%	19	23%
Peabody Trust	1,239	196	16%	165	13%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	4	27%	4	27%
Places for People Group Limited	195	46	24%	20	10%
Platform Housing Group Limited	16	2	13%	2	13%
Plus Dane Housing Limited	10	3	30%	3	30%
Plymouth Community Homes Limited	55	4	7%	0	0%
Poplar Housing And Regeneration Community Association Limited	118	31	26%	7	6%
Portsmouth City Council	55	22	40%	4	7%
Providence Row Housing Association	11	1	9%	0	0%
Raven Housing Trust Limited	13	0	0%	0	0%
Reading Borough Council	18	3	17%	3	17%
Regenda Limited	18	4	22%	1	6%
Richmond Housing Partnership Limited	43	18	42%	16	37%
Rochdale Boroughwide Housing Limited	14	9	64%	9	64%
Rooftop Housing Group Limited	6	1	17%	1	17%
Royal Borough of Greenwich	193	10	5%	10	5%
Royal Borough of Kensington and Chelsea	208	9	4%	8	4%
Royal Borough of Kingston Upon Thames	34	0	0%	0	0%
Salix Homes Limited	20	8	40%	0	0%
Salvation Army Housing Association	14	1	7%	0	0%
Sanctuary Housing Association	424	87	21%	68	16%
Sandwell Metropolitan Borough Council	55	4	7%	0	0%
Seymour Housing Co-operative Limited	8	0	0%	0	0%
Sheffield City Council	359	1	0%	0	0%
Soho Housing Association Limited	46	0	0%	0	0%
Solihull Metropolitan Borough Council	37	16	43%	11	30%
Southampton City Council	196	83	42%	83	42%
Southend on Sea City Council	18	0	0%	0	0%
Southern Housing	550	170	31%	150	27%
Southwark Council	852	128	15%	59	7%
Southway Housing Trust (Manchester) Limited	6	0	0%	0	0%
Sovereign Network Group	300	102	34%	53	18%
Spitalfields Housing Association Limited	11	4	36%	4	36%
St Mungo Community Housing Association	20	1	5%	1	5%
Stevenage Borough Council	12	5	42%	5	42%
Stockport Homes Limited	30	15	50%	15	50%
Stoke on Trent City Council	18	12	67%	12	67%
Stonewater Limited	33	7	21%	6	18%
Swindon Borough Council	8	0	0%	0	0%
Tamworth Borough Council	7	0	0%	0	0%
Teign Housing	8	1	13%	1	13%
Thanet District Council	10	5	50%	5	50%
The ExtraCare Charitable Trust	10	1	10%	0	0%
The Guinness Partnership Limited	313	26	8%	17	5%
The Housing Plus Group Limited	13	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	35	0	0%	0	0%
The Riverside Group Limited	301	91	30%	91	30%
Thirteen Housing Group Limited	15	0	0%	0	0%
Thrive Homes Limited	6	0	0%	0	0%
Thurrock Council	18	0	0%	0	0%
Together Housing Group Limited	45	14	31%	0	0%
Torus62 Limited	6	0	0%	0	0%
Trident Housing Association Limited	12	0	0%	0	0%
Vico Homes Limited	19	4	21%	4	21%
Vivid Housing Limited	54	9	17%	1	2%
Walsall Housing Group Limited	20	0	0%	0	0%
Wandle Housing Association Limited	40	14	35%	14	35%
Warwick District Council	9	5	56%	5	56%
Watford Community Housing Trust	11	0	0%	0	0%
Watmos Community Homes	35	0	0%	0	0%
West Hampstead Housing Co-operative Limited	11	0	0%	0	0%
West Northamptonshire Council	14	8	57%	2	14%
Wigan Council	7	0	0%	0	0%
Winchester City Council	9	0	0%	0	0%
Woking Borough Council	25	14	56%	14	56%
Wolverhampton City Council	52	9	17%	9	17%
Women’s Pioneer Housing Limited	63	0	0%	0	0%
Worthing Homes Limited	6	2	33%	1	17%
Wythenshawe Community Housing Group Limited	12	7	58%	0	0%
YMCA St Paul’s Group	6	1	17%	1	17%
Yorkshire Housing Limited	14	0	0%	0	0%
Your Housing Group Limited	24	11	46%	10	42%
Zebra Housing Association Limited	8	0	0%	0	0%
Other RPs	522	51	10%	32	6%

## Social_4
Provider by provider breakdown of buildings, by remediation status, England, 30 June 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey as of 30 June 2025
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51] [Note 91]	Number of buildings with EWS life-critical fire safety defects since June 2017	Remediation Status
		Number and proportion of buildings identified as having EWS life-critical fire-safety defects [Note 35] [Note 67] since June 2017, where remediation...
		…plans are unclear from survey		…works are planned		…has started		... has completed since the most recent works assessment [Note 54]		... has completed prior to the most recent works assessment
		Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total	2,810	523	19%	980	35%	265	9%	157	6%	885	31%
A2Dominion Housing Group Limited	44	1	2%	15	34%	8	18%	0	0%	20	45%
Abri Group Limited	5	0	0%	2	40%	0	0%	0	0%	3	60%
Accent Group Limited	3	0	0%	1	33%	0	0%	0	0%	2	67%
Acis Group Limited	1	0	0%	1	100%	0	0%	0	0%	0	0%
Agudas Israel Housing Association Limited	1	0	0%	1	100%	0	0%	0	0%	0	0%
Anchor Hanover Group	10	0	0%	10	100%	0	0%	0	0%	0	0%
Ashford Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Ashton Pioneer Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Aster Group Limited	8	1	13%	2	25%	1	13%	0	0%	4	50%
B3 Living Limited	5	4	80%	1	20%	0	0%	0	0%	0	0%
Beyond Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Birkenhead Forum Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Birmingham City Council	140	0	0%	1	1%	4	3%	11	8%	124	89%
Bolton at Home Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	2	0	0%	0	0%	0	0%	0	0%	2	100%
bpha Limited	5	2	40%	0	0%	0	0%	0	0%	3	60%
Bridgwater Young Men’s Christian Association	0	0	0%	0	0%	0	0%	0	0%	0	0%
Brighter Places	0	0	0%	0	0%	0	0%	0	0%	0	0%
Brighton and Hove City Council	-	-	-	-	-	-	-	-	-	-	-
Bristol City Council	44	5	11%	28	64%	1	2%	10	23%	0	0%
Broadland Housing Association Limited	2	1	50%	0	0%	0	0%	0	0%	1	50%
Bromford Flagship Limited	2	0	0%	1	50%	1	50%	0	0%	0	0%
Cambridge City Council	3	2	67%	1	33%	0	0%	0	0%	0	0%
Central Bedfordshire Council	1	0	0%	1	100%	0	0%	0	0%	0	0%
Christian Action (Enfield) Housing Association Limited	3	0	0%	3	100%	0	0%	0	0%	0	0%
Citizen Housing Group Limited	2	0	0%	2	100%	0	0%	0	0%	0	0%
City of Doncaster Council	9	4	44%	0	0%	4	44%	1	11%	0	0%
City of London Corporation	0	0	0%	0	0%	0	0%	0	0%	0	0%
City of Westminster Council	8	0	0%	2	25%	0	0%	0	0%	6	75%
Clarion Housing Group Limited	115	17	15%	25	22%	19	17%	4	3%	50	43%
Curo Group (Albion) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Dacorum Borough Council	4	2	50%	0	0%	2	50%	0	0%	0	0%
Dudley Metropolitan Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
East End Homes Limited	8	2	25%	3	38%	0	0%	1	13%	2	25%
Ekaya Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Estuary Housing Association Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
Exeter City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Fairhazel Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
First Choice Homes Oldham Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
ForHousing Limited	11	4	36%	1	9%	0	0%	0	0%	6	55%
Gateshead Metropolitan Borough Council	1	0	0%	0	0%	0	0%	0	0%	1	100%
Gateway Housing Association Limited	1	0	0%	1	100%	0	0%	0	0%	0	0%
Gentoo Group Limited	11	3	27%	1	9%	0	0%	1	9%	6	55%
Gloucester City Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Golding Homes Limited	3	1	33%	0	0%	2	67%	0	0%	0	0%
Gosport Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Gravesham Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Great Places Housing Group Limited	6	1	17%	5	83%	0	0%	0	0%	0	0%
GreenSquareAccord Limited	9	0	0%	9	100%	0	0%	0	0%	0	0%
Haringey London Borough Council	49	0	0%	20	41%	0	0%	0	0%	29	59%
Harlow District Council	2	0	0%	0	0%	0	0%	0	0%	2	100%
Hastoe Housing Association Limited	3	0	0%	2	67%	1	33%	0	0%	0	0%
Heart of Medway Housing Association Limited	5	0	0%	0	0%	0	0%	0	0%	5	100%
Hexagon Housing Association Limited	19	14	74%	3	16%	1	5%	1	5%	0	0%
HFL Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Hightown Housing Association Limited	2	0	0%	1	50%	0	0%	0	0%	1	50%
Home Group Limited	25	0	0%	8	32%	9	36%	2	8%	6	24%
Housing 21	0	0	0%	0	0%	0	0%	0	0%	0	0%
Housing For Women	0	0	0%	0	0%	0	0%	0	0%	0	0%
Hyde Housing Association Limited	82	0	0%	26	32%	5	6%	12	15%	39	48%
Incommunities Limited	11	11	100%	0	0%	0	0%	0	0%	0	0%
Irwell Valley Housing Association Limited	6	1	17%	0	0%	4	67%	0	0%	1	17%
Islington and Shoreditch Housing Association Limited	14	1	7%	5	36%	1	7%	0	0%	7	50%
Jigsaw Homes Group Limited	14	3	21%	2	14%	0	0%	1	7%	8	57%
Karbon Homes Limited	18	0	0%	17	94%	0	0%	1	6%	0	0%
Karibu Community Homes Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Kingston upon Hull City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Kirklees Metropolitan Borough Council	15	10	67%	2	13%	2	13%	0	0%	1	7%
Lambeth and Southwark Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Leeds City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Legal & General Affordable Homes (AR) LLP	0	0	0%	0	0%	0	0%	0	0%	0	0%
Legal & General Affordable Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Legal and General Affordable Homes (Development 3) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Leicester City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
LiveWest Homes Limited	7	6	86%	0	0%	0	0%	0	0%	1	14%
Livv Housing Group	0	0	0%	0	0%	0	0%	0	0%	0	0%
London & Quadrant Housing Trust	80	21	26%	4	5%	5	6%	27	34%	23	29%
London Borough of Barking and Dagenham	2	2	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Barnet	13	0	0%	7	54%	0	0%	0	0%	6	46%
London Borough of Brent	-	-	-	-	-	-	-	-	-	-	-
London Borough of Camden Council	12	0	0%	4	33%	1	8%	0	0%	7	58%
London Borough of Croydon	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Ealing	2	2	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Enfield	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hackney	75	71	95%	1	1%	1	1%	0	0%	2	3%
London Borough of Hammersmith and Fulham	7	0	0%	4	57%	3	43%	0	0%	0	0%
London Borough of Havering Council	1	0	0%	1	100%	0	0%	0	0%	0	0%
London Borough of Hillingdon	1	0	0%	0	0%	0	0%	0	0%	1	100%
London Borough of Hounslow	1	0	0%	0	0%	0	0%	0	0%	1	100%
London Borough of Islington	3	1	33%	0	0%	0	0%	0	0%	2	67%
London Borough of Lambeth	7	0	0%	4	57%	0	0%	0	0%	3	43%
London Borough of Lewisham	34	0	0%	26	76%	0	0%	0	0%	8	24%
London Borough of Newham	43	3	7%	9	21%	19	44%	1	2%	11	26%
London Borough of Redbridge	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Sutton	1	1	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Tower Hamlets	34	1	3%	27	79%	2	6%	0	0%	4	12%
London Borough of Waltham Forest	30	14	47%	0	0%	6	20%	0	0%	10	33%
London Borough of Wandsworth	2	0	0%	2	100%	0	0%	0	0%	0	0%
Look Ahead Care and Support Limited	4	3	75%	0	0%	0	0%	0	0%	1	25%
Luton Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Magenta Living	3	0	0%	0	0%	0	0%	0	0%	3	100%
Manchester City Council	21	3	14%	12	57%	1	5%	0	0%	5	24%
Metropolitan Housing Trust Limited	114	92	81%	0	0%	14	12%	0	0%	8	7%
Midland Heart Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Moat Homes Limited	5	0	0%	2	40%	1	20%	1	20%	1	20%
New Foundations Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newark and Sherwood District Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newcastle City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newlon Housing Trust	52	0	0%	42	81%	5	10%	0	0%	5	10%
North Devon Homes	0	0	0%	0	0%	0	0%	0	0%	0	0%
North London Muslim Housing Association Limited	8	0	0%	8	100%	0	0%	0	0%	0	0%
Norwich City Council	2	0	0%	2	100%	0	0%	0	0%	0	0%
Notting Hill Genesis	116	0	0%	45	39%	4	3%	0	0%	67	58%
Nottingham City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Nottingham Community Housing Association Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Octavia Housing	24	7	29%	16	67%	0	0%	0	0%	1	4%
One Manchester Limited	16	0	0%	0	0%	0	0%	0	0%	16	100%
One Vision Housing Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
Onward Group Limited	19	0	0%	15	79%	0	0%	0	0%	4	21%
Orbit Group Limited	28	16	57%	1	4%	10	36%	0	0%	1	4%
Oxford City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
P3 Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Paradigm Housing Group Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Paragon Asra Housing Limited	21	0	0%	16	76%	3	14%	0	0%	2	10%
Peabody Trust	196	62	32%	79	40%	13	7%	11	6%	31	16%
Phoenix Community Housing Association (Bellingham and Downham) Limited	4	0	0%	2	50%	2	50%	0	0%	0	0%
Places for People Group Limited	46	10	22%	8	17%	2	4%	0	0%	26	57%
Platform Housing Group Limited	2	0	0%	1	50%	1	50%	0	0%	0	0%
Plus Dane Housing Limited	3	1	33%	2	67%	0	0%	0	0%	0	0%
Plymouth Community Homes Limited	4	0	0%	0	0%	0	0%	0	0%	4	100%
Poplar Housing And Regeneration Community Association Limited	31	0	0%	5	16%	2	6%	0	0%	24	77%
Portsmouth City Council	22	0	0%	4	18%	0	0%	0	0%	18	82%
Providence Row Housing Association	1	0	0%	0	0%	0	0%	0	0%	1	100%
Raven Housing Trust Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Reading Borough Council	3	0	0%	3	100%	0	0%	0	0%	0	0%
Regenda Limited	4	0	0%	0	0%	1	25%	0	0%	3	75%
Richmond Housing Partnership Limited	18	0	0%	4	22%	3	17%	9	50%	2	11%
Rochdale Boroughwide Housing Limited	9	9	100%	0	0%	0	0%	0	0%	0	0%
Rooftop Housing Group Limited	1	1	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Greenwich	10	10	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Kensington and Chelsea	9	1	11%	3	33%	0	0%	4	44%	1	11%
Royal Borough of Kingston Upon Thames	0	0	0%	0	0%	0	0%	0	0%	0	0%
Salix Homes Limited	8	0	0%	0	0%	0	0%	0	0%	8	100%
Salvation Army Housing Association	1	0	0%	0	0%	0	0%	0	0%	1	100%
Sanctuary Housing Association	87	1	1%	60	69%	7	8%	0	0%	19	22%
Sandwell Metropolitan Borough Council	4	0	0%	0	0%	0	0%	0	0%	4	100%
Seymour Housing Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Sheffield City Council	1	0	0%	0	0%	0	0%	0	0%	1	100%
Soho Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Solihull Metropolitan Borough Council	16	0	0%	11	69%	0	0%	0	0%	5	31%
Southampton City Council	83	0	0%	46	55%	6	7%	31	37%	0	0%
Southend on Sea City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Southern Housing	170	0	0%	142	84%	8	5%	0	0%	20	12%
Southwark Council	128	45	35%	12	9%	1	1%	1	1%	69	54%
Southway Housing Trust (Manchester) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Sovereign Network Group	102	0	0%	34	33%	19	19%	0	0%	49	48%
Spitalfields Housing Association Limited	4	4	100%	0	0%	0	0%	0	0%	0	0%
St Mungo Community Housing Association	1	0	0%	0	0%	1	100%	0	0%	0	0%
Stevenage Borough Council	5	0	0%	5	100%	0	0%	0	0%	0	0%
Stockport Homes Limited	15	15	100%	0	0%	0	0%	0	0%	0	0%
Stoke on Trent City Council	12	7	58%	0	0%	3	25%	2	17%	0	0%
Stonewater Limited	7	2	29%	3	43%	0	0%	1	14%	1	14%
Swindon Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Tamworth Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Teign Housing	1	0	0%	1	100%	0	0%	0	0%	0	0%
Thanet District Council	5	0	0%	5	100%	0	0%	0	0%	0	0%
The ExtraCare Charitable Trust	1	0	0%	0	0%	0	0%	0	0%	1	100%
The Guinness Partnership Limited	26	4	15%	6	23%	5	19%	2	8%	9	35%
The Housing Plus Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
The Riverside Group Limited	91	0	0%	46	51%	25	27%	20	22%	0	0%
Thirteen Housing Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Thrive Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Thurrock Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Together Housing Group Limited	14	0	0%	0	0%	0	0%	0	0%	14	100%
Torus62 Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Trident Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Vico Homes Limited	4	0	0%	2	50%	2	50%	0	0%	0	0%
Vivid Housing Limited	9	1	11%	0	0%	0	0%	0	0%	8	89%
Walsall Housing Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Wandle Housing Association Limited	14	2	14%	8	57%	4	29%	0	0%	0	0%
Warwick District Council	5	0	0%	5	100%	0	0%	0	0%	0	0%
Watford Community Housing Trust	0	0	0%	0	0%	0	0%	0	0%	0	0%
Watmos Community Homes	0	0	0%	0	0%	0	0%	0	0%	0	0%
West Hampstead Housing Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
West Northamptonshire Council	8	0	0%	2	25%	0	0%	0	0%	6	75%
Wigan Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Winchester City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Woking Borough Council	14	0	0%	0	0%	14	100%	0	0%	0	0%
Wolverhampton City Council	9	0	0%	9	100%	0	0%	0	0%	0	0%
Women’s Pioneer Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Worthing Homes Limited	2	0	0%	1	50%	0	0%	0	0%	1	50%
Wythenshawe Community Housing Group Limited	7	0	0%	0	0%	0	0%	0	0%	7	100%
YMCA St Paul’s Group	1	0	0%	1	100%	0	0%	0	0%	0	0%
Yorkshire Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Your Housing Group Limited	11	5	45%	5	45%	0	0%	0	0%	1	9%
Zebra Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Other RPs	51	10	20%	14	27%	6	12%	2	4%	19	37%

## Social_5
Remediation status of buildings with cladding defects monitored under the social housing surveys, time series, England, 31 August 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [Note 34] [Note 35] [Note 69]	Aug-23 / Number	Aug-23 / Percentage (%)	Dec-23 / Number	Dec-23 / Percentage (%)	Mar-24 [Note 68] / Number	Mar-24 [Note 68] / Percentage (%)	Jun-24 / Number	Jun-24 / Percentage (%)	Sep-24 / Number	Sep-24 / Percentage (%)	Dec-24 / Number	Dec-24 / Percentage (%)	Mar-25 / Number	Mar-25 / Percentage (%)	Jun-25 [Note 92] / Number	Jun-25 [Note 92] / Percentage (%)
Remediation complete [Note 37] [Note 54]	106	7%	204	10%	661	27%	703	28%	728	28%	857	32%	953	34%	1,099	37%
Remediation started [Note 72]	394	25%	525	27%	544	23%	565	23%	448	18%	370	14%	273	10%	286	10%
Remediation works planned	591	37%	658	34%	717	30%	699	28%	845	33%	990	36%	997	36%	991	34%
Remediation plans unclear from survey	510	32%	559	29%	488	20%	540	22%	585	21%	496	18%	571	20%	577	20%
Work is not required	7	0%	6	0%	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	1,608	100%	1,952	100%	2,410	100%	2,507	100%	2,606	100%	2,713	100%	2,794	100%	2,953	100%

## Enforcement_1
Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 20 October 2025
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [note 19] [note 76].

Local Authority [note 2]	BSF or CSS only (non-ACM cladding only) / Number / Previous month	BSF or CSS only (non-ACM cladding only) / Number / Current month	ACM cladding only / Number / Previous month	ACM cladding only / Number / Current month	Both ACM and non-ACM cladding in either the BSF or CSS / Number / Previous month	Both ACM and non-ACM cladding in either the BSF or CSS / Number / Current month	Not in any remediation fund (non-ACM cladding only) / Number / Previous month	Not in any remediation fund (non-ACM cladding only) / Number / Current month	Total / Number / Previous month	Total / Number / Current month
Barking and Dagenham	1	1	0	0	0	0	5	5	6	6
Barnet	3	3	3	3	1	1	3	3	10	10
Birmingham	4	4	1	1	0	0	12	12	17	17
Bournemouth, Christchurch and Poole	2	2	2	2	0	0	1	4	5	8
Bradford	0	0	1	1	0	0	0	0	1	1
Brent	0	0	2	2	0	0	0	0	2	2
Brighton and Hove	0	0	0	0	0	0	0	0	0	0
Bristol, City of	6	6	1	1	0	0	9	9	16	16
Bromley	0	0	0	0	0	0	0	0	0	0
Calderdale	0	0	0	0	0	0	0	0	0	0
Camden	16	16	1	1	0	0	28	28	45	45
City of London	3	3	0	0	0	0	8	8	11	11
Croydon	4	4	0	0	1	1	1	1	6	6
Dacorum	0	0	0	0	0	0	1	1	1	1
Ealing	2	2	1	1	1	1	1	1	5	5
Gateshead	0	0	0	0	0	0	0	0	0	0
Greenwich	4	4	0	0	0	0	7	7	11	11
Hackney	5	5	2	2	2	2	6	6	15	15
Hammersmith and Fulham	12	12	1	1	2	2	80	86	95	101
Haringey	0	0	0	0	0	0	0	0	0	0
Harrow	0	0	0	0	0	0	0	0	0	0
Hillingdon	3	3	1	1	0	0	10	10	14	14
Hounslow	0	0	0	0	0	0	1	1	1	1
Ipswich	0	0	0	0	0	0	0	0	0	0
Islington	3	10	0	0	0	0	7	7	10	17
Kensington and Chelsea	0	0	0	0	0	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0	0	0	0	0	0
Kirklees	0	0	0	0	0	0	0	0	0	0
Lambeth	2	2	2	2	0	0	0	0	4	4
Leeds	0	0	0	0	0	0	0	0	0	0
Leicester	0	0	0	0	0	0	0	0	0	0
Lewisham	0	0	0	0	0	0	0	0	0	0
Liverpool	4	4	2	2	3	3	2	2	11	11
Maidstone	0	0	0	0	0	0	0	0	0	0
Manchester	0	0	0	0	0	0	0	0	0	0
Medway	0	0	1	1	0	0	0	0	1	1
Merton	0	0	0	0	0	0	0	0	0	0
Milton Keynes	1	1	0	0	0	0	5	5	6	6
Newcastle upon Tyne	6	6	0	0	0	0	11	11	17	17
Newham	18	18	1	1	1	1	30	30	50	50
North Somerset	0	0	0	0	0	0	0	0	0	0
Norwich	0	0	0	0	0	0	0	0	0	0
Nottingham	3	3	1	1	0	0	1	1	5	5
Plymouth	3	3	0	0	0	0	3	3	6	6
Portsmouth	0	0	1	1	0	0	4	4	5	5
Reading	3	3	1	1	0	0	1	1	5	5
Redbridge	3	3	0	0	0	0	4	4	7	7
Salford	1	1	0	0	0	0	0	0	1	1
Sheffield	1	1	0	0	0	0	0	0	1	1
Slough	0	0	0	0	0	0	0	0	0	0
Southampton	3	3	0	0	0	0	0	0	3	3
Southwark	30	30	3	3	3	3	25	25	61	61
Sunderland	2	2	0	0	0	0	0	0	2	2
Sutton	0	0	0	0	1	1	0	0	1	1
Thanet	0	0	0	0	0	0	0	0	0	0
Tower Hamlets	26	26	8	8	5	5	32	32	71	71
Trafford	0	0	0	0	0	0	0	0	0	0
Waltham Forest	1	1	0	0	0	0	1	1	2	2
Wandsworth	1	1	2	2	1	1	0	0	4	4
Westminster	32	33	4	4	6	6	76	82	118	125
Windsor and Maidenhead	0	0	0	0	0	0	0	0	0	0
Others	17	17	0	0	2	2	36	36	55	55
Total	225	233	42	42	29	29	411	426	707	730

## Enforcement_2
Category rating of buildings inspected by local authorities, England, 20 October 2025
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [note 2]	Inspections with the building rated Category 1 [note 20] [note 68] / Number	Inspections with the building rated Category 2 [note 20] [note 68] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	3	3	0	6
Barnet	6	4	0	10
Birmingham	2	14	1	17
Bournemouth, Christchurch and Poole	7	0	1	8
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	13	3	16
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	3	39	3	45
City of London	7	3	1	11
Croydon	2	4	0	6
Dacorum	0	1	0	1
Ealing	2	3	0	5
Gateshead	0	0	0	0
Greenwich	3	4	4	11
Hackney	8	4	3	15
Hammersmith and Fulham	0	94	7	101
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	3	5	6	14
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	2	13	2	17
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	3	7	1	11
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	1	5	6
Newcastle upon Tyne	1	13	3	17
Newham	13	32	5	50
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	0	5	0	5
Plymouth	2	4	0	6
Portsmouth	0	2	3	5
Reading	0	5	0	5
Redbridge	3	3	1	7
Salford	0	1	0	1
Sheffield	0	0	1	1
Slough	0	0	0	0
Southampton	1	0	2	3
Southwark	29	29	3	61
Sunderland	1	1	0	2
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	13	43	15	71
Trafford	0	0	0	0
Waltham Forest	0	2	0	2
Wandsworth	1	3	0	4
Westminster	6	118	1	125
Windsor and Maidenhead	0	0	0	0
Others	13	34	8	55
Total	140	511	79	730

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 20 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [note 2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number	Improvement notice appeals / Number
Barking and Dagenham	2	0	0	2	0
Barnet	9	0	0	9	3
Birmingham	14	0	0	14	1
Bournemouth, Christchurch and Poole	4	0	0	4	4
Bradford	1	0	0	1	1
Brent	0	0	0	0	0
Brighton and Hove	0	0	0	0	0
Bristol, City of	0	0	0	0	0
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	15	3	0	18	4
City of London	4	0	0	4	0
Croydon	1	0	0	1	0
Dacorum	1	0	0	1	0
Ealing	2	0	0	2	0
Gateshead	0	0	0	0	0
Greenwich	6	1	0	7	0
Hackney	11	1	0	12	0
Hammersmith and Fulham	0	6	0	6	0
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	5	1	0	6	3
Hounslow	1	0	0	1	0
Ipswich	0	0	0	0	0
Islington	14	1	0	15	2
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	4	0	0	4	0
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	6	0	0	6	1
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	1	0	0	1	1
Merton	0	0	0	0	0
Milton Keynes	1	0	0	1	0
Newcastle upon Tyne	3	4	0	7	0
Newham	36	5	0	41	13
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	3	0	0	3	0
Plymouth	3	3	0	6	1
Portsmouth	1	0	0	1	0
Reading	0	0	0	0	0
Redbridge	4	1	0	5	1
Salford	0	0	0	0	0
Sheffield	0	0	0	0	0
Slough	0	0	0	0	0
Southampton	1	0	0	1	1
Southwark	34	4	0	38	10
Sunderland	1	0	0	1	0
Sutton	1	0	0	1	0
Thanet	0	0	0	0	0
Tower Hamlets	18	22	0	40	2
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	1	1
Wandsworth	1	0	0	1	0
Westminster	1	20	1	22	1
Windsor and Maidenhead	0	0	0	0	0
Others	19	1	0	20	7
Total	229	73	1	303	57

## Enforcement_4
Number of inspections by local authorities supported by the Joint Inspection Team, England, 20 October 2025
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team [note 76].
Local Authority [note_2]	Inspections supported by the Joint Inspection Team [note 21] / Number	Inspections supported by the Joint Inspection Team [note 21] / Number	Buildings inspected with support from the Joint Inspection Team [note 75] / Number	Buildings inspected with support from the Joint Inspection Team [note 75] / Number
	Previous month	Current month	Previous month	Current month
Barking and Dagenham	2	2	2	2
Barnet	3	3	3	3
Birmingham	15	15	14	14
Bournemouth, Christchurch and Poole	2	2	2	2
Bradford	0	0	0	0
Brent	2	2	2	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	6	6	6	6
City of London	1	1	1	1
Croydon	6	6	6	6
Dacorum	0	0	0	0
Ealing	5	5	5	5
Gateshead	0	0	0	0
Greenwich	12	12	11	11
Hackney	12	12	12	12
Hammersmith and Fulham	3	3	2	2
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	1	1	1	1
Hounslow	1	1	1	1
Ipswich	0	0	0	0
Islington	3	3	3	3
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	2	2
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	9	9	9	9
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	0	0	0	0
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	2	2	2
Newham	28	28	28	28
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	3	3	3	3
Plymouth	1	1	1	1
Portsmouth	3	3	3	3
Reading	0	0	0	0
Redbridge	4	4	4	4
Salford	1	1	1	1
Sheffield	1	1	1	1
Slough	0	0	0	0
Southampton	3	3	3	3
Southwark	5	5	5	5
Sunderland	1	1	1	1
Sutton	1	1	1	1
Thanet	0	0	0	0
Tower Hamlets	22	22	22	22
Trafford	0	0	0	0
Waltham Forest	2	2	2	2
Wandsworth	4	4	4	4
Westminster	3	3	3	3
Windsor and Maidenhead	0	0	0	0
Others	10	10	10	10
Total	179	179	176	176

## JIT_1
Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for the number of Joint Inspection Team training sessions attended by local authority officers. [Note 71]
Local Authority [note_22]	Intro to Fire Safety (Level 1) Total attendees 2024 [note 89] / Number	Intermediate Fire Safety (Level 2) Total attendees 2024 [note 89] / Number	Intro to Fire Safety (Level 1) Total attendees 2025 [note 89] / Number	Intermediate Fire Safety (Level 2) Total attendees 2025 [note 89] / Number	Intro to Fire Safety (Level 1) Total attendees [note 90] / Number	Intermediate Fire Safety (Level 2) Total attendees [note 90] / Number
Barking and Dagenham	0	2	0	1	0	3
Barnet	0	3	0	0	4	6
Birmingham	0	3	0	0	10	21
Bournemouth, Christchurch and Poole	0	0	0	1	10	6
Bradford	0	0	0	2	24	7
Brent	0	0	0	0	1	4
Brighton and Hove	0	0	0	0	0	12
Bristol, City of	0	0	0	0	10	8
Bromley	0	0	0	0	3	0
Calderdale	0	0	0	0	3	1
Camden	0	1	0	3	16	20
City of London	0	0	0	0	8	5
Croydon	0	3	0	2	26	10
Dacorum	0	0	0	0	4	3
Ealing	0	6	0	1	10	7
Gateshead	0	0	0	0	6	3
Greenwich	0	1	0	2	2	12
Hackney	0	9	0	3	18	16
Hammersmith and Fulham	0	6	0	0	20	16
Haringey	0	0	0	0	4	2
Harrow	0	2	0	0	1	2
Hillingdon	0	1	0	0	3	2
Hounslow	0	1	0	0	4	4
Ipswich	0	0	0	0	0	0
Islington	0	3	0	1	11	10
Kensington and Chelsea	0	0	0	0	0	1
Kingston upon Thames	0	0	0	0	3	0
Kirklees	0	0	0	1	2	2
Lambeth	0	7	0	1	16	16
Leeds	0	0	0	3	6	5
Leicester	0	0	0	0	0	0
Lewisham	0	0	0	0	5	3
Liverpool	0	0	0	0	32	15
Maidstone	0	0	0	0	0	0
Manchester	0	2	0	0	8	7
Merton	0	5	0	2	6	7
Medway	0	0	0	3	12	8
Milton Keynes	0	0	0	0	6	7
Newcastle upon Tyne	0	0	0	0	6	5
Newham	0	2	0	3	10	10
North Somerset	0	0	0	0	8	5
Norwich	0	0	0	0	11	7
Nottingham	0	27	0	0	34	43
Plymouth	0	0	0	0	3	3
Portsmouth	0	0	0	3	2	17
Richmond and Wandsworth	0	0	0	1	8	11
Reading	0	2	0	0	15	5
Redbridge	0	1	0	0	4	3
Salford	0	0	0	0	11	7
Sheffield	0	1	0	3	0	4
Slough	0	0	0	3	5	10
Southampton	0	0	0	0	1	1
Southwark	0	1	0	0	7	1
Sunderland	0	0	0	0	3	5
Sutton	0	0	0	0	2	0
Thanet	0	1	0	0	2	2
Tower Hamlets	0	8	0	3	9	16
Trafford	0	0	0	0	7	3
Waltham Forest	0	3	0	2	6	9
Westminster	0	5	0	1	17	12
Windsor and Maidenhead	0	1	0	0	8	5
Others	0	31	0	20	414	266
Total	0	138	0	65	887	701

## Estimated_1
Estimates of the number of residential buildings, containing dwellings, that have or had unsafe cladding requiring work, 11 metres and over in height, England, January 2025
Back to Contents
This worksheet contains two tables. Figures are for number of 11m+ buildings, containing dwellings, estimated to have unsafe cladding, and the percentage of the 11m+ residential buildings stock, containing dwellings, that relates to.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height [Note_10, Note_77, Note_79, Note_80, Note_81, Note_82]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	2,900	5,800
18m+	2,900	3,200
Total 11m+	5,900	9,000

Building height	Estimated prevalence of unsafe cladding in residential buildings 11 metres and over (low) / Percentage (%)	Estimated prevalence of unsafe cladding in residential buildings 11 metres and over (high) / Percentage (%)
11-18m	8%	10%
18m+	24%	27%
Total 11m+	12%	13%

## Estimated_2
Estimates of the number of residential buildings, that have or had unsafe cladding requiring work, expected to be remediated or mitigated as part of a government remediation programme, 11 metres and over in height, England, January 2025
Back to Contents
This worksheet contains one table. All figures are for number of 11m+ residential buildings with unsafe cladding estimated to be remediated or mitigated as part of the department's five remediation programmes (ACM programme, BSF, CSS, developer-led remediation, and social housing remediation).
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height [Note_10, Note_77, Note_79, Note_81, Note_82]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	2,800	5,400
18m+	3,000	3,200
Total 11m+	5,700	8,600

## Estimated_3
Estimated proportion of buildings with unsafe cladding expected to be remediated or mitigated in a government remediation programme that are currently monitored in a government remediation programme, 30 September 2025
Back to Contents
This worksheet contains one table. All figures are for proportion of 11m+ residential buildings with unsafe cladding estimated to be remediated or mitigated as part of the department's five remediation programmes (ACM programme, BSF, CSS, developer-led remediation, and social housing remediation), that are currently monitored in a government remediation programme.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Building height [Note_77, Note_79, Note_81]	Estimated percentage of buildings 11 metres and over with unsafe cladding that are monitored by MHCLG (low estimate) / Percentage (%)	Estimated percentage of buildings 11 metres and over with unsafe cladding that are monitored by MHCLG (high estimate) / Percentage (%)
11-18m	88%	45%
18m+	106%	98%
Total 11m+	97%	65%

## Estimated_4
Estimates of the number of residential buildings, that have or had unsafe cladding requiring remediation or mitigation work, expected to be remediated or mitigated as part of a government funded scheme, based on January 2025 eligibility criteria, 11 metres and over in height, England, January 2025
Back to Contents
This worksheet contains one table. All figures are for number of 11m+ residential buildings estimated to be remediated in a government funded scheme (ACM programme, BSF, CSS).
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height [Note_77, Note_78, Note_79, Note_81, Note_88]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	800	3,700
18m+	1,500	1,600
Total 11m+	2,300	5,300