Public Service Delivery Review Board
Teams Meeting Minutes
18 June 2025

Attendees: Patrick Kiernan (GDS), Julian Firth (GDS), Rhian Jones (GDS), Sadia Siema (GDS), Sulaiman Saeed (GDS), Mark Brewin (HMRC), Stephen Mak (MHCLG), Mark Williams (LGA), Ruth Richmond (DESNZ)
Observers: Sarah Lawrence (ICO)
Apologies: Andy Gregory (HO), Helen Walker (DWP), Vicky Chico (NHSX), Louise Greenrod (DHSC)

1	Welcome and introduction from the Chair
1.1	Members are welcomed by Patrick Kiernan, deputising for the chair.
2	Conflicts of interest, minutes, and actions brought forward
2.1	No Conflicts
2.3	The following action points are ongoing: / Action Point 74: Discussions have taken place with UKSA regarding their Code of Practice and potential changes. / Action point 80: Secretariat to review comments raised on the data sharing register. Work has been done with the team to define formatting for the debt and fraud powers / Action point 81: Discussions with Homes England and MHCLG regarding homes buying as a potential PSD data share, however yet to be defined.
3	Work programme update
3.1	Data Use and Access Bill / The DUA Bill has cleared parliamentary passage and is awaiting Royal Assent. / Commencement to extend PSD powers to businesses is expected to support businesses. / Data sharing will help deliver grants and support economic growth. / GDS will work with DBT to submit a new proposal for the Review Board to consider, potentially for September.
3.2	Section 36 Amendment and Passported Benefits: / In order to make good use of Parliamentary time, one Statutory instrument will be used, combining Section 36 and Passported Benefits. This will be submitted for Write Round before recess, with the consultation launching shortly after, subject to ministerial approval.
3.3	Northern Ireland Commencement / Following commencement, work will begin with the Department of Finance Team for Schedule 4 PSD and Debt Fraud Powers / Timeline for commencement: October
3.4	DEA Register Update / Currently at 472 ISAs. / Action Point xx To present an update on the Register at the next Review Board / Supplementary guidance may be necessary to explain the difference between terms such as “pilot” and “BAU” to the public.
3.5	Code of Practice / GDS will reach out to stakeholders and ICO to provide views on areas of the Code of Practice to be updated.
3.6	Energy Efficient Homes Consumer Advice & Information / The Consumer Advice & Information team in DESNZ are reviewing feedback from the board and will come back with a finalised proposal.
3.7	Homes England are currently working with DWP and HMRC to identify the data necessary to support their policy initiative.
3.8	Early Help and Prevention / Work continues on proactive data sharing to support the most vulnerable. / 2 key areas include: / Financial Hardship with Scottish Local Authorities has focussed on how data could support reducing child poverty, particularly in rural areas. Scoping a new PSD objective. Likely to come to the board in March 2026 / Skills Development by DfE, GMCA and Scottish Government to help increase employability for those aged 16-24 not in education or training.
4	Discussion
4.1	The board agreed to the “light touch” update format as an alternative to written papers for future meetings, provided meeting minutes are circulated afterwards. / SAAVI was mentioned as a potential speaker to present at the next meeting.
5	AOB
6	DONM 17 September 2025 2 - 4pm