Public Service Delivery Review Board Teams Meeting Minutes
17 September 2025

Chair: Dr. Shruti Kohli (GDS)
Attendees: Rhian Jones (GDS), Patrick Kiernan (GDS), Sadia Siema (GDS), Ebru Yilmaz (GDS), Roisin Hogarth (GDS), Sue Wharram (DfE), Stephen Mak (MHCLG), Mark Williams (LGA), Ruth Richmond (DESNZ)
Observers: Sarah De Bruin (ICO), Samuel Higley (HMRC), Lara Kaplan (DSIT), Scott Colin (DoF, NI), Glyn Jones (WG)
Apologies: Andy Gregory (HO), Helen Walker (DWP), Vicky Chico (NHSX), Louise Greenrod (DHSC), Alessia Morris (SG), Mark Brewin (HMRC)

1	Welcome and introduction from the Chair
1.1	Members are welcomed, and members are introduced to the new Chair of the board, Dr. Shruti Kohli.
2	Conflicts of interest, minutes, and actions brought forward
2.1	No conflicts of interest raised
2.2	Minutes from the previous meeting 18 June 2025 were approved / Action Point 82: secretariat to publish minutes from 18 June 2025 on GOV.UK
2.3	The following action points are ongoing: / ACTION POINT 74: Discussions have taken place with UKSA regarding their Code of Practice and potential changes. / ACTION POINT 75: secretariat to engage with interested review board members when progressing discussions with the resilience and recovery directorates / The following action points have been closed: / ACTION POINT 80: Secretariat to review comments raised on the data sharing register. Work has been done with the team to define formatting for the debt and fraud powers / ACTION POINT 81: Discussions with Homes England and MHCLG regarding home buying as a potential PSD objective
3	Work programme update
3.1	Data Use and Access Act 2025 / The DUA Act 2025 received Royal Assent in June 2025. / The secretariat will undertake the legislative process to commence the changes outlined in clause 123 of the DUA Act 2025. On completion, section 35 of the DEA will extend to enable objectives to be set with a view to delivering benefits and improving public services for businesses and undertakings. / GDS will work with DBT to submit a new proposal for the Review Board to consider in due course
3.2	Section 36 amendment and passported benefits objective: / The public consultation seeking views on the section 36 amendment and the education related passported benefits objective is currently live and will close on 23 September 2025. Work to commence the consultation analysis and drafting of the government response will follow.
3.3	Northern Ireland Commencement / The secretariat informed members that regulations are to be signed by the Minister to commence the Public Service Delivery, Debt and Fraud powers of the DEA in Northern Ireland. Following commencement, the secretariat will support the Department of Finance with adding relevant public bodies to the relevant schedules of the DEA.
3.4	DEA Register Update / Members were briefed on the latest updates to the register of information sharing agreements which now include 479 entries.
3.7	New objective: Dormant Assets / The Secretariat has been working with HMT to engage with stakeholders to understand the required data items which would be needed to support the reunification of individuals with their lost assets.
3.8	New objective: Homes England / Homes England are currently working with DWP and HMRC to identify the data necessary to support the help to buy scheme and whether a PSD objective would support delivery of additional support to customers. A new objective under section 35 of the Digital Economy Act 2017 could allow Homes England to support financially vulnerable customers through the provision of access to tailored products.
3.9	New objective: skills development Scotland / This objective could potentially allow data to be shared to help identify and target individuals aged between 16-24 who may be eligible for the offer to take up education and training opportunities. The secretariat confirmed that contact will be made with officials from DfE, the Welsh Government and Northern Ireland (contingent on commencement regulations) to assess whether expanding the territorial application of the proposal could deliver wider benefits in their respective regions.
3.10	New objective: parental imprisonment / The secretariat is exploring whether a data sharing legal gateway could help target support for children who are affected by parental imprisonment.
3.11	New objective: Early Help and Prevention / The secretariat continues to progress discussions to identify ways in which proactive data sharing could support the most vulnerable. / This includes an enquiry to look into Financial Hardship with Scottish Local Authorities, focussing on how data could support reducing child poverty, particularly in rural areas.
4	Review: Code of Practice
4.1	The secretariat informed members that work is in progress to conduct a review of the statutory Code of Practice for disclosures under chapters 1,3,4 of Part 5 of the DEA. Members were also informed that a copy of the Code would be circulated in due course, for members to have an opportunity to suggest changes and amendments. / ACTION POINT 82: secretariat to circulate the Code of Practice / ACTION POINT 83: members to provide comments and suggestions by the agreed deadline
5	Ways of working: legal process review
5.1	The secretariat briefed members on new ways of working, which will potentially involve a single annual cycle for establishing new objectives or changes to the DEA.
6	Review: Terms of Reference
6.1	The Terms of Reference (ToR) will be reviewed and the updated ToR will be published on GOV.UK / ACTION POINT 84: The Terms of Reference will be updated and circulated to members for comments and feedback / ACTION POINT 85: Members to review the proposed Terms of Reference within the set timeframe.
7	AOB
7.1	None raised
8	DONM 10 December 2025 2 - 4pm