Project’s Information Production Methods and Procedures

Employer’s requirements

Project code: [SRP/FS/FE code]

Project name: [Name of school/college]

[Month] 20[XX]

Contents

Summary	4

Review date	4

Who this publication is for?	4

Document history	6

Template	6

Project specific	6

Abbreviations	7

References	7

1 Introduction	8

2 Information delivery planning	9

2.1 Check availability of reference information and shared resources	9

2.2 Task Information Delivery Plan template	9

2.3 Task Information Delivery Plan(s)	10

2.4 Master Information Delivery Plan	10

3 Capture of existing asset information	12

4 Generation of new information	15

4.1 Generating documents	15

4.2 Generating drawings	15

4.3 Generating native models – General	16

4.4 Generating native models – Software specific	16

4.5 Generating IFC-SPF files – General	17

4.6 Generating IFC-SPF files – Software specific	17

4.7 Generating federated models	17

4.7.1 Generating federated coordination models	17

4.7.2 Generating federated information models	17

4.8 Generating COBie	18

4.9 Generating the Risk Register	18

4.10 Generating surveys	18

5 Review of new information	19

5.1 Undertake quality assurance check	19

5.2 Review information and approve for sharing	19

5.3 Information model review	20

5.3.1 Native model review	20

5.3.2 IFC-SPF file review	20

5.3.3 Federated model(s) review	20

6 Approval of new information	22

6.1 Document review	22

6.2 Drawing review	22

6.3 Native model review	22

6.4 Federated model review	23

6.5 COBie review	23

7 Security of information	24

8 Distribution of information	25

8.1 Project’s common data environment	25

8.2 Distributed common data environment(s)	25

9 Delivery of information to the DfE	26

9.1 Submitting the information model for Contractor authorisation	26

9.2 Review and authorise the information model	26

9.3 Submit information for DfE acceptance	27

9.4 Review and accept the information model	27

9.5 Acceptance workflow	28

10 Lessons learned	29

# Summary

This document is the Project’s Information Production Methods and Procedures for use on all DfE delivered schemes using the DfE Construction Framework 2025 (CF25). The completed Project’s Information Production Methods and Procedures forms part of the DfE’s information management requirements for schemes and shall be read in conjunction with:

Project’s Information Protocol

Exchange Information Requirements

Detailed Exchange Information Requirements

Project’s Information Standard

Advisory note

This document contains a series of advisory notes that should be deleted once addressed by the Technical Advisor, including this one.

## Review date

This document shall normally be reviewed at 12-month intervals however, DfE reserve the right to update it at any time.

## Who this publication is for?

This guidance is for:

local authorities (for community, voluntary-controlled schools, foundation schools and maintained nursery schools)

academy trusts (for academies and free schools)

governing bodies (for voluntary-aided schools)

school/college leaders, staff and governing bodies in; further education colleges and designated institutions, sixth form colleges, maintained schools, academies and free schools, pupil referral units, City Technology Colleges, non-maintained special schools and maintained nursery schools

technical professionals involved in the design, construction and maintenance of school and college premises.

Academy trusts with a religious character and the responsible bodies for voluntary-aided and voluntary controlled schools should engage with the land/site trustees for their land and buildings and the relevant religious body, most often their Diocese.

## Document history

This table lists the key changes in each update

### Template

| Revision code | Status code | Date | Amendment |
| --- | --- | --- | --- |
| C01 | A | 2026-01-12 | GOV.UK publication |

### Project specific

| Revision code | Status code | Date | Amendment |
| --- | --- | --- | --- |
| Pnn | Sn | 20YY-MM-DD | Employer's Representative to add amendments made to document here and rename file to make project specific |

The DfE and its agents and advisers accept no liability whatsoever for any expense, liability, loss, claim or proceedings arising from reliance placed upon this resource.

# Abbreviations

For the list of commonly used abbreviations in the context of DfE’s information management requirements, refer to the Project’s Information Standard.

## References

A number of documents and files, in whole or in part, are referenced in this resource.  Where a date is referenced, the edition cited applies. Where a date is not referenced the latest edition of the referenced resource, document or file (including any amendments) applies.

# 1 Introduction

DfE have established the specific information production methods and procedures required by the DfE organisation within this Project’s Information Production Methods and Procedures.

In doing this, DfE have considered:

information delivery planning

the capture of existing asset information

the generation, review or approval of new information

the security or distribution of information, and

the delivery of information to the DfE

The Contractor may propose additions and amendments to the Project’s Information Production Methods and Procedures within their (pre-appointment) BIM Execution Plan during the tender response phase. The minimum requirements are set out in the Exchange Information Requirements.

Further changes to this resource required by the Contractor and the delivery team post-appointment shall be agreed through a formal change control/derogations process.

This resource satisfies the requirements of BS EN ISO 19650-2 clause 5.1.5 and clause 5.4.1 d).

# 2 Information delivery planning

This section satisfies the requirements of BS EN ISO 19650-2 clauses 5.4.4, 5.4.5 and 5.6.1.

The use of information delivery plans is to ensure information is planned in advance to reduce waste and to provide information at the right time for other parties’ needs.

## 2.1 Check availability of reference information and shared resources

This section satisfies the requirement of BS EN ISO19650-2 clause 5.6.1.

Prior to generating information, each task team shall check that they have access to the relevant reference information and shared resources within the project’s common data environment. If not, they shall, as soon as practicable, inform the Contractor and assess the potential impact that this could have on their Task Information Delivery Plan(s).

## 2.2 Task Information Delivery Plan template

A Task Information Delivery Plan template shall be developed by the Contractor to ensure information coordination and consistency. This template shall list and identify, as a minimum, for each file:

the name (following the required file naming set out in the Project’s Information Standard)

the description as it will appear on the output and in the common data environment

the classification according to Uniclass PM Project management table

the Detailed Exchange Information Requirements’ ID No

the scale

the format for exchange

the predecessors or dependencies (optional)

the (estimated) production duration (optional), and

the delivery milestones

The Task Information Delivery Plan template shall also be uploaded to the project’s common data environment or access provided to a cloud-based solution if appropriate.

## 2.3 Task Information Delivery Plan(s)

Each task team shall complete the Task Information Delivery Plan template provided (refer to 2.2 Task Information Delivery Plan template) and maintain throughout its appointment.

The Technical Advisor and any other information authors outside the Contractor team shall also complete a Task Information Delivery Plan.

In completing the task information delivery plan, each task team shall consider:

the project’s information delivery milestones

the task team’s responsibilities within the detailed responsibility matrix

the exchange information requirements (DfE and Contractor)

the availability of shared resources within the delivery team, and

the time the task team will need to produce (generate, coordinate, review and approve) information

All files to be produced for the project shall be listed in the Task Information Delivery Plan. This includes all documents (including drawings) and models.

File names listed in the Task Information Delivery Plan shall be provided in accordance with the Project’s Information Standard. If information is required to complete the naming in the Task Information Delivery Plan, but is not available in the information naming protocol, please contact the Technical Advisor to update accordingly.

The Task Information Delivery Plan shall be named correctly for each task team and uploaded to the project’s common data environment in .xlxs format.

## 2.4 Master Information Delivery Plan

The Contactor shall aggregate the information contained within the task information delivery plans produced by the task teams, to establish the Master Information Delivery Plan.

In doing this, the Contractor shall consider:

the assigned responsibilities within the detailed responsibility matrix

the information predecessors or dependencies on information between task teams

the time the Contractor will need to review and authorise the information model, and

the time the DfE (Technical Advisor) will need to review and accept the information model

Once the Master Information Delivery Plan has been established, the Contractor shall:

baseline the deliverables and dates within the Master Information Delivery Plan

inform each task team and notify if any changes are required to the Task Information Delivery Plan, and

inform the DfE of any risks or issues which could impact on the project’s information delivery milestones

The Master Information Delivery Plan shall list the Task Information Delivery Plan for each originator which forms the aggregated document and include the revision as a minimum.

The selected Contractor shall confirm the file name for the Master Information Delivery Plan in an Appendix of the BIM Execution Plan (refer to EIR Section D3). The file name shall be transposed from the Appendix of the BIM Execution Plan to the Information Particulars within the Project’s Information Protocol by the Technical Advisor.

# 3 Capture of existing asset information

Advisory note

The text for this section is dependent on whether existing asset information is required for the project. The Technical Advisor shall select the appropriate green placeholder text from the options below:

- Option 1 shall be selected for a new building with no proposed alterations or connections to existing assets

- Option 2 shall be selected for a project that includes some existing assets and an element of refurbishment or consequential works

The Technical Advisor shall identify in this section any existing asset information that has been collected during Feasibility (e.g., specific surveys undertaken or the discovery of existing asset information like O&M manuals).

Advisory note

For Option 1, delete Option 2. Update table to reflect specific asset information.

This project is a new building therefore, existing asset information has not been captured other than the survey information listed below:

| Asset Information | Filename |
| --- | --- |
| Topographical Survey Information |  |
| Transport Survey Information |  |
| Underground Utilities Survey Information |  |
| Archaeology Preliminary Survey Information |  |
| Intrusive Geotechnical and Geo-Environmental Investigations |  |
| Acoustic Survey Information |  |
| Air Quality Survey Information |  |
| Flood Risk Assessment Information |  |
| Unexploded Ordnance Risk Assessment Survey Information |  |

Advisory note

For Option 2, delete Option 1. Update table to reflect specific asset information.

The project has some parts that include existing assets. The following existing asset and survey information has been captured:

| Asset Information | Filename |
| --- | --- |
| Building Services Stage 1 Condition Survey Information (Basic) |  |
| Building Services Stage 2 Condition Survey Information (Detailed) |  |
| Legacy FF&E Schedule |  |
| Building Condition Survey Information |  |
| Historic Building Survey Information (Preliminary) |  |
| Photogrammetry Survey Information |  |
| Topographical Survey Information |  |
| Transport Survey Information |  |
| Underground Utilities Survey Information |  |
| Archaeology Preliminary Survey Information |  |
| Intrusive Geotechnical and Geo-Environmental Investigations |  |
| Underground Drainage CCTV Survey Information |  |
| Acoustic Survey Information |  |
| Air Quality Survey Information |  |
| Flood Risk Assessment Information |  |
| Measured Building Survey Information |  |
| Detailed Measured Building Survey Information |  |
| Asbestos Survey Information |  |
| Unexploded Ordnance Risk Assessment Survey Information |  |
| Structural Stage 1 Condition Survey Information (Basic) |  |
| Structural Stage 2 Condition Survey Information (Detailed) |  |

# 4 Generation of new information

This section satisfies the requirements of BS EN ISO 19650-2 clause 5.6.2.

Each task team shall generate information in accordance with their respective Task Information Delivery Plan. In doing this, the task team shall:

- generate information:

  - in compliance with the Project’s Information Standard, and

  - in accordance with the Project’s Information Production Methods and Procedures

- not generate information that:

  - exceeds the required level of information need

  - extends beyond the allocated element of the file (information container) breakdown structure

  - duplicates information generated by other task teams, or

  - contains superfluous detail

- coordinate and cross-reference all information with information shared within the project’s common data environment, in accordance with the Project’s Information Production Methods and Procedures, and

- spatially coordinate geometrical models with other geometrical models shared with the appropriate status, residing within the project’s common data environment

In the event of a coordination issue, the relevant task teams shall collaborate to identify a possible resolution. If a resolution cannot be found the task teams shall notify the Contractor.

## 4.1 Generating documents

Documents shall be generated in accordance with 4 Generation of new information.

## 4.2 Generating drawings

Drawings shall be generated in accordance with 4 Generation of new information.

Drawing outputs from the model shall be shared using traditional drawing conventions.

Drawings shall adhere to the following:

information optimised for the purpose of the intended use

minimise repetition of illustrated details

no duplication of drawings

## 4.3 Generating native models – General

Native models shall be generated in accordance with 4 Generation of new information.

Models shall be developed with the proposed outputs in mind at all times.

Data therefore authored in the native modelling tools needs to be suitable for creating a compliant IFC-SPF output, which in turn can create a valid COBie output.

All model authors shall adhere to the following methods and procedures:

the model shall be produced in line with the Project’s Information Standard, Project’s Information Production Methods and Procedures and the BIM Execution Plan

final finishing items, such as skirtings, architraves, dado rails, picture rails, grouting and similar may be excluded where construction is not compromised or there is nominal cost significance

building entities shall be authored using the correct entity classification (Category) within the native authoring tool or Industry Foundation Classes (IFC) mapping settings to allow correct export of entities in line with the IFC schema

objects shall be modelled in accurate locations, with accurate dimensions in alignment with design intent

error logs/messages shall be regularly checked and issues resolved (e.g., duplicate objects)

objects shall comprise of correct materials in line with the design intent, or shall be indicated as Concept or TBC

all Spaces shall be modelled to ensure objects can be associated to them i.e., Spaces shall meet entities (i.e., meet Walls, Curtain Walls, Columns etc) where appropriate

representations of model components’ material specifications and scopes shall be modelled correctly and accurately in respect to the actual physical materials of the components to allow for material take-off and accurate design calculations

modelling shall follow the method of construction e.g., internal walls shall not span across structural elements

objects shall not appear in more than one model, and

for the benefit of all, accurately assigned content will improve the efficiency of teams’ drawing production and support ‘turning off’ unrequired content for model optimisation

## 4.4 Generating native models – Software specific

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1).

## 4.5 Generating IFC-SPF files – General

The following is required for each IFC-SPF file created and issued by each task team:

shall be generated in accordance with 4 Generation of new information

shall be generated in accordance with the Project’s Information Standard

shall use the agreed settings and configurations required to create a compliant IFC-SPF file output from the agreed model authoring tools, and

shall be reviewed and checked by the authoring organisation before upload to the project’s common data environment – this may be as simple as reviewing in a free IFC-SPF model viewer

## 4.6 Generating IFC-SPF files – Software specific

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1). It shall set out any specific processes required to generate compliant IFC-SPF outputs from specific native software solutions.

## 4.7 Generating federated models

### 4.7.1 Generating federated coordination models

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1).

This section shall include information on the following:

responsibility for producing the federated coordination model(s)

formats used for model federation

software used to federate the models for clash detection

frequency of model federation

clash detection identification process

issue management process, and

clash resolution workshops

### 4.7.2 Generating federated information models

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1).

This section shall include information on the following:

responsibility for producing the federated information model(s)

formats used for model federation

software used to federate the models for data review

frequency of model federation, and

data issues identification and resolution process

## 4.8 Generating COBie

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1). This section shall set out the process for producing the federated COBie output.

## 4.9 Generating the Risk Register

This section satisfies the requirements of BS EN ISO 19650-2 clause 5.3.6.

The Contractor shall establish the delivery team’s Risk Register containing the risks associated with the timely delivery of information (i.e., the potential impact of late, insufficient or missing information), in accordance with the Exchange Information Requirements and the Detailed Exchange Information Requirements, and how the delivery team intends to manage these risks.

In doing this, the Contractor shall consider risks associated with:

assumptions the delivery team has made in relation to the Exchange Information Requirements and the Detailed Exchange Information Requirements

meeting the DfE’s project information delivery milestones

the contents of the Project’s Information Protocol

achieving the proposed information delivery strategy

adopting the Project’s Information Standard and Project’s Information Production Methods and Procedures

inclusion (or non-inclusion) of proposed amendments to the Project’s Information Standard and Project’s Information Production Methods and Procedures, and

the mobilisation of the delivery team to achieve the required capability and capacity

## 4.10 Generating surveys

Measured and photogrammetry surveys shall support the progressive build-up of information for a project in accordance with ISO 19650-2. All survey files shall be named in accordance with the Project’s Information Standard.

# 5 Review of new information

This section satisfies the requirements of BS EN ISO 19650-2 clauses 5.6.3, 5.6.4 and 5.6.5.

## 5.1 Undertake quality assurance check

This section satisfies the requirements of BS EN ISO 19650-2 clause 5.6.3.

Each task team shall undertake a quality assurance check of each information container, in accordance with the Project’s Information Production Methods and Procedures, prior to undertaking a review of the information within it.

In doing this, the task team shall check the file name in accordance with the Project’s Information Standard.

Once the check is complete, the task team shall:

- if the check is successful:

  - mark the file as checked, and

  - record the outcome of the check, or

- if the check is unsuccessful:

  - reject the file, and

  - inform the information author of the outcome and corrective action required

## 5.2 Review information and approve for sharing

This section satisfies the requirements of BS EN ISO 19650-2 clause 5.6.4.

In accordance with the Project’s Information Production Methods and Procedures, each task team shall undertake a review of the information within each file prior to sharing within the project’s common data environment.

In doing this, the task team shall consider:

the information requirements

the level of information need, and

information needed for coordination by other task teams

Once the review is complete, the task team shall:

- if the review is successful:

  - assign the status for which the information contained within the file can be used, and

  - approve the file for sharing

- if the review is unsuccessful:

  - record why the review was unsuccessful

  - record any amendments for the task team to complete, and

  - reject the file

Internal review processes shall be documented by each task team as part of their capability assessment.

## 5.3 Information model review

This section satisfies the requirements of BS EN ISO 19650-2 clause 5.6.5.

### 5.3.1 Native model review

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1).

### 5.3.2 IFC-SPF file review

All IFC-SPF files shall be reviewed against the requirements set out in 4.5 Generating IFC-SPF files – General and 4.6 Generating IFC-SPF files – Software specific.

As a minimum, IFC-SPF files shall be reviewed manually/visually in a free or paid for IFC-SPF viewer by model authors before upload to the project’s common data environment.

This section shall be further populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1).

### 5.3.3 Federated model(s) review

Clash detection review

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1). The responsibility for clash detection shall be confirmed by the Contractor.

An agreed timescale for these checks shall be included in the project programme but it is anticipated models are reviewed monthly.

Dates for clash analysis cycles and subsequent workshops shall also be documented in the project programme.

Data Review

An agreed timescale for these checks shall be included in the project programme but it is anticipated models are reviewed monthly.

Issue Management – Clash Detection

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1).

Issue Management - Data

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1).

# 6 Approval of new information

In order for information to be submitted to the DfE, it shall be submitted to the agreed party for authorisation. Information that is rejected shall be returned to the author for corrective action to take place.

Once the output is authorised, the information shall be shared with the DfE.

The following reviews shall take place before the information is shared with the DfE:

document review

drawing review

native model review

federated model review

COBie review

## 6.1 Document review

Documents shall be reviewed by the Contractor prior to submission to the DfE.

All documents shall be reviewed against the requirements set out in 4.1 Generating documents.

The Contractor shall review the project’s common data environment at each information exchange to ensure that documents identified on the Master Information Delivery Plan have been uploaded.

## 6.2 Drawing review

Drawings shall be reviewed by the Contractor prior to submission to the DfE.

All drawings shall be reviewed against the requirements set out in 4.2 Generating drawings.

The Contractor shall review the project’s common data environment at each information exchange to ensure that drawings identified on the Master Information Delivery Plan have been uploaded.

## 6.3 Native model review

Native model files shall be reviewed by the Contractor prior to submission to the DfE.

All native model files shall be reviewed against the requirements set out in 4.3 Generating native models – General and 4.4 Generating native models – Software specific.

The Contractor shall review the project’s common data environment at each information exchange to ensure that native models identified on the Master Information Delivery Plan have been uploaded.

## 6.4 Federated model review

Federated models shall be reviewed by the Contractor prior to submission to the DfE.

All federated models shall be reviewed against the requirements set out in 4.7 Generating federated models.

The Contractor shall review the project’s common data environment at each information exchange to ensure that the federated model(s) identified on the Master Information Delivery Plan have been uploaded.

## 6.5 COBie review

COBie (Construction Operations Building information exchange) outputs shall be reviewed by the Contractor prior to submission to the DfE.

Once the individual COBie files have been created in line with 4.8 Generating COBie, it is imperative that the files are checked against the COBie schema. The requirement for COBie delivery includes the submission of a COBie Quality Control (QC) Report with each submitted COBie file. The QC report of each asset register shall be based on the rules outlined within the NBIMS COBie Quality control test rule definition.

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1).

# 7 Security of information

Information shall be distributed through the information sharing platform at tender phase and via the project’s common data environment during the project delivery phase.

Refer to the Project’s Information Standard for more information on the security of information.

# 8 Distribution of information

## 8.1 Project’s common data environment

This section satisfies the requirements of BS EN ISO 19650-2 clause 5.1.7.

All information shall be distributed through the project’s common data environment in line with the Project’s Information Standard.

The project’s common data environment is:

| Project’s common data environment | Details |
| --- | --- |
| Name of CDE solution | TBC |
| Provided by | TBC |
| Managed by | TBC |
| Training and support provided by | TBC |

## 8.2 Distributed common data environment(s)

Where appropriate, distributed common data environments shall be set up in line with the Project’s Information Standard.

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1) in relation to any distributed common data environment(s) used by the delivery team for this project.

Where distributed common data environments do not apply, confirm within this section.

# 9 Delivery of information to the DfE

The DfE and Technical Advisor shall be provided with access to the project’s common data environment.

All information to be provided at agreed information exchanges shall be made available through the project’s common data environment for the DfE’s approval.

To ensure that documents, drawings and models are adequately checked, the approvals process to enable the DfE to approve and sign-off the development of the information provided shall be via the project’s common data environment.

## 9.1 Submitting the information model for Contractor authorisation

Prior to the delivery of the information model to the DfE, each task team shall submit their information to the Contractor for authorisation within the project’s common data environment.

## 9.2 Review and authorise the information model

The Contractor shall undertake a review of the information model in accordance with the Project’s Information Production Methods and Procedures.

In doing this, the Contractor shall consider:

the deliverables listed in the Master Information Delivery Plan

the Exchange Information Requirements

the Detailed Exchange Information Requirements

the Contractor’s Exchange Information Requirements

the acceptance criteria for each information requirement, and

the level of information need for each information requirement

If the review is successful, the Contractor shall authorise the information model and submit the information for DfE acceptance within the project’s common data environment.

If the review is unsuccessful, the Contractor shall reject the information model and instruct the task teams to amend the information and re-submit for Contractor authorisation.

## 9.3 Submit information for DfE acceptance

The Contractor shall submit their information, in accordance with ISO 19650 S5 Workflow, for the DfE’s review and acceptance within the project’s common data environment.

## 9.4 Review and accept the information model

The DfE’s Technical Advisor shall undertake a review of the information model in accordance with the DfE’s information management requirements. The review and acceptance process is covered in detail within the Information Management Process Map.

In doing this, the DfE’s Technical Advisor shall consider:

the deliverables listed in the Master Information Delivery Plan

the Exchange Information Requirements

the Detailed Exchange Information Requirements

the acceptance criteria for each information requirement, and

the level of information need for each information requirement

If the review is successful, the DfE’s Technical Advisor shall accept the information model as a deliverable within the project’s common data environment.

If the review is unsuccessful, the DfE’s Technical Advisor shall reject the information model and instruct the Contractor to amend the information and re-submit for the DfE’s acceptance.

In accordance with DfE’s archiving policy, a facsimile digital copy of accepted information at each information exchange as per the Exchange Information Requirements shall be archived onto the DfE’s Electronic Data Management System (EDMS) by the Technical Advisor.

Information copied from the project’s common data environment shall be named in accordance with Section 5.1.10 File naming examples in the Project’s Information Standard.

## 9.5 Acceptance workflow

The Pnn to Cnn workflow shall be as below:

information shall be submitted with a Pnn revision on the title block and recorded as metadata in the project’s common data environment

post review, an A (Accepted) or B (Accepted with Comments) shall be watermarked onto the document (generated from the project’s common data environment metadata) to record the outcome

the information author shall update the title block with the new Cnn revision and an An or Bn status (status optional if managed via the project’s common data environment as metadata)

updated information with a Cnn revision shall be uploaded to the project’s common data environment

two archives shall be created from the project’s common data environment onto the DfE’s Electronic Data Management System (EDMS) by the Technical Advisor in accordance with 9.4 Review and accept the information model, one capturing the review outcome (e.g., S5-Pnn with watermark), the other capturing published deliverables (e.g., A4-Cnn)

This section shall be populated with information provided by the selected Contractor within their (pre-appointment) BIM Execution Plan Appendix (refer to EIR Section C1) if they want to deviate from the workflow set out above.

# 10 Lessons learned

In collaboration with the Contractor, the DfE shall capture lessons learned during the project and record them in a Lessons Learned Register, to be called upon by future projects.

Lessons learned shall be raised at a lessons learned workshop at the completion of each RIBA Stage. The aim of each workshop is to discuss the previous stage and assess what lessons could be learned for other projects and for the next stage of this project.

Lessons learned workshops shall be arranged and led by the Technical Advisor with the Contractor and delivery team, and held immediately after each information exchange (i.e., after the completion of each RIBA work stage).

Agreed dates for these workshops shall be added to the Project Programme.

© Crown copyright 2026

This publication is licensed under the terms of the Open Government Licence v3.0, except where otherwise stated. To view this licence, visit nationalarchives.gov.uk/doc/open-government-licence/version/3.

Where we have identified any third-party copyright information, you will need to obtain permission from the copyright holders concerned.

About this publication:

enquiries  https://www.gov.uk/contact-dfe

download 	www.gov.uk/government/publications

Follow us on Twitter: @educationgovuk
Connect with us on Facebook: facebook.com/educationgovuk

When not using the DfE Construction Framework 2025, seek appropriate advice on how the DfE’s Employer’s Requirements can be incorporated into the relevant Contract(s).

Where this document has been incorporated into a Scheme Contract, the version which is incorporated at the date of that Scheme Contract shall apply under the terms of that Scheme Contract, unless varied in accordance with the terms of the relevant Scheme Contract.

Optional DfE template available.

The file name satisfies the requirement to include the information author responsible for its production.

This information is important as it provides the connection between the Task Information Delivery Plan, the Detailed Exchange Information Requirements and information uploaded to the project’s common data environment.

Status is termed ‘suitability’ in BS EN ISO 19650-2 (clause 5.6.2). Status used by DfE.

Various free IFC-SPF viewers are available to open and validate IFC-SPF exports.