To:	Carolyn Bartlett, Senior Responsible Owner for the NextGen Rating Programme

From:	Jonathan Russell, Chief Executive Officer of the Valuation Office Agency; and
Becky Wood, Chief Executive Officer of the National Infrastructure and Service Transformation Authority and the Senior Accountable Officer for Project Delivery across Government

01/10/2024

Dear Carolyn,

APPOINTMENT AS SENIOR RESPONSIBLE OWNER FOR THE NEXTGEN RATING PROGRAMME.

We are writing to confirm your appointment as Senior Responsible Owner (SRO) of the NextGen Rating Programme (NGR) with effect from 01 October 2024. This letter sets out your responsibilities and the support you can expect from your department, Government Project Delivery and the National Infrastructure and Service Transformation Authority (Previously Infrastructure Projects Authority).
As SRO, you are directly accountable to Jonathan Russell, VOA Chief Executive of the VOA, and Dan Tomlinson, Minister.
Your programme forms part of the VOA Transformation Portfolio, under the oversight of the Exchequer Secretary to the Treasury and is included in the Government Major Projects Portfolio (GMPP).
You have personal responsibility for the delivery of the NGR Programme and will be held accountable for the delivery of its objectives, policy intent and outcomes. This encompasses securing and protecting its vision, ensuring that it is governed responsibly, reported on honestly, escalated appropriately and for influencing the context, culture, and operating environment of the programme. You are also responsible for ensuring the ongoing viability of the programme and recommending its pause or termination if appropriate. Where issues arise which you are unable to resolve, you are responsible for escalating these to ExCom.
You remain accountable to Ministers, as set out in the Civil Service Code, and should deliver the project in accordance with the objectives and policy intent as set by Ministers.
In addition to your internal accountabilities, SROs for GMPP projects and programmes are personally accountable to Parliamentary Select Committees. This means that, from the date of this letter, you will be held personally accountable to and could be called by Select Committees to account for and explain the decisions and actions you have taken to deliver the programme.
It is important to be clear that your accountability relates only to implementation, within the agreed terms in this letter; it will remain for the Minister to account for the relevant policy decisions and development.
More information on this is set out in Giving Evidence to Select Committees - Guidance for Civil Servants, sometimes known as the Osmotherly Rules. Information on the roles and responsibilities of the SRO are detailed in Government Project Delivery’s guidance on the role of the senior responsible owner.
You are expected to run your project/programme in accordance with the Government Functional Standard for Project Delivery, and the requirements of other functional standards as required, which is mandated for government departments and arm’s length bodies to follow. You should also make yourself familiar with The Teal Book, Government Project Delivery’s code of practice for project delivery, and any further guidance and requirements set by the VOA.
## Time commitment and tenure
This role will require at least 50% of your time to enable effective delivery of the role and execute your responsibilities in full.
You are required to undertake this role until achievement of programme closure planned for 31/03/2029. Progress towards this will be reflected in your personal objectives. Any changes to the agreed time commitment or tenure of the role, as set out above, will require both departmental and National Infrastructure and Service Transformation Authority consent.
## Objectives and performance criteria
The policy intent supported by this programme is the government’s commitment to a 3 yearly revaluation cycles.
Any proposed changes to scope which impacts on this intent or the realisation of benefits must be authorised by ExCom and may be subject to further levels of approval.
The vision of the programme is to:
‘Provide an excellent experience for rate-payers, our people, and agency partners through new tools and services, and give flexibility to adapt to policy changes including more frequent re-valuations’.
Its objectives are to:
- Increased Organisational Agility: Improve VOA’s organisational agility to implement changing government policy priorities. This enables the commitment to move to 3 yearly revaluation cycles and ensures the VOA can respond to any future ambition to shorten revaluation cycles further.
- Improved Valuation Accuracy: Improve consistency in valuation outcomes through new data structures. Improve quantity and quality of information, resulting in more accurate valuations. Single integrated system resulting in consistent use of data and evidence.
- Reduced Operational Risk: A modern, resilient, and consolidated technology estate that facilitates continuous improvement in our operations and avoids mounting cost and risk of outdated, out of support and end-of-life systems.
- Improved Customer Services: Improved services for our customers, with better ways to share information, quicker turnaround times and improved communication.
- Improved Productivity and Efficiency: New data structures, systems and tools that allow for increased automation and better operational management, combined with improved ways of working.

Your personal objectives and performance criteria which relate to the programme are:
- Implement a new duty that mandates information provision and annual confirmation from ratepayers (or their representatives), developing a digital service that meets user needs, and introducing a fair and proportionate compliance and penalty regime;
- Introduce a new Improvement Relief, and changes to the assessment of heat networks;
- Reform the current system for challenging valuations through introducing changes to the Material Change of Circumstance criteria, removing Check from the current Check, Challenge and Appeal (CCA) process, and altering the window in which a valid Challenge to a valuation can be made;
- Provide additional information for customers on how their rateable value has been calculated;
- Ensure effective VOA internal services and capabilities to manage new processes, including information processing and compliance, and support for customers; and
- Deliver a new platform and case working processes for the delivery of Non-Domestic Rates, migrating VOA’s main IT systems from legacy platforms and improving the quality and efficiency of its decision making.
## Extent and limit of accountability
### Finance and Controls
HM Treasury spending controls will apply on the basis set out within the department’s delegated authority letter. Where the programme exceeds the delegated authority set by HM Treasury, the Treasury Approval Point process will apply, and the details of each approval process must be agreed with your HM Treasury spending team. You should consult departmental finance colleagues on how to go about this.
You should note that where expenditure is considered novel, contentious, repercussive, or likely to result in costs to other parts of the public sector, HM Treasury approval will be required, regardless of whether the programme expenditure exceeds the delegated authority set by HM Treasury. If in doubt about whether approval is required you should, in the first instance, consult departmental finance colleagues before raising with the relevant HM Treasury spending team.
The overall estimated budget, resourcing requirements and tolerances for your project/programme will be agreed as part of the approval process. You will be expected to deliver within these tolerances and report quarterly on these as part of GMPP reporting.
You should operate at all times within the rules set out in Managing Public Money. In addition, you must be mindful of, and act in accordance with, the specific HM Treasury delegated limits and Cabinet Office controls relevant to NGR. Information on these controls can be found here: Cabinet Office controls.
### Delegated authority
You are authorised to:
Approve expenditure of:
Resource / Pay Budget	Resource / Non-Pay Budget	Resource / Total Budget	Capital / Total Budget	Financial Authority
£12,459,699	£8,082,821	£20,542,520	£33,333,000	Up to £5m

- Agree project rescheduling of Level 2 milestones within a 10-working day tolerance. This may be sub-delegated to the Programme Director, and Programme Delivery Director. Rescheduling beyond this level (e.g., for Level 0 or Level 1 milestones) must follow the tolerances outlined by VOA Transformation Portfolio Office governance processes.
- Recommend to ExCom the need to either pause or terminate the programme where necessary and in a timely manner.
These authority limits are subject to change and other conditions or tolerances may be set as part of the business case approval and ongoing monitoring processes which you should then operate within.
Where issues arise which take you outside of these authority limits which you are unable to resolve, you are responsible for escalating these issues to ExCom.
## Appointments
You should appoint a full-time programme director to support you in the management of this programme and make other appointments as required for the control and delivery of your programme within your delegated authority.
## Governance and assurance
You should pay attention to ensuring effective governance for your programme, including the establishment of a programme board with appropriate membership and clear terms of reference.
As primary owner, you must ensure that the programme secures business case approval from the VOA, HMRC and HMT. You should also ensure that the programme remains aligned to the strategic outcomes, costs, timescales, and benefits in line with the approved business case as well as monitoring the context within which the programme is being delivered to ensure it remains valid.
Where a change impacts the scope, costs, benefits, or planned delivery milestones agreed as part of an agreed business case, you are responsible for following the agreed change request approval process and setting a new, approved, business case baseline.
You should ensure that an accounting officer assessment is completed alongside the approval of the Outline Business Case and that this is published on GOV.UK as part of the government’s transparency requirements on major projects. You are responsible for bringing to the attention of the accounting officer any material changes in the programme which could require a new accounting officer assessment to be completed and published. Guidance on completing accounting officer assessments for major projects is available from HM Treasury.
Although you are directly accountable for this programme, you are also expected to support delivery of the department’s overall strategic objectives. This means that you are expected to work collaboratively with other SROs and project directors in adjacent projects and programmes and with the VOA portfolio management office and portfolio director to manage dependencies, resources, schedules, and funding to support delivery of the overall change the department needs to achieve its strategic objectives.
You should ensure that appropriate and proportionate assurance is in place and agree on the level and frequency of assurance reviews through the maintenance of an integrated assurance and approvals plan. You should develop this plan and its maintenance in collaboration with the Departmental Assurance Coordinator and the National Infrastructure and Service Transformation Authority.
## Programme status, reporting and transparency requirements
The programme status at the date of your appointment is reflected in the most recent quarterly return on the programme to the National Infrastructure and Service Transformation Authority and is the agreed position as you assume formal ownership of the programme.
You are responsible for ensuring the honest and timely reporting on the position of the programme to the National Infrastructure and Service Transformation Authority while it remains on the GMPP and for providing reports and information to the VOA portfolio management office as required. Reporting should include carbon measurement, and other sustainable development goals demonstrating evidence that the project contributes to an overarching environmental strategy and is aligned with defined Net Zero pathways. Information on the programme will be published annually by the National Infrastructure and Service Transformation Authority.
As part of the government’s commitment to transparency on major projects, you are responsible for publishing on GOV.UK:
- A Programme Business Case and deposit a copy in the House of Commons Library within 4 months of HM Treasury’s formal approval of the Programme Business Case;
- A summary of the accounting officer assessment completed in line with the approval of the Outline Business Case and summaries of any subsequent assessments should they be required;
- A close out report after the programme has completed.
Guidance on the publication of business cases and on the completion of accounting officer assessments is available from HM Treasury.
## Evaluation
Evaluation of major projects is a requirement. Given the scale and complexity of major projects, it is essential that they are evaluated properly to learn lessons and help ensure accountability. As an SRO of a GMPP project, you are responsible for ensuring that your project/programme has proportionate and suitably resourced evaluation in place. Evaluation planning should begin from the very start of the policy development and the initiation of the programme or project. Progress with the development and implementation of evaluation plans will be monitored through the major project assurance process.
You are also responsible for registering all planned, live and completed evaluations on the Government Evaluation Registry. Guidance on using the evaluation registry is available on GOV.UK.
## Development and support
As a graduate of the Major Projects Leadership Academy, you are expected to maintain your continuing professional development as a project leader, including your status as an accredited assurance reviewer. To maintain your accreditation, you will be required to participate in a review at least once every 12 months.
The department will assist you in securing the necessary resources to support the programme, and will set clear guidance, requirements and standards, which align to the Government Functional Standard on Project Delivery, to enable good governance and effective delivery. You will be part of the department’s cohort of major project leaders who will be expected to support each other, share good practice and lessons learned and to collectively develop solutions. You should liaise with the department’s Head of Profession for project delivery to discuss the maintenance and development of your delivery and leadership skills.
The National Infrastructure and Service Transformation Authority and Government Project Delivery will be available to you for support, advice, and assurance throughout the programme’s time on the GMPP. Government Project Delivery’s suite of standards, guidance, tools, templates and services can be accessed from projectdelivery.gov.uk and we encourage you and your team to register for accounts
Following approval of the business case and entry onto the VOA Transformation Portfolio, the portfolio will provide ongoing oversight and support and will take steps to help resolve and escalate risks, issues or constraints that are acting as a blocker to successful delivery.
We would like to take this opportunity to wish you every success in your role as SRO.

Yours sincerely,

JONATHAN RUSSELL		BECKY WOOD

Chief Executive Officer / Valuation Office Agency		Chief Executive Officer, National Infrastructure and Service Transformation Authority / Senior Accountable Officer for Project Delivery across Government

CONFIRMATION OF ACCEPTANCE OF APPOINTMENT

I confirm that I accept the appointment of Senior Responsible Owner for the programme, including my personal accountability for implementation, as set out in the letter above.

CAROLYN BARTLETT