## Theory of Change Supplement
| Theory (of Change) Elements & Assumptions | [10 empty] | Associated Metrics/Benefits + Details of Measurements / Data Collection | [5 empty] | Governance / Admin | [8 empty] | Expected Values (Cumulative)
Column1 | Indicator # | Objective | Type | ToC Element | Caused by | ...because... (a.k.a. assumption) | Causal Narrative: X causes Y because Z | Causes | Element Type | Intermediate or End Benefit? | Benefit Category | Measurement (aka evidence gathering to evaluate/judge whether ToC element is valid) | Data Type | Unit | Collection Method / Information Source | Timeframe | Current Value | % Confidence of Achieveing Expected Value | Owner (Responsible for *realisation* - if applicable) | Measurer | Costs of Measurement | Date Agreed | Date Last Reviewed | Date Next Review | Date of Final Review / Evaluation | Remedial Actions Taken? | Total Value Aiming For (Phase 1, 2 & 3 Total)
| 1 | 1,2,3 | Input | Private Capital | - | - | - | 6 | Indicator | - | - | - | - | - | - | - | - |  | - | - | - | 2023-05-23 |  |  | -
| 2 | 1,2,3 | Input | DESNZ Capital | - | - | - | 6 | Indicator | - | - | - | - | - | - | - | - |  | - | - | - | 2023-05-23 |  |  | -
| 3 | 1,2,3 | Input | Business time/expertise/resource (inc. contractors) | - | - | - | 5 | Indicator | - | - | - | - | - | - | - | - |  | - | - | - | 2023-05-23 |  |  | -
| 4 | 1,2,3 | Input | DESNZ time/expertise/resource (inc.contractors) | - | - | - | 5 | Indicator | - | - | - | - | - | - | - | - |  | - | - | - | 2023-05-23 |  |  | -
| 5 | 1,2,3 | Activities & Inputs | Businesses submit good-quality applications to the scheme | 3,4 | Businesses have sufficiently experienced and knowledgeable staff and/or contractors to prepare good-quality applications and the pre-application and application process is designed effectively by DESNZ so that business awareness of the scheme is high, application windows are sufficiently long, application requirements are clear and adequate guidance and support is provided to applicants | 3 with 4 causes 5 because businesses have sufficiently experienced and knowledgeable staff and/or contractors to prepare good-quality applications and the pre-application and application process is designed effectively by DESNZ so that business awareness of the scheme is high, application windows are sufficiently long, application requirements are clear and adequate guidance and support is provided to applicants | 6 | Indicator | - | - | Perception of quality of applications submitted by applicants | Qual | - | Evaluation interview/survey with IETF delivery team (and contractors) | Interim impact evaluation and final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033 |  | Good quality applications
[12 empty] | Estimated energy savings of EE deployment projects according to applications | Quant | MWh/£ Grant | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 46.388
[12 empty] | Estimated carbon savings of EE deployment projects according to applications | Quant | tCO2e/£ Grant | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 0.0078586
[12 empty] | Estimated bill savings of EE deployment projects according to applications | Quant | £/£ Grant | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 1.7218
[12 empty] | Estimated carbon savings of DD deployment projects according to applications | Quant | tCO2e/£ Grant | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 0.059628
[12 empty] | Estimated economic benefit of EE projects according to applications | Quant | NBPP | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Estimated economic benefit of DD projects according to applications | Quant | NBPP | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Perception of IETF pre-application and application process design | Qual | - | Evaluation interview/survey with scheme applicants, IETF policy and delivery team (and contractors) | Final process evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2024 |  | Good quality process
[12 empty] | Perception of IETF pre-application and application process design | Qual | - | Post-application survey | End of application stage of each scheme window, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Good quality process
| 6 | 1,2,3 | Activities & Inputs | Good-quality projects receive provisional grants from DESNZ subject to their match-funding with private capital | 1,2,5 | There is sufficient grant funding available from the IETF pot to invest in projects and the scheme is effective in leveraging private capital or finance from businesses in line with the scheme's eligibility requirements and the scheme's assessment process is well-designed to ensure that only good-quality projects receive provisional grants | 1 with 2 and 5 causes 6 because there is sufficient grant funding available from the IETF pot to invest in projects and the scheme is effective in leveraging private capital or finance from businesses in line with the scheme's eligibility requirements and the scheme's assessment process is well-designed to ensure that only good-quality projects receive provisional grants | 8,9,10 | Indicator | - | - | Total amount of IETF grant funding allocated | Quant | £m | IETF Finance Database | Throughout scheme delivery, final review in final impact evaluation |  |  | IETF Policy & Delivery Team (including assessment analysts) | IETF M&E Team | - | 2023-05-23 |  |  | 2033 |  | 474
[12 empty] | Percentage of private capital leveraged for EE deployment | Quant | % | IETF Project Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Percentage of private capital leveraged for DD deployment | Quant | % | IETF Project Database | Throughout scheme delivery, final review in final impact evaluation
[12 empty] | Estimated energy savings of EE deployment projects according to applications | Quant | GWh | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation | 15398 |  |  |  | - | 2023-05-23 | 2022-12-01 | 2023-07-01 | 2033 |  | 21987.9217
[12 empty] | Estimated carbon savings of EE deployment projects according to applications | Quant | MtCO2e | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation | 3.08 |  |  |  |  | 2023-05-23 | 2022-12-01 | 2023-07-01 | 2033 |  | 3.725
[12 empty] | Estimated bill savings of EE deployment projects according to applications | Quant | £m | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation | 844 |  |  |  |  | 2023-05-23 | 2022-12-01 | 2023-07-01 | 2033 |  | 816.1455
[12 empty] | Estimated carbon savings of DD deployment projects according to applications | Quant | tCO2e | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation | 4.16 |  |  |  |  | 2023-05-23 | 2022-12-01 | 2023-07-01 | 2033 | PIC/Treasury informed of expected benefits shortfall. Permission granted to continue scheme | 28.2637
[12 empty] | Estimated economic benefit of EE projects according to applications | Quant | NBPP | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation | 6.8 (Window 2.1, 2.2 and 2.3 only) |  |  |  |  | 2023-05-23 |  |  | 2033
[12 empty] | Estimated economic benefit of DD projects according to applications | Quant | NBPP | Applicants' Project Benefit Calculators | End of assessment stage of each scheme window, final review in final impact evaluation | 10.7 (Window 2.1, 2.2 and 2.3 only) |  |  |  |  | 2023-05-23 |  |  | 2033
[12 empty] | Perception of IETF assessment process design | Qual | - | Evaluation interview/survey with scheme applicants, IETF policy and delivery team (and contractors), technical assessors | Final process evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2024 |  | Good quality process
| 7 | 1,2 | Activities & Inputs | Ineligible projects are signposted to other potential sources of funding | 4 | A designated support team was set-up by DESNZ who provide good-quality advice about other schemes and funds, which are viable funding routes for ineligible projects | 4 causes 7 because a designated support team was set-up by DESNZ who provide good-quality advice about other schemes and funds, which are viable funding routes for ineligible projects | 26 | Indicator | - | - | Perception of advice provided by IETF applicant support team | Qual | - | Evaluation interview/survey with ineligible scheme applicants and IETF policy and delivery | Final process evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2024 |  | Good quality advice
| 8 | 1,2 | Activities & Inputs | Grants are allocated to good quality FEED and feasibility studies | 6 | An effective technical and financial due diligence process was established by DESNZ to ensure that project applications are realistic and accurate | 6 causes 8 because An effective technical and financial due diligence process was established by DESNZ to ensure that project applications are realistic and accurate | 12 | Indicator | - | - | Perception of IETF technical and financial due diligence process | Qual | - | Evaluation interview/survey with project beneficiaries, IETF policy and delivery team (and contractors) | Final process evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2024 |  | Good quality process
[12 empty] | Study 'drop-out' rate due to technical or financial reasons | Quant | % | IETF Project Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 0
| 9 | 1,2 | Activities & Inputs | Grants are allocated to good quality Energy Efficiency Deployment Projects | 6 | An effective technical and financial due diligence process was established by DESNZ to ensure that project applications are realistic and accurate | 6 causes 9 because An effective technical and financial due diligence process was established by DESNZ to ensure that project applications are realistic and accurate | 13 | Indicator | - | - | Perception of IETF technical and financial due diligence process | Qual | - | Evaluation interview/survey with project beneficiaries, IETF policy and delivery team (and contractors) | Final process evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2024 |  | Good quality process
[12 empty] | EE deployment project 'drop-out' rate due to technical or financial reasons | Quant | % | IETF Project Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 0
| 10 | 2,3 | Activities & Inputs | Grants are allocated to good quality Deep Decarbonisation Deployment Projects | 6 | An effective technical and financial due diligence process was established by DESNZ to ensure that project applications are realistic and accurate | 6 causes 10 because An effective technical and financial due diligence process was established by DESNZ to ensure that project applications are realistic and accurate | 14 | Indicator | - | - | Perception of IETF technical and financial due diligence process | Qual | - | Evaluation interview/survey with project beneficiaries, IETF policy and delivery team (and contractors) | Final process evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2024 |  | Good quality process
[12 empty] | DD deployment project 'drop-out' rate due to technical or financial reasons | Quant | % | IETF Project Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 0
| 11 | 3 | Activities & Inputs | BEIS facilitates knowledge-sharing | 4 | The IETF delivery team organise knowledge-sharing events with industry stakeholders outside of project beneficiaries and publish case studies of successful projects which are accessed by industry stakeholders | 4 causes 11 because the IETF delivery team organise knowledge-sharing events with industry stakeholders outside of project beneficiaries and publish case studies of successful projects which are accessed by industry stakeholders | 15 | Indicator | - | - | Number of IETF knowledge-sharing events held by DESNZ | Quant | - | IETF Delivery Team | Throughout scheme delivery, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Number of IETF case studies published by DESNZ | Quant | - | IETF Delivery Team | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 12 | 1,2 | Barriers Overcome | The risk of financial loss is abated if the study shows the project is unfeasible (financial barrier is overcome) | 8 | Successful FEED/feasibility studies are delivered as planned | 8 causes 12 because successful FEED/feasibility studies are delivered as planned | 16 | Indicator | - | - | Perception of effectiveness of project delivery process | Qual | - | Post-completion survey | End of delivery stage of each scheme window, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033 |  | Good quality process
[12 empty] | Perception of effectiveness of project delivery process | Qual | - | Evaluation interview/survey with project beneficiaries, IETF policy and delivery team (and contractors) | Final process evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2024 |  | Good quality process
[12 empty] | Number of IETF-delivered FEED/feasibility studies | Quant | - | IETF Projects Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Grant spent on IETF-delivered FEED/feasibility studies | Quant | £m | IETF Projects Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 13 | 1,2 | Barriers Overcome | The payback period of EE projects are reduced to an acceptable level (financial barrier is overcome) | 9 | Successful EE deployment projects are delivered as planned | 9 causes 13 because successful EE deployment projects are delivered as planned | 17 | Indicator | - | - | Perception of effectiveness of project delivery process | Qual | - | Post-completion survey | End of delivery stage of each scheme window, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033 |  | Good quality process
[12 empty] | Perception of effectiveness of project delivery process | Qual | - | Evaluation interview/survey with project beneficiaries, IETF policy and delivery team (and contractors) | Final process evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2024 |  | Good quality process
[12 empty] | Number of IETF-delivered EE projects | Quant | - | IETF Projects Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Grant spent on IETF-delivered EE projects | Quant | £m | IETF Projects Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 14 | 2,3 | Barriers Overcome | The grant makes the (riskier) lower carbon project more financially applicable to first movers (financial barriers is overcome) | 10 | Successful DD deployment projects are delivered as planned | 10 causes 14 because successful DD deployment projects are delivered as planned | 18 | Indicator | - | - | Perception of effectiveness of project delivery process | Qual | - | Post-completion survey | End of delivery stage of each scheme window, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033 |  | Good quality process
[12 empty] | Perception of effectiveness of project delivery process | Qual | - | Evaluation interview/survey with project beneficiaries, IETF policy and delivery team (and contractors) | Final process evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2024 |  | Good quality process
[12 empty] | Number of IETF-delivered DD projects | Quant | - | IETF Projects Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Grant spent on IETF-delivered DD projects | Quant | £m | IETF Projects Database | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 15 | 3 | Barriers Overcome | There is a lack of knowledge and skills to deliver Deep Decarbonisation deployment technologies (capability barrier is overcome) | 19 or, 11 and 19 | Knowledge about DD tech, including deployment best practices and costs and benefits is gained and shared across organisational boundaries, through DESNZ stakeholder engagement events, published case studies of successful deployment projects and organically from the movement of consultants and engineers involved with IETF projects to non-IETF-funded firms | 11 with 19 causes 15 because knowledge about DD tech, including deployment best practices and costs and benefits is gained and shared across organisational boundaries, through DESNZ stakeholder engagement events, published case studies of successful deployment projects and organically from the movement of consultants and engineers involved with IETF projects to non-IETF-funded firms | 29 | Indicator | - | - | Attendees of IETF stakeholder engagement events | Qual | - | IETF Delivery Team | Throughout scheme delivery, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Online engagement/ downloads of published case studies | Quant | Number of downloads | DESNZ Digital Team | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Perceived quality of DD knowledge-gained through deployment projects | Qual | - | Evaluation interview/survey with DD project beneficiaries, IETF policy and delivery team, engineers, consultants, attendees of stakeholder engagement events | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Good quality knowledge
[12 empty] | Perceived quality of DD knowledge-gained through deployment projects | Qual | - | Post stakeholder engagement surveys | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Good quality knowledge
| 16 | 1,2 | Outputs | High-quality IETF-funded studies are completed, which enable decision-making on deployment | 12 | The risk of financial loss for a business if a FEED/feasibility study shows a deployment project is unfeasible is abated | 12 causes 16 because the risk of financial loss for a business if a FEED/feasibility study shows a deployment project is unfeasible is abated | 26 | Indicator | - | - | Financial abatement for FEED/feasibility studies due to IETF funding | Quant | £ | IETF Project Database | Throughout scheme delivery, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Perceptions around financial viability of project without IETF funding (additionality) | Qual | - | Evaluation interview/survey with project beneficiaries | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Unviable without IETF funding
[12 empty] | Perceptions around financial viability of project without IETF funding (additionality) | Qual | - | Survey submitted alongside M&V data | Throughout monitoring period, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Unviable without IETF funding
| 17 | 1,2 | Outputs | IETF-funded EE tech were installed and became operational as expected | 13 | The payback period for EE projects is improved and becomes financially viable for businesses | 13 causes 17 because the payback period for EE projects is improved and becomes financially viable for businesses | 20 | Indicator | - | - | Financial abatement for EE deployment projects due to IETF funding | Quant | £ | IETF Project Database | Throughout scheme delivery, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Reduction in payback period for EE projects due to IETF funding | Quant | Years | Monitored data from M&V process compared to adjusted counterfactual | Throughout monitoring period, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 2.5
[12 empty] | Perceptions around financial viability of project without IETF funding (additionality) | Qual | - | Evaluation interview/survey with project beneficiaries | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Unviable without IETF funding
[12 empty] | Perceptions around financial viability of project without IETF funding (additionality) | Qual | - | Survey submitted alongside M&V data | Throughout monitoring period, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Unviable without IETF funding
| 18 | 2,3 | Outputs | IETF-funded DD tech were installed and became operational as expected | 14 | The risk of financial loss for a business investing in DD technologies is abated and becomes financially viable for businesses | 14 causes 18 because the risk of financial loss for a business investing in DD technologies is abated and becomes financially viable for businesses | 19,21,25 | Indicator | - | - | Financial abatement for DD deployment projects due to IETF funding | Quant | £ | IETF Project Database | Throughout scheme delivery, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Perceptions around financial viability of project without IETF funding (additionality) | Qual | - | Evaluation interview/survey with project beneficiaries | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Unviable without IETF funding
[12 empty] | Perceptions around financial viability of project without IETF funding (additionality) | Qual | - | Survey submitted alongside M&V data | Throughout monitoring period, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Unviable without IETF funding
| 19 | 3 | Outputs | Knowledge is gained by project beneficiaries, consultants and engineers about 'best practice' deploying DD technologies and their associated costs and benefits | 18 | Knowledge and understanding around deployment 'best practices' and associated costs and benefits was previously limited due to the novelty of the DD technologies, but is gained through demonstration by early-adopters | 18 causes 19 because knowledge and understanding around deployment 'best practices' and associated costs and benefits was previously limited due to the novelty of the DD technologies, but is gained through demonstration by early-adopters | 15 | Indicator | - | - | New knowledge or insights around DD technology deployment 'best practices' and/or costs and benefits | Qual | - | Case studies from IETF-funded DD deployment projects | Throughout scheme delivery, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[10 empty] | - | - | New knowledge or insights around DD technology deployment 'best practices' and/or costs and benefits | Qual | - | Evaluation interview/survey with DD project beneficiaries | Final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 20 | 1,2 | Outcome | Energy usage associated with the industrial processes of EE deployment project beneficiaries decreased | 17 | The EE tech works as expected and improves the energy efficiency of the beneficiary's site | 17 causes 20 because the EE tech works as expected and improves the energy efficiency of the beneficiary's site | 21,23 | Primary Benefit | Intermediate | Non-financial | Reduction in Energy Consumption of EE projects due to IETF | Quant | GWh | Monitored data from M&V process compared to adjusted counterfactual | Throughout monitoring period, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033 |  | 21987.9217
| 21 | 2 | Outcome | Carbon intensity associated with the industrial processes of EE and DD deployment project beneficiaries decreased | 18 and/or 20 | EE projects lower their total energy usage without switching fuels, so less carbon is emitted from energy use and/or DD projects either switch to a fuel with lower carbon intensity or implement carbon capture technology, which work as expected and reduce carbon emissions of the site | 20 causes 21 because EE projects lower their total energy usage without switching fuels, so less carbon is emitted from energy use and/or 18 causes 21 because DD projects either switch to a fuel with lower carbon intensity or implement carbon capture technology, which work as expected and reduce carbon emissions of the site | 22,24 | Primary Benefit | Intermediate | Non-financial | Reduction in Emissions of EE projects due to IETF | Quant | MtCO2e | Monitored data from M&V process compared to adjusted counterfactual | Throughout monitoring period, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033 |  | 3.725
[12 empty] | Reduction in Emissions of DD projects due to IETF | Quant | MtCO2e | Monitored data from M&V process compared to adjusted counterfactual | Throughout monitoring period, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | 28.2637
| 22 | 2 | Outcome | Improved air quality impacts from deployment project beneficiaries' industrial processes | 21 | Carbon emissions directly relate to air quality so reduced emission levels mean improved air quality | 21 causes 22 because carbon emissions directly relate to air quality so reduced emission levels mean improved air quality | - | Secondary Benefit | Intermediate | Non-financial | Estimated monetised air quality improvements | Quant | £ | Monitored data from M&V process compared to adjusted counterfactual | Throughout monitoring period, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Perceptions of air quality at the site | Qual | - | Evaluation interview/survey with beneficiaries | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033 |  | Improvement in perception of air quality
[12 empty] | Perceptions of air quality at the site | Qual | - | Post-completion survey | End of delivery stage of each scheme window, final review in final impact evaluation |  |  |  |  | - |  |  |  | 2033 |  | Improvement in perception of air quality
| 23 | 1 | Outcome | Energy costs associated with the industrial processes of EE deployment project beneficiaries decreased | 20 | The cost savings associated with the energy usage of the EE technology are greater than any increase in costs due to changes in fuel prices | 20 causes 23 because the cost savings associated with the energy usage of the EE technology account for any increase in fuel costs due to changes in fuel prices | 24 | Primary Benefit | Intermediate | Non-financial | Reduction in Energy Costs of EE projects due to IETF | Quant | £m | Monitored data from M&V process compared to adjusted counterfactual | Throughout monitoring period, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033 |  | 816.1455
| 24 | 1 | Outcome | Improved competitiveness for deployment project beneficiaries | 21 and/or 23 | (Short-term) Cost savings from reduced energy usage (EE projects only) can be reinvested into the firm, enabling more competitive business prices or improved business scalability and/or (Short-term) Carbon savings (from EE and DD projects) improve the businesses' image, making them more attractive to investors and/or customers and/or (Long-term) Avoids potential Net Zero decarbonisation costs in the future because the business is further along its decarbonisation pathway than would otherwise have been the case | 21 causes 24 because cost savings from reduced energy usage (EE projects only) can be reinvested into the firm, enabling more competitive business prices or improved business scalability and/or 23 causes 24 because carbon savings (from EE and DD projects) improve the businesses' image, making them a more attractive option to investors and/or customers and/or 23 causes 24 because it avoids potential Net Zero decarbonisation costs in the future because the business is further along its decarbonisation pathway than would otherwise have been the case | 29 | Secondary Benefit | Intermediate | Non-financial | Level of investment back into businesses as a result of cost savings from IETF-funded EE projects | Quant | £ | Evaluation interview/survey with EE project beneficiaries | Final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Level of investment back into businesses as a result of cost savings from IETF-funded EE projects | Quant | £ | Survey submitted alongside M&V data | Throughout monitoring period, final review in final impact evaluation |  |  |  |  | - |  |  |  | 2033
[12 empty] | Increases in external investment due to a shift towards 'greener' production and better business image | Quant | £ | Evaluation interview/survey with EE and DD project beneficiaries | Final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Increases in business sales due to a shift towards 'greener' production and better business image | Quant | Business sales | Evaluation interview/survey with EE and DD project beneficiaries | Final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Customer/investor interest in carbon emittance of businesses | Qual | - | Evaluation interview/survey with trade bodies and consultants | Final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 25 | 2 | Outcome | Energy usage and costs associated with the industrial processes of DD deployment project beneficiaries decreased | 18 | DD projects involve switching to less carbon-intensive fuels, which are often more expensive per unit of fuel or DD projects involve deploying carbon capture technology, which increases projects' energy usage | 18 causes 25 because DD projects involve switching to less carbon-intensive fuels, which are often more expensive per unit of fuel or DD projects involve deploying carbon capture technology, which increases projects' energy usage | - | Disbenefit | Intermediate | Non-financial | Reduction in Energy Consumption of DD projects due to IETF | Quant | MWh | Monitored data from M&V process compared to adjusted counterfactual | Throughout monitoring period, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Increase in Energy Costs of DD projects due to IETF | Quant | £ | Monitored data from M&V process compared to adjusted counterfactual | Throughout monitoring period, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 26 | 1,2 | Outcome | Increased pipeline of deployment projects | 7 and/or 16 and/or 29 | Projects that are ineligible for IETF successfully deploy EE or DD technologies through other DESNZ funds or schemes due to signposting from the IETF team and/or Successful IETF FEED/feasibility studies conclude that it is financially viable to deploy EE/DD technologies, enabling beneficiaries to commit to tech deployment and/or The perceived risk-adjusted cost of DD technologies becomes low enough that they fall within the investable range for firms, enabling businesses to commit to DD tech deployment | 7 causes 26 because projects that are ineligible for IETF successfully deploy EE or DD technologies through other DESNZ funds or schemes due to signposting from the IETF team and/or 16 causes 26 because successful IETF FEED/feasibility studies conclude that it is financially viable to deploy EE/DD technologies, enabling beneficiaries to commit to tech deployment and/or 29 causes 26 because the perceived risk-adjusted cost of DD technologies becomes low enough that they fall within the investable range for firms, enabling businesses to commit to DD tech deployment | 27,28 | Secondary Benefit | Intermediate | Non-financial | Number of IETF-funded FEED/feasibility studies that led to project deployment | Quant | - | (For P1 & P2 early windows) Case studies from FEED/feasibility study projects | Final process evaluation and interim impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Number of IETF-funded FEED/feasibility studies that led to project deployment | Quant | - | (For P2 later windows and P3) Monitored data on success of FEED/feasibility studies | Throughout monitoring period, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Number of projects ineligible for IETF that successfully deployed EE/DD technologies through funds signposted by IETF | Quant | - | Evaluation interviews/surveys with ineligible projects | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Perceptions around any increase in numbers of EE/DD deployment projects in E, W & NI | Qual | - | Evaluation interviews/surveys with trade bodies | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 27 | 1 | Impact | Reduced energy consumption across UK industry | 26 | The combined energy savings from increasing numbers of EE projects in industry in England, Wales and NI has a non-negligible impact on total energy consumption in E, W & NI | 26 causes 27 because the combined energy savings from increasing numbers of EE projects in industry in England, Wales and NI has a non-negligible impact on total energy consumption in E, W & NI | 28,30 | Secondary Benefit | End | Non-financial | Annual energy consumption by sector for UK industry | Quant | Millions of barrels of oil equivalent | National statistics on energy consumption in the UK (ECUK) | Final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
| 28 | 2 | Impact | Reduced emissions across UK industry | 26 and/or 27 | The combined emissions savings from increasing numbers of EE and DD projects in industry in England, Wales and NI has a non-negligible impact on total emissions in E, W & NI | 27 causes 28 because the combined emissions savings from increasing numbers of EE projects in industry in England, Wales and NI has a non-negligible impact on total emissions in E, W & NI and/or 26 causes 28 because the combined emissions savings from increasing numbers of DD projects in industry in England, Wales and NI has a non-negligible impact on total emissions in E, W & NI | 31 | Secondary Benefit | End | Non-financial | Greenhouse gas emissions from manufacturing sectors | Quant | CO2e | UK Environmental Accounts (ONS) | Final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
| 29 | 3 | Impact | Perceived risk-adjusted cost of DD technologies is reduced | 15 | Demonstration of novel DD technologies and the associated increase in knowledge, understanding and familiarity of the tech increases their TRL and gives firms, consultants and engineers across industry greater confidence in the technologies' costs and benefits | 15 causes 29 because demonstration of novel DD technologies and the associated increase in knowledge, understanding and familiarity of the tech increases their TRL and gives firms, consultants and engineers across industry greater confidence in the technologies' costs and benefits | 26 | Primary Benefit | End | Non-financial | Perception of risk-adjusted cost of DD technologies | Qual | - | Survey submitted alongside M&V data | Throughout monitoring period, final review in final impact evaluation |  |  | IETF Policy & Delivery Team | IETF M&E Team | - | 2023-05-23 |  |  | 2033
[12 empty] | Perception of risk-adjusted cost of DD technologies | Qual | - | Evaluation interview/survey with beneficiaries, trade bodies, engineers and consultants | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Change in TRL of DD technologies deployed via IETF | Qual | - | Evaluation interview/survey with engineers and consultants | Interim impact evaluation and final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
[12 empty] | Perception of risk-adjusted cost of DD technologies | Qual | - | Post stakeholder engagement surveys | Throughout scheme delivery, final review in final impact evaluation |  |  |  |  | - | 2023-05-23 |  |  | 2033
| 30 | - | Government Strategic Objectives | Energy Security | 27 | Reduced energy consumption across industry in E, W & NI means reduced nationwide energy demand | 27 causes 30 because reduced energy consumption across industry in E, W & NI means reduced nationwide energy demand | - | - | - | - | - | - | - | - | - |  |  |  |  | - | 2023-05-23
| 31 | - | Government Strategic Objectives | Climate Security | 28 | Reduced carbon emissions across industry in E, W & NI decreases the level of carbon reduction required for the UK to reach its 2050 Net Zero goal | 28 causes 31 because reduced carbon emissions across industry in E, W & NI decreases the level of carbon reduction required for the UK to reach its 2050 Net Zero goal | - | - | - | - | - | - | - | - | - |  |  |  |  | - | 2023-05-23