TERMS OF REFERENCE / AI for Climate-Smart Agriculture and Food Security / (Kenya) / February – September 2026

1. BACKGROUND

1.1 About the Evidence Fund
The Foreign, Commonwealth & Development Office (FCDO) wants accessible high-quality research, evaluation and evidence products which target policy, country-specific and regional priorities and are available for use by FCDO and the international development sector. FCDO’s Research and Evidence Directorate (RED) has as its mission to develop and deliver new technologies and innovations that can help solve development challenges, test high potential interventions, and support the delivery of His Majesty’s Government (HMG) objectives. The Evidence Fund is a co-ordinated effort to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers.
1.2 Details on the Research Context
Agriculture is the backbone of Kenya’s economy, accounting for roughly a fifth of the GDP and employing over 40% of the population. The majority are smallholder farmers whose livelihoods are increasingly threatened by climate variability, pest outbreaks and declining soil fertility. In recent years, Kenya has experienced recurrent droughts and pest invasions that undermine crop yields and food security.
Climate-smart agriculture known to be the practices that enhance productivity and resilience is urgently needed. Emerging technologies, particularly artificial intelligence (AI) combined with techniques such as data analytics, hold significant promise for supporting climate-smart agriculture by helping farmers anticipate and adapt to these challenges. AI-enabled tools such as predictive weather forecasting, early pest/disease warning systems and precision soil analytics could empower Kenyan farmers with timely and tailored advisory services. It’s also important to note that Kenya still faces critical evidence gaps regarding the data foundations required for such AI-enabled tools and their real-world effectiveness in improving farm outcomes.
Despite several pilot initiatives, there are notable gaps in evidence that hinder the effective deployment of AI in agriculture. Key agricultural datasets such as detailed soil profiles, localized weather data, pest surveillance records and yield statistics etc are fragmented, incomplete or not easily accessible hence limiting the development of robust AI advisory systems. Additionally, little empirical data exists on the adoption, usability and impact of existing AI-driven advisory tools among farmers across different regions. This lack of evidence inhibits both government and private sector investment in scaling up digital agriculture solutions. Without reliable insights into what works or not, Kenya risks investing in AI innovations that may not translate into improved productivity, resilience or food security for smallholder farmers. Overall, the potential of AI for climate-smart agriculture is recognized however the decision-makers lack the evidence on data needs and on-the-ground impact to guide policies and investments.
As such, addressing these evidence gaps is particularly urgent and timely. The Government of Kenya has made Climate-Smart Agriculture and Food Security a priority sector in its recently launched Kenya National Artificial Intelligence Strategy 2025–2030 which explicitly identifies agriculture and food security as a key focus for AI deployment. Similarly, the country’s Agricultural Sector Transformation and Growth Strategy (ASTGS, 2019–2029) provides a ten-year roadmap for transforming agriculture, emphasizing innovation, data-driven practices and resilience building. FCDO and other development partners are already supporting Kenya’s agricultural and rural development agenda through programs aligned with the ASTGS, climate-smart agriculture initiatives and digital innovation pilots. FCDO has a strategic commitment to leveraging digital technology and innovation to enhance food security and climate resilience in its partner countries. This includes supporting Kenya’s goals for inclusive growth, sustainable agriculture and adaptation to climate change. The AI for Climate-Smart Agriculture and Food Security research project has been conceived against this backdrop so as to generate rigorous evidence that will inform Kenyan policymakers e.g. the Ministry of Agriculture and Livestock Development, Kenya Agricultural & Livestock Research Organisation (KALRO) etc and FCDO on how AI can be harnessed responsibly and effectively to improve agricultural outcomes. By filling critical knowledge gaps and co-creating solutions, the research will contribute to Kenya’s national strategies (AI Strategy 2025–2030 and ASTGS) and ensure that future investments in digital agriculture are grounded in evidence, ultimately strengthening food security and farmer resilience.
2. KEY EVIDENCE GAPS

This research is designed to fill several key evidence gaps identified in the current context of AI and agriculture in Kenya. These include:
- Incomplete and siloed datasets: Essential agricultural datasets including soil health profiles, granular weather data, pest/disease incidence records and crop yield statistics are currently fragmented, incomplete or inaccessible. These data gaps hinder the development of effective AI models for climate-smart advisory services. The research will document which data are missing or insufficient and how that limits AI tool development.
- Limited evidence of AI tool adoption and impact: While several AI-enabled advisory tools like mobile apps for weather forecasts, pest alerts or diseases detection have been piloted in Kenya, there is little empirical data on their actual uptake by farmers, their usability in local contexts and their tangible impacts on farmer decision-making, productivity or incomes. It is unclear which tools, if any, are making a positive difference at the smallholder farmer level and why. This gap in understanding user adoption and impact will be a central focus of the study.
- Absence of scalable data-sharing models: There is currently no proven model or framework for how the public sector, private agri-tech companies and farming communities can share data with each other in a secure, sustainable and equitable way. Without an inclusive data-sharing architecture, high-quality data remains siloed hence limiting AI innovation at scale. The research will explore and propose evidence-based models for public–private–community data sharing that could enable AI-driven agriculture solutions while protecting farmer data rights and privacy. This addresses a critical gap in governance and infrastructure for scaling digital agriculture.
By investigating these gaps, the project will build the evidence base needed to design effective interventions. Filling these gaps is expected to unlock opportunities for AI to contribute to climate-smart agriculture and food security in Kenya.
3. OBJECTIVES AND SCOPE OF WORK

3.1. Objectives
The overarching objective of this research is to examine how AI can be effectively deployed to strengthen climate-smart agriculture in Kenya by addressing data gaps, adoption barriers and farmer-level impacts. In service of this overall goal, the research will pursue the following specific objectives:
1. Assess Kenya’s Agricultural data landscape: Map the critical agricultural datasets like soil, weather, pest and yield data that are currently incomplete, fragmented or inaccessible in Kenya then assess their importance for AI tool development in agriculture.
2. Examine the adoption and use of AI-enabled agricultural and advisory tools focusing on usability, accessibility, perceived value and evidence of outcomes for smallholder famers across selected regions.
3. Identify system-level barriers and enables to scaling AI solutions in agriculture, including factors such as affordability of technologies, farmer trust and digital literacy, gender and social inclusion issues, infrastructure constraints and policy/regulatory factors. The study will identify what conditions facilitate or hinder wider rollout of AI for smallholders, with particular attention to ensuring women and marginalized groups benefit equally.
4. Assess feasible data sharing and governance approaches that could support AI innovation in agriculture while safeguarding farmers rights, privacy and data protection.
3.2 Scope
Geographic scope: The study will be national in scope, with primary data collection undertaken in a purposive sample of approximately 4-6 counties selected to represent Kenya’s agro-ecological and socio-economic diversity like arid/semi-arid areas, high-rainfall zones and key agricultural belts. Counties will be confirmed during inception in consultation with FCDO and Kenya stakeholders.
Target population: The primary focus is on smallholder farmers in Kenya, who are the end-users of climate-smart agricultural innovations and the most vulnerable to climate risks. Within this group, the research should explicitly consider diversity by gender, age, region, farm size, etc. and include voices of women, youth and other marginalized farmers. In addition, the research will engage agri-tech innovators and service providers like Kenyan startups or companies developing AI tools for agriculture to understand the supply side of innovations.
Key government stakeholders notably, the Ministry of Information, Communications and Digital Economy – MoICDE, which leads the national digital and AI agenda and the Ministry of Agriculture and Livestock Development – MoALD, which oversees the agriculture sector, are also within scope as both information sources and end-users of the research findings.
3.3 Research/Evaluation Questions
Drawing from the above objectives, the study will be guided by the following key research questions and sub-questions:
Agricultural Data Gaps:

1. What are the critical agricultural datasets ranging from soil, weather, pests, yields etc. that remain incomplete or inaccessible in Kenya?
2. How do the key evidence gaps identified in section 2 above constrain the development and effectiveness of AI enabled climate smart Agriculture solutions?

AI Tool Adoption and Use:
To what extent have existing AI-enabled advisory tools been adopted by Kenyan farmers, how user-friendly are these tools in practice and what impact, if any, have they had on farming decisions, productivity and income?
Barriers and Enablers for Scaling:
What institutional, economic, infrastructural, regulatory and social factors enable or hinder the scaling of AI solutions in Kenyan Agriculture? How do those factors differentially affect women youth and other marginalised groups?
Data Sharing and Governance Models:
What data sharing and governance models are feasible within Kenya’s legal, institutional and policy context to support AI innovation while protecting farmers right and privacy?
The above research questions provide the core inquiry areas that the supplier’s methodology must address. Answers to these questions will form the basis of the research outputs and recommendations.
3.4 Research/Evaluation Methodology
The supplier is expected to employ a mixed method approach appropriate for a 6-7 months study, combining qualitative and secondary data analysis. The methodology should include but not limited to:
- Desk review and secondary data analysis: Review existing literature, policies and available datasets. Analyse secondary data on agriculture and climate from various sources to map current data availability and gaps. This may include an audit of existing soil databases, weather station coverage, pest outbreak records etc.
- Key informant interviews: Conduct semi-structured interviews with key stakeholders, including government officials from MDAs such as MoICDE, MoALD, agri-tech entrepreneurs, researchers, extension officers and community leaders. These interviews will provide insights into data issues, policy environment, experiences with AI pilot projects and perceptions of barriers to scale.
- Field based qualitative research: Hold focus group discussions, interviews or case studies with smallholder farmers in the selected counties to gather farmer-level evidence. This could involve surveys to quantify adoption rates of certain digital advisory services as well as focus group discussions or participatory workshops to delve into farmers’ experiences, challenges and suggestions regarding AI tools. Special effort should be made to include women farmers and other underrepresented groups in these consultations.
- Product/technology assessments: Review a purposive sample of existing AI-enabled agriculture tools or services in Kenya for instance a weather forecast SMS service, a crop disease diagnostic app, an AI-driven irrigation advisory amongst others. This might involve usability testing, collect or reviewing any available usage data from the providers.
- Stakeholder validation: Consider convening a technical workshop or roundtable with data providers and technology developers to test the findings and refine recommendation. This would support the objective of proposing practical data-sharing solutions and ensure the recommendations are co-created with those who would implement them.
Throughout the research, the methodology should ensure triangulation of findings i.e. verifying information through multiple sources to enhance reliability. All research must adhere to FCDO ethical research standards, including informed consent, safeguarding and data protection.
3.5 Expected outputs and deliverables
The supplier will be expected to deliver the following:
1. Inception report (including a refined methodology, workplan, county selection and stakeholder mapping and dissemination strategy). Please refer to guidance on Annex 1.
2. Land scape and evidence mapping summary.
3. Draft final report (policy-facing, analytical and evidence based) this should be accompanied by validation workshop feedback.
   Final report incorporating feedback received from steering committee and the validation workshop.
4. Policy brief (5-6 pages) summarising key findings and recommendations.
5. Validation/Dissemination workshop summary note.
3.6 Theory of Change
The project is underpinned by a simple theory of change that aligns with Kenya’s digital development goals and FCDO’s strategic outcomes.
“If key evidence gaps on data, adoption, impacts and governance of AI in agriculture are filled through this research then policymakers, donors and innovators will have the information needed to make better decisions and investments which will result in more effective and scaled deployment of AI solutions in climate-smart agriculture leading to improved agricultural productivity, resilience and food security for Kenyan smallholders.”
In practice, this means the research will produce actionable evidence and recommendations/outputs that inform the design of government policies, development programmes and private sector initiatives(outcomes). A case in point is where insights on critical data gaps could lead to investments in data infrastructure, evidence on farmer adoption could shape training or extension approaches, identified barriers could be addressed by new policies or business models and proposed data-sharing frameworks could be piloted to improve collaboration. The ultimate impact envisioned is that Kenyan farmers benefit from AI-driven services that help them adapt to climate variability and boost their productivity in a sustainable way.
This theory of change is closely aligned with national and international strategies. By focusing on climate-smart agriculture, the research directly supports one of the priority sectors in Kenya’s National AI Strategy 2025–2030 and provides evidence to guide its implementation in the agriculture domain. It also complements the objectives of the ASTGS (2019–2029), which seeks to increase agricultural innovation, data use and climate resilience.
On the part of FCDO, the outcomes of this project will contribute to the UK’s development objectives in Kenya by promoting inclusive economic growth, food security, and climate change adaptation while also exemplifying the use of frontier technology (AI) for development impact. In essence, the research will help FCDO and Kenyan partners to deliver on their commitments to digital innovation and climate resilience, ensuring that AI investments are evidence-based and aligned with both Kenyan Vision 2030 and FCDO’s strategic priorities. By demonstrating responsible and impactful use of AI in agriculture, the project also reinforces the UK’s role as a partner in ethical, development-oriented AI innovation.
3.7 Required Skills
Given the innovative and interdisciplinary nature of this project, the selected research supplier or consortium must demonstrate a strong combination of skills and experiences below:
- AI and Digital Agriculture: At least three years’ proven experience in artificial intelligence, data science, and climate-smart agriculture technologies, with a portfolio of projects relevant to developing countries.
- Agricultural Context: Minimum of five years’ experience working in Kenyan or East African agricultural development, particularly with smallholder systems. Evidence of established local networks and successful stakeholder engagement is essential.
- Participatory Field Research: Demonstrated track record of conducting inclusive, field-based research using participatory methods, with at least two major projects involving women, youth, and marginalised groups.
- Policy Analysis: Strong analytical skills with a minimum of three policy research assignments, including translating research into actionable recommendations. Familiarity with Kenya’s agricultural policy environment is required.
- Safeguarding and Ethics: Documented commitment to ethical research and safeguarding, including compliance with data protection, informed consent, and FCDO standards, evidenced by relevant certifications or policies.
- Project Management: At least five years’ experience in project and stakeholder management, with a record of delivering complex research projects on time
- Communications and Design: Demonstrated ability to design and implement communications strategies, with at least two examples of developing materials and disseminating research results to diverse audiences.
Evidence of the above skills should be detailed in the supplier’s proposal. FCDO encourages the formation of multi-disciplinary teams or partnerships to ensure all these skill areas are covered.
4. PROJECT MANAGEMENT ARRANGEMENTS

The supplier (contracted research team/organization) will be responsible for leading and managing all aspects of the research project, in close coordination with FCDO and Kenyan stakeholders. The supplier is expected to handle the detailed research design, recruitment and training of any research assistants or enumerators, supervision of data collection, data analysis, and the production of deliverables. Effective project management and internal quality control must be in place to keep the research on track and to maintain high standards.
The supplier will also manage all logistical arrangements for fieldwork like travel, permissions, local facilitation etc. and ensure compliance with ethical standards throughout. Regular progress updates at an agreed cadence should be provided to FCDO and key partners, highlighting interim findings, any risks or delays and next steps. The supplier is accountable for delivering the agreed outputs on time and within budget and for promptly communicating any issues that might require adaptive measures.
While the supplier will lead implementation, the research will be carried out in partnership with the Government of Kenya and FCDO to ensure relevance and uptake of results. The Ministry of Information, Communications and Digital Economy (MoICDE) will be the primary government counterpart, as it is the lead ministry for Kenya’s AI Strategy and digital innovation agenda. The Ministry of Agriculture and Livestock Development (MoALD), as the custodian of agriculture sector policy, will also be a key partner. The project will leverage existing collaboration between MoICDE and MoALD to ensure joint ownership of the research process and findings. It is expected that an official or technical focal point from each Ministry will be designated to liaise with the research team. FCDO’s office in Nairobi (including the Science, Innovation & Tech (SI&T) team) will provide oversight and coordination support, building on its established relationships with MoICDE under the UK-Kenya Strategic Partnership and digital initiatives.
A steering or advisory committee will be formed comprising representatives from FCDO, MoICDE, MoALD and potentially other stakeholders such as the Kenya Agricultural and Livestock Research Organization or private sector reps to guide the project. This group would review key deliverables (inception report, interim findings, draft final report) and assist in problem-solving or facilitating high-level buy-in. is the supplier will be expected to engage proactively with this committee, attend briefing and debriefing meetings, and incorporate feedback to keep the research aligned with stakeholder needs.
In terms of reporting, the supplier will have a designated FCDO contract manager or Task Manager for day-to-day communication. All formal deliverables will be submitted to FCDO for approval.
5. Administrative arrangements

The study would be supported through The Evidence Fund, an FCDO programme intended to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2023, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects and conduct due diligence assessments on prospective sub – contracted Research Pool providers, where relevant.
The Foreign, Commonwealth & Development Office (FCDO) is the sole contracting authority for all projects funded through the Evidence Fund. The FCDO holds full responsibility for issuing contracts and managing all contract and project management activities throughout the lifecycle of each project. The Fund Manager’s role is limited to pre-contracting activities and does not extend to contract execution or post-award management.
6. TIMEFRAME, EXPECTED DELIVERABLES, AND OVERALL BUDGET

The study should be completed in a maximum period of 7 months, starting March 2026. The budget for the study should not exceed £80,000, excluding UK VAT and including all other applicable taxes.
The deliverables and timelines/milestones expected of the Supplier are as follows:
Milestone	Description	Milestone Payments / (% of Overall Budget Amount)	Delivery By
	Inception Report: This report will detail the refined research methodology, sampling framework, data collection instruments, a work plan with specific dates, and any updates to the research questions or scope. The inception report will be discussed with FCDO and the advisory committee for approval before full fieldwork begins.	20%	Week 2
	Landscape and evidence mapping summary Update: A brief update(report/presentation) summarizing progress to date, preliminary findings or emerging themes from the research, and any adjustments required.	10%	Week 12
	Draft Final Report: A comprehensive research report covering the entire study addressing address all the research questions, presenting findings supported by evidence and providing clear analysis. It should have an executive summary, background/context, methodology, findings per question, conclusions and actionable recommendations. The supplier will also hold a validation workshop to test the findings.	30%	Week 24
	Final Research Report: The final, revised version of the report will serve as the authoritative record of the study. It will incorporate feedback from the steering committee and the validation workshop. It must be professionally edited and formatted, suitable for publication.	20%	Week 28
	Policy Brief: A concise, up to 6 pages, policy brief highlighting the key findings and recommendations of the research. This should be written in an accessible manner for senior policymakers and program designers. It should distil the most important messages, supported by quick facts or graphics, and outline clear options or recommendations for government and partners.	20%	Week 30
	Dissemination Workshop: The supplier will plan and facilitate a dissemination event in Nairobi and virtually to share the research findings with stakeholders. The workshop should present the findings, allow for discussion and questions and seek feedback on the recommendations. The goal is to ensure the evidence is communicated effectively and to spur dialogue on next steps. The supplier should produce any presentation materials and a brief report on the event.		31st March 2026

7. QUALITY ASSURANCE MECHANISMS

Peer review/Quality Assurance Required
Peer review/ quality assurance completed in-house by FCDO
Peer review/ quality assurance arranged by the research provider as part of their contract	×
Independent peer review independently carried out, through a contract with the Fund Manager
Further EqUALS review for all evaluation products

8. COMPETENCIES

It is expected that the core team delivering this work will have the requisite technical and contextual experience in the collation, interpretation, synthesis, and communication of the research findings and recommendations.
9. SUBMISSIONS

The Supplier is required to submit all outputs in accordance with the expectations set out in sections 3, 4 and 5 above.
10. MANAGEMENT ARRANGEMENTS

1. The Supplier will design and manage this research study, including drawing together the findings for reporting.
2. This project will be administered by a FDCO EARIH lead adviser.
3. The Supplier will quality-assure all outputs before submission to the EARIH lead adviser. The Supplier will be required to comply with FCDO reporting requirements. The Supplier will be responsible for alerting the EARIH lead adviser as early as possible of any emerging issues and risks, to ensure that the project is staying on track.
4. All deliverables will need to be reviewed and approved by the FCDO technical steering group; however, the Supplier is encouraged to embed their own internal mechanisms for quality assurance.
5. The Supplier will be required to review and outline how they plan to manage any potential conflicts of interest identified during proposal development.
6. The Supplier will be required to attend several meetings during all phases of the work, comprising largely of virtual meetings.
11. BIDDING PROCESS

Technical and financial proposals should be sent as two separate files to ke_evidencefundeastafrica@pwc.com by 27 February 2026 (23:59 EAT). Since these will be assessed independently of each other, they should, in no case, be combined or cross-referenced.
The instructions for submitting the tender and details on scoring methodology and evaluation criteria are detailed in ITT Volume 1. The application forms for submitting the technical proposal (sent as a clearly titled PDF file) are detailed in ITT Volume 3 and ITT Volume 4 provides the Pro Formas for the commercial proposal.
12. DUTY OF CARE ARRANGEMENTS

The Supplier should set out duty of care arrangements for any country visits or field-based activities.
13. ETHICAL CONSIDERATIONS, DATA PROTECTION, AND SAFEGUARDING

The Supplier will be responsible for ensuring that all research activities comply with high ethical standards, data protection requirements and FCDO safeguarding policies.
Ethical considerations:
The study will involve human participants. The Supplier must obtain ethical approval from a recognised institutional ethics review board in Kenya and/or their home institution, where applicable prior to commencing fieldwork.
All participants must give informed consent, written or verbal but documented, after being clearly informed about the purpose of the study, what participation entails, risks/benefits, how data will be used and their right to withdraw at any time without consequence.
The research will follow a Do No Harm principle. Questioning and engagement must be culturally sensitive, avoid raising unrealistic expectations of support and be designed to minimise any potential distress or reputational harm to participants or communities.
Inclusion and power dynamics:
The Supplier must use inclusive methods that actively seek participation from women, youth, persons with disabilities and other marginalised groups. This may include gender-sensitive facilitation like women-only focus groups, use of local languages and appropriate timing and venues.
Team composition should reflect gender balance and, where possible, include local researchers to build trust and ensure contextual understanding.
Data protection:
All personal data must be collected and processed in line with Kenya’s Data Protection Act (2019) and FCDO data protection policies.
Data must be stored securely and only used for the purposes of this research.
Analytical datasets and reports shared with FCDO will be anonymised/de-identified, so that individuals or specific farms cannot be identified without explicit consent.
Safeguarding:
The Supplier must have and enforce a safeguarding policy consistent with FCDO standards, including clear procedures for reporting and responding to safeguarding concerns or incidents.
All team members must receive safeguarding and ethical research training before engaging with participants.
Any safeguarding incident or serious concern arising during fieldwork must be reported immediately to FCDO and relevant authorities, where appropriate, along with steps taken to protect affected individuals.
The Supplier should outline their ethics, data protection and safeguarding approach in the proposal and provide full documentation like safeguarding plan, consent forms etc during inception.
14. GENERAL DATA PROTECTION REGULATIONS (GDPR)

The Supplier will be required to comply with applicable data protection laws, including:
- The UK General Data Protection Regulation (UK GDPR) and Data Protection Act 2018, in so far as they apply to any processing of personal data on behalf of FCDO.
- The Kenya Data Protection Act (2019) and any related regulations for data collected and processed in Kenya.
Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Section 15: Interpretation, the clause on Data Protection Laws in Volume 6: Pro Forma Contract of the ITT Application Pack.4
15. RISK MANAGEMENT

The supplier will be expected to set out their understanding of the most anticipated risk in the proposal, with an explanation of their mitigating strategies in a risk matrix.
15. FCDO RESEARCH GUIDANCE DOCUMENTS

Annex 1: Guidance on Communication and Research Uptake Strategy
Stakeholder Mapping and Research Uptake Strategy
	Key communications and research uptake considerations
Audience mapping	Which organisations are the main intended audiences for the research? Who are the key decision-makers in the policy area and are they involved and aware of the research (and how are they involved in the research design and intent)? Are there other actors who may use findings or are involved in this policy area? / Within FCDO – which teams and departments are involved?
Knowledge requirements of stakeholders	What are the evidence gaps that actors are interested in? Are there key statistics or data that can define the research? What new evidence does the research offer to both strategic planning and informing programming?
Decisions to be influenced	What are the key programming decisions that the research will influence – both for FCDO policy teams and country offices? Will the research support decision-making among other actors? E.g., multilateral, and bilateral donors, non-government organisations, regional governments? What decisions are those?
What are the outputs?	Largely defined by the ToR, but what outputs will be produced? I.e., will there be supporting infographics, summary briefs, or single case studies in order to land the research more effectively/efficiently with particular audiences? How do these map to particular stakeholders?
How will outputs be communicated?	How will various audiences be kept abreast or informed about the research? Will different audiences require different communications? What will be the balance of different dissemination techniques: i.e., seminars, emails, social media, meetings, slide decks, use of the internet or published documentation?
Relevance of research products	The communications plan (and research products) should be iterative and reflect research needs from all stakeholders. Considering responses to the points outlined above, how will the research be designed, produced, and disseminated to meet these needs?
How will research impact be measured?	What methods and indicators can be used to measure or assess how useful the research is? I.e., to what extent has it been used and by which audiences, what are the outcomes of the research, and what impact has it had on policy making and programming?