## 00_DocumentHistory
Soft landings checklist
Shared resources
Project code: |  | [SRP/FS/FE code]
Project name: |  | [Name of school/college]
[Month] 20[XX]
Template
Revision Code | Status Code | Date | Amendment
C01 | A | 2026-01-12 | GOV.UK publication
Project-specific
Revision Code | Status Code | Date | Amendment
Pnn | Sn | 20YY-MM-DD | DfE/Employer's Representative to add amendments made to document here and rename file to make project specific
Contents
Worksheet |  |  | Description
00_DocumentHistory |  |  | Sheet sets out information about this resource, the file (name, revision, status and revision history) and list of contents including descriptions
01_ProjectInputs |  |  | Project specifics to be entered into this worksheet (organisation names for the Employer, Employer's Representative, Responsible Body and Contractor)
02_SoftLandingsChecklist |  |  | Soft Landings Checklist for all stages of a project
A_Picklists |  |  | Sheet sets out the picklists used to configure the 01_ProjectInputs and 02_SoftLandingsChecklist sheets

## 01_ProjectInputs
Subject | Value
Project Code | [SRP/FS/FE code]
Project Name | [Name of school/college]
Employer (DfE) | Department for Education
Responsible Body (RB) | Responsible Body Name
Employer's Representative (TA) | Organisation Name
Contractor | Organisation Name
Number of tasks outstanding | 128
Number of tasks completed | 0
Organisation Type | Organisation Name | Name (First and Last) | Role | Role Code
Employer (DfE) | Department for Education | Name of individual | Project Director | PD
Employer (DfE) | Department for Education | Name of individual | Project Manager (Soft Landings Champion) | PM
Responsible Body (RB) | Responsible Body Name | Name of individual | Responsible Body/School/College Coordinator | n/a
Responsible Body (RB) | Responsible Body Name | Name of individual | Responsible Body Representative | n/a
Employer's Representative (TA) | Organisation Name | Name of individual | Employer's Representative | n/a
Employer's Representative (TA) | Organisation Name | Name of individual | Employer's Representative | n/a
Contractor | Organisation Name | Name of individual | Contractor's Soft Landings Representative | n/a
Contractor | Organisation Name | Name of individual | Contractor's Representative | n/a

## 02_SoftLandingsChecklist
ID | Task Completed | Task Category | Task | RACI Code and Party | Responsible | Accountable | Consulted | Informed | Employer | Employer's Representative | Contractor | Responsible Body | Project Stage | RIBA Stage 0: Pre-Feasibility (GW1) | RIBA Stage 2: Feasibility (GW2) | RIBA Stage 2: Procurement (GW3) | RIBA Stage 3: Planning | RIBA Stage 4: Contractor's Proposal (GW4) | RIBA Stage 5: Construction | RIBA Stage 5: 6 Months Pre-Handover | RIBA Stage 5: 1 Month Pre-Handover (GW5) | RIBA Stage 6: Rectification Period | RIBA Stage 6: End of Rectification Period (GW6)
001 | No | Governance | Compilation of lessons learned from other DfE centrally delivered projects and/or Responsible Body self-delivered projects to inform this project. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 0: Pre-Feasibility (GW1); RIBA Stage 2: Feasibility (GW2) | YES | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
002 | No | Stakeholder | Production of a stakeholder map which defines all stakeholders (including facilities/estates management from the Responsible Body through to end user operators), roles, responsibilities, communication and reporting lines. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
003 | No | Governance | Establishment of a project programme for inclusion within the Contractor’s Master Programme in due course. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
004 | No | Operation | Issue of the DfE's Soft Landings Guide and Soft Landings Checklist to the Project Team. Note: Project Team to review the documents to ensure all parties are familiar with the DfE Soft Landings process and that all Soft Landings tasks are assigned and completed prior to the conclusion of the relevant RIBA stage. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | A | R | I | I | RIBA Stage 2: Feasibility (GW2); RIBA Stage 2: Procurement (GW3) | n/a | YES | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a
005 | No | Delivery | Assurance that all deliverables outlined in the Detailed Exchange Information Requirements (DEIR) for Information Exchange IE201 meet the relevant content requirements. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  |  | A | R | n/a | n/a | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
006 | No | Delivery | Issue of all deliverables for Information Exchange IE201 as outlined in the Detailed Exchange Information Requirements (DEIR) to the Employer for review and acceptance. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  |  | A | R | n/a | n/a | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
007 | No | Delivery | Completion of a ‘day in the life’ visit to the School/College to observe daily operations including, but not limited to, drop-off/arrival, learning, dining, play, and pick-up/departure along with staff/pupil interactions, educational methods, safeguarding considerations and use of the indoor and outdoor environment. Note: Analysis shall be recorded in the Project Brief. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
008 | No | Operation | Understanding how the School/College's systems operate at present and the identification of any key facility requirements/facilities management needs and/or operator capability challenges when the new and/or refurbished building(s) and outdoor environment are ready for occuation and use. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
009 | No | Delivery | Establishment of the project's objectives within the Project Brief with key survey findings documented in the Constraints and Opportunities Report. Note: These documents must reflect and record long-term operational performance goals and user needs. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
010 | No | Delivery | Establishment of the project's design requirements (where additional to DfE's Employer's Requirements) for operation and facilities management in the new and/or refurbished building(s) and outdoor environment. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
011 | No | Delivery | Completion of a transition plan outlining the process for moving pupils/students and staff into the new and/or refurbished building(s) and outdoor environment, including whether an extended period is required between Practical Completion and full operational use of the facilities. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
012 | No | Regulatory | Review of the existing Operation and Maintenance (O&M) Manual(s), including the Health & Safety File where available, to inform design development and assess site specific risks. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | n/a | C | RIBA Stage 2: Feasibility (GW2) | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
013 | No | Stakeholder | Confirmation of the name/contact details for the Contractor's Soft Landings Representative. Note: This person should attend all project meetings at the earliest opportunity. | R : Responsible Body/School/College Coordinator A : Employer's Representative (TA) I : Employer's Soft Landings Champion (DfE); Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Representative (TA) |  | Employer's Soft Landings Champion (DfE); Contractor's Soft Landings Representative | I | A | I | R | RIBA Stage 2: Procurement (GW3); RIBA Stage 3: Planning | n/a | n/a | YES | YES | n/a | n/a | n/a | n/a | n/a | n/a
014 | No | Delivery | Verification that the legacy fittings, furniture and equipment (FF&E), and technology equipment schedules provided during procurement are accurate and fully integrated into the design proposals. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 2: Procurement (GW3); RIBA Stage 3: Planning; RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | YES | YES | YES | n/a | n/a | n/a | n/a | n/a
015 | No | Delivery | Agreement of the Zoning Strategy with the Employer's Project Team and Responsible Body. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 3: Planning | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a
016 | No | Quality | Verification that the proposals to date for the integrated environmental design are on track to meet DfE's environmental performance targets/requirements. | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) |  | Employer's Soft Landings Champion (DfE) | I | A | R | n/a | RIBA Stage 2: Procurement (GW3); RIBA Stage 3: Planning; RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | YES | YES | YES | n/a | n/a | n/a | n/a | n/a
017 | No | Delivery | Issue and validation of the Carbon Report for the relevant RIBA stage. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 3: Planning; RIBA Stage 4: Contractor's Proposal (GW4); RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | YES | YES | n/a | n/a | n/a | n/a | YES
018 | No | Delivery | Assurance that all deliverables outlined in the Detailed Exchange Information Requirements (DEIR) for Information Exchanges IE301 and IE311 meet the relevant content requirements. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 3: Planning | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a
019 | No | Delivery | Issue of all deliverables for Information Exchanges IE301 and IE311 as outlined in the Detailed Exchange Information Requirements (DEIR) to the Employer's Project Team for review and acceptance. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 3: Planning | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a | n/a
020 | No | Delivery | Completion of a planned and phased provision for temporary accommodation (as required) to ensure educational continuity and reduce overall disruption to end users throughout construction. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 2: Procurement (GW3); RIBA Stage 3: Planning; RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | YES | YES | YES | n/a | n/a | n/a | n/a | n/a
021 | No | Quality | Analysis of the new and/or refurbished building(s) and outdoor environment's maintenance requirements relative to the Responsible Body's existing facilities management processes and requirements. Identification of any key omissions and/or operator capability challenges requiring mitigation. | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) C : Responsible Body/School/College Coordinator I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | I | A | R | C | RIBA Stage 3: Planning; RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | YES | YES | n/a | n/a | n/a | n/a | n/a
022 | No | Governance | Completion of an Employer’s Representative arranged, chaired and managed lessons learned workshop at the end of the RIBA stage with the Project Team, including the Employer, Responsible Body, Contractor and their delivery team (as applicable) with all outcomes and actions/recommendations recorded in a Lessons Learned Register. | R : Employer's Representative (TA) A : Employer's Representative (TA) C : Employer's Soft Landings Champion (DfE); Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE); Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator |  | C | R/A | C | C | RIBA Stage 2: Feasibility (GW2); RIBA Stage 3: Planning; RIBA Stage 4: Contractor's Proposal (GW4); RIBA Stage 5: 1 Month Pre-Handover (GW5) ; RIBA Stage 6: End of Rectification Period (GW6) | n/a | YES | n/a | YES | YES | n/a | n/a | YES | n/a | YES
023 | No | Regulatory | Review of the Contractor's Construction Phase Plan in conjunction with the Responsible Body to ensure it is up-to-date with disruption to the School/College minimised as far as is reasonably practicable during the works, handover and the 12-month Rectification Period. | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) C : Responsible Body/School/College Coordinator I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | I | A | R | C | RIBA Stage 3: Planning; RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | YES | YES | n/a | n/a | n/a | n/a | n/a
024 | No | Quality | Understanding of the high level operational and maintenance costs for the new facilities relative to the DfE/Responsible Body’s expectations. | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) C : Responsible Body/School/College Coordinator I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | I | A | R | C | RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a
025 | No | Quality | Verification of the proposed metering and sub-metering strategy relative to the DfE's Employer's Requirements. | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) C : Responsible Body/School/College Coordinator I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | I | A | R | C | RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a
026 | No | Stakeholder | Verify all pre-commencement planning conditions have been discharged by the Local Planning Authority. | R : Contractor's Soft Landings Representative A : Contractor's Soft Landings Representative I : Employer's Soft Landings Champion (DfE); Employer's Representative (TA) | Contractor's Soft Landings Representative | Contractor's Soft Landings Representative |  | Employer's Soft Landings Champion (DfE); Employer's Representative (TA) | I | I | R/A | n/a | RIBA Stage 4: Contractor's Proposal (GW4); RIBA Stage 5: Construction | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a | n/a | n/a
027 | No | Delivery | Assurance that all deliverables outlined in the Detailed Exchange Information Requirements (DEIR) for Information Exchange IE401 meet the relevant content requirements. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a
028 | No | Delivery | Issue of all deliverables for Information Exchange IE401 as outlined in the Detailed Exchange Information Requirements (DEIR) to the Employer's Project Team for review and acceptance. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a
029 | No | Quality | Agreement of the decant strategy (where applicable), aligned with the Master Programme, for legacy fittings, furniture and equipment (FF&E) and technology equipment. | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) |  | Employer's Soft Landings Champion (DfE) | I | A | R | n/a | RIBA Stage 4: Contractor's Proposal (GW4); RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | YES | n/a | YES | n/a | n/a | n/a
030 | No | Regulatory | Collation of Pre-Construction Information in response to the existing Operation and Maintenance (O&M) Manual(s), including the Health & Safety File where available, to inform design development and assess site specific risks. | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) |  | Employer's Soft Landings Champion (DfE) | I | A | R | n/a | RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a
031 | No | Regulatory | Submittal of a Building Control Full Plans Client Statement of Consent to the Contractor. | R : Employer's Soft Landings Champion (DfE) A : Employer's Soft Landings Champion (DfE) I : Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Soft Landings Champion (DfE) |  | Employer's Representative (TA); Contractor's Soft Landings Representative | R/A | I | I | n/a | RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a
032 | No | Operation | Submittal of the underground drainage cleaning and CCTV condition survey for review by the Employer's Representative alongside any remedial works where included in Operation and Maintenance (O&M) Manual. | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) |  | Employer's Soft Landings Champion (DfE) | I | A | R | n/a | RIBA Stage 4: Contractor's Proposal (GW4); RIBA Stage 5: Construction; RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a | YES | n/a
033 | No | Governance | Agreement of key dates (e.g., for examinations) where noisy works are strictly prohibited, for inclusion in the Master Programme. | R : Responsible Body/School/College Coordinator A : Employer's Representative (TA) C : Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Representative (TA) | Contractor's Soft Landings Representative |  | n/a | A | C | R | RIBA Stage 4: Contractor's Proposal (GW4); RIBA Stage 5: Construction | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a | n/a | n/a
034 | No | Governance | Agreement of dates for key site visits during construction by pupils/students, teaching and facilities staff, govenors etc as required (e.g., for topping out ceremony, ministerial visit etc). | R : Contractor's Soft Landings Representative A : Employer's Representative (TA) C : Responsible Body/School/College Coordinator I : Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | I | A | R | C | RIBA Stage 5: Construction | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a
035 | No | Quality | Issue of the CQM Monthly Report by the Construction Quality Monitoring (CQM) Team. Refer to Detailed Exchange Information Requirements (DEIR) for content requirements. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | A | R | I | I | RIBA Stage 5: Construction | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a
036 | No | Quality | Issue of the information release schedule for all deliverables (Contractor Design Documents) listed in Schedule 1: Design Submission Procedure of the Contract. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 5: Construction | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a
037 | No | Quality | Review of the Landscape and Ecological Maintenance and Management Plan and 5 year Planned Maintenance Plan in monthly progress meetings. | R : Employer's Representative (TA); Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA); Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | R | RIBA Stage 5: Construction | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a
038 | No | Quality | Review/monitoring of any non conformance matters recorded on the Non Conformance and Observation Register. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 5: Construction | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a
039 | No | Stakeholder | Verify all pre-occupation planning conditions have been discharged by the Local Planning Authority. | R : Contractor's Soft Landings Representative A : Contractor's Soft Landings Representative I : Employer's Soft Landings Champion (DfE); Employer's Representative (TA); Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Contractor's Soft Landings Representative |  | Employer's Soft Landings Champion (DfE); Employer's Representative (TA); Responsible Body/School/College Coordinator | I | I | R/A | I | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
040 | No | Operation | Finalisation of the Building Readiness and Maintenance Programme (part of the Master Programme). | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Responsible Body/School/College Coordinator |  | A | C | R | C | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
041 | No | Operation | Finalisation of the Outdoor Environment Readiness and Maintenance Programme (part of the Master Programme). | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Responsible Body/School/College Coordinator |  | A | C | R | C | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
042 | No | Governance | Agreement of commissioning strategy including key dates for attendance. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 4: Contractor's Proposal (GW4) | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a | n/a
043 | No | Stakeholder | Confirmation that non-conditional items on the Building Regulations Compliance Tracker have been closed 1 month prior to Practical Completion. | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) |  | A | C | R | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
044 | No | Operation | Issue of Soft Landings Letter 1: 6 months prior to Practical Completion to the Responsible Body. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Responsible Body/School/College Coordinator | A | R | n/a | I | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
045 | No | Quality | Inspection and approval of a pre-agreed sample room to a sufficiently advanced stage, ahead of the overall programme, to demonstrate the good quality and workmanship standard required for Practical Completion for the building as a whole. | R : Employer's Representative (TA); Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative | Employer's Representative (TA); Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative | A | R | I | R | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
046 | No | Governance | Agreement of Decant Protocol (where applicable) including key dates/programme, roles and responsibilities (e.g., Migration Manager), contact details, finalised legacy schedules etc. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator |  | A | R | C | C | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
047 | No | Operation | Issue of Soft Landings Letter 2: 3 months prior to Practical Completion to the Responsible Body. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Responsible Body/School/College Coordinator | A | R | n/a | I | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
048 | No | Operation | Update of the Project Organogram to include the Contractor’s Aftercare Team to ensure clear lines of communication post handover. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) I : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  | Responsible Body/School/College Coordinator | A | R | R | I | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
049 | No | Delivery | Agreement of a suitable base within the School/College for the Contractor's Soft Landings Representative during the six weeks of aftercare post Practical Completion. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative I : Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Employer's Representative (TA) | A | I | C | R | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
050 | No | Delivery | Agreement of an installation and commissioning process for Technology equipment with the Responsible Body and Education Technology Advisor (from the Employer). | R : Employer's Soft Landings Champion (DfE); Employer's Representative (TA); Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE); Employer's Representative (TA); Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | R/A | R | C | R | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
051 | No | Delivery | Agreement of a Technology Equipment Implementation Report (aligned with the requirements of the Technology Programme) with the Responsible Body and the Education Technology Advisor (on behalf of the Employer). | R : Employer's Representative (TA); Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA); Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | R | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
052 | No | Operation | Completion of the draft Fire Safety Management Plan with input from the Responsible Body. | R : Employer's Representative (TA); Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA); Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | R | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
053 | No | Delivery | Finalisation of the Landscape and Ecological Maintenance and Management Plan and 5 year Planned Maintenance Plan. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
054 | No | Operation | Procurement by the Responsible Body of the necessary access, maintenance and cleaning equipment required to operate the building effectively from Day One. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) |  |  | A | n/a | n/a | R | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
055 | No | Operation | Confirmation of the name(s)/contact details for the Responsible Body/School/College Coordinator(s). Note: This person should attend all project meetings at the earliest opportunity. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) I : Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Contractor's Soft Landings Representative | A | C | I | R | RIBA Stage 2: Feasibility (GW2); RIBA Stage 5: Construction | n/a | YES | n/a | n/a | n/a | YES | n/a | n/a | n/a | n/a
056 | No | Operation | Confirmation that the School/College has experienced site facilities management personnel with the skills necessary to ensure a smooth transition between construction and occupation as well as realising optimal operational performance for the life of the new facilities. Identification of gaps to inform recruitment/training planning. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative |  | A | C | C | R | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
057 | No | Operation | Confirmation of individual(s) with delegated authority to make decisions relating to the handover process on behalf of the Responsible Body/School/College Coordinator(s) where required. Note: These nominated individuals must report to the Responsible Body/School/College Coordinator(s). | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) I : Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Contractor's Soft Landings Representative | A | C | I | R | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
058 | No | Governance | Finalisation of the Training Schedule tailored to suit the facilities/estates management structure, including identification of individuals needing to be trained for the operation of the new and/or refurbished building(s) and outdoor environment, and agreement of key dates. Note: Responsible Body to ensure sufficient staff time is allocated as required by the Training Schedule. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
059 | No | Operation | Confirmation that all Access Agreements (as necessary) are in place. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
060 | No | Operation | Confirmation that insurance will be in place when the new and/or refurbished building(s) and outdoor environment have been handed over to the Responsible Body (i.e., from the date of Practical Completion). | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) |  | A | C | n/a | R | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
061 | No | Delivery | Confirmation that the School/College has the in-house expertise and/or service agreements in place to carry out all necessary building and equipment maintenance in accordance with the 5 year Planned Maintenance Plan. Note: Contractor should provide cost-effective service support arrangements for the building service systems for the School/College to adopt/fund, if they so wish, from Practical Completion. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) |  | A | C | n/a | R | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
062 | No | Delivery | Confirmation that the School/College has the in-house expertise and/or service agreements in place to carry out all necessary outdoor environment and equipment maintenance in accordance with the Landscape and Ecological Maintenance and Management Plan. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) |  | A | C | n/a | R | RIBA Stage 5: 1 Month Pre-Handover (GW5) ; RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | YES
063 | No | Operation | Provision of specialist support for the School/College Facilities Team in addressing facilities management or technology related issues during initial operation (part of aftercare service). | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator I : Employer's Representative (TA) | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator | Employer's Representative (TA) | A | I | R | C | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | YES | n/a
064 | No | Quality | Confirmation of date(s) for the completion of all snagging inspections (including FF&E, Technology and Landscape) prior to handover. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
065 | No | Governance | Confirmation of dates for the monthly aftercare meetings during the Rectification Period. | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Responsible Body/School/College Coordinator |  | A | C | R | C | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
066 | No | Quality | Confirmation that all matters on the Non Conformance and Observation Register have been remedied and signed off. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
067 | No | Quality | Written confirmation from consultants and sub-contractors with design responsibility (such as architects, structural engineers, building services engineers, landscape architects etc) that they have inspected the building(s) and outdoor environment, and that all works are compliant with the DfE's Employer's Requirements. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
068 | No | Regulatory | Confirmation that all actions identified on the Planning Conditions Tracker have been closed out with no outstanding matters remaining. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
069 | No | Regulatory | Confirmation that all statutory requirements have been met prior to Practical Completion. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 5: 6 Months Pre-Handover | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a | n/a
070 | No | Operation | Confirmation that broadband and telephone lines are in place to ensure continuity of service. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
071 | No | Regulatory | Notification to Building Control of anticipated date of Practical Completion with a request to inspect the works. | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) |  | A | C | R | n/a | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
072 | No | Quality | Issue of all deliverables (Contractor Design Documents) listed in Schedule 1: Design Submission Procedure of the Contract to the Employer's Project Team for review and acceptance. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
073 | No | Operation | Review of the draft Operation & Maintenance (O&M) Manual, including Building Log Book and Building User Guide. | R : Responsible Body/School/College Coordinator A : Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Representative (TA) |  |  | n/a | A | n/a | R | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
074 | No | Regulatory | Finalisation of the Health and Safety File for inclusion in the Operation and Maintenance (O&M) Manual. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
075 | No | Delivery | Assurance that all deliverables outlined in the Detailed Exchange Information Requirements (DEIR) for Information Exchanges IE511 and IE521 meet the relevant content requirements. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
076 | No | Delivery | Issue of all deliverables for Information Exchanges IE511 and IE521 as outlined in the Detailed Exchange Information Requirements (DEIR) to the Employer's Project Team for review and acceptance. This shall include all testing, commissioning and certification information and final record drawings for inclusion in the Operation and Maintenance (O&M) Manuals. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
077 | No | Quality | Update to Contract Notice Register to ensure all issued Contract Notices have been accurately recorded. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative | A | R | I | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
078 | No | Quality | Confirmation that all legacy fittings, furniture and equipment (FF&E) and technology equipment have been decanted to final locations and tested/certified as safe (as required) as per the agreed Decant Protocol. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
079 | No | Quality | Satisfactory completion of all mechanical and electrical services testing, commissioning and witnessing (including Technology) with certification in place. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
080 | No | Operation | Confirmation in writing that all meters and sub-meters are connected and functioning as required by the DfE’s Employer’s Requirements. | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator I : Employer's Representative (TA) | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator | Employer's Representative (TA) | A | I | R | C | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
081 | No | Operation | Satisfactory completion of soak test of all mechanical and electrical services in normal/auto operation mode prior to Practical Completion, with outcomes recorded in the Soak Test Report. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
082 | No | Operation | Issue of the completed Training Register recording attendance, dates and confirmation of staff names/signatures, and following pre-agreed Training Schedule. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: Construction; RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | YES | YES | YES | n/a | n/a
083 | No | Operation | Confirmation in writing that the meter tariff(s) is in place for exporting excess electricity generated by on site renewable technology to the grid. | R : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) |  | A | C | R | R | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
084 | No | Operation | Confirmation of arrangements to switch over gas supply to the School/College (where applicable). | R : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) |  | A | C | R | R | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
085 | No | Operation | Confirmation of arrangements to switch over water supply to the School/College. | R : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) |  | A | C | R | R | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
086 | No | Governance | Confirmation that the School/College are in receipt of all key contact details, including out of hours/emergency telephone numbers, and are aware of the procedures for the reporting of defects. | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Responsible Body/School/College Coordinator |  | A | C | R | C | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
087 | No | Regulatory | Written confirmation from the Responsible Body confirming receipt of fire safety information relating to the works, and that the information is sufficient to enable them to understand, operate and maintain the building and its fire safety systems. | R : Employer's Representative (TA); Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA); Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | R | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
088 | No | Quality | Confirmation that the Fire Safety Management Plan has been finalised by the School/College, including notification to the local fire and rescue service of any significant layout changes to the site or to buildings. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative |  | A | C | C | R | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
089 | No | Operation | Confirmation that the Responsible Body has installed all regulatory fire safety equipment including, but not limited to, fire extinguishers, fire blankets and carry down facilities such as evacuation chairs and that they are ready for use. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | n/a | C | R | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
090 | No | Regulatory | Confirmation that all statutory certification has been received. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
091 | No | Regulatory | Submittal of a Building Control Practical Completion Client Compliance Declaration to the Contractor. | R : Employer's Soft Landings Champion (DfE) A : Employer's Soft Landings Champion (DfE) I : Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Soft Landings Champion (DfE) |  | Employer's Representative (TA); Contractor's Soft Landings Representative | R/A | I | I | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
092 | No | Regulatory | Receipt of the Building Control Completion Certificate. | R : Contractor's Soft Landings Representative A : Contractor's Soft Landings Representative I : Employer's Soft Landings Champion (DfE); Employer's Representative (TA); Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Contractor's Soft Landings Representative |  | Employer's Soft Landings Champion (DfE); Employer's Representative (TA); Responsible Body/School/College Coordinator | I | I | R/A | I | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
093 | No | Regulatory | Issue of the completed Building Regulations Compliance Tracker. Note: A copy shall be included in the Operation and Maintenance (O&M) Manual. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) ; RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a
094 | No | Quality | Issue of the Snagging Report to the Contractor. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative | A | R | I | n/a | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
095 | No | Quality | Issue of the Fittings, Furniture and Equipment (FF&E) Snagging Report to the Contractor. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative | A | R | I | n/a | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
096 | No | Quality | Issue of the Technology Snagging Report to the Contractor. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative | A | R | I | n/a | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
097 | No | Quality | Issue of the Landscape Snagging Report to the Contractor. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative | A | R | I | n/a | RIBA Stage 5: 6 Months Pre-Handover; RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a | n/a
098 | No | Operation | Issue of Soft Landings Letter 3: Practical Completion to the Responsible Body. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Responsible Body/School/College Coordinator | A | R | n/a | I | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
099 | No | Governance | Issue of the Practical Completion Statement relating to the works or Section. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  |  | A | R | n/a | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
100 | No | Governance | Confirmation that the Contractor has acted in accordance with all written instructions, including Provisional Sums and Contract Variations. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  |  | A | R | n/a | n/a | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
101 | No | Operation | Confirmation that the full package of Collateral Warranties, signed by all parties, have been provided to the Responsible Body by the date of Practical Completion. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative I : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | A | R | C | I | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
102 | No | Operation | Confirmation that the full package of Product Guarantees have been issued/assigned to the Responsible Body. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative I : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | A | R | C | I | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
103 | No | Operation | Confirmation that all labelled keys, swipe cards, proximity fobs etc have been handed over to the pre-agreed representative of the School/College and have been checked to function as expected via a test run. | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator I : Employer's Representative (TA) | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator | Employer's Representative (TA) | A | I | R | C | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
104 | No | Operation | Confirmation of outcomes from planned fire drill post handover to test procedures and identify any unexpected consequences from the new arrangements. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) I : Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Contractor's Soft Landings Representative | A | C | I | R | RIBA Stage 5: 1 Month Pre-Handover (GW5) ; RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a
105 | No | Governance | Scheduling of all on site attendance dates for seasonal commissioning and monthly building performance evaluation reporting by the Contractor during the Rectification Period with access agreed with School/College (as part of the Master Programme). | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 5: 1 Month Pre-Handover (GW5) ; RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a
106 | No | Governance | Scheduling of all on site attendance dates for soft landscape aftercare by the Contractor during the Rectification Period with access agreed with School/College (as part of the Master Programme). | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator I : Employer's Representative (TA) | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator | Employer's Representative (TA) | A | I | R | C | RIBA Stage 5: 1 Month Pre-Handover (GW5) ; RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a
107 | No | Operation | Update to the Risk Register on handover with risks adjusted and residual risks captured with a plan to mitigate against an agreed timeframe. Where risks cannot be fully mitigated and require management by the Responsible Body, reasonable management procedures shall be discussed and agreed with the Responsible Body and recorded in the Residual Risk Register. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) I : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  | Responsible Body/School/College Coordinator | A | R | R | I | RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a
108 | No | Quality | Example of Defects Register following DfE standard template to be agreed. Any residual minor snagging items to be transferred to the Defects Register for ongoing monitoring. Note: Defects Register to be reviewed at the monthly aftercare meetings during the Rectification Period, with the DfE and their representatives agreeing the status of each defect until remedied. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a
109 | No | Operation | Issue of prerecorded training videos and material from all training sessions to the School/College as documented in the Training Register. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) I : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  | Responsible Body/School/College Coordinator | A | R | R | I | RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a
110 | No | Governance | Date of inspection that will confirm whether the new grass sports pitch(es) are ready for use (as applicable). | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator I : Employer's Representative (TA) | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator | Employer's Representative (TA) | A | I | R | C | RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a
111 | No | Operation | Issue of Soft Landings Letter 4: Practical Completion of planted areas due to seasonal constraints (where applicable). | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Responsible Body/School/College Coordinator | A | R | n/a | I | RIBA Stage 5: 1 Month Pre-Handover (GW5) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a | n/a
112 | No | Operation | Confirmation that additional training requirements identified post handover have been actioned and recorded in an updated Training Schedule. | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Responsible Body/School/College Coordinator |  | A | C | R | C | RIBA Stage 5: 1 Month Pre-Handover (GW5) ; RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES | n/a
113 | No | Quality | Confirmation that seasonal commissioning adjustments, any associated maintenance, and soft landscape aftercare have been recorded within an updated version of the Operation & Maintenance (O&M) Manual, Building Log Book and Health and Safety File as applicable. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 6: Rectification Period; RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES
114 | No | Quality | Confirmation that the School/College are completing routine maintenance requirements in accordance with the 5 year Planned Maintenance Plan with all activity recorded within an updated version of the Operation & Maintenance (O&M) Manual, Building Log Book and Health and Safety File as applicable. | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) I : Employer's Representative (TA) | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) |  | Employer's Representative (TA) | A | I | n/a | R | RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a
115 | No | Quality | Issue and validation of 15 monthly building performance evaluation reports (part of the Building Performance Evaluation process). | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA) I : Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Responsible Body/School/College Coordinator | A | C | R | I | RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a
116 | No | Quality | Issue and validation of the initial building performance review (part of the Building Performance Evaluation process). | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 6: Rectification Period | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | n/a
117 | No | Operation | Issue and validation of the final building performance review (part of the Building Performance Evaluation process). | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
118 | No | Quality | Confirmation that a site inspection has been arranged and completed no later than 6 months after Practical Completion to confirm all residual Snagging Items have been addressed by the Contractor. | R : Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Responsible Body/School/College Coordinator | Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Responsible Body/School/College Coordinator |  | A | C | R | C | RIBA Stage 6: Rectification Period; RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES | YES
119 | No | Operation | Confirmation that the Post Occupancy Evaluation (POE) has been arranged, completed and POE Report issued. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator |  | A | R | C | C | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
120 | No | Quality | Completion of the final inspection at the end of the Rectification Period wth any further defects identified added to the Defects Register. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator |  | A | R | C | C | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
121 | No | Quality | Confirmation that all defects as recorded on the Defects Register have been remedied in full. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) C : Responsible Body/School/College Coordinator | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) | Responsible Body/School/College Coordinator |  | A | R | R | C | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
122 | No | Operation | Issue and validation of final Environmental Benefits from Nature tool ouptut after a re-measure of soft landscape at the end of the Rectification Period. | R : Employer's Representative (TA); Contractor's Soft Landings Representative A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative | Employer's Soft Landings Champion (DfE) |  |  | A | R | R | n/a | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
123 | No | Delivery | Issue of all deliverables for Information Exchange IE611 as outlined in the Detailed Exchange Information Requirements (DEIR) to the Employer's Project Team for review and acceptance. This shall include all testing, commissioning and certification information and final record drawings for inclusion in the Operation and Maintenance (O&M) Manuals. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
124 | No | Delivery | Assurance that all deliverables outlined in the Detailed Exchange Information Requirements (DEIR) for Information Exchange IE611 meet the relevant content requirements. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) C : Contractor's Soft Landings Representative | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) | Contractor's Soft Landings Representative |  | A | R | C | n/a | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
125 | No | Governance | Issue of the Notice of Completion of Making Good or any other notice or certification of completion of making good as the Contract requires. Note: There could be more than one with Sectional Completion Contracts. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Contractor's Soft Landings Representative; Responsible Body/School/College Coordinator | A | R | I | I | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
126 | No | Operation | Issue of Soft Landings Letter 4/5: End of Rectification Period to the Responsible Body. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) I : Responsible Body/School/College Coordinator | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  | Responsible Body/School/College Coordinator | A | R | n/a | I | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
127 | No | Regulatory | Confirmation that the Responsible Body has received the Energy Performance Certificate (EPC) and that a valid Display Energy Certificate (DEC) is on display (required after the first full year of operation). | R : Responsible Body/School/College Coordinator A : Employer's Soft Landings Champion (DfE) C : Employer's Representative (TA); Contractor's Soft Landings Representative | Responsible Body/School/College Coordinator | Employer's Soft Landings Champion (DfE) | Employer's Representative (TA); Contractor's Soft Landings Representative |  | A | C | C | R | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES
128 | No | Governance | Issue of the Project Close Out Report. | R : Employer's Representative (TA) A : Employer's Soft Landings Champion (DfE) | Employer's Representative (TA) | Employer's Soft Landings Champion (DfE) |  |  | A | R | n/a | n/a | RIBA Stage 6: End of Rectification Period (GW6) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | YES

## A_Picklists
Revision Code | Status Code | Status Code and Description | YesNo | Party | Task Completed | Task Category | Code | Title | Code and Title | Organisation Type | Code | Description
n/a | n/a | n/a | n/a | n/a | Yes | Delivery | RIBA Stage 0 | Strategic Definition | RIBA Stage 0 : Strategic Definition | Employer (DfE) | n/a
P01.01 | S0 | S0: Work in Progress | YES | Employer (DfE) | No | Governance | RIBA Stage 1 | Preparation and Brief | RIBA Stage 1 : Preparation and Brief | Employer's Representative (TA) | R | Responsible
P01.02 | S1 | S1: For Coordination |  | Employer (Project Manager) | n/a | Operation | RIBA Stage 2 | Concept Design | RIBA Stage 2 : Concept Design | Responsible Body (RB) | R/A | Responsible and Accountable
P01.03 | S2 | S2: For Information |  | Employer (Project Director) |  | Quality | RIBA Stage 3 | Spatial Coordination | RIBA Stage 3 : Spatial Coordination | Contractor | A | Acountable
P01.04 | S3 | S3: For Review and Comment |  | Employer (Regional Head) |  | Regulatory | RIBA Stage 4 | Technical Design | RIBA Stage 4 : Technical Design | Other | C | Consulted
P01.05 | S4 | S4: For Review and Authorisation |  | Employer's Project Team (DfE/TA) |  | Stakeholder | RIBA Stage 5 | Manufacturing and Construction | RIBA Stage 5 : Manufacturing and Construction |  | I | Informed
P01.06 | S5 | S5: For Review and Acceptance by the DfE |  | Employer's Project Team (DfE/TA) and Responsible Body (RB) |  |  | RIBA Stage 6 | Handover | RIBA Stage 6 : Handover
P01.07 | Sn | Sn: Status Placeholder |  | Contractor |  |  | RIBA Stage 7 | Use | RIBA Stage 7 : Use
P01.08 | A | A: Accepted for all RIBA Stages as complete by the DfE |  | Project Team (All)
P01.09 | A0 | A0: Accepted in RIBA Stage 0 as complete by the DfE |  | Responsible Body (RB)
P01.10 | B0 | B0: Accepted with comments in RIBA Stage 0 as complete by the DfE |  | Employer's Representative (TA)
P01.11 | A1 | A1: Accepted in RIBA Stage 1 as complete by the DfE
P01.12 | B1 | B1: Accepted with comments in RIBA Stage 1 as complete by the DfE
P01.13 | A2 | A2: Authorised in RIBA Stage 2 as complete by the Contractor OR Accepted in RIBA Stage 2 as complete by the DfE
P01.14 | B2 | B2: Authorised with comments in RIBA Stage 2 as complete by the Contractor OR Accepted with comments in RIBA Stage 2 as complete by the DfE
P01.15 | A3 | A3: Authorised in RIBA Stage 3 as complete by the Contractor OR Accepted in RIBA Stage 3 as complete by the DfE
P01.16 | B3 | B3: Authorised with comments in RIBA Stage 3 as complete by the Contractor OR Accepted with comments in RIBA Stage 3 as complete by the DfE
P01.17 | A4 | A4: Authorised in RIBA Stage 4 as complete by the Contractor OR Accepted in RIBA Stage 4 as complete by the DfE
P01.18 | B4 | B4: Authorised with comments in RIBA Stage 4 as complete by the Contractor OR Accepted with comments in RIBA Stage 4 as complete by the DfE
P01.19 | A5 | A5: Authorised in RIBA Stage 5 as complete by the Contractor OR Accepted in RIBA Stage 5 as complete by the DfE
P01.20 | B5 | B5: Authorised with comments in RIBA Stage 5 as complete by the Contractor OR Accepted with comments in RIBA Stage 5 as complete by the DfE
P01 | A6 | A6: Authorised as in RIBA Stage 6 as complete by the Contractor OR Accepted in RIBA Stage 6 as complete by the DfE
P02.01
P02.02
P02.03
P02.04
P02.05
P02.06
P02.07
P02.08
P02.09
P02.10
P02.11
P02.12
P02.13
P02.14
P02.15
P02.16
P02.17
P02.18
P02.19
P02.20
P02
P03.01
P03.02
P03.03
P03.04
P03.05
P03.06
P03.07
P03.08
P03.09
P03.10
P03.11
P03.12
P03.13
P03.14
P03.15
P03.16
P03.17
P03.18
P03.19
P03.20
P03
P04.01
P04.02
P04.03
P04.04
P04.05
P04.06
P04.07
P04.08
P04.09
P04.10
P04.11
P04.12
P04.13
P04.14
P04.15
P04.16
P04.17
P04.18
P04.19
P04.20
P04
P05.01
P05.02
P05.03
P05.04
P05.05
P05.06
P05.07
P05.08
P05.09
P05.10
P05.11
P05.12
P05.13
P05.14
P05.15
P05.16
P05.17
P05.18
P05.19
P05.20
P05
P06.01
P06.02
P06.03
P06.04
P06.05
P06.06
P06.07
P06.08
P06.09
P06.10
P06.11
P06.12
P06.13
P06.14
P06.15
P06.16
P06.17
P06.18
P06.19
P06.20
P06
P07.01
P07.02
P07.03
P07.04
P07.05
P07.06
P07.07
P07.08
P07.09
P07.10
P07.11
P07.12
P07.13
P07.14
P07.15
P07.16
P07.17
P07.18
P07.19
P07.20
P07
P08.01
P08.02
P08.03
P08.04
P08.05
P08.06
P08.07
P08.08
P08.09
P08.10
P08.11
P08.12
P08.13
P08.14
P08.15
P08.16
P08.17
P08.18
P08.19
P08.20
P08
P09.01
P09.02
P09.03
P09.04
P09.05
P09.06
P09.07
P09.08
P09.09
P09.10
P09.11
P09.12
P09.13
P09.14
P09.15
P09.16
P09.17
P09.18
P09.19
P09.20
P09
P10.01
P10.02
P10.03
P10.04
P10.05
P10.06
P10.07
P10.08
P10.09
P10.10
P10.11
P10.12
P10.13
P10.14
P10.15
P10.16
P10.17
P10.18
P10.19
P10.20
P10
P11.01
P11.02
P11.03
P11.04
P11.05
P11.06
P11.07
P11.08
P11.09
P11.10
P11.11
P11.12
P11.13
P11.14
P11.15
P11.16
P11.17
P11.18
P11.19
P11.20
P11
P12.01
P12.02
P12.03
P12.04
P12.05
P12.06
P12.07
P12.08
P12.09
P12.10
P12.11
P12.12
P12.13
P12.14
P12.15
P12.16
P12.17
P12.18
P12.19
P12.20
P12
P13.01
P13.02
P13.03
P13.04
P13.05
P13.06
P13.07
P13.08
P13.09
P13.10
P13.11
P13.12
P13.13
P13.14
P13.15
P13.16
P13.17
P13.18
P13.19
P13.20
P13
P14.01
P14.02
P14.03
P14.04
P14.05
P14.06
P14.07
P14.08
P14.09
P14.10
P14.11
P14.12
P14.13
P14.14
P14.15
P14.16
P14.17
P14.18
P14.19
P14.20
P14
P15.01
P15.02
P15.03
P15.04
P15.05
P15.06
P15.07
P15.08
P15.09
P15.10
P15.11
P15.12
P15.13
P15.14
P15.15
P15.16
P15.17
P15.18
P15.19
P15.20
P15
P16.01
P16.02
P16.03
P16.04
P16.05
P16.06
P16.07
P16.08
P16.09
P16.10
P16.11
P16.12
P16.13
P16.14
P16.15
P16.16
P16.17
P16.18
P16.19
P16.20
P16
P17.01
P17.02
P17.03
P17.04
P17.05
P17.06
P17.07
P17.08
P17.09
P17.10
P17.11
P17.12
P17.13
P17.14
P17.15
P17.16
P17.17
P17.18
P17.19
P17.20
P17
P18.01
P18.02
P18.03
P18.04
P18.05
P18.06
P18.07
P18.08
P18.09
P18.10
P18.11
P18.12
P18.13
P18.14
P18.15
P18.16
P18.17
P18.18
P18.19
P18.20
P18
P19.01
P19.02
P19.03
P19.04
P19.05
P19.06
P19.07
P19.08
P19.09
P19.10
P19.11
P19.12
P19.13
P19.14
P19.15
P19.16
P19.17
P19.18
P19.19
P19.20
P19
P20.01
P20.02
P20.03
P20.04
P20.05
P20.06
P20.07
P20.08
P20.09
P20.10
P20.11
P20.12
P20.13
P20.14
P20.15
P20.16
P20.17
P20.18
P20.19
P20.20
P20
P21.01
P21.02
P21.03
P21.04
P21.05
P21.06
P21.07
P21.08
P21.09
P21.10
P21.11
P21.12
P21.13
P21.14
P21.15
P21.16
P21.17
P21.18
P21.19
P21.20
P21
P22.01
P22.02
P22.03
P22.04
P22.05
P22.06
P22.07
P22.08
P22.09
P22.10
P22.11
P22.12
P22.13
P22.14
P22.15
P22.16
P22.17
P22.18
P22.19
P22.20
P22
P23.01
P23.02
P23.03
P23.04
P23.05
P23.06
P23.07
P23.08
P23.09
P23.10
P23.11
P23.12
P23.13
P23.14
P23.15
P23.16
P23.17
P23.18
P23.19
P23.20
P23
P24.01
P24.02
P24.03
P24.04
P24.05
P24.06
P24.07
P24.08
P24.09
P24.10
P24.11
P24.12
P24.13
P24.14
P24.15
P24.16
P24.17
P24.18
P24.19
P24.20
P24
P25.01
P25.02
P25.03
P25.04
P25.05
P25.06
P25.07
P25.08
P25.09
P25.10
P25.11
P25.12
P25.13
P25.14
P25.15
P25.16
P25.17
P25.18
P25.19
P25.20
P25
P26.01
P26.02
P26.03
P26.04
P26.05
P26.06
P26.07
P26.08
P26.09
P26.10
P26.11
P26.12
P26.13
P26.14
P26.15
P26.16
P26.17
P26.18
P26.19
P26.20
P26
P27.01
P27.02
P27.03
P27.04
P27.05
P27.06
P27.07
P27.08
P27.09
P27.10
P27.11
P27.12
P27.13
P27.14
P27.15
P27.16
P27.17
P27.18
P27.19
P27.20
P27
P28.01
P28.02
P28.03
P28.04
P28.05
P28.06
P28.07
P28.08
P28.09
P28.10
P28.11
P28.12
P28.13
P28.14
P28.15
P28.16
P28.17
P28.18
P28.19
P28.20
P28
P29.01
P29.02
P29.03
P29.04
P29.05
P29.06
P29.07
P29.08
P29.09
P29.10
P29.11
P29.12
P29.13
P29.14
P29.15
P29.16
P29.17
P29.18
P29.19
P29.20
P29
P30.01
P30.02
P30.03
P30.04
P30.05
P30.06
P30.07
P30.08
P30.09
P30.10
P30.11
P30.12
P30.13
P30.14
P30.15
P30.16
P30.17
P30.18
P30.19
P30.20
P30
P31.01
P31.02
P31.03
P31.04
P31.05
P31.06
P31.07
P31.08
P31.09
P31.10
P31.11
P31.12
P31.13
P31.14
P31.15
P31.16
P31.17
P31.18
P31.19
P31.20
P31
P32.01
P32.02
P32.03
P32.04
P32.05
P32.06
P32.07
P32.08
P32.09
P32.10
P32.11
P32.12
P32.13
P32.14
P32.15
P32.16
P32.17
P32.18
P32.19
P32.20
P32
P33.01
P33.02
P33.03
P33.04
P33.05
P33.06
P33.07
P33.08
P33.09
P33.10
P33.11
P33.12
P33.13
P33.14
P33.15
P33.16
P33.17
P33.18
P33.19
P33.20
P33
P34.01
P34.02
P34.03
P34.04
P34.05
P34.06
P34.07
P34.08
P34.09
P34.10
P34.11
P34.12
P34.13
P34.14
P34.15
P34.16
P34.17
P34.18
P34.19
P34.20
P34
P35.01
P35.02
P35.03
P35.04
P35.05
P35.06
P35.07
P35.08
P35.09
P35.10
P35.11
P35.12
P35.13
P35.14
P35.15
P35.16
P35.17
P35.18
P35.19
P35.20
P35
P36.01
P36.02
P36.03
P36.04
P36.05
P36.06
P36.07
P36.08
P36.09
P36.10
P36.11
P36.12
P36.13
P36.14
P36.15
P36.16
P36.17
P36.18
P36.19
P36.20
P36
P37.01
P37.02
P37.03
P37.04
P37.05
P37.06
P37.07
P37.08
P37.09
P37.10
P37.11
P37.12
P37.13
P37.14
P37.15
P37.16
P37.17
P37.18
P37.19
P37.20
P37
P38.01
P38.02
P38.03
P38.04
P38.05
P38.06
P38.07
P38.08
P38.09
P38.10
P38.11
P38.12
P38.13
P38.14
P38.15
P38.16
P38.17
P38.18
P38.19
P38.20
P38
P39.01
P39.02
P39.03
P39.04
P39.05
P39.06
P39.07
P39.08
P39.09
P39.10
P39.11
P39.12
P39.13
P39.14
P39.15
P39.16
P39.17
P39.18
P39.19
P39.20
P39
P40.01
P40.02
P40.03
P40.04
P40.05
P40.06
P40.07
P40.08
P40.09
P40.10
P40.11
P40.12
P40.13
P40.14
P40.15
P40.16
P40.17
P40.18
P40.19
P40.20
P40
C01
C02
C03
C04
C05
C06
C07
C08
C09
C10
C11
C12
C13
C14
C15
C16
C17
C18
C19
C20
C21
C22
C23
C24
C25
C26
C27
C28
C29
C30
C31
C32
C33
C34
C35
C36
C37
C38
C39
C40
Pnn
Cnn