## Intro and notes
Operational PFI Decarbonisation Actions Checklist
About this guidance:
This document is aligned with:
Decarbonisation of Operational PFI Projects, Part One - Developing a Decarbonisation Plan
Government Commercial College PFI e-learning series - Decarbonisation module
This guidance has been developed primarily with PFI accommodation projects in mind, such as hospitals, schools, offices, courts, prisons, emergency services stations and community leisure facilities.
This document has been developed to assist PFI parties with the development of a project decarbonisation plan following the 5 recommended steps of:
This checklist should be read in full before starting to work through the recommended actions. It is recommended that the project partners identify and agree at each stage who is responsible for completing each action. Reducing PFI project emissions will in most cases have a benefit to all parties involved in a PFI project. Collaboration with project stakeholders will be important, to ensure that the interests of all parties are taken into account and to ensure that there is a consistent understanding of the data required and how this will be sourced and shared.
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Text runs over box right hand border Reply: this is not seen in studio please advise. Reply: Hi Steve - this isn't seen on our side in Account Management either. Please can this be checked and screenshotted. Reply: Ignore for now, client to check if this is a viewing issue

## Stage One Checklist
Stage One: Preparation
Guidance steps: Data First; Know Your Contract
Preparatory actions at stage one are to be taken by the contracting authority, with support from the SPV general manager or contract lead where applicable, before engaging stakeholders in decarbonisation planning. If the review activities at this stage identify contractual non-compliances, it is recommended that these are resolved as a priority before progressing to stage two.
Data First
No. | Area | Action | Notes | Status
1 | Know your project and boundaries of responsibility | Identify the PFI project’s contractual and physical boundaries and reporting responsibilities. | Where a project (or site) includes both PFI and non-PFI estate, multiple stakeholders are likely to be responsible for managing and reporting data.
2 | Access to Information | Identify what utilities metering arrangements are in place on your site. | On more complex sites, multiple fiscal metering arrangements may be in place. The project company and FM provider can be asked to share the current metering strategy including existing fiscal metering and sub-metering for both energy and water consumption.
|  | Prioritise installation of fiscal smart meters, if not yet done. | Smart meters provide real-time utility monitoring, which improves data accuracy and helps identify opportunities to reduce consumption, ultimately reducing cost and associated emissions. Identify which party is responsible for liaising with suppliers to arrange installation of fiscal smart-meters. These often can be installed by the network operator at little or no charge.
|  | Review sub-metering arrangements. | Project parties should consider whether additional sub-metering for specific areas of the site or large pieces of equipment would also be beneficial.
|  | Identify what data is collected and reported and by which party or parties. | Metered energy, water and waste volumes are the starting point for calculating project emissions and will usually be available from utilities and services invoices. For some projects, the SPV or FM provider will also regularly report this information.
3 | Establish baseline energy and emissions performance | Review resources to support understanding of how to calculate project emissions. | Resources to support understanding of emissions calculations are widely available:
Government Commercial College PFI Contract management e-learning - Decarbonisation module (https://www.govcommercialcollege.co.uk/course/view.php?id=220)
NISTA+Local Partnerships Project Emissions Calculator (https://www.gov.uk/government/collections/public-private-partnerships)
Greenhouse Gas Protocol guidance and resources (https://ghgprotocol.org/)
DESNZ emissions factors used in the calculation of a project’s carbon emissions (https://www.gov.uk/government/collections/government-conversion-factors-for-company-reporting)
|  | Ask SPV whether project emissions data is already available that can be shared. | The reporting of project green house gas emissions is often also an objective for owners and managers of PFI assets and the SPV and FM provider are likely to already collect emissions data and can be asked to share this.
|  | Calculate your project’s baseline energy and utilities consumption, carbon emissions and performance metrics such as energy and carbon intensity. | The starting year for monitoring carbon emissions as part of a decarbonisation plan is referred to as a project’s baseline year. Select a baseline year that aligns with the net zero strategy of the contracting authority or other sponsoring public sector body - subject to availability of data for that year that is representative of typical performance and energy use of the PFI project assets.
The project’s baseline carbon emissions can be calculated using data including the gross internal area of the project site, total energy consumption, volumes of water and waste consumed and produced, refrigerant gas emissions and any on site energy generation and export.
Metrics such as energy use intensity (energy consumption kwh / GIA m2) and carbon intensity (total carbon emissions Co2e / GIA m2) can be useful to compare performance with other projects and with industry benchmarks as well as to set decarbonisation targets.
|  | Ensure that stakeholders share a consistent understanding of baseline performance. | Collaboration with private sector partners is recommended to ensure consistency of reporting and to avoid duplication of effort. Check whether the project currently reports to a calendar or fiscal year end. Stakeholders may have different reporting year ends. It is recommended that the project partners agree on a calendar or fiscal year period for which baseline project carbon emissions can be calculated and share available source data and emissions calculations.
4 | Energy review | Commission an energy review that identifies current project energy consumption from different activities and equipment. The current energy performance of the project (or a site within the project) can be calculated and benchmarked against typical values for the asset type. | Check whether an energy review has already been carried out.
Free tools and resources are available to assist with benchmarking project energy performance (including the CIBSE Benchmarking Tool https://www.cibse.org/knowledge-research/knowledge-resources/knowledge-toolbox/benchmarking-registration), without requiring external consultancy support.
If a new energy review is required, care should be taken to establish in advance the accuracy and adequacy of data provided to support the review. The review might be commissioned from the project contractors, or from external consultants. Whoever is preparing the review would benefit from understanding the PFI contract arrangements, for example: lifecycle expenditure profiling and lender approval requirements.
The cost effectiveness of the energy review could be maximised by 1) including other sites under the scope of works; 2) conducting a decarbonisation options study alongside the energy review to recommend actionable proposals which align with lifecycle expenditure profiling.
The review scope should ask for energy saving recommendations tailored to the site characteristics and based on information gathered from site visits. There is a risk of wasted resources on desktop reports that use generic assumptions and do not take into account site specific factors.
Any relevant public sector net zero strategy should be provided to consultants as part of the scope so that recommendations can be framed against the strategic aims for the project.
Engagement with the private sector partners is recommended at the scoping phase to ensure there is adequate data for the exercise and that the scope of works considers PFI responsibilities.
Know your contract
No. | Area | Action | Notes | Status
5 | Energy Management obligations | Review existing environment management and energy obligations under the PFI contract and whether they are being met. | Check any contractual requirements for energy monitoring and reporting, whether these are being met and whether the reporting format is suited to all parties' needs.
Where applicable, review the most recent energy reports with private sector partners to ensure existing reporting takes advantage of new and better data where available.
Who manages energy risk with respect to consumption and/or tariff? If there is an energy consumption pain/gain share mechanism in the contract, review how this has been operating.
|  | Does your PFI contract already support decarbonisation goals? | Does the contract specifically require energy management and energy saving initiatives to be presented by the SPV, for example, requiring an annual energy conservation plan to be developed?
Is ISO14001 environmental management certification required on the project?
|  | If not, are stakeholders willing to collaborate to identify how decarbonisation goals can be met? | If the contract does not consider these areas, discuss whether project parties are open to collaboration to reflect aligned interests in project decarbonisation.
6 | Contract Change | Review the contractual change mechanism. | Check the contract change mechanism, which will usually set out a process to be followed for small, medium and high value changes, including lender notification, consent and/or waiver requirements. Being familiar with the contract change process will help later planning for delivery of decarbonisation change proposals.
7 | Lifecycle and Maintenance | Review the contract arrangements for lifecycle and maintenance. | Identify which party (or parties) takes the risk of lifecycle expenditure being above or below financial close expectations.
Check the contract requirements for lifecycle plans to be provided by the SPV and review the most recent lifecycle plans.
|  | Ask Project co and FM provider to present decarbonisation options for consideration as part of lifecycle planning. | Lifecycle replacement plans will usually assume a like for like replacement at end of life of project assets. The project co and FM provider can be asked to table alternative options to improve energy efficiency and reduce carbon emissions. If costs of alternative options are higher than like for like replacement then there may be a supplementary authority cost to be considered, together with any wider system dependency issues.
8 | Risk allocation, accounting treatment and classification | Assess potential impacts of interventions on risk allocation of the project. | For some complex contract change proposals, if the contracting authority takes back responsibility for parts of the site or parts of the service, or if the SPV or FM provider seek reliefs or other protection from the contracting authority for performance impacts of the change, there is the potential that these could fundamentally alter the performance incentives in the contract and undermine the transfer of risk to the project partners. In some cases this could also result in a change to the accounting treatment, classification and budgeting that is required for project payments.
|  | Consider whether accounting treatment and classification and budgeting of the project could be affected. | This is a complex area. When decarbonisation change proposals are identified, contract managers should engage with their sponsoring department at an early stage to be aware how change proposals may impact the classification and budgeting for the project. This will minimise the risk of delays or required approvals not being granted at a later stage.
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The text in A12 ‘No.’ should have same vertical alignment as adjacent field title cells Reply: query inclear please advise as text across appears aligned already.

## Stage Two Checklist
Stage Two: Developing a Decarbonisation Plan
Engage Stakeholders; Prioritise; Make a Plan
It is recommended that the contracting authority seeks support from the SPV and FM provider to work collaboratively to complete the stage two actions. If there is no existing project stakeholder sustainability or net zero group that could lead this activity, then it is recommended that a joint stakeholder decarbonisation group could be established using the NISTA template terms of reference. The stage one actions should be completed and any non-compliances resolved before starting these stage 2 actions.
Engage Stakeholders
No. | Area | Action | Notes | Status
9 | Know your Stakeholders | Identify the project stakeholders and document their interests. | Stakeholders include the SPV (usually represented by the management services provider), FM providers, building users, investor organisations, funders, sponsoring departments.
10 | Stakeholder groups | Identify whether existing project stakeholder forums exist that discuss energy management and sustainable innovation. | Decarbonisation could be considered within existing contract management meetings or project liaison meetings.
Where the SPV or FM provider is required to hold ISO 14001 environment management or ISO 50001 energy management certification, decarbonisation-focused stakeholder engagement sessions should already be in place.
|  | Consider establishing a joint stakeholder decarbonisation group to develop a decarbonisation plan for the project. | The establishment of a joint stakeholder decarbonisation group, can support the development of a decarbonisation plan for the project. This group would typically include the contracting authority, SPV and FM provider. NISTA has developed a template terms of reference for a joint stakeholder decarbonisation group (https://www.gov.uk/government/collections/public-private-partnerships). This group would be able to support the contracting authority to work through Stage Two of this Actions Checklist.
Prioritise
No. | Area | Action | Notes | Status
11 | Energy reviews and decarbonisation studies | To support the identification of decarbonisation intervention options, commission an energy review that identifies current project energy consumption from different activities and equipment, benchmarked against typical values for the asset and project type. A decarbonisation options study could be included alongside the energy review. | Check whether an energy review has already been carried out.
Free tools and resources are available to assist with benchmarking project energy performance (including the CIBSE Benchmarking Tool https://www.cibse.org/knowledge-research/knowledge-resources/knowledge-toolbox/benchmarking-registration), without requiring external consultancy support.
If a new energy review is required, care should be taken to establish in advance the accuracy and adequacy of data provided to support the review. The review might be commissioned from the project contractors, or from external consultants. Whoever is preparing the review would benefit from understanding the PFI contract arrangements, for example: lifecycle expenditure profiling and lender approval requirements.
The cost effectiveness of the energy review could be maximised by 1) including other sites under the scope of works; 2) conducting a decarbonisation options study alongside the energy review to recommend actionable proposals which align with lifecycle expenditure profiling.
The review scope should ask for energy saving recommendations tailored to the site characteristics and based on information gathered from site visits. There is a risk of wasted resources on desktop reports that use generic assumptions and do not take into account site specific factors.
Any relevant public sector net zero strategy should be provided to consultants as part of the scope so that recommendations can be framed against the strategic aims for the project.
Engagement with the private sector partners is recommended at the scoping phase to ensure there is adequate data for the exercise and that the scope of works considers PFI responsibilities.
A decarbonisation study will be informed by an energy review and a site visit to explore potential interventions - including short term changes in user behaviour as well as medium to longer term investment proposals - and make initial recommendations, from which preferred options can be shortlisted. It may be possible to combine a decarbonisation report with an energy review instead of commissioning two separate reports, to minimise costs. For less complex projects and assets, PFI partners may be able to work with the contracting authority to prepare a decarbonisation options analysis without external advisers. Good collaboration between the parties will support this and it is recommended that contracting authorities liaise with private sector partners prior to engaging external consultants. Where external consultants are commissioned to prepare a decarbonisation report, engagement with private sector partners will still be required at an early stage to ensure necessary information relating to project assets, lifecycle and maintenance is able to be shared.
12 | Energy Conservation | With project partners, identify opportunities to reduce energy demand through fabric improvements or optimising use of existing facilities and equipment. | Interventions in this category are often nil-or-low cost and can deliver energy and cost savings over short timescales. Early energy cost savings can help to offset the potential higher costs of later stage interventions such as heating system electrification. Be aware that nil or low cost changes may still require formalisation into the contract through a “small works” notice, “change notice” or variation form. This is to ensure there exists a formal agreement of the change and any associated responsibilities.
Review energy reports and metering data to identify areas of high usage.
‘Walk the site’ with the SPV and FM provider(s) to identify quick win opportunities. Examples could include: - Upgrading insulation of hot water pipes where degraded/missing - Potential for higher levels of building insulation may be relevant for consideration subject to cost and disruption trade-offs - Ensure locally controlled ventilation fan uints and air conditioning are on timers and/or thermostatic control and switched off when rooms not in use (eg overnight/weekends) - Review plant operational hours for areas not in use 24/7 - Verify chillers are being correctly cleaned and maintained - Thermostat temperature set point optimisation and 'dead band' widening - Closing doors and windows when room heating and air conditioning is operational - If applicable, doors to be closed for areas that have PIR lighting sensors when not in use - Equipment left in standby when not in use to be switched off - including IT, monitors, TVs, local manually operated air con and lighting if applicable - For catering services: not turning on catering equipment until required; not leaving hot taps running; not propping open exit doors; not propping open doors to chillers; closing windows; turning appliances off fully when not in use, installation of fridge and freezer open door monitoring and alarms
Could an ‘energy campaign’ take place to promote better ‘energy-hygiene’ among building users?
Ask FM when the last BMS review was undertaken, whether there are opportunities to optimise controls and how these can be delivered.
13 | Energy Efficiency | With project partners, review opportunities to increase the energy efficiency of project assets, including through the lifecycle programme. | Interventions in this category will often result in an upfront capital cost. Costs may be minimised by addressing energy efficiency upgrades through the project lifecycle plan as far as possible.
|  | Ask for energy efficient or lower carbon alternatives to like-for-like lifecycle replacement to be identified for all planned lifecycle interventions. | Examples include: - Upgrading lighting systems by installing LEDs or upgrading lighting controls to include energy saving technology, e.g. daylight sensors, motion sensors - Upgrading AC fans to EC fans - Upgrading air handling units to more efficient models - Upgrading heating and cooling systems to more efficient models - Upgrading the building management system (‘BMS’) - For intensive cooling 24/7 of IT server/comms rooms, potential for more effective dedicated rack cooling system instead of room air conditioning
Consider the possible impact of measures for energy bill payers as well as other stakeholders. Private sector partners will be able to assist with calculating the impact of changes.
Ensure any positive and negative changes to the ongoing cost of project services are included within priced proposals.
14 | Water and waste | Opportunities to reduce water consumption and minimise waste volumes should be included in this category. | Ask FM to support with options to reduce water consumption and waste volumes
15 | Renewables | With project partners, discuss opportunities to increase the use of renewable energy. | If not already done, switch purchased energy to renewable tariffs (particularly REGO-backed tariffs).
Investigate whether the project site may be suitable for the installation of on-site electricity generation, such as solar photovoltaic panels and battery-storage.
|  | Consider options for end of use replacement of fossil fuel heating systems, including area programmes, like district heating, if available. | Review potential for replacement of fossil fuel boilers with electric boilers, district heating, or heat pumps powered by energy from renewable sources. This may only be appropriate as part of end-of-life replacement of existing heating systems. Consider whether contract expiry asset condition requirements are aligned with the contracting authority’s long-term strategy for the project assets beyond the contract term, including heating system technologies adopted for the wider estate.
|  | Identify whether upgrades to grid connections would be needed, which often have long lead times. | Identify at an early stage whether an upgrade to building infrastructure would be required to support renewable power generation. Note that there may be long lead times for infrastructure upgrades/installation.
|  | Identify funding options such as grant schemes. | Some options, in particular for heating system decarbonisation, may have a higher capital cost than the liike for like replacement included in project lifecycle budgets. Contracting authorities will need to consider the affordability of any capital contribution that may be needed. The availability of grant schemes can be explored, noting that the project lifecycle budget allocation could in some cases be available alongside grant funding support.
Make a Plan
No. | Area | Action | Notes | Status
16 | Strategy and targets | Identify existing public sector decarbonisation strategies and targets that would apply to the project. | Review the net zero or decarbonisation strategy of the contracting authority or other public sector sponsoring body and identify the decarbonisation targets that apply to the project. If there is no pre-existing strategy or target, reference can be made to published targets by bodies such as RIBA and LETI.
Is there a sustainability team in the contracting authority able to provide support?
Are there parties within other stakeholder organisations that are able to support?
Communicate objectives with project stakeholders. Is there alignment?
17 | Decarbonisation pathway | Agree the starting emissions position and a series of potential that could deliver emissions reductions on a pathway to net zero by the target date | A strategic decarbonisation pathway can be developed to set out the project’s starting or baseline carbon emissions position and a series of emissions reduction milestones to be achieved over an agreed timeframe from a number of identified interventions.
The milestone and target dates should align with any existing decarbonisation strategy of the contracting authority or sponsor organisation (eg a local authority or NHS Trust).
The potential interventions to be explored in the categories of energy conservation, energy efficiency and renewable energy should include short term, low cost options as well as higher value options that may require complex contract change and need detailed preparation over a longer timeframe.
18 | Establish annual emissions calculation and reporting process | Identify the source of required datasets to monitor and evidence emissions reductions on an annual basis | Establishing an annual data collection process for project energy consumption, water use and waste is the starting point for the periodic calculation of carbon emissions and for tracking progress against a strategic decarbonisation pathway.
|  | Agree a process with project partners for the annual collection, reporting and tracking of calculated emissions | Some data can be sourced from contracting authority utilities bills and metered consumption of energy and water. Other data (such as waste volumes) may need collaboration and support from project partners who may already be collecting this data and able to share with the contracting authority.
The NISTA + Local Partnerships Project Emissions Calculator is a tool that can support with emissions calculations (https://www.gov.uk/government/collections/public-private-partnerships)
19 | Make a strategic decarbonisation plan for the project | Bring together the information gathered in preceding steps to develop a project-specific decarbonisation plan | Stakeholder engagement will be vital to develop a deliverable plan, capturing the learning from all preceding steps (data first, know your contract, engage stakeholders, prioritise). Depending on complexity and availability of resources, this plan could be developed by the project partners or with external support. For large multi-site projects, it may be appropriate to have a strategic plan for the project that breaks down into detailed site-specific plans to account for differences in stakeholders or contract obligations.
Suggested Contents: 1. Applicable sponsor public sector organisation decarbonisation strategy 2. Project / site boundaries 3. Stakeholders and their responsibilities 4. Decarbonisation targets and timeframes applicable to the project 5. Project baseline emissions position and components including energy use, water consumption and waste volumes 6. Establish a project decarbonisation pathway, including a baseline, a target and expected carbon reduction contributions from prioritised interventions 7. Calculate where current project performance is, mapped against the pathway 8. Establish a short-, medium- and long-term plan for interventions, with due consideration to lifecycle expenditure over the course of the remaining project timeline and with consideration of potential additional funding and finance requirements and potential sources, including applicable grant schemes 9. Identify process for annual collection of data, calculation of emissions and tracking of progress against the pathway 10. Identify the process and group(s) through which management and delivery of the interventions will be managed
20 | Feasibility study | Consider when a detailed feasibility study will be required to support delivery of more complex interventions identified in the decarbonisation plan | A feasibility study is a technical deliverability assessment for one or multiple interventions. The survey may include analysis of site characteristics and technical requirements. This would usually carry a cost for the contracting authority.Due to the contractual requirements and risk around change and variations, it is recommended that contracting authorities engage with private sector partners early on to ensure all necessary considerations have been taken into account in any procurement of a feasibility study.
To the extent that grant funding is being applied for, the eligibility criteria and any technical or other information requirements should be reflected in the feasibility study scope and shared with external consultants, so that the output from the study can be used as part of the grant application.