## Noisy Activities
Southern North Sea (SNS) Special Area Of Conservation (SAC) Noise Tracker |  | Daily Threshold: Harbour porpoise not excluded from more than 20% of the SAC on any day. |  |  |  | Winter 25/26 | 2025-10-01 | Summer 26 | 2026-04-01 |  | Summer Area (km2) | 27028 | Summer Days | 183
|  | Seasonal Threshold: Harbour porpoise not excluded for more than 10% of the SAC per day, on average over the season. |  |  |  |  | 2026-03-31 |  | 2026-09-30 |  | Winter Area (km2) | 12696 | Winter Days | 182
Project/Activity Name | Applicant | Regulator | Activity Type | Which seasonal area of the SAC does this activity impact? | Quad/Block (OPRED only) | Case Reference | Wildlife Licence Reference | Case Status | Tracker Last Updated | Start Date | End Date | Duration of Activity Impacting SAC (days) | Area Overlap with SAC (km2) | Magnitude (OPRED only) | Abatement/Mitigation (MMO only) | Any Other Comments | Include in assessment? | Include in Winter Calendar | Include in Summer Calendar | % of Winter SAC Impacted | % of Summer SAC Impacted | TrackerID | TrackerID3
East Anglia Three - Monopiling (Unabated) | Scottish Power Renewables | MMO | Piling | Both |  | DCO/2018/00001 |  | Approved | 2025-11-25 | 2025-04-17 | 2026-09-30 | 100 | 1927 |  |  |  | No | TRUE | TRUE | 15.18 | 7.13 | 10 | 6
East Anglia Three - Monopiling (Abated Scanario 2)) | Scottish Power Renewables | MMO | Piling Abated | Both |  | DCO/2018/00001 |  | Approved | 2025-11-25 | 2025-05-21 | 2026-09-30 | 100 |  |  | MENCK Hammer | Most probable scenario - X1 pile per day. | No | TRUE | TRUE | 0 | 0 | 11 | 7
Rough Storage - Geophysical Survey | Centrica Energy Storage Ltd | OPRED | Geophysical Survey | Winter | 47/2, 47/3, 4/7, 47/8 | GS/1822/0 |  | Postponed | 2025-07-15 | 2025-09-01 | 2026-03-31 | 3 | 586 | 160 cu in |  | Postponed until Autumn 2025. 2D High-Resolution Seismic, Ultra-High-Resolution Seismic, Sub-Bottom Profiler Pinger, Single and Multibeam Echo Sounder, Sidescan Sonar, Grab Sampling, Drop-Down Camera. | No | FALSE | FALSE | 0 | 0 | 30 | 9
Sofia - UXO Investigations | RWE Ltd | MMO | Geophysical Survey | Summer |  | MLA/2020/00489 |  | Approved | 2025-07-15 | 2024-10-01 | 2028-05-31 | 0 | 133.37 |  |  | Sofia have confirmed that no geophysical surveys will be conducted in 2025. | No | FALSE | TRUE | 0 | 0.49 | 33 | 10
Sizewell C - Pin Piling | EDF Energy | MMO | Pin Piling | Winter |  | DCO/2013/00021 |  | Submitted | 2025-10-21 | 2025-11-01 | 2026-03-30 | 55 | 0.1 |  | Soft / slow start and marine mammal obervers | 55 piling days within a 180 day window | Yes | TRUE | FALSE | 0 | 0 | 53 | 14
Sizewell C - Pin Piling | EDF Energy | MMO | Pin Piling | Winter |  | DCO/2013/00021 |  | Submitted | 2025-10-21 | 2026-04-30 | 2027-02-28 | 30 | 0.1 |  | Soft / slow start and marine mammal obervers | 30 piling days within a 180 day window | Yes | TRUE | FALSE | 0 | 0 | 54 | 17
Ithaca - Conductor Piling | Ithaca | OPRED | Conductor Piling | Summer |  |  |  | Submitted | 2025-09-08 | 2026-07-01 | 2026-09-30 | 3 | 78.54 |  | Soft start, marine mammal observer | Conductor piling | Yes | FALSE | TRUE | 0 | 0.29 | 56 | 22
Hoton Platform - New Well Conductor | Perenco | OPRED | Conductor Piling | Summer |  |  |  | Submitted | 2025-09-08 | 2026-04-29 | 2026-05-09 | 3 | 78.54 |  | Soft start, marine mammal observer | Conductor piling | Yes | FALSE | TRUE | 0 | 0.29 | 57 | 23
NEP Phase 1 UXO Clearance (LO) | BP | OPRED | UXO Low Order | Summer |  |  |  | Submitted | 2025-11-05 | 2026-04-01 | 2026-09-30 | 10 | 100 |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | Main UXO clearance planned fro winter months outside the SAC. Contingency for 'low order' clearance of up to 10 chance encountered UXO during construction | Yes | FALSE | TRUE | 0 | 0.37 | 65 | 32
NEP Phase 1 UXO Clearance (HO Contingency) | BP | OPRED | UXO High Order | Summer |  |  |  | Submitted | 2025-11-05 | 2026-04-01 | 2026-09-30 | 3 | 1950 |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | Main UXO clearance planned fro winter months outside the SAC. Contingency for 'high order' clearance of up to 3 chance encountered UXO during construction | Yes | FALSE | TRUE | 0 | 7.21 | 66 | 33
NEP Expansion Pipeline Routing Geophysical Survey | BP | OPRED | Geophysical Survey | Summer |  |  |  | Submitted | 2025-11-05 | 2026-05-01 | 2026-06-30 | 5 | 650 |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines |  | Yes | FALSE | TRUE | 0 | 2.4 | 67 | 36
NEP Phase 1 Development Wells Vertical Seismic Profiling | BP | OPRED | Seismic Survey | Summer |  |  |  | Submitted | 2025-11-05 | 2026-04-01 | 2026-09-30 | 3 | 450 |  | 450 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines |  | Yes | FALSE | TRUE | 0 | 1.66 | 70 | 40
NEP Expansion Appraisal Well Vertical Seismic Profiling | BP | OPRED | Seismic Survey | Summer |  |  |  | Submitted | 2025-11-05 | 2026-04-01 | 2026-06-30 | 2 | 800 |  | 400 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines |  | Yes | FALSE | TRUE | 0 | 2.96 | 71 | 46
Norfolk Vanguard West - UXO Clearance (HO) | RWE Renewables UK | MMO | UXO High Order | Summer |  | MLA/2025/00512 |  | Submitted | 2025-10-21 | 2026-04-01 | 2026-07-30 | 1 | 380.13 |  |  | Data has been provided with and without NAS. Without NAS the area overlap would be 938.31. | No | FALSE | TRUE | 0 | 1.41 | 73 | 48
East Anglia Three - Monopiling (Abated Scenario 1) | Scottish Power Renewables | MMO | Piling Abated | Both |  | DCO/2018/00001 |  | Approved | 2025-11-25 | 2025-05-21 | 2026-09-30 | 100 |  |  | MENCK Hammer | Worst case scenario - X2 piles per day. This is outlined in the SIP, but is logisitcially and operationally unlikely. | No | TRUE | TRUE | 0 | 0 | 74 | 49
Norfolk Vanguard West - UXO Clearance (HO) | RWE Renewables UK | MMO | UXO High Order | Summer |  | MLA/2025/00512 |  | Submitted | 2025-10-21 | 2026-04-01 | 2026-07-30 | 1 | 380.13 |  |  | Data has been provided with and without NAS. Without NAS the area overlap would be 938.31. | No | FALSE | TRUE | 0 | 1.41 | 75 | 51
Hornsea Three - Contingency UXO Clearance (Transmission & Generation) (LO) | Orsted | MMO | UXO Low Order | Summer |  | MLA/2025/00366 |  | Submitted | 2025-12-02 | 2025-12-01 | 2028-09-30 | 9 | 79 |  | MMMP ( MMObs, PAM, ADD's), 500m safety zone, Ntms, post-clearance MBES surveys | LO deflagration only. | No | FALSE | TRUE | 0 | 0.29 |  | 52
2026 Conductor driving (slot) Cygnus A Wellhead Platform | Ithaca (NE) E&P Ltd | OPRED | Conductor Piling | Summer | 44/12 | DR/2628/0 | N/A | Approved |  | 2026-03-02 | 2026-05-31 | 1 | 78.54 | N/A |  |  | Yes | FALSE | TRUE | 0 | 0.29 | 57 | 53
Sizewell C - Pin Piling | EDF Energy | MMO | Pin Piling | Winter |  | DCO/2013/00021 |  | Submitted | 2025-10-21 | 2025-11-01 | 2026-03-30 | 55 | 0.1 |  | Soft / slow start and marine mammal obervers | 55 piling days within a 180 day window | TRUE | FALSE | 0 | 0 | 53 | 0 | 54
Sizewell C - Pin Piling | EDF Energy | MMO | Pin Piling | Winter |  | DCO/2013/00021 |  | Submitted | 2025-10-21 | 2026-04-30 | 2027-02-28 | 30 | 0.1 |  | Soft / slow start and marine mammal obervers | 30 piling days within a 180 day window | TRUE | FALSE | 0 | 0 | 54 | 0 | 61
Platypus | Perenco | OPRED | Geophysical Survey | Summer |  | GS/1976/0 |  | Completed | 2025-09-15 | 2025-09-15 | 2025-09-30 | 15 | 275.2 |  |  |  | FALSE | TRUE | 0 | 1.02 | 61 | 1.0182 | 68
Harbour Energy - Geophysical Survey |  | OPRED | Geophysical Survey | Winter |  |  |  | Completed | 2025-10-21 | 2026-01-01 | 2026-06-30 |  |  |  |  | Awaiting further information from the developer. | TRUE | FALSE | 0 | 0 | 62 | 0 | 69
NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | BP | OPRED | Pin Piling | Summer |  |  |  |  | 2025-11-05 | 2026-07-01 | 2026-08-31 | 0 | 0 |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | Instalation methodology tbc. Pin piling worst case assumption | FALSE | TRUE | 0 | 0 | 68 | 0
NEP Expansion (C5025) Seismic Survey - CANCELLED | BP | OPRED | Seismic Survey | Summer |  |  |  |  | 2025-11-05 | 2026-04-01 | 2026-06-30 | 0 | 0 |  | 400 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines |  | FALSE | TRUE | 0 | 0 | 69 | 0
2026 Conductor driving (slot) Cygnus A Wellhead Platform | Ithaca (NE) E&P Ltd | OPRED | Conductor Piling | Summer | 44/12 | DR/2628/0 |  | Approved |  | 2026-03-02 | 2026-05-31 | 1 | 78.54 | N/A |  |  | Yes |  | FALSE | TRUE | 0 | 0.29 | 57

## Assessment summary (New) (hidden)
| Select Season | Summer |  | Season start | 2026-04-01 | Days in season | 183
| Date of assessment: | 2026-03-16 |  | Season end | 2026-09-30 | SAC Area (km2) | 27028
Projected disturbance levels - worst case scenario
|  | Projected maximum daily disturbance (% of the SAC disturbed) | 0% | Projected seasonal disturbance (Absolute worst case scenario) | 0%
|  | Number of days with >20% disturbance | 0 | Projected seasonal disturbance (Realistic worst case scenario) | 0%
These summary figures are based on a worst case scenario, and further management measures will be employed to ensure that there is no AEOI. Please see Desk Note for guidance on how these figures have been calculated.
The following projects were included in the in-combination assesssment -
Tracker ID | Project name | Activity Type | Proposed Start Date | Proposed End Date | Proposed days | Impact on SAC (km2) | Impact on SAC (%) | Contribution to seasonal disturbance (absolute worst case) | Contribution to seasonal disturbance (realistic worst case)
#REF!
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
| NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | Pin Piling | 2026-07-01 | 2026-08-31 | 0 | Instalation methodology tbc. Pin piling worst case assumption
Formulas:
Proposed Start Date = IFERROR(XLOOKUP([Tracker ID],Table13[TrackerID3],Table13[Start Date]),"")
Proposed End Date = IFERROR(XLOOKUP([Tracker ID],Table13[TrackerID3],Table13[End Date]),"")