PFI Contract 
Management Guidance

Governance

Toolkit 5: Managing Risk – A toolkit to help you understand and manage PFI risks

PFI Centre of Excellence

Published 2026

Governance

Toolkit 5: Managing Risk

This toolkit provides PFI specific information to support risk management of your PFI contract, recognising that most contracting authorities will have corporate risk management systems in place which you will be required to use.

In practice, most PFI contracts will have two types of risk registers:

An internal risk register used by the contracting authority to track risks from its own perspectives. You should expect the PFI Co and services provider to have their own internal risk registers too.

A joint risk register maintained jointly between the contracting authority, PFI Co and service provider focusing on shared operational and contractual risks.

This toolkit contains:

The common fields that you should expect to see in a PFI risk register along with guidance notes for completing these fields. It is likely that you will already be provide with this information in your corporate risk processes, but the aim is to provide you with more PFI specific information.

A list of common risks in a PFI project which will help you populate or review your PFI risk registers.

Common fields in a risk register

The table below provides a list of common fields you should expect, as a minimum, in a PFI risk register. You should cross-check this with your current risk systems and make changes as required.

| Field | Description |
| --- | --- |
| Risk ID | Use a standard convention e.g. 1, 2, 3 or YYYY-1, to ensure ease of reference. |
| Risk category | Categorising your risks helps ensure clarity and consistency in how risks are understood and managed. See Appendix 1 for a list of categories. |
| Risk description | Describe the risk: Cause: the underlying threat or danger. Event: what activates the threat. Effect: the consequence of the event. |
| Risk owner | Assign an owner to the risk who will be responsible for managing the risk. |
| Risk rating | You should record your current and target rating for your risk, noting that the risk rating is a combination of likelihood and impact (see Appendix 1 for more details). |
| Mitigation | Identify the mitigation actions, owner for the actions and a target date. |
| Trend | Indicate whether the risk rating is increasing, stable or decreasing so it is clear how the risk is changing because of mitigation actions, wider circumstance, etc. |
| Status | Indicate the status of the risk to allow easy understanding and filter of risks to improve management and escalation. The list below provides an illustrative list of statuses: Open: Risk is identified and not yet mitigated. In progress: Mitigation actions are underway. Under review: Risk or mitigation is being reassessed. Escalated: Risk has been escalated to senior management. Closed: Risk has been fully mitigated or is no longer relevant. Tolerated: Risk is acknowledged and accepted without further action or where mitigations are fully complete and residual risk is accepted. |
| Latest updated | Record the date of the last update to provide an indication of the need to review. |

List of common PFI risks

The table below provides a list of common risks in PFI contracts. You should use the list to support regular risk reviews to ensure that you have captured all risks to your PFI project.

Consider using joint risk workshops with the PFI Co and service provider to review and update your risk registers. These workshops can help identify shared risks, clarify ownership and ensure that mitigation actions are aligned across parties. This approach supports the governance principle of collaborative oversight and strengthens the effectiveness of risk management arrangements.

| Common risk | Common mitigations |
| --- | --- |
| Design and construction |  |
| Latent defects affecting long-term asset condition | Asset surveys prior to end of latent defect period for design and construction related. Asset surveys during operation phase to identify defects from changes and maintenance. |
| Unresolved construction issues impacting expiry | Expiry planning reviews, asset condition surveys, escalation procedures. |
| Operational |  |
| Service delivery failures | Use performance monitoring reports. Apply contractual deductions. Escalate through governance structures. |
| Inadequate maintenance | Review lifecycle and maintenance plans. Request evidence of compliance. Raise concerns via formal contract mechanisms. |
| Failure to meet KPIs | Validate monthly reports. Challenge inaccuracies. Apply deductions or escalate. |
| Staff shortages or capability gaps | Raise concerns through contract meetings. Request staffing plans. Escalate persistent issues via dispute resolution routes. |
| Financial |  |
| Affordability pressures | Budget forecasting and scenario testing, e.g. for inflation. Savings and efficiency reviews. |
| Payment mechanism errors | Validation checks. Reconciliation processes. |
| Legal and regulatory |  |
| Non-compliance with statutory obligations | Request evidence of compliance (e.g. fire safety, H&S). Escalate failures. Involve legal or technical advisors. |
| Gaps, ambiguities or different interpretations of the contract | Refer to contract clauses. Seek internal legal advice. Seek to negotiate resolution. Use formal dispute resolution mechanisms if needed. |
| Unclear expiry provisions | Review contract expiry clauses early. Seek legal advice. Engage with PFI Co to clarify expectations. |
| Demand |  |
| Under or over-utilisation of facilities | Demand forecasting. Stakeholder engagement to understand future occupancy. Consider developing flexibility. |
| Mismatch between service need and provision | Needs assessments. Stakeholder feedback. Consider contract changes. |
| Force majeure |  |
| Natural disasters or pandemics | Review force majeure clauses. Ensure business continuity plans are in place. Document impacts formally. |
| Civil unrest or external threats | Liaise with local authorities for both planning and operational aspects. Ensure emergency protocols are contractually supported. Escalate if service is affected. |
| Interface |  |
| Poor coordination between parties | Use governance meetings to clarify roles. Document issues. Escalate persistent coordination failures. |
| Impact of third parties | Review third-party agreement for coordination requirements. Document agreements on interfaces and communications protocols. Escalate persistent issues. |
| Misalignment of systems or processes | Raise through joint reviews. Request integration plans. Escalate where misalignment affects service delivery. |
| Technology |  |
| System failure or downtime | Develop contingency plans. Request incident logs and recovery plans. Escalate repeated failures. Validate against contract obligations. |
| Obsolescence of systems | Review asset registers and lifecycle plans. Raise concerns in expiry planning. |
| Cybersecurity threats | Request evidence of compliance with data protection and security standards. Escalate gaps. Involve IT advisors if needed. |
| Reputational |  |
| Negative media coverage | Prepare factual briefings. Ensure issues are logged and addressed. Engage communications teams. |
| Public dissatisfaction with services | Use feedback mechanisms. Escalate service failures. Ensure transparency in governance reporting. |
| Expiry and handover |  |
| Poor asset condition at expiry | Commission asset condition surveys. Compare against lifecycle obligations. Plan for remediation or deductions. |
| Lack of documentation or knowledge transfer | Request documentation early. Include in expiry planning. Escalate gaps formally. |
| Service disruption during transition | Develop a transition plan. Engage stakeholders. Use contract mechanisms to ensure continuity. |

Appendix 1: List of risk categories

The table below includes a list of risk categories. These can be adapted to suit the needs of your PFI project.

| Risk category | Description |
| --- | --- |
| Design and construction | Risks arising during the build phase, such as delays, cost overruns, design flaws or quality failures that may affect long-term performance or compliance. |
| Operational | Risks related to service delivery, maintenance, performance standards or failure to meet contractual KPIs and SLAs. |
| Financial | Risks associated with funding, payment mechanisms, inflation, interest rates, affordability or financial viability of the project. |
| Legal and regulatory | Risks from changes in law, compliance failures, legal disputes or breaches of contractual obligations. |
| Demand | Risks due to variability in usage, occupancy or service need – particularly relevant in demand-based PFI contracts. |
| Force majeure | Risks from external events beyond control, such as natural disasters, pandemics or other unforeseeable disruptions. |
| Interface | Risks arising from coordination failures between multiple contractors, stakeholders, systems or governance bodies. |
| Technology | Risks related to obsolescence, underperformance, failure or integration issues with technical systems or equipment. |
| Reputational | Risks to public perception, media scrutiny, political sensitivity or stakeholder confidence in the project or authority. |
| Expiry and handover | Risks associated with contract end, including asset condition, knowledge transfer, continuity of service and post-expiry arrangements. |

Appendix 1: Risk ratings

In your risk register you will need to rate your risk by assessing the likelihood of the risk occurring and the impact it will have if it occurs. The information below provides you with some guidance on making this assessment within the PFI context – which you will need to adapt and align with your corporate framework.

The rating section of your risk register make look similar to below (some will also include the original risk rating).

| Current risk rating |  |  | Target risk rating |  |  |
| --- | --- | --- | --- | --- | --- |
| Likelihood | Impact | Rating | Likelihood | Impact | Rating |

We set out below a 5-level approach to rating risk – others are routinely in use. Note that we recommend that you consider risk impact from a range of different perspectives and that you should generally record the highest assessment.

Assessing likelihood:

| Rating | Probability | Percentage | Criteria |
| --- | --- | --- | --- |
| 5 | Very high | 80–100% | Almost certain to occur |
| 4 | High | 60–80% | More likely to occur than not |
| 3 | Medium | 40–60% | Fairly likely to occur |
| 2 | Low | 20–40% | Unlikely but not unforeseeable |
| 1 | Very low | 0–20% | Unlikely to occur |

Assessing impact:

| Rating | Impact |  | Service and performance | Financial and commercial | Legal, regulatory and contractual | People and capability | Health, safety and environment | Reputation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Very high | Complete service breakdown or prolonged outage |  | Critical financial loss, threatens contract | Litigation, fines or contract termination | Critical loss of key personnel or leadership | Fatality or significant environmental disaster | Severe reputational damage, public outcry |
| 4 | High | Major disruption, significant service failure |  | Major financial impact, affects project viability | Legal action or significant breach of contract | Major capability gap, affects delivery | Major incident, serious injury or environmental harm | National media attention or political scrutiny |
| 3 | Medium | Moderate disruption, affects some KPIs |  | Moderate cost overrun, requires budget adjustment | Regulatory warning or minor breach | Moderate staffing or skill shortage | Moderate incident, minor injury or local impact | Regional media coverage or stakeholder concern |
| 2 | Low | Minor service disruption, quickly resolved |  | Minor cost increase, manageable within contingency | Minor compliance issue, no penalties | Minor resource gap, easily covered | Minor incident, no injury or damage | Local concern, no media attention |
| 1 | Very low | Negligible impact on service delivery or KPIs |  | Minimal financial impact, within budget | No legal or compliance issues | No impact on staffing or capability | No HSE incidents or environmental impact | No reputational impact |

Assessing overall rating:

| Impact |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Likelihood |  |  | 1 | 2 | 3 | 4 | 5 |
|  | 5 |  | 5 | 10 | 15 | 20 | 25 |
|  | 4 |  | 4 | 8 | 12 | 16 | 20 |
|  | 3 |  | 3 | 6 | 9 | 12 | 15 |
|  | 2 |  | 2 | 4 | 6 | 8 | 10 |
|  | 1 |  | 1 | 2 | 3 | 4 | 5 |