PFI Contract 
Management Guidance

Contract Management Plan

Toolkit 1: CMP Template – An annotated template to support the development of a CMP for your PFI contract

PFI Centre of Excellence

Published 2026

Contract Management Plan

Toolkit 1: Contract Management Plan Template

This Contract Management Plan (CMP) template is designed to support PFI contract managers and their teams in developing a structured, practical plan for managing their contract.

The CMP is not a one-size-fits-all document. It should be tailored to reflect the specific characteristics of your contract, its complexity, maturity, risk profile, and available resources. You are encouraged to build the CMP in layers, starting with the most critical sections and expanding over time.

Key Principles for Using This Template

Start with what you know: Use existing documentation, contract reviews, and team knowledge to populate the template.

Be proportionate: Not every section needs to be completed in full. Focus on what matters most for your current priorities.

Phased: Start with the most critical sections.

Event-Drive: Use key events as triggers to develop or update.

Comprehensive: Develop the CMP in a coordinated approach.

Use it actively: The CMP is a live document. It should be reviewed regularly and updated following key events (e.g. variations, refinancing, expiry planning).

Support continuity: The CMP helps ensure that knowledge is retained and shared across the team, especially during staff changes or transitions.

Reference, don’t repeat: Where possible, link to source documents (e.g. contract schedules, risk registers) rather than duplicating content.

✅ Alignment and Deliverability Checklist

- Does the CMP reflect the strategic intent and priorities set out in your CM Strategy.

- Does the Intelligent Client Function have the capacity and capability to implement?

- Are the governance arrangements well defined, practical and proportionate?

- Have you been transparent about any rights or activities that won’t be exercised and explain why.

This template includes:

🎯 Purpose of this Section

📄 What to Include

🔍 Where to Find the Information: including references to the contract or guidance

🧰 Template Text: suggested text which you may wish to edit and included in your CMP.  Note this is only provided for some section where it enhances the ‘What to Include’ section
Red text provides guidance on what to include or where to find information
Blue text provides draft text or example text

This template does not replace the Project Agreement or other contractual documents. It is a tool to support their effective implementation.

[Insert Logo]

[Project Name] PFI Contract

Contract Management Plan

[Insert Site Image]

Version Number:

Date:

Version Control

| Version Number | Changes | Author | Approver | Date Approved |
| --- | --- | --- | --- | --- |

Contents

1.	Introduction and Purpose	7

2.	Contract Summary and Overview	8

3.	Governance, Roles, and Stakeholder Interfaces	15

4.	Intelligent Client Function	17

5.	Stakeholder Engagement and Communications	19

6.	Knowledge Management and Continuity Planning	21

7.	Management Information and Authority Information Rights	23

8.	Performance Management	25

9.	Asset and Environmental Management	27

10.	Operational Risk, Contingency Planning, and Service Continuity	29

11.	Financial Management	31

12.	Refinancing	33

13.	Change Management and Variations	35

14.	Benchmarking, Market Testing, and Value for Money	37

15.	Legal and Regulatory Compliance	39

16.	Contractual Protections	40

17.	Insurance Management	41

18.	Land, Lease and Property Arrangements	42

19.	Contractual Interfaces and Dependencies	43

20.	Workforce and Employment Matters	44

21.	Intellectual Property and Information Management	46

22.	Disputes Resolution	47

23.	Exit, Termination and Expiry Planning	48

Introduction and Purpose

🎯 Purpose of this Section

To explain the role of the CMP, its relationship to the CMS, and how it supports effective contract management.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Purpose and scope of the CMP |  |  |
| Link to the Contract Management Strategy (CMS) |  |  |
| Live and evolving nature of the CMP |  |  |
| Intended users of the CMP |  |  |
| Review and update process |  |  |

🔍 Where to Find the Information

Your Contract Management Strategy (and CMS Guidance).

Contract Management Plan Guidance.

🧰 Template Text

This Contract Management Plan (CMP) sets out how the [Project Name] PFI contract will be managed throughout its life. It provides a structured, operational plan for delivering the contract effectively and consistently, and is intended to be used by the contract management team and wider stakeholders.

The CMP is developed in alignment with the Contract Management Strategy (CMS) and translates its strategic intent into day-to-day delivery. It supports key contract management activities such as governance, performance monitoring, risk management, financial oversight, and change control.

The CMP is a working document that supports the contract team in their day-to-day responsibilities. It provides a single reference point for how the contract is managed, helping to ensure continuity, consistency, and informed decision-making. It should be used actively to guide meetings, track obligations, respond to issues, and onboard new team members.

⚠️ This CMP does not override the Project Agreement. The Project Agreement is the legally binding document and takes precedence in all cases. The CMP is a practical tool to support its implementation—not a substitute for it.

This CMP will be reviewed annually by the Contract Manager and updated as required. Updates may also be triggered by significant events such as variations, refinancing, expiry planning, or changes in personnel. All updates will be subject to approval by the Senior Responsible Owner (SRO). Version control is maintained to ensure users are working from the most current version.

Contract Summary and Overview

🎯 Purpose of this Section

To provide a concise overview of the contract, including key facts, parties, and structure. This helps orient new users, supports continuity, and provides a reference point for key contractual information.

📄 What to Include (see templates below for more details)

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Project name and summary |  |  |
| Key dates and milestones |  |  |
| Financial overview |  |  |
| Contracting parties and key personnel |  |  |
| Occupiers and users |  |  |
| Contract structure and timeline |  |  |
| Linked agreements or third-party arrangements |  |  |

🔍 Where to Find the Information

Document Stocktake outputs.

Project Agreement and Schedules, and the Contract Review output if completed.

Project Financial Model.

Companies House for information about the PFI Co.

HMT PFI Data Return.

Other internal stakeholders (you may also ask the PFI Co or Service Providers if you cannot locate the information internally).

🧰 Template Key Information Table

Note that this table is the same as the one found in Toolkit 2 (Based Data) in the Contract Review Guidance. Blue text provides illustrative examples.

| Key Contract Information |  |
| --- | --- |
| HMT ID number | The HMT code and name used against reference. If unsure, then can be sought via www.gov.uk |
| Project Name |  |
| Project Summary | Provide a summary of the key elements of the contract purpose, assets and services The contract provides for the build of 5 new secondary schools and ongoing maintenance and facility management services. Additional service provided to manage the school library services. The schools are located as follows: John Inverdale School – Ox Lane, DS1 3PX Anaheim School, Sea Road DS23 2LM etc. |
| Date of Financial Close |  |
| Date of Construction Completion | Usually the construction period end date (completion certification may have been issued). If construction end was phased, you may wish to include these dates too) |
| First Date of Operations | Usually the Service Commencement Date. This may be the last date of the construction phase. Where construction end was phased then you may wish to include subsequent phases of service commencement. |
| Date of 1st Operations | The date where the construction phase is complete, and all requirements have been met to enable the facility to move into the operational phase, including the issuing of the certificate of Availability. |
| Expiry Date | The date at which the contract expires through the effluxion of time. If there are break clauses you may wish to capture these here |
| Capital Value £m | This is the total nominal capitalised costs of the project as recorded in the financial model at financial close and forecast to be incurred during the core investment period. This should equate to the total project company debt plus total shareholder financing (equity and shareholder loans) plus any Authority capital contribution, all as committed at financial close. |
| Total Forecast Annual Unitary Charge (£m) | Insert the total forecast annual UC payment, make a note of whether this is nominal or outturn. |
| Remaining UC (£m) | Insert the remaining UC payable from the start of the FY to expiry, make a note of the current FY and whether the UC is nominal or outturn |
| Index Regime | Insert details of the index regime use to calculate future unitary charge payments e.g. CPI, RPI, AWE |
| On/Off Balance Sheet (IFRS) | International Financial Reporting Standards (IFRS) are a set of accounting standards developed by the International Accounting Standards Board (IASB) that provide guidance on how to prepare and present financial statements. |
| On/Off Balance Sheet (ESA) | Each PFI / PF2 is assessed under the ESA rules applying at the time it reached financial close. Eurostat has not, to date, required older PFIs recording to be reassessed under the latest rules unless contractual changes have occurred that would change the recording under ESA. Where contractual changes have occurred, the contract should be reassessed under the rules applying when the contract changes took place. A Guide to the Statistical Treatment of PPPs is available here |
| Bond or Debt Financed | Insert details of financing arrangements. You may wish to include the size of the bond/debt, its final repayment dates and interest/coupon rate. |
| Payment Mechanism Type |  |
| Benchmarking/Market Testing Frequency |  |
| Insurance Review Frequency |  |
| Other periodic events | Insert other key periodic contract events |
| Contracting Authority’s Information |  |
| Contracting Authority | Insert the contracting authority’s name – this is typically the public body who is party to the PA |
| CA’s Senior Responsible Owner | Insert name and role |
| Authority Representative | This role is typically defined in the Project Agreement and is generally the contract manager. |
| Contract Manager | Insert name and role |
| Key People | Insert the names/role of key people in the contracting authority including service lead, finance manager, commercial lead, health & safety lead etc. |
| Sponsoring Department |  |
| Sponsoring Department |  |
| Department Sponsor Contact | Insert name and role |
| User Details |  |
| Senior User Representative(s) | Insert name and role of senior user representatives. This may be people in your organisation or external organisation e.g. Academy Trust |
| Occupiers | Insert details of occupiers and the scale of their occupation e.g. % of building, number of desks. |
| PFI Project Company (also known as SPV) |  |
| Company Name | This is the name of the counter party to the Project Agreement. Note it is not the service provider. |
| Company’s House Number | An 8-digit number for the PFI Project Company available from Company’s House where you can find statutory company records including accounts and ownership details. |
| Company Directors | Include the names of company directors and which shareholder they represent. |
| General Manager | Insert name and role |
| Key Personnel | Insert the names/role of key people including finance manager, commercial lead, lifecycle lead etc. |
| Management Service Provider | Insert the name of the management service provider to the PFI Project Company. The MSP typically provides staff and services to allow the PFI Project Company to carry out its duties. You should also note any common ownership between the PFI Project Company and the MSP. |
| Service Provider |  |
| Services Provider(s) | Insert the name of the service provider(s) to the PFI Project Company. This may include FM companies, housing management providers, care providers etc. |
| Key Personnel in Service Provider | Insert name and role. This may include general managers and leads for key service lines |
| Key Sub-contractors | Add details of any key sub-contractors – this may include OEM providers or those required to run the services day to day e.g. catering provider, fire systems companies Security – Night Owl Ltd – 0135 754 254 Catering – Good Food Plc – 0164 247 259 |
| Interfaces and Third Pary Agreements |  |
| Share Access | Littlemore Leisure Centre – shared access road |
| Utility Supply | Clean Power Ltd – supply of gas and electricity |
| Utility Network Provider | Network SW Ltd – gas networks provider |
| Contracting authority’s Sub-Tenant | Happy Nursery – tenant on adjoining authority land (not PFI) but catering provided |

🧰 Template Contract Parties Diagram

You may wish to insert a diagram of the project structure like the example below.

🧰 Template Contract Timelines

You may wish to insert a timeline of key historic and future contract events to serve both as a record of major events and to help with planning for future activity.

| Milestone | Date | Notes |
| --- | --- | --- |
| Financial Close | [dd/mm/yyyy] | Contract signed and funding secured |
| Construction Completion | [dd/mm/yyyy] | Practical completion achieved |
| Service Commencement | [dd/mm/yyyy] | Availability certificate issued |
| End of Latent Defects Period | [dd/mm/yyyy] | As defined in the contract |
| Expiry Planning Start | [dd/mm/yyyy] | Typically, 7 years before expiry |
| Contract Expiry | [dd/mm/yyyy] | End of contract term |

🧰 Template Location of Key Documents

You may wish to add key documents; their location and date they were last update or current version number.

| Document Title | File Location | Date |
| --- | --- | --- |
| Project Agreement & Schedules | \SharedDrive\PFI\Legal\PA | 01/04/2020 |
| Financial Model (Base Case) | \SharedDrive\PFI\Finance\Models\BaseCase.xlsx | 01/04/2020 |
| Variations Register | \SharedDrive\PFI\Legal\Variations\Register.xlsx | 15/03/2025 |
| Risk Register | \SharedDrive\PFI\Governance\RiskRegister.xlsx | 01/06/2025 |
| Exit Plan | \SharedDrive\PFI\Expiry\ExitPlan.docx | 01/01/2025 |

Governance, Roles, and Stakeholder Interfaces

🎯 Purpose of this Section

To describe how the contracting authority manages the contract through a structured governance framework, clearly defined roles and responsibilities, and a robust approach to risk and issue management. This section ensures that all parties understand who is responsible for what, how decisions are made, and how performance, compliance, and risks are monitored and escalated.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Roles and Responsibilities |  |  |
| Key roles within the contracting authority e.g. Authority’s representative, SRO, Contract Manager, Finance Lead |  |  |
| Key roles within the PFI Co and service providers e.g. General Manager, Lifecycle Lead |  |  |
| Key users and tenants |  |  |
| Third parties and external stakeholders e.g. Lenders, Government Departments |  |  |
| A RACI matrix or similar tool to clarify accountability and decision-making responsibilities |  |  |
| Governance Structures |  |  |
| Description of governance forums |  |  |
| Meeting schedules and frequency |  |  |
| Terms of reference and escalation routes |  |  |
| Delegated authority and decision-making protocols |  |  |
| Risk Management |  |  |
| How risks are identified, owned, mitigated, and reviewed |  |  |
| Use of internal and joint risk registers |  |  |
| Escalation and reporting processes |  |  |
| Links to governance meetings and assurance processes |  |  |

🔍 Where to Find the Information

📜 Contractual References

Authority’s Rights – for oversight, enforcement, and access powers

Contractor’s Obligations – for service delivery, reporting, and cooperation

Authority’s Representative and Contractor’s Representative – for formal roles and delegated authority

Governance-related provisions, covering:

Joint liaison boards or governance groups

Meeting structures, escalation routes, and decision-making protocols

Risk allocation and issue management responsibilities

🗺️ Guidance Materials

Governance Guidance

Appendix 1: Governance Elements – What Good Looks Like

Toolkit 2: Governance Mapping – to document current structures

Toolkit 3: Governance Effectiveness Review – to assess and improve arrangements

Intelligent Client Function Guidance

Appendix 1: Core ICF Functions – for defining internal roles

Toolkit 2: ICF Capability Diagnostic – to assess capacity and resilience

Contract Management Strategy

Sections on strategic leadership, stakeholder engagement, and risk appetite

Contract Review Guidance

Toolkit 3: Clause Tracker – to extract and summarise relevant contractual provisions

Gaps and Ambiguities Guidance

For identifying unclear or missing role definitions or governance mechanisms

🏛️ Internal Resources

Organisational charts and team structures

Internal RACI matrices and role descriptions

Internal governance frameworks or escalation protocols

Risk registers and issue logs

Local policies on risk management, assurance, or decision-making

Intelligent Client Function

🎯 Purpose

To describe the Intelligent Client Function (ICF) as the internal capability that enables the contracting authority to act as a strategic, informed, and empowered client in managing the PFI contract. This section outlines how the ICF supports both day-to-day contract delivery and long-term outcomes through commercial, technical, legal, financial, and operational functions.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Definition of the ICF and its purpose |  |  |
| Summary of the ICF’s core functions |  |  |
| How the ICF supports governance, performance monitoring and contract events |  |  |
| Description of ICF structure and resourcing |  |  |
| Alignment with wider contract management framework |  |  |

🔍 Where to Find the Information

📜 Contractual References

Authority’s Representative – defines the formal role and delegated authority typically associated with the ICF lead

🗺️ Guidance Materials

Intelligent Client Function Guidance

Appendix 1: Core ICF Functions – defines the full range of ICF responsibilities

Toolkit 1: Context Mapping Worksheet – to align the ICF with contract needs

Toolkit 2: ICF Capability Diagnostic – to assess current maturity and gaps

Toolkit 3: ICF Calculator – to estimate required FTEs and sourcing strategies

Contract Management Strategy

Sections on resourcing, capability, and strategic alignment of the ICF

Governance Guidance

For how the ICF supports governance structures and decision-making

🏛️ Internal Resources

ICF team structure and job descriptions

Internal workforce plans

Training and succession planning materials

Local sourcing strategies (e.g. make/buy/borrow models)

Stakeholder Engagement and Communications

🎯 Purpose of this Section

To describe how the contracting authority engages with internal and external stakeholders, including service users, to support effective contract management. This includes defining communication protocols, engagement methods, and how stakeholder feedback informs performance monitoring and service improvement.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Stakeholder Identification |  |  |
| Identification of internal and external stakeholders e.g. internal: SRO, Contract Manager, ICF, service users, sponsoring departments e.g. external: PFI Co, service providers, lenders, regulators |  |  |
| Consider tools such as: A stakeholder map to visualise relationships and influence. A stakeholder register to track contact details, roles, and engagement needs. A power-interest matrix to prioritise engagement strategies. |  |  |
| Engagement and Communications Protocols |  |  |
| Internal and external engagement methods, such as: Internal methods: team briefings, dashboards, shared drives, internal newsletters. External methods: governance meetings, site visits, user forums, formal correspondence. |  |  |
| Define escalation routes and feedback loops |  |  |
| Cross reference relevant governance forums (see section 3) |  |  |
| Feedback Mechanisms |  |  |
| Outline how feedback is gathered e.g. surveys, complaints, user forums |  |  |
| Explain how feedback is reviewed, escalated, and used to inform performance monitoring and service improvement |  |  |
| Explain linkage to performance management and change control processes |  |  |
| Integration with Governance |  |  |
| Describe how stakeholder engagement supports transparency, accountability, and continuous improvement |  |  |
| Reference governance documents, terms of reference, and reporting structures |  |  |

🔍 Where to Find the Information

📜 Contractual References

Monitoring Schedule – for provisions on user involvement in service monitoring or feedback

Payment Mechanism Schedule – where user satisfaction or service quality may influence deductions or incentives

Governance-related provisions – for escalation routes and joint communication forums

🗺️ Guidance Materials

Governance Guidance

Appendix 1: Governance Elements – What Good Looks Like – includes stakeholder engagement as a core governance element

Toolkit 2: Governance Mapping – to identify internal and external engagement structures

Intelligent Client Function Guidance

For how the ICF supports stakeholder engagement and communication

Performance Management Guidance (if available)

For how stakeholder feedback informs service monitoring and improvement

🏛️ Internal Resources

Stakeholder maps or engagement plans

Communication protocols or templates

Records of user feedback, surveys, or complaints

Escalation procedures and contact directories

Meeting schedules and terms of reference for stakeholder forums

Knowledge Management and Continuity Planning

🎯 Purpose of this Section

To describe how the contracting authority manages contract-related knowledge, documentation, and continuity planning. This includes protocols for document management, onboarding, succession planning, and lessons learned, ensuring that knowledge is retained and accessible throughout the contract term.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Document and Records Management |  |  |
| Systems and tools used e.g. shared drives, document management systems |  |  |
| File naming conventions, version control, and access protocols |  |  |
| Location of key documents e.g. Project Agreement, risk register, variation log |  |  |
| Knowledge Retention and Transfer |  |  |
| How contract-specific knowledge is captured and shared e.g. handover notes, knowledge hubs, user guides |  |  |
| Use of lessons learned logs or post-incident reviews |  |  |
| Succession Planning and Onboarding |  |  |
| Processes for onboarding new team members e.g. induction packs, shadowing |  |  |
| Succession planning for key roles e.g. Contract Manager, SRO |  |  |
| Use of role profiles and capability frameworks |  |  |
| Training and Capability Development |  |  |
| Reference to ICF capability development plans |  |  |
| Internal or external training resources e.g. PFI Centre of Excellence materials |  |  |
| Continuity Planning |  |  |
| How continuity is maintained during staff turnover or organisational change |  |  |
| –Links to business continuity or disaster recovery plans |  |  |

🔍 Where to Find the Information

📜 Contractual References

Confidentiality and Data Protection clauses – for requirements on information handling and access

Expiry and Handover provisions – for expectations around knowledge transfer and documentation at contract end

🗺️ Guidance Materials

Intelligent Client Function Guidance

Appendix 1: Core ICF Functions – includes knowledge management and succession planning

Toolkit 2: ICF Capability Diagnostic – to assess continuity risks and capability gaps

Contract Management Strategy

Sections on knowledge management, succession planning, and strategic resilience

Governance Guidance

For how governance structures support knowledge retention and handover

🏛️ Internal Resources

Document management systems and file structures

Onboarding materials and role handover notes

Succession plans and training records, or HR support

Lessons learned logs or post-event reviews

Policies on data retention, access, and confidentiality

Management Information and Authority Information Rights

🎯 Purpose of this Section

To describe how the contracting authority’s rights to receive and request Management Information (MI) are exercised under the contract. This includes identifying what information is required, how it is used to support contract management, and how compliance with these obligations is monitored and assured.

This section ensures that the contracting authority’s contractual rights to information are clearly understood, actively used, and embedded in governance, performance, financial, and risk management processes.

📄 What to Include

| Item | Included? | Notes / File Reference |
| --- | --- | --- |
| Summary of MI obligations under the contract e.g. monthly reports, helpdesk logs, lifecycle updates, insurance certificates |  |  |
| Authority’s rights to request additional information e.g. audit, inspection, FOI, data access |  |  |
| How MI is used in governance and decision-making e.g. dashboards, meeting packs, assurance reviews |  |  |
| Escalation routes for non-compliance or missing MI |  |  |
| Table or diagram of key MI flows Include frequency, format, responsible party |  |  |
| Cross-references to related CMP sections (e.g. Performance, Financial, Risk, Expiry) to show how MI supports those areas |  |  |

🔍 Where to Find the Information

📜 Contractual References

Audit and Records Clauses – define the contracting authority’s rights to inspect, request, and audit information.

Monitoring and Reporting Schedules – set out the frequency, format, and content of required reports (e.g. performance, lifecycle, insurance).

Data Protection and FOI Clauses – outline obligations for handling, storing, and disclosing information.

Refinancing, Insurance, and Lifecycle Clauses – may include specific MI obligations or notification requirements.

🗺️ Guidance Materials

Contract Review Guidance

Use the clause tracker to identify MI related provisions

Performance Management

🎯 Purpose of this Section

To describe how the contracting authority monitors, assures and manages service performance under the PFI contract. This includes how performance data is used to:

Ensure services are delivered to the required standard.

Identify and address risks early.

Apply deductions or incentives in line with the contract.

Inform governance, decision-making, and continuous improvement.

Performance management supports both day-to-day operations and strategic oversight. It is a key enabler of effective contract management and value for money.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Performance Management Framework |  |  |
| Overview of how performance is monitored, assured and managed |  |  |
| Reference to relevant contract schedules (e.g. Schedule 5: Payment Mechanism) |  |  |
| Key Performance Indicators (KPIs) and Service Level Agreements (SLAs) |  |  |
| Description of the KPIs and SLAs used to assess service delivery |  |  |
| How these are measured, reported, and reviewed |  |  |
| Assurance Arrangements |  |  |
| Describe the PFI Co’s internal assurance regime (e.g. quality management systems, internal audits) |  |  |
| Describe the contracting authority’s own assurance activities (e.g. spot checks, independent audits, third-party validation). |  |  |
| Monitoring and Reporting Arrangements |  |  |
| Frequency and format of performance reporting |  |  |
| Roles and responsibilities for reviewing and validating performance data |  |  |
| Use of dashboards, helpdesk systems, or audit tools |  |  |
| Escalation and Issue Resolution |  |  |
| How underperformance is identified, escalated, and addressed |  |  |
| Links to governance forums (e.g. Operational Review, Management Meeting) |  |  |
| Deductions and Incentives |  |  |
| How deductions are calculated and validated |  |  |
| Any incentive mechanisms in place (if applicable) |  |  |
| Integration with Other Sections |  |  |
| Reference to lifecycle and asset performance (see Section 9) |  |  |
| Link to change control (Section 13) and risk management (Section 3 & 10) |  |  |

🔍 Where to Find the Information

📜 Contractual References

Monitoring Schedule – defines KPIs, SLAs, and performance monitoring obligations

Payment Mechanism Schedule – outlines how deductions and incentives are applied

Authority’s Rights and Contractor’s Obligations – establish oversight and reporting duties

Helpdesk and Reporting Clauses – may be found in service-specific schedules

🗺️ Guidance Materials

Document Stocktake Guidance

Toolkit 2: lists operational documents such as monthly reports, helpdesk logs, and annual service reports

Intelligent Client Function Guidance

Appendix 1: Core ICF Functions – defines the ICF’s role in performance oversight

Toolkit 2: ICF Capability Diagnostic – to assess performance management capacity

Governance Guidance

Appendix 1: Governance Elements – describes how performance is reviewed through governance

Toolkit 4: Operational Review Meeting Terms of Reference

Performance Management Guidance suite

🏛️ Internal Resources

Locally maintained trackers or dashboards (where used) to support performance oversight

Asset and Environmental Management

🎯 Purpose of this Section

To describe how the contracting authority oversees the PFI Co’s responsibilities for maintaining asset condition, ensuring statutory compliance, and supporting environmental and sustainability objectives. This includes how lifecycle planning is monitored, how asset data is reviewed, and how environmental performance is integrated into contract management.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Asset Management Oversight |  |  |
| How the contracting authority monitors the condition, performance, and statutory compliance of assets |  |  |
| Reference to asset condition surveys, maintenance schedules, and statutory testing |  |  |
| Lifecycle Planning and Capital Replacement |  |  |
| How lifecycle plans are reviewed and challenged |  |  |
| How the contracting authority ensures alignment between lifecycle delivery, asset condition, and the payment mechanism |  |  |
| Use of forward maintenance plans and independent surveys |  |  |
| Data and Reporting |  |  |
| What asset data is provided by the PFI Co and how it is reviewed |  |  |
| Use of asset registers, condition reports, and performance dashboards |  |  |
| Environmental and Sustainability Considerations |  |  |
| How environmental obligations are monitored (e.g. energy use, waste, emissions) |  |  |
| How the contracting authority supports or leads decarbonisation or sustainability initiatives |  |  |
| Reference to any local or national environmental targets |  |  |
| Integration with Expiry Planning |  |  |
| How asset condition and lifecycle delivery are linked to handback planning (see Section 23) |  |  |

🔍 Where to Find the Information

📜 Contractual References

Maintenance Schedule – sets out the PFI Co’s obligations for planned and reactive maintenance

Lifecycle Schedule – defines lifecycle responsibilities, planning, and funding

Environmental Obligations – may be included in the Output Specification or Contractor’s Proposals

Construction Requirements / Contractor’s Proposals – describe the original asset design and performance expectations

Payment Mechanism Schedule – links asset condition and availability to deductions

Expiry and Handover provisions – define asset condition requirements at contract end

🗺️ Guidance Materials

Performance Management Guidance: For monitoring asset-related KPIs and statutory compliance

Asset Condition Playbook: Provides guidance on assessing and managing asset condition throughout the contract term.

Expiry Guidance: Covers asset handback standards and alignment with lifecycle delivery

Intelligent Client Function Guidance Appendix 1: Core ICF Functions – includes technical oversight and lifecycle planning

Decarbonisation Guidance: For integrating environmental and sustainability objectives into contract management

🏛️ Internal Resources

Locally maintained asset registers, condition surveys, or lifecycle trackers (where used) to support oversight and planning

Operational Risk, Contingency Planning, and Service Continuity

🎯 Purpose of this Section

To describe how operational risks are identified, managed, and mitigated, and how contingency and continuity plans are developed and maintained. This includes the roles of both the contracting authority and the PFI Co in ensuring service continuity during disruptions, emergencies, or other unplanned events.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Operational Risk Management |  |  |
| Reference Section 3 (Governance) for the overall risk management framework |  |  |
| Describe how operational risks are identified, categorised, and monitored e.g. service disruptions, system failures, staffing shortages |  |  |
| Explain how these risks are linked to contingency and continuity planning |  |  |
| Contingency Planning |  |  |
| PFI Co’s obligations for business continuity and disaster recovery |  |  |
| Contracting authority’s role in reviewing, approving, and testing contingency plans |  |  |
| Frequency of plan reviews and updates, and how they are documented |  |  |
| Service Continuity Protocols |  |  |
| How continuity of service is maintained during disruptions e.g. strikes, IT failures, extreme weather |  |  |
| Escalation routes and communication protocols during incidents |  |  |
| Links to statutory requirements e.g. emergency planning, health and safety |  |  |
| Assurance and Testing |  |  |
| How contingency plans are tested e.g. tabletop exercises, live drills |  |  |
| How lessons learned are captured and used to improve future planning |  |  |
| Integration with Governance |  |  |
| How risks and continuity planning are reported through governance forums |  |  |
| Links to audit, assurance, and performance management processes |  |  |

🔍 Where to Find the Information

📜 Contractual References

Maintenance Schedule – may include obligations for business continuity and emergency response

Authority Step-In provisions – define the contracting authority’s rights in the event of service failure (also see Section 16 for step-in)

Business Continuity and Emergency Planning clauses – set out the PFI Co’s contingency planning responsibilities

Dispute Resolution and Escalation clauses – may define how issues are raised and managed during operational disruption (also see Section 22)

🏛️ Internal Resources

Locally maintained risk registers or business continuity plans (where used) to support operational resilience

Financial Management

🎯 Purpose of this Section

To describe how the contracting authority manages the financial aspects of the PFI contract, including the unitary charge, deductions, approvals, and internal financial governance. This section supports transparency, accountability, and value for money throughout the contract term.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Unitary Charge Management |  |  |
| How the contracting authority reviews and approves monthly invoices including time scales for payment |  |  |
| Calculation of the unitary payment including indexation of the unitary charge |  |  |
| How deductions are calculated and validated (see section 11 also) e.g. for performance or availability failures |  |  |
| How to manage disputed amounts |  |  |
| Reference to the Unitary Payment clauses and Payment Mechanism schedule in the contract |  |  |
| Financial Governance and Controls |  |  |
| Internal processes for financial approvals, budget forecasting, and affordability tracking |  |  |
| Roles and responsibilities (see Section 3 & 4 also) e.g. Contract Manager, Finance Lead, SRO |  |  |
| Use of financial systems or tools e.g. finance dashboards, payment trackers |  |  |
| Audit and Compliance |  |  |
| How financial records are maintained and audited |  |  |
| Compliance with internal audit requirements and external reporting obligations |  |  |
| Risk and Exception Management |  |  |
| How financial risks are identified and managed e.g. affordability pressures, payment disputes |  |  |
| Escalation routes for financial issues |  |  |
| Integration with Other Sections |  |  |
| Link to performance management (Section 8) for deductions |  |  |
| Link to change control (Section 13) for financial implications of variations |  |  |

🔍 Where to Find the Information

📜 Contractual References

Payment Mechanism Schedule – defines how the Unitary Charge is calculated, including deductions and adjustments

Invoicing and Payment Clauses – set out the process for submitting, validating, and approving payments

Audit and Records Clauses – define the contracting authority’s rights to review financial information

Change Protocol – may include provisions for financial adjustments linked to variations

Benchmarking and Market Testing Schedule – may result in price changes affecting the Unitary Charge

Insurance Schedule – may include cost-sharing arrangements or financial recoveries

🏛️ Internal Resources

Locally maintained payment trackers, deduction logs, or financial dashboards (where used) to support financial oversight

Internal finance policies and procedures for approvals, controls and audit requirements

Refinancing

🎯 Purpose of this Section

To describe how the contracting authority manages refinancing events under the PFI contract. This includes understanding its contractual rights, gain share mechanisms, and the governance processes for reviewing and approving refinancing proposals.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Contractual Rights and Obligations |  |  |
| Summary of the contracting authority’s rights under the refinancing provisions e.g. consent, notification, gain share |  |  |
| Reference to the relevant clauses in the Project Agreement |  |  |
| Governance and Decision-Making |  |  |
| Internal process for reviewing refinancing proposals |  |  |
| Roles and responsibilities e.g. Contract Manager, Finance Lead, Legal Advisor, SRO |  |  |
| Need for external advisors to support assessment e.g. financial or legal |  |  |
| Gain Share Mechanism |  |  |
| How financial benefits from refinancing are calculated and shared |  |  |
| How the contracting authority ensures transparency and compliance with the mechanism |  |  |
| Triggers and Monitoring |  |  |
| How refinancing events are identified or triggered e.g. voluntary refinancing, changes in funding structure |  |  |
| How the contracting authority monitors for potential refinancing activity |  |  |
| Integration with Other Sections |  |  |
| Link to financial management (Section 10) and governance (Section 4) |  |  |

🔍 Where to Find the Information

📜 Contractual References

Refinancing Clause – defines the contracting authority’s rights, including consent, notification, and gain share mechanisms

Financial Model Schedule – may be referenced for baseline assumptions and financial structure

Audit and Records Clauses – may support access to refinancing-related information

Change Protocol – may apply if refinancing results in contractual amendments

🏛️ Internal Resources

Locally maintained records of past refinancing events, gain share calculations, or legal/financial advice (where used) to support future assessments

Change Management and Variations

🎯 Purpose of this Section

To describe how changes to the PFI contract are initiated, assessed, approved, and implemented. This includes the contractual change protocol, internal governance arrangements, and how changes are documented and communicated.

📄 What to Include

| Item to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Contractual Change Protocol |  |  |
| Summary of the change mechanism set out in the Project Agreement |  |  |
| Steps for initiating, assessing, and agreeing changes |  |  |
| Roles of the contracting authority, PFI Co and services provider, and any other parties |  |  |
| Internal Governance and Approvals |  |  |
| How the contracting authority assesses proposed changes e.g. legal, financial, operational impact |  |  |
| Approval routes and delegated authority levels |  |  |
| Use of internal change request forms or templates |  |  |
| Documentation and Audit Trail |  |  |
| How changes are recorded, tracked, and version controlled |  |  |
| Where variation agreements and supporting documents are stored |  |  |
| How and when the contract documentation is updated |  |  |
| How changes are communicated to stakeholders |  |  |
| Types of Changes |  |  |
| Examples of common changes e.g. service adjustments, asset modifications, policy-driven changes |  |  |
| Distinction between material and minor changes, if applicable |  |  |
| Integration with Other Sections |  |  |
| Link to financial management (Section 11) for cost implications |  |  |
| Link to performance management (Section 8) if changes affect KPIs or SLAs |  |  |
| Link to expiry planning (Section 23) for changes with long-term impact |  |  |

🔍 Where to Find the Information

📜 Contractual References

Variation Clause – defines the contracting authority’s right to request changes and the scope of permissible variations

Change Protocol – sets out the formal process for initiating, assessing, approving, and implementing changes

Audit and Records Clauses – support tracking and validation of changes

🏛️ Internal Resources

Locally maintained variations register, change request forms, or approval records (where used) to support auditability and governance

Benchmarking, Market Testing, and Value for Money

🎯 Purpose of this Section

To describe how the contracting authority uses benchmarking, market testing, and other value testing mechanisms to assess and improve the cost efficiency and quality of services delivered under the PFI contract. This includes how these processes are governed, implemented, and used to inform decision-making.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Contractual Requirements |  |  |
| Summary of the benchmarking / market testing provisions in the Project Agreement |  |  |
| Frequency and scope of required value testing e.g. soft FM services every 5–7 years |  |  |
| Governance and Oversight |  |  |
| Internal processes for planning, approving, and overseeing value testing exercises |  |  |
| Roles and responsibilities e.g. Contract Manager, Commercial Lead, Legal, Finance |  |  |
| Use of external advisors to support analysis and negotiation |  |  |
| Implementation and Outcomes |  |  |
| How benchmarking or market testing is conducted (e.g. data collection, comparator selection, tendering) |  |  |
| How results are assessed and agreed with the PFI Co |  |  |
| How outcomes are implemented (e.g. price adjustments, service changes) |  |  |
| Other VfM Mechanisms |  |  |
| Use of Best Value Reviews, service redesign, or continuous improvement initiatives |  |  |
| How user feedback and performance data inform VfM assessments |  |  |
| Integration with Other Sections |  |  |
| Link to performance management (Section 8), change control (Section 13), and financial management (Section 11) |  |  |

🔍 Where to Find the Information

📜 Contractual Reference

Benchmarking and Market Testing Schedule – sets out the frequency, scope, and process for value testing (typically for soft FM services)

Value for Money or Best Value Clauses – may define additional mechanisms such as Best Value Reviews or continuous improvement obligations

Audit and Records Clauses – may support access to comparator data or financial information

🏛️ Internal Resources

Locally maintained benchmarking reports, market testing records, or value for money assessments (where used) to support planning and implementation

Legal and Regulatory Compliance

🎯 Purpose of this Section

To ensure that the contracting authority has robust processes in place to monitor and enforce the PFI Co’s compliance with all applicable legal and regulatory obligations. This includes statutory requirements (e.g. health and safety, planning, environmental law), sector-specific regulations, and any obligations arising from changes in law. It also supports the contracting authority’s own compliance responsibilities and helps mitigate legal and reputational risks.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Summary of key legal and regulatory obligations under the contract e.g. statutory compliance, planning permissions, environmental law |  |  |
| How the PFI Co demonstrates compliance (e.g. certifications, audit reports, statutory testing) |  |  |
| The contracting authority’s internal processes for monitoring and verifying compliance |  |  |
| Escalation routes and governance oversight for non-compliance |  |  |
| Integration with performance management, audit, assurance, and risk management processes |  |  |
| Reference to relevant clauses in the Project Agreement and supporting documentation |  |  |

🔍 Where to Find the Information

📜 Contractual References

Statutory Requirements Clause – sets out the PFI Co’s obligations to comply with applicable laws and regulations

Audit and Inspection Clauses – define the contracting authority’s rights to verify compliance

Health and Safety, Environmental, and Planning Clauses – may be included in the Output Specification or Contractor’s Proposals

Change in Law Clauses – define how legal or regulatory changes are managed and whether they trigger compensation or variation

🏛️ Internal Resources

Locally maintained compliance reports, certificates, or legal advice (where used) to support monitoring and assurance

Contractual Protections

🎯 Purpose of this Section

To summarise the key contractual protections available to the contracting authority, such as warranties, indemnities, guarantees, and step-in rights, and explain how these are monitored, enforced, and used to manage risk. This section helps ensure that the contracting authority is aware of its rights and has processes in place to act on them when needed.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Overview of key protections e.g. warranties on construction, indemnities for third-party claims, guarantees from parent companies |  |  |
| How these protections are tracked e.g. registers, contract summaries |  |  |
| How and when these protections may be invoked |  |  |
| Roles and responsibilities for monitoring and enforcement |  |  |
| Processes for managing claims and disputes related to these protections |  |  |
| Reference to relevant contract clauses and supporting legal advice |  |  |

🔍 Where to Find the Information

📜 Contractual References

Warranties Clause – outlines the warranties provided by the PFI Co, service provider, construction contractor or third parties

Indemnities Clause – defines the scope of indemnification for losses, liabilities, or claims

Guarantees Clause – may include parent company guarantees or performance bonds

Claims and Dispute Clauses – may set out procedures for enforcing contractual protections

Audit and Records Clauses – support evidence gathering for enforcement or claims

🏛️ Internal Resources

Locally maintained claims logs, legal advice, or warranty registers (where used) to support monitoring and enforcement

Insurance Management

🎯 Purpose of this Section

To describe how the contracting authority oversees the PFI Co’s insurance obligations, ensuring that appropriate coverage is maintained throughout the contract term. This includes monitoring renewals, verifying compliance, and managing claims and cost-sharing arrangements.

📄 What to Include

| Item to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Summary of insurance obligations under the contract |  |  |
| How insurance coverage is monitored and verified |  |  |
| How renewals and compliance are tracked |  |  |
| Roles and responsibilities for insurance oversight |  |  |
| Processes for managing claims and cost-sharing arrangements |  |  |
| Reference to relevant contract clauses and supporting legal advice |  |  |

🔍 Where to Find the Information

📜 Contractual References

Insurance Schedule – sets out the PFI Co’s insurance obligations, including required cover types, limits, and renewal processes

Insurance Clauses – may define evidence requirements, cost-sharing arrangements, and rights to review or approve policies

Claims and Notification Clauses – outline procedures for reporting and managing insurance claims

Audit and Records Clauses – support verification of insurance compliance

🏛️ Internal Resources

Locally maintained insurance certificates, claims records, or cost-sharing calculations (where used) to support oversight and assurance

Land, Lease and Property Arrangements

🎯 Purpose of this Section

To summarises the land, lease, and property arrangements that underpin the PFI contract, including the ownership structure, lease or licence terms, access rights, and any third-party interfaces. This supports understanding the legal and operational responsibilities of the contracting authority, the PFI Co, and any third parties. Clear documentation of these arrangements supports effective management of access, maintenance, compliance, and expiry planning.

📄 What to Include

| Item to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Summary of land, lease, and property arrangements |  |  |
| Ownership structure and lease/licence terms |  |  |
| Access rights and third-party interfaces |  |  |
| Roles and responsibilities for property management |  |  |
| Processes for managing compliance and maintenance |  |  |
| Reference to relevant contract clauses and legal documents |  |  |

🔍 Where to Find the Information

📜 Contractual References

Site and Land Clauses – define the contracting authority’s property interests, including ownership, lease/licence arrangements, and access rights

The Site Schedule – may include boundaries, legal interfaces, and site-specific responsibilities

Planning and Environmental Clauses – may relate to land use, statutory consents, or third-party obligations

See also Section 19 for third-party Interface Agreements where relevant to land or access

🏛️ Internal Resources

Locally maintained land registry records, lease documents, or site plans (where used) to support property oversight

Contractual Interfaces and Dependencies

🎯 Purpose of this Section

To identify and manage key contractual interfaces and dependencies with third parties that affect the delivery of services under the PFI contract. This includes linked agreements (e.g. utilities, local authorities, funders) and coordination protocols to ensure continuity and mitigate risks.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| List of key third-party agreements and dependencies e.g. utility providers, shared services |  |  |
| Roles and responsibilities for managing these interfaces |  |  |
| Coordination and communication protocols |  |  |
| Risk mitigation strategies for interface failures or disputes |  |  |
| Escalation routes and governance oversight |  |  |
| Reference to interface clauses in the Project Agreement and linked contracts |  |  |

🔍 Where to Find the Information

📜 Contractual References

Interface Agreements – define relationships with third parties such as utility providers, local authorities, or funders

The Site Schedule – may include shared access or boundary responsibilities

Linked Agreements – may be referenced in the Project Agreement or its schedules

Dispute Resolution Clauses – may apply where interface issues arise

🏛️ Internal Resources

Locally maintained interface maps, third-party agreements, or contact records (where used) to support coordination and risk management

Workforce and Employment Matters

🎯 Purpose of this Section

To describe how the contracting authority monitors the PFI Co’s workforce arrangements, including staffing continuity, compliance with employment obligations, and planning for contract expiry. This includes oversight of TUPE processes, workforce-related risks, and assurance that appropriate checks and vetting procedures are in place to protect service users and ensure legal compliance.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| PFI Co’s staffing obligations under the contract, including minimum staffing levels or key personnel requirements |  |  |
| Authority’s rights to approve or veto PFI Co and service provider staff, require investigations (e.g. conduct), remove from site. Requirements for clearance and other checks including maintenance of records etc. |  |  |
| How workforce continuity and performance are monitored (e.g. turnover rates, absence, training) |  |  |
| TUPE planning and coordination for contract expiry or service transfer |  |  |
| Workforce-related risks that may impact service delivery or continuity |  |  |
| Requirements for staff checks, including right to work, DBS checks, security clearance, health & safety training |  |  |
| How the contracting authority assures itself that these checks are being carried out e.g. audit rights, spot checks, reporting |  |  |
| Reference to employment clauses in the Project Agreement and relevant HR or safeguarding policies |  |  |

🔍 Where to Find the Information

📜 Contractual References

Employment and Staffing Clauses – define the PFI Co’s obligations regarding workforce continuity, key personnel, and staffing levels

TUPE Clauses – set out requirements for staff transfer at contract expiry or service change

Health and Safety Clauses – may include training and vetting requirements

Expiry and Handover Clauses – may reference workforce transition planning

🏛️ Internal Resources

Locally maintained workforce transition plans, TUPE logs, or staff compliance records (where used) to support assurance and expiry readiness

Intellectual Property and Information Management

🎯 Purpose of this Section

To ensure that intellectual property (IP), digital systems, and data are managed in accordance with contractual and legal requirements. This includes ownership, licensing, access rights, and compliance with data protection and freedom of information (FOI) obligations.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Ownership and licensing arrangements for IP and digital systems |  |  |
| Access and usage rights for the contracting authority and third parties |  |  |
| Data storage, security, and retention protocols |  |  |
| Compliance with GDPR, FOI, and confidentiality clauses |  |  |
| Roles and responsibilities for managing IP and information |  |  |
| Reference to relevant contract clauses and internal policies |  |  |

🔍 Where to Find the Information

📜 Contractual References

Intellectual Property Clauses – define ownership, licensing, and usage rights for IP and digital systems

Confidentiality Clauses – set out obligations for handling sensitive information

Data Protection Clauses – define responsibilities under applicable data protection laws

Freedom of Information (FOI) Clauses – outline procedures for supporting/ responding to FOI requests

🏛️ Internal Resources

Locally maintained IP registers, data access logs, or FOI response records (where used) to support compliance and continuity

Disputes Resolution

🎯 Purpose of this Section

To outline how disputes are managed under the PFI contract, including the formal resolution process and supporting governance arrangements. This ensures disputes are handled consistently and in line with contractual obligations.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Contractual dispute resolution process (e.g. mediation, adjudication). |  |  |
| Internal governance and legal support for disputes. |  |  |
| Documentation and record retention. |  |  |
| Expiry-related disputes that may be anticipated and approaches for mitigating through contract management or early expiry activity. |  |  |

🔍 Where to Find the Information

📜 Contractual References

Dispute Resolution Clause – sets out the formal process for resolving disputes, including escalation, mediation, adjudication, and arbitration

Governance Clauses – may define informal resolution routes or escalation protocols

🏛️ Internal Resources

Locally maintained dispute logs, legal correspondence, or resolution records (where used) to support risk management and continuity

Exit, Termination and Expiry Planning

🎯 Purpose of this Section

To describe how the contracting authority plans for contract expiry or early termination, including asset handback, knowledge transfer, and service continuity.

📄 What to Include

| Items to Include | Included? | Notes / File Reference |
| --- | --- | --- |
| Overview of the different exit scenarios: natural expiry, early termination e.g. default, voluntary termination, force majeure |  |  |
| PFI Co’s obligations for developing and implementing exit and handback plans |  |  |
| The contracting authority’s approach to planning and governance for each scenario |  |  |
| Knowledge transfer protocols, including documentation, systems access, and staff briefings |  |  |
| Asset handback requirements, including condition surveys and lifecycle delivery |  |  |
| TUPE and workforce transition planning |  |  |
| Service continuity arrangements during transition or handover |  |  |
| Legal and commercial considerations, including dispute resolution and claims management |  |  |
| Reference to relevant clauses in the Project Agreement and supporting guidance |  |  |

🔍 Where to Find the Information

📜 Contractual References

Expiry and Handover Clauses – define the PFI Co’s obligations for asset handback, knowledge transfer, and service continuity

Termination Clauses – set out early termination scenarios and associated rights and responsibilities

Authority Step-In Clauses – define the contracting authority’s rights in the event of service failure or early exit

TUPE and Workforce Clauses – may include staff transition requirements

Audit and Records Clauses – support documentation and knowledge transfer

🏛️ Internal Resources

Locally maintained exit/expiry plans, asset condition surveys, or contingency plans