PFI Contract 
Management Guidance

Contract Management Plan

Toolkit 2: Obligations Matrix – A template to record the obligations in your contract

PFI Centre of Excellence

Published 2026

Contract Management Plan

Toolkit 2: Obligations Matrix

The obligations matrix is a practical tool that helps contract managers identify, track and manage the key contractual obligations and rights set out in the PFI contract. It provides a structured summary of what each party is required to do, when and under what conditions. This matrix supports the development and ongoing use of the contract management plan (CMP) by ensuring that obligations are understood and actively managed throughout the contract term. It helps contract managers:

Populate key sections of the CMP (e.g. governance, performance, risk, expiry).

Monitor compliance and identify missed or upcoming obligations.

Support continuity and onboarding by providing a clear reference point for responsibilities.

Inform governance meetings, performance reviews and expiry planning.

Obligations may be:

Time-based (e.g. monthly reporting, annual insurance renewals, expiry milestones), or

Event-based (e.g. triggered by a variation, refinancing, dispute or change in law).

The ‘Trigger/Frequency’ column in the matrix should clearly indicate the nature of each obligation. This distinction supports appropriate scheduling and monitoring.

Where possible, authorities are encouraged to maintain an electronic project diary or shared calendar that draws from the obligations matrix. This could be implemented using your IT systems calendar or a contract management system. It should include:

Recurring obligations (e.g. monthly reports, annual reviews)

One-off milestones (e.g. expiry planning start date)

Event-based triggers (e.g. refinancing, disputes)

To support this, the obligations matrix can be linked to Toolkit 3: Contract Calendar Template, which provides a structured format for building a contract-specific calendar or diary of obligations.

⚙️ How to build it

To develop the obligations matrix you will draw on the Contract Management Plan (Toolkit 1) and the output of the contract review (see contract review guidance. The obligations matrix provides a comprehensive record of contractual obligations, while the calendar distils this into a focused, action-oriented tool for day-to-day contract management.

The matrix should be treated as a live document and updated as the contract evolves, for example, following variations, benchmarking reviews or expiry planning milestones.

A suggested format is provided in the accompanying template and can be adapted to suit your project’s needs.

| Clause ref | Obligation summary | Responsible party | Trigger/ frequency | Due date/ milestone | Dependencies/ linked clauses | Implications if missed | Follow-up action/notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| e.g. Sch 5, 2.1 | Submit monthly performance report | PFI Co | Monthly | 5th of each month | Payment mechanism | Risk of overpayment or dispute | Add to CMP Section 8 |
| e.g. Cl 18.5 | Provide asset handback plan | PFI Co | Two years before expiry | 01/04/2028 | Lifecycle plan, exit plan | Risk of non-compliance at expiry | Review with expiry team |
| Cl 10.2 | Maintain insurance cover | PFI Co | Annual (time-based) | 01/01 each year | Insurance schedule | Financial exposure | Confirm renewal |
| Cl 15.4 | Notify contracting authority of refinancing | PFI Co | On refinancing event (event-based) | N/A | Gain share clause | Missed financial recovery | Add to risk log |
| Cl 17.2 | Payment of the unitary charge | Contracting authority | Submission of invoice | 20 days from invoice submission | Submission of invoice and supporting information and reports | Interest payments Impact on relationship | Add routine payments to UC. Ensure payment processes reflect timelines |