PFI Contract 
Management Guidance

Contract Management Plan

Toolkit 3: Contract Calendar Template – A document for planning and tracking time-based obligations

PFI Centre of Excellence

Published 2026

Contract Management Plan

Toolkit 3: Contract Calendar Template

The contract calendar is a practical tool that helps contract managers plan and track time-based obligations under the PFI contract. It converts selected entries from the Obligations Matrix (Toolkit 2) into a structured, date-based format that supports:

Forward planning of key activities and reviews.

Governance scheduling (e.g. meetings, reporting cycles).

Continuity and handover (e.g. onboarding new staff).

Expiry preparation (e.g. lifecycle reviews, handback milestones).

It is particularly useful for ensuring that recurring and one-off obligations are not missed and that the contract is managed proactively.

⚙️ How to build it

The contract calendar should be populated using the time-based obligations identified in the Obligations Matrix (Toolkit 2). These may include:

Monthly or quarterly reporting.

Annual insurance renewals.

Benchmarking or market testing cycles.

Lifecycle plan reviews.

Expiry planning milestones.

Statutory compliance checks.

Contractual review points (e.g. variations, refinancing).

Where possible, the contract calendar should be maintained in a shared digital format (or in a contract management system) to enable alerts, reminders and team-wide visibility.

A suggested format is provided in the accompanying template and can be adapted to suit your project’s needs. The text is illustrative and should be deleted before use.

| Task | Frequency | Responsible | CMP section | Notes | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Liaison meeting (working day 15) | Monthly | Contracting authority | Governance | Standard agenda and action log | X | X | X | X | X | X | X | X | X | X | X | X |
| Quarterly performance review | Quarterly | Contracting authority | Governance | Escalations & improvement plan check |  |  | X |  |  | X |  |  | X |  |  | X |
| Performance reporting and unitary payment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PFI Co submits monthly report (working day 5) | Monthly | PFI Co | Performance management | Align with payment mechanism; validate MI | X | X | X | X | X | X | X | X | X | X | X | X |
| Monthly performance review meeting (working day 10) | Monthly | PFI Co | Performance management | CA to raise and discuss queries with PFI Co and service provider | X | X | X | X | X | X | X | X | X | X | X | X |
| Accept or dispute monthly report (working day 15) | Monthly | Contracting authority | Performance management | Only dispute areas of disagreement. Refer to CMP for how to do this | X | X | X | X | X | X | X | X | X | X | X | X |
| Approve and pay unitary payment (Invoice + 10 working days) | Monthly | Contracting authority | Financial management | Check deductions, indexations and other calculations | X | X | X | X | X | X | X | X | X | X | X | X |
| Asset management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual maintenance plan submission | Annual | PFI Co | Asset and environmental management | To be issued by 31 Jan each year (Schedule 25) | X |  |  |  |  |  |  |  |  |  |  |  |
| Annual maintenance plans approvals | Annual | Contracting authority | Asset and environmental management | To be approved or rejected within 15 working days |  | X |  |  |  |  |  |  |  |  |  |  |
| Draft lifecycle plan (1 & 5yr) submission | Annual | PFI Co | Asset and environmental management | To be issued by 31 Jan each year (Schedule 25) | X |  |  |  |  |  |  |  |  |  |  |  |
| Lifecycle plan approval | Annual | Contracting authority | Asset and environmental management | To be approved or rejected within 15 working days |  | X |  |  |  |  |  |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Insurance renewal | Annual | Contracting authority | Insurance | Public liability, business interruptions and buildings insurance |  |  |  | X |  |  |  |  |  |  |  |  |
| Benchmarking | 5-yearly | PFI Co | BM/MT & VFM | Due date – needs commencing 18 months in advance |  |  |  |  |  |  | X |  |  |  |  |  |
| Market testing | 5-yearly | PFI Co | BM/MT & VFM | Due date – needs commencing 18 months in advance |  |  |  |  |  |  |  |  | X |  |  |  |