Cluster Sequencing for Carbon Capture Usage and Storage Deployment: 
NPT Pathfinder Selection Process

Non-Pipeline Transport Pathfinder – Power BECCS NPT Project Plan for Projects applying under the Transition Access Agreement

© Crown copyright 2026

This publication is licensed under the terms of the Open Government Licence v3.0 except where otherwise stated. To view this licence, visit nationalarchives.gov.uk/doc/open-government-licence/version/3 or write to the Information Policy Team, The National Archives, Kew, London TW9 4DU, or email: psi@nationalarchives.gsi.gov.uk.

Where we have identified any third-party copyright information you will need to obtain permission from the copyright holders concerned.

Any enquiries regarding this publication should be sent to us at: NPTPathfinder@energysecurity.gov.uk

# Contents

Contents	3

NPT Pathfinder Project Plan Introduction	4

1	Applicant information	16

2	Eligibility	16

3	Project Overview	19

4	Deliverability	29

# NPT Pathfinder Project Plan Introduction

The Department for Energy Security and Net Zero (DESNZ) is seeking to fully utilise the capacity of Track-1 Clusters through Build Out processes. HMG is running two complementary processes to select Projects that could connect to the planned ECC T&S infrastructure and utilise remaining network capacity: (1) the ECC Teesside Selection Process (for Projects with direct pipeline access to T&S infrastructure) which launched on the 5th of February 2026; and (2) the Non-Pipeline Transport (NPT) Pathfinder Selection Process.

This document is an Annex to the NPT Pathfinder Selection Process Application Guidance. The publication of this form accompanies the opening of an application window for Projects and should be read alongside the NPT Pathfinder Selection Process Application Guidance to understand what Projects are required to submit and why; the timelines for submitting clarification questions; timelines for submitting the final application forms; and further detail on the assessment process. Note that the caveats and reservations set out in Chapter 2 of the NPT Pathfinder Selection Process Application Guidance apply equally here.

This document sets out the questions that Projects in the Power BECCS sector which are applying for a TAA should answer as part of their NPT Pathfinder Submission. Questions relate to the Project as a whole, including the Capture Facility(ies) and the NPT solution (made up of all fixed infrastructure and transport assets required to transport CO2 from the Capture Facility(ies) to the T&S delivery point).

The information and relevant supporting evidence provided by the Project within the completed Project Plan will, alongside the Cost Assessment Form (Annex B), Financial Statement Form (Annex C), and the Economic Benefits Forms (Annexes D1 & D2), form the basis of the assessment to determine which Projects meet the requirements to be shortlisted.

The NPT Pathfinder Selection Process will be run by DESNZ. If Applicants have any general questions about the Submission process or about completing any part of the Submission documentation, please email queries to NPTPathfinder@energysecurity.gov.uk. Please refer to Section 2.3.2 of the ECC Teesside Selection Process Application Guidance for information on the clarification question process.

## Important information regarding this process

The deadline for finalised NPT Pathfinder Selection Process Submissions is 23:59 on 12 June 2026.

The assessment process will be run fairly, transparently, and objectively in accordance with the published NPT Pathfinder Selection Process Application Guidance.

- The Project shall ensure that it provides a clear response to every applicable question asked in this Project Plan. This should detail both the current status and/or plans with respect to Project delivery.

- The information provided within this form will be used throughout the NPT Pathfinder Selection Process and the negotiations/due diligence phase. Entering a negotiation does not mean that a contract will be awarded. Any decision to award support would only be made subject to the successful completion of any negotiation and due diligence.

- Further timetable details for this process are set out in the NPT Pathfinder Selection Process Application Guidance.

- DESNZ will not be responsible for any costs incurred in the preparation of any Submission, irrespective of whether the Project is successful in the NPT Pathfinder Selection Process.

- Projects will need to satisfy the eligibility criteria to be considered in the Deliverability Assessment.

- Cost and Economic Benefits information will also be collected. As part of the deliverability assessment, cost information provided will be evaluated for credibility and checked for consistency against the commercial and financial information provided. It will then be used to inform the value for money assessment. Economic Benefits data will neither be considered when assessing Projects against the eligibility criteria nor as part of the deliverability assessment. However, capturing the economic benefits of Net Zero is an important priority for HMG and to do this we hope to develop robust, resilient, UK supply chains. If Applicants proceed to negotiations, and/or are offered access to the T&S Network, HMG may ask the Applicant to submit or publish more detailed plans on supply chains, skills and economic benefits, as is explained in section 2.4.4 of the Application Guidance document.

- This combined Power BECCS NPT Pathfinder Project Plan, for Projects applying under the TAA, is divided into four sections:

  - Section 1, Applicant Information.

  - Section 2, Eligibility, information submitted in this section will be used to determine the eligibility of the Project.

  - Section 3, Project Overview, information submitted in this section will be used to improve DESNZ’s understanding of the Project. This information may be used to inform the Triage and Deliverability assessment.

  - Section 4, Deliverability, information submitted in this section will be used for the Triage and to assess the Project against the Deliverability criteria set out in the NPT Pathfinder Selection Process Guidance and subsequent shortlisting process. Compliance with the eligibility criteria must be maintained.

- Information submitted in response to any part of this application may be used to assess the Project against the outlined Eligibility and Deliverability criteria. The Deliverability Triage will consider information from Sections 3 and 4. Eligibility and Deliverability will be assessed continuously until FID. Responses in any section may also be used to inform value for money and affordability assessments, and also to evaluate the Project’s alignment with the CCUS programme and DESNZ’s wider strategic goals when shortlisting.

- Alongside the NPT Project Plan the assessment of the Project will be supported by the Submission of several forms:

  - Annex B –Cost Assessment Form will be used to collect the cost data for the Project.

  - Annex C - Financial Statement Form will be used to assess the financial and commercial health of participating companies within the Deliverability criterion. This form should be considered supplementary to the questions to assess the Project’s deliverability. The figures included in the form should be supported by relevant accounting notes and documentation.

  - Annex D1 & D2 – Economic Benefits Forms seek to understand how key components and services required to deliver the Project will be sourced; how risks that may affect the supply of these key components may be mitigated; and how Projects are engaging with new entrants and small and medium-sized enterprises (SMEs).

- Across the assessment DESNZ will place significant emphasis on the credibility and consistency of information provided.

- Information provided in the Eligibility and Project Overview section will be used to, as well as subsequent engagement, inform the Deliverability Assessment. The word count in each section must be adhered to. This is to allow for consistency and credibility checks and not so answers can be continued in other sections. Applicants should not use other sections to continue their answers and any obvious continuation will be removed.

- After Project Submissions have been individually assessed for eligibility and deliverability, DESNZ will carry out a shortlisting process with those Projects that have met the required standard to pass. The shortlisting process will ensure that the overall outcome of the process meets the strategic objectives of the NPT Pathfinder Selection Process and the goals of the Department as a whole. The process used for this step is described in Chapter 10 of the NPT Pathfinder Selection Process Application Guidance.

- DESNZ reserves the right not to accept any Submission and reserves the right to cancel the process before it has completed or at any time before any support has been awarded.

- DESNZ reserves the right not to consider a Submission further if an Applicant fails to disclose information requested.

- Each individual piece of supporting evidence can be referenced multiple times in the NPT Pathfinder Project Plan but should be uploaded only once to the portal.

- Please note that the word limit does not cover the references sections. This is so Applicants can be specific as to where information can be found in any documents provided. If this section is used to continue answers, the words will be removed before the assessment.

Any information provided above the word limits will be removed before information is provided to assessors and will not count towards the score. Graphics and diagrams are welcomed and do not count toward the word count.  We will remove words in excess of the count from the end of the relevant question or section. This will be completed before the documentation is provided to assessors.

## Disclosure of information

Reasons for decisions on Submissions will be recorded at all stages for good administration and to ensure that there is a clear audit trail for all decisions. Administrative records will be maintained for all Submissions irrespective of whether they are successful or not.

Please refer to Section 2.2 (Application Process) of the NPT Pathfinder Selection Process Guidance Document for additional detail on entry into non-disclosure agreements and Chapter 3 (Further Considerations) for additional detail on parties involved in the NPT Pathfinder Selection Process.

All information provided by Applicants may be disclosed in accordance with DESNZ’s legal obligations (including under the Freedom of Information Act 2000 (FOIA), the Data Protection Act 2018, General Data Protection Regulation (GDPR) and the Environmental Information Regulations 2004 (EIR) in the event that a request for information is received). More information on the FOIA, Data Protection Act 2018, GDPR and EIR (including information on exemptions) can be found at: https://ico.org.uk/for-organisations/

To help DESNZ deal with information requests and without prejudice to the paragraph above, in the box below, please set out the reasons why you consider any specific information should not be disclosed, including (if possible) by reference to the specific exemption contained in the relevant legislation (for example, because disclosure of the information would prejudice your commercial interests under section 43 of the FOIA), explaining why this is the case.

Where appropriate, please also state whether you consider the reason(s) information should not be disclosed by DESNZ only apply for a particular time period. If we receive an information request, we will consider your views as stated on the Submission form. However, DESNZ will ultimately decide how to respond to an information request and whether any information should be withheld, subject to the Information Commissioner's Office decision in the event of the requestor appealing the decision.

Please detail what specific information, if any, within this Submission should not be disclosed and the reasons why. Please include (if possible) reference to the specific exemption contained in the relevant legislation. Boxes will expand to content.

## Glossary of terms

Table 1 – Acronyms

| Acronym | Definition |
| --- | --- |
| ACT | Advanced Conversion Technologies |
| APRi | Availability Payment Rates |
| ATT | Advanced Thermal Treatment |
| BECCS | Bioenergy with Carbon Capture & Storage |
| CAF | Cost Assessment Form |
| CapEx | Capital Expenditure |
| CHP | Combined Heat and Power |
| CO2 | Carbon Dioxide |
| COD | Commercial Operation Date |
| CRI | Commercial Readiness Index |
| DevEx | Development Expenditure |
| DESNZ | Department for Energy Security and Net Zero |
| DPA | Dispatchable Power Agreement |
| EA | Environment Agency |
| EIR | The Environmental Information Regulations 2004 |
| EOI | Expression Of Interest |
| ERR | Economic Regulatory Regime |
| FEED | Front-End Engineering Design |
| FID | Final Investment Decision |
| FOIA 2000 | The Freedom of Information Act 2000 |
| GDPR | General Data Protection Regulation |
| HMG | His Majesty’s Government |
| ICC | Industrial Carbon Capture |
| ICVCM | Integrity Council for Voluntary Carbon Markets |
| IDHRS | Industrial Decarbonisation and Hydrogen Revenue Support |
| ktpa | Kilo-tonnes per annum |
| LCA | Life Cycle Analysis |
| MoU | Memorandum of Understanding |
| MRV | Monitoring, Reporting and Verification |
| MtCO2 | Megatonnes of CO₂ |
| Mtpa | Megatonnes per annum |
| MWe | Megawatt electric |
| NDA | Non-Disclosure Agreement |
| NISTA | National Infrastructure and Service Transformation Authority |
| OCP | Operational Conditions Precedent |
| OpEx | Operating Expenditure |
| pBECCS | Power Bioenergy with Carbon Capture and Storage |
| RED | Renewable Energy Directive |
| RO | Renewables Obligation |
| SIMOPs | Simultaneous Operations |
| SMEs | Small and Medium-Sized Enterprises |
| TAA | Transition Access Agreement |
| T&S | Transport and Storage Network |
| T&S Co | Transport and Storage Company is a licensed company operating and maintaining a T&S Network (T&S Operator) |
| tpa | Tonnes per annum |
| tph | Tonnes per hour |
| TRL | Technology Readiness Level (see definitions section for further information) |
| UKGI | United Kingdom Government Investments |

## Definitions

Table 2 – Definitions

| Term | Definition |
| --- | --- |
| Applicant | Legal entity that intends to apply for support and will be taken through to negotiations if successful (see also Project Representative). |
| Battery Limit | The geographic boundaries identifying scope of works for process units or the Project. |
| Capture Facility | For the purpose of this application guidance, a Capture Facility is the industrial plant, process unit, or other emissions source within a Project boundary where carbon dioxide (CO₂) emissions originate and are captured prior to transport. It includes both (a) the upstream plant or process equipment responsible for generating the CO₂ bearing gas stream, and (b) the CO₂ capture equipment and all associated systems required to separate, condition, and deliver a CO₂ stream suitable for onward transportation and eventual injection into the T&S Network. |
| CCS or CCUS | Carbon Capture and Storage or Carbon Capture, Usage and Storage |
| Cluster | T&S Network (incorporating the onshore and offshore network and offshore Storage facility) and associated Projects. |
| Commercial Operation Date (COD) | The date the Project is operational, defined as the Project being fully commissioned and able to export CO₂ to the T&S Network (including each individual Capture Facility where a Project aggregates CO2 from multiple capture facilities). See Section 4.1 of the NPT Pathfinder Selection Process Application Guidance for further details. |
| Cross Chain | All elements of the Cluster including development, delivery and operation of all Projects as well as Onshore, Offshore and Storage infrastructure. |
| Design CO2 Capture Rate | The maximum instantaneous design capture rate, i.e., the percentage of CO₂ emissions captured from the specific emissions streams that the capture technology is applied to, which is expected to be continuously achievable by the facility for extended periods, i.e., during normal steady state operation. |
| Direct Economic Benefits | Benefits relating directly to the developer’s own activity, and/or the activity of primary contractors. |
| Engineered Greenhouse Gas Removal (GGR) | Projects that ultimately achieve atmospheric CO₂ removal and require geological Storage (CCS) to do so (achieving ‘negative emissions’). For the purpose of the Application Guidance, this includes Projects such as Direct Air Carbon Capture and Storage (DACCS) and BECCS, and excludes engineered GGR Projects that do not require CCS access, such as enhanced weathering. |
| Final Investment Decision (FID) | FID is the point in the Project planning process when the decision to make major financial commitments is taken and contracts are signed for engineering, procurement, and construction. |
| Minimum CO2 supply rate | The CO2 below which the carbon capture plant cannot operate. |
| Mobile Transport Assets | The mobile equipment used to move the CO2 (e.g. ship, barge, rail or truck). |
| NPT Solution | A Project’s means for transporting CO2 from the Capture Facility(ies) to the T&S delivery point by any means other than a direct pipeline connection. This includes all Pre-Transportation Infrastructure and Post- Transportation Infrastructure and Mobile Transport Assets, such as CO2 liquefaction and regasification equipment, temporary storage and transportation via trucking, shipping and/or rail. |
| Operational Conditions Precedent | The Operational Conditions Precedent (OCPs) are a set of requirements a Project must demonstrate to the appropriate counterparty to prove that they have commissioned their facility and are ready for commercial operations. The OCP requirements are outlined in the relevant business model Terms and Conditions. |
| Post-Transport Infrastructure | Intermodal facilities situated after the final NPT mode. This may include but is not limited to, temporary storage and regasification services. |
| Pre-Transport Infrastructure | Intermodal facilities outside the Battery Limit of the Capture Facility. This may include but is not limited to liquefaction and temporary storage services, for the onward travel of CO2 via trucking, shipping and/or rail. |
| Project | Power CCUS, Industrial carbon Capture (ICC) including Waste ICC, Hydrogen, GGRs or Power Bioenergy with Carbon Capture and Storage (pBECCS) production facility – including carbon dioxide emission source(s) targeted for abatement – development and its associated CO₂ Capture Facilities, that will be assessed in the NPT Pathfinder Selection Process. This includes the Capture Facility(ies) as well as the NPT Solution. |
| Project Representative | Legal entity responsible for accessing the Submission Portal and submitting the Project Plan and associated Annexes to DESNZ. The Project Representative is expected to be from the primary, or partner, organisation responsible for Project development. Project Representative may be the same person as the Applicant. |
| Replacement Facility | A new build facility replacing an existing similar facility, making use of pre-existing external infrastructure. E.g., a new power station on the site of a decommissioned old station but using pre-existing gas and grid connections. |
| Retrofit Facility | Project where new carbon capture facilities are being added as an extension to a facility in operations at the time of construction. |
| Storage | Geological store for the captured CO₂ from the end of the injection well. |
| Submission | The total Submission submitted by the Project including the Project Plan and associated Annexes. |
| Technology Readiness Level | Technology Readiness Levels are an indication of the maturity stage of development of a technology on its way to being developed for an application or product. The section below defines TRLs 1 to 9. Research and development TRL 1 – Basic Research: Scientific research begins to be translated into applied research and development. TRL 2 – Applied Research: Basic physical principles are observed, practical applications of those characteristics can be 'invented' or identified. At this level, the application is still speculative: there is not experimental proof or detailed analysis to support the conjecture. Applied research and development TRL 3 – Critical Function or Proof of Concept Established: Active research and development are initiated. This includes analytical and laboratory studies to physically validate analytical predictions of separate elements of the technology. Examples include components that are not yet integrated or representative. TRL 4 – Laboratory Testing/Validation of Component(s)/Process(es): Basic technological components are integrated to establish that the pieces will work together. TRL 5 – Laboratory Testing of Integrated/Semi-Integrated System: The basic technological components are integrated with reasonably realistic supporting elements so it can be tested in a simulated environment. TRL 6 – Prototype System Verified: Representative model or prototype system is tested in a relevant environment. TRL 7 – Integrated Pilot System Demonstrated: Prototype near or at planned operational system, requiring demonstration of an actual system prototype in an operational environment. Pre-commercial deployment TRL 8 – System Incorporated in Commercial Design: Technology is proven to work - actual technology completed and qualified through test and demonstration. TRL 9 – System Proven and Ready for Full Commercial Deployment: Actual application of technology is in its final form - technology proven through successful operations. |
| Transport & Storage Network (T&S Network) | The network consisting (wholly or mainly) of: • pipelines used for the transportation of captured carbon dioxide from one capture plant to a storage facility or to or from any T&S Network; or • pipeline routes used for the transportation of captured carbon dioxide from one capture plant to a storage site or to or from any T&S Network; and • Storage site for the geological Storage of carbon dioxide. |
| Transition Access Agreement Users | This has the meaning given to it in Chapter 3 of the NPT Pathfinder Selection Process – Application Guidance. |

## Units

Where possible please use units of measurement defined by the International System of Units (SI) within your answers. For example:

- Electrical Power: MW.

- Thermal Power: MW.

- Electrical energy MWhe

- Electrical Power: MWe.

- Thermal energy:  MWhth

- Power:  MWth.

- Gas energy: MWh – Gross Calorific Value basis.

- Gas Power: MW – Gross Calorific Value basis.

- Gas calorific value: MJ/kg – Gross Calorific Value basis.

The below exceptions to SI units should be used due to industrial conventions.

- CO2 flow rate: mass basis – tonnes per annum, (tpa, ktpa or Mtpa) for annual average or total annual flow rate. Instantaneous or peak flow rates should be provided in tonnes per hour (tph).

- Stored inventory: mass basis - tonnes

- Energy: Watt Hours (MWh, GWh)

- Temperature: Degrees Celsius (oC)

- Gas Flow Rates: standard volume basis – Sm3/h (kSm3/h)

- Gas Flow Rates: mass basis - tonnes per annum, (tpa, ktpa or Mtpa) for annual average or total annual flow rate. Instantaneous or peak flow rates should be provided in tonnes per hour (tph).

# Applicant information

Completed versions of this document, Cost Assessment Form (Annex B), Financial Statement Form (Annex C), and Economic Benefits Form (Annex D1 & D2) are to be uploaded to the individual SharePoint site alongside any supporting evidence.

# Eligibility

Eligibility Criteria are fully described in the NPT Pathfinder Selection Process Application Guidance.

Eligibility will be checked against the evidence submitted within this section, Section 3, and Section 4. Applicants will be notified via email on whether or not they have met the eligibility criteria. Only eligible Projects will progress to the next stage, the Deliverability Assessment.

Please confirm and evidence how the Project meets the Eligibility Criteria and provide appropriate supporting evidence for the following requirements.

## General Eligibility Criteria

The entity which will be party to the connection agreement and/or the subsidy contract must be incorporated and registered in the UK. Please confirm that you understand and accept this requirement and provide details of the entity where you are able. We recognise that some Applicants may not yet have identified or incorporated this entity yet. (250 words)

Supporting evidence is expected to include a UK company registration number demonstrating that the Applicant is incorporated and registered in the UK.

For Projects planning to establish a new legal entity, Project may provide Memoranda of Understanding or Letters of Intent.

While a new legal entity need not have been created at the point of application, no Project will be eligible for inclusion on the Project Negotiation List without having confirmed creation of the appropriate compliant entity.

Evidence:

| Document reference | Document name | Relevant page/section |
| --- | --- | --- |

Capture Facilities must be entirely located in the UK. Capture Facilities which generate electricity must be entirely located in Great Britain. (250 words)

Supporting evidence could include a site layout or map and proof that the facility is located above mean low tide (with the exemption of jetties or loading facilities).

Evidence:

| Document reference | Document name | Relevant page/section |
| --- | --- | --- |

The Project must be able to be operational no later than the end of December 2032. (250 words)

Supporting evidence is expected to include a Project schedule at minimum.

We define operational as the NPT Project being fully commissioned and able to export CO₂ emissions to the T&S Network. Note that at the assessment stage we will consider the NPT Project’s schedule and the suggested completion date.

Evidence:

| Document reference | Document name | Relevant page/section |
| --- | --- | --- |

The Project must demonstrate an average annual CO2 capture of at least 30 ktpa CO2 to Storage. Where Projects aggregate CO₂ from multiple Capture Facilities, each individual Capture Facility must capture at least 5 ktpa. (250 words)

Supporting evidence could include a basis of design, heat and mass balance, performance guarantee, or engineering study. Evidence should demonstrate how the individual Capture Facilities CO2 capture flow rates are aggregated to meet the 30 ktpa CO2 to Storage.

Evidence:

| Document reference | Document name | Relevant page/section |
| --- | --- | --- |

Projects must be able to accede to the Network Code without the need for material modifications thereto. This includes the Project having a single, unique delivery point to the onshore ECC T&S Network and injecting gaseous, single-title CO₂ which meets the specification included in the Network Code. Please refer to Section 4.1.2 of the NPT Pathfinder Application Guidance for further details. (250 words)

Completing this section will be taken as confirmation that your Project intends to fulfil the requirements above.

Evidence of access to a T&S Network should include as a minimum:

- an MOU with the T&S Co;

- a high-level pipeline connection study including routing of intermediate pipelines or pipework to connect to the T&S Network.

The connection study need not be detailed for this eligibility criterion but must identify onshore, pipeline route options between the Post-Transport Infrastructure and delivery point to the T&S Network. Further detail, if available, would be beneficial for the Deliverability assessment question 4.7.

Evidence:

| Document reference | Document name | Relevant page/section |
| --- | --- | --- |

Applicants must demonstrate that their Submission includes the Capture Facility (or all capture facilities for aggregated Projects) which will export CO2 to the ECC T&S Infrastructure. (250 words)

Supporting evidence is expected to include company ownership information, letters of support or similar confirmation of capture facilities participation.

Evidence:

| Document reference | Document name | Relevant page/section |
| --- | --- | --- |

Projects will be expected to work with the department during the negotiations phase of the competition to set a target for the use of either short or sustainable supply chains to support the construction of your Project.

Short supply chains are defined as:

- Services: provided by a company carrying out business in the UK

- Goods: made, changed or improved in the UK, consistent with goods eligible for a UK country of origin certificate. Thresholds specifying the level of UK value-add required for non-originating materials to qualify as UK content.

Sustainable supply chains are defined as:

- A manufacturer or service provider that can evidence having set or committed to a Science Based Target through the Science-Based Targets initiative.

Further detail can be found in section 6.3.5 of the NPT Pathfinder Application Guidance.

Please agree to set and meet a minimum threshold for investment into shorter or more sustainable supply chains during negotiations phase of the competition:

[  ]    Tick box

# Project Overview

Information submitted in response to any part of this application may be used to assess the Project against the outlined Eligibility and Deliverability criteria. The triage stage of the Deliverability Assessment may consider the whole Submission, and in particular information from subsections:

- 3.4 NPT Solution Description

- 3.5 NPT Solution status and key metrics

- 4.1.4 Logistics

- 4.2 Project Programme

- 4.3 Planning and Consents

- 4.7 CO2 T&S Network Connection

## Power BECCS Project summary key metrics

Please fill in the metrics within the table below, to provide a summary of the Project. The content held within this summary table should be summary of the data provided in Section 3.3 and Section 3.5.

| Metric | Value |
| --- | --- |
| Final Investment Decision date (overall Project) |  |
| Commercial Operation Date (overall Project) |  |
| NPT Solution carbon intensity (gCO₂e/kgCO2 transported) |  |
| Project capital costs (£m – real – define base year) |  |
| Project operational costs (£m – real – define base year) |  |
| Project replacement costs (£m – real – define base year) |  |
| Project operational costs to end of 2050 (£m – real – define base year) |  |
| Project’s maximum annual CO2 transported (Mtpa) |  |
| Project’s average annual CO2 transported rate (Mtpa) |  |
| Project’s net negative emissions (Mtpa) |  |
| Additional potential emissions avoidance from co-products (Mtpa) |  |
| Peak instantaneous CO2 delivery to T&S delivery point (tph) |  |
| Average instantaneous CO2 delivery to T&S delivery point (tph) |  |
| Minimum instantaneous CO2 delivery to T&S delivery point (tph) |  |
| Buffer storage within the NPT Solution’s Post-Transport Infrastructure receiving terminal (tonnes) |  |

## Power BECCS Capture Facility Description (2000 words, additional 1000 words per additional Capture Facility if aggregating multiple capture facilities)

The description of the Power BECCS Capture Facility should include reference to appropriate supporting information to include, but not be limited to the following:

- Details of the type of generating plant, the source of the CO₂ stream for capture, proposed capture plant, CO₂ treatment, any storage, compression facilities.

- A Power BECCS process description including CO₂ average and design mass flowrates and CO2 specifications. As well as the proposed Capture technology type and provider, or shortlist of potential suppliers (including the extent to which this is a firm position).

- Clear diagram(s) / schematic(s) of the. Capture Facility (e.g., Process Flow Diagrams, Plot Plans, etc.).

- Details of the Capture Facility interface connections, transmission/distribution connection point, connection point to the CO2 T&S Network, connection point to the gas network, water intake/cooling. Including whether the facility is dependent on, integrated with, or provides support or products to other local industrial plant(s)?

- Maps showing the location of the Power BECCS CCUS Capture Facility, including, but not necessarily limited to, its location in relation to the grid connection point, gas network connection point, and other relevant local industrial plant(s), along with any available agreements in place for ownership or lease of the proposed site/location.

- Biomass supply chain details including feedstock details, suppliers, offshore and onshore feedstock transportation, and on-site feedstock storage.

- Utility supply requirements and agreements, including power and thermal energy requirements (transient and normal operations), water and other utilities with proposed route to supply.

- If the power plant is separate from the capture plant, is it in operation, construction or development.

- Current state of development of the Project (e.g., FEED complete %) and when is FID anticipated for a) the underlying facility, if applicable, and b) the CCUS plant.

- Include details of the Engineering work completed and the status of ongoing work for facilities in development.

- The design life of the Power BECCS Facility, including the Capture Facility and overall plant life for any pre-existing plants. Please provide any plans for life extension.

- The CO₂ capture rate and carbon intensity of power at full capacity, steady state operation.

- The anticipated annual CO₂ captured and the hourly CO₂ mass flow during an hour of operation at full load. Please include the assumptions for load factor, planned and unplanned maintenance, start-up and shut-down times which inform the profile of captured CO₂.

- The expected reliability and availability, and relevant studies e.g., Reliability, Availability, and Maintainability (RAM) Analysis Report.

- The design turndown capability of the Capture Facility

- To what extent the power BECCS Capture Facility is dependent on third party agreements (e.g., fuel supply, grid connection) to be able to confirm programme delivery dates and volume certainties.

- A projected lifetime CO2 profile.

- A description on the degree of flexibility to adjust the scale of network access required through, e.g., flexible dispatch of CO2.

If aggregating Projects have common Capture Facility designs then the Applicant does not have to describe the same content for each Capture Facility but should state this commonality clearly.

| References to supporting documentation for Section 3.2 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## Power BECCS Capture Facility status and key metrics (250 words per Capture Facility)

Please fill in the metrics within the table below. Any additional graphs to summarise the captured CO₂ profile would be beneficial. Please also refer to Annex B Cost Assessment Form. Where metrics are repeated across annexes it is expected that the same figures and methodologies should be used.

If aggregating multiple capture facilities, please repeat the table for each Capture Facility.

| Metric | Value |
| --- | --- |
| Commercial Operation Date |  |
| Plant Design Life (Carbon Capture Facility and overall if different for other plant facilities) |  |
| Design/Typical CO₂ Rate to the NPT Solution from the Capture Facility (tph) |  |
| Peak CO₂ flow rate to the NPT Solution from the Capture Facility (tph) |  |
| Expected annual average CO₂ Rate to the NPT Solution from the Capture Facility (Mtpa) |  |
| Capture Facility capital costs (£m – real – define base year) |  |
| Annual average operational costs (£m – real – define base year) |  |
| Expected Plant Availability (%) |  |
| Design Capture Rate, if applicable (%) The maximum instantaneous design capture rate, i.e., the percentage of CO₂ emissions captured from the specific emissions streams that the capture technology is applied to, which is expected to be continuously achievable by the facility for extended periods, i.e., during normal steady state operation. |  |
| Plant efficiency at full load (%) |  |
| Net Dependable Capacity (MW) |  |

| References to supporting documentation for Section 3.3 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## NPT Solution Description (2000 words)

Non-pipeline transportation allows Capture Facilities to access an established CCUS Cluster without the need for a direct pipeline connection to the T&S Network.

This section is for Projects to describe their NPT Solution (i.e. the additional infrastructure and assets required for an NPT Project that are not required for a piped Project – e.g. liquefaction, temporary storage, trucks/rail/shipping assets, etc). For the purposes of this document, the associated fixed infrastructure and mobile transportation assets are collectively grouped into what is termed the NPT Solution. The NPT Solution is linked to the upstream CO2 Capture Facility and the downstream T&S Network as illustrated in Figure 1.

Figure 1 - NPT Solution for this application is highlighted in the orange box

Please provide a high-level description of the proposed NPT Solution covering the following points. Applicants are encouraged to provide supporting information with more detail on the technical details and specifications of the infrastructure and assets described.

- Description of the Pre-Transportation Infrastructure and processes required from the Battery Limit of the Capture Facility(ies) to the Battery Limit of the Mobile Transport Assets. This might include compressors, liquefaction plants, buffer storage, loading infrastructure, pumping, heating and utility systems.

- Description of the process involved to transport CO2 via the Mobile Transport Assets from Pre-Transportation Infrastructure Battery Limit to Post-Transport Infrastructure Battery Limit. This should include the mode of transportation, transport fuel, fuel consumption, journey start and end points, route between start and end points, journey times, Mobile Transport Asset fleet capacity and size (number).

- The transportation route should be described detailing:

  - Transport journey distance (one-way) (km)

  - Transport journey duration (hrs)

  - Time at loading and receiving terminal (hrs)

  - Transportation route and any considerations relating to congestion both en-route and at loading and receiving terminals

  - For rail transportation, demonstration that sufficient freight paths are potentially available on the rail network

  - Frequency of journeys

  - Demonstration of transport fleet dimension compatibility with loading and receiving terminals

  - CO2 emissions associated with mobile transportation – broken down by activity (fugitive and fuel (t/yr)) and any actions being taken to minimise these in a cost-effective manner

- Description of Post-Transportation Infrastructure and processes required from the Mobile Transport Assets Battery Limit up to the T&S Network Delivery Point. For instance, CO2 unloading infrastructure, temporary storage, CO2 conditioning facilities, interconnecting pipelines, and any other equipment and systems used.

- The Battery Limits of each entity, the intended interface point where responsibility for the connection is assumed, custody transfer of the captured CO2 will take place, and the construction responsibility, eventual ownership and operational boundaries;

- Please explain whether any of these facilities or transport assets will be re-used following prior service, reuse asset condition, and any related constraints. Providing supporting evidence such as condition surveys would be beneficial.

- Please explain whether NPT assets will be shared with other users. If so, please describe the nature of sharing arrangements.

- Description of the metering conducted along the value chain.

- Any other infrastructure that is required to deliver and operate the NPT Solution.

NPT Solution description. (2000 words)

| References to supporting documentation for Section 3.4 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## NPT Solution status and key metrics (250 words)

Please fill in the metrics within the table below. Any additional graphs to summarise the CO₂ profile delivered to the T&S delivery point would be beneficial. Please also refer to Annex B Cost Assessment Form. Where metrics are repeated across annexes it is expected that the same figures and methodologies should be used.

| Metric | Value |
| --- | --- |
| Commercial Operation Date |  |
| NPT Solution carbon intensity (gCO₂e/kgCO2 transported) |  |
| NPT-related capital costs (£m – real – define base year) |  |
| NPT-related operational costs (£m – real – define base year) |  |
| NPT-related replacement costs (£m – real – define base year) |  |
| Overall NPT-related operational costs to end of 2050 (£m – real – define base year) |  |
| Maximum annual CO2 transported (Mtpa) |  |
| Average annual CO2 transported rate (Mtpa) |  |
| Peak instantaneous CO2 delivery to T&S delivery point (tph) |  |
| Average instantaneous CO2 delivery to T&S delivery point (tph) |  |
| Minimum instantaneous CO2 delivery to T&S delivery point (tph) |  |
| Buffer storage within the NPT Solution’s Post-Transport Infrastructure (tonnes) |  |

| References to supporting documentation for Section 3.5 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## Potential Expansion Phases

Please provide a concise description of how this Project could deliver future decarbonisation including the potential to link to expansion of existing Capture Facility(ies), additional future potential Capture Facility(ies) deploying via NPT and/or expansion of the NPT Solution. Please include a description of the uncertainty around these future phases in terms of execution, CO2 volumes, and costs.

Please also provide any information on whether the key infrastructure is likely to be shared either immediately or in the future.

| References to supporting documentation for Section 3.6 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## Removal quantification methodology (2000 words per Project with an additional 500 words if aggregating multiple Capture Facilities)

To be eligible to apply, pBECCS Projects must result in net negative GHG emissions, when compared to a relevant baseline. Ahead of the publication of the detailed UK GGR methodologies currently in development by HMG (due in 2027), Applicants must quantify GHG removals in accordance with the EU Carbon Removal and Carbon Farming (CRCF) directive and permanent carbon removal delegated act. The EU CRCF defines the equations and parameters which must be used and identifies all elements required to be considered in the evaluation.

Lifecycle evaluation to quantify predicted GHG removals

Quantification of GHG removals predicted to be achieved by the proposed Project must be provided, and this evaluation shall be in accordance with the EU CRCF permanent carbon removal regulation. Any desktop lifecycle assessment to predict GHG removals shall make use of the equations defined within the EU CRCF permanent carbon removal regulation and consider the boundaries also defined therein, taking into account all required elements specified by the EU CRCF regulation. If the EU CRCF permanent carbon removal regulation provides insufficient details on any specific aspect, Projects may supplement the CRCF requirements with guidance from existing methodologies from the voluntary carbon markets, with justification for their selection. Justification must be provided for all inputs, and calculations must be fully documented and submitted as supporting evidence to allow verification. Any areas of uncertainty, due to design maturity or other factors, must be clearly identified.

Monitoring, Reporting, and Verification Protocol to Quantify Actual GHG Removals

A monitoring, reporting and verification (MRV) protocol must be provided, demonstrating a clear understanding of the requirements to measure and calculate the GHG removal over the Project lifetime, and detailing the proposed procedures for measuring and calculating the GHG removal over the Project lifetime, covering all elements specified by the EU CRCF permanent carbon removal regulation. Any MRV plan for the actual GHG removals must also be in accordance with the EU CRCF permanent carbon removal regulation and consider the boundaries defined therein, taking into account all required elements specified by the EU CRCF regulation. If the EU CRCF permanent carbon removal regulation provides insufficient details on some monitoring aspects, Projects may supplement the CRCF requirements with guidance from existing methodologies from the voluntary carbon markets, with justification for their selection. Evidence of adherence to industry best practices is expected.

Evidence is expected to include a LCA and MRV protocol including supporting calculations, appendices or references in line with EU CRCF regulations.

| References to supporting documentation for Section 3.7 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

# Deliverability

## Organisational and Technical Maturity – Project

### Organisational structure – company level (1000 words)

Please describe the company structure and provide a chart which positions the Project company within any wider company structure highlighting the following information for each entity within the structure:

- Primary activity and location

- Ownership (including details of any stock market listings)

- Where within the company/group structure will key investment decisions be taken.

- If a new legal entity is to be created for the purpose of this Project, where in the company/group structure this will sit and the expected timing of its incorporation.

Please provide a capability statement, which shall includes:

- Relevant corporate experience, including, but not limited to:

- Ongoing plant operations.

- Recent major investments at process facilities (Including EPC management),

- Managing joint ventures (including information sharing between partners)

- Experience navigating the UK regulatory regime.

- Identification of personnel with key roles and responsibilities and their relevant experience.

- Please also provide brief details of the company’s approach to ensuring Corporate Governance best practice.

Please provide details of the ultimate beneficial owner of the corporate group, as well as the details of any shareholder (or group of related shareholders) owning more than 5% of the group’s equity capital.

| References to supporting documentation for Section 4.1.1 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### Organisational structure and governance – Project level (800 words)

Please describe the organisational structure at a Project level including how the delivery of the Project will be managed. Where possible, provide evidence of the experience of key personnel which shall include CVs/ Career statements for, but not necessarily limited to:

- Project manager(s) / director(s)

- Financial, procurement, and costs lead(s)

- Lead engineer(s)

- Any construction, commissioning and operational lead(s)

- For retrofit Projects the site manager(s)

Where capability gaps exist, please provide the approach to securing them. For key personnel who are not yet in post, as well as temporary work scopes/ roles, please provide details of recruitment plans/strategies.

Please describe the status of any commercial agreements between parties within the delivery structure alongside plans to progress future agreements, including key milestones and any dependencies.

Please also provide details of any new legal entity to be created for the purpose of this Project. Where relevant please include any anticipated joint venture arrangements or agreements alongside the activities and associated timeline to finalise any joint venture arrangements.

Please describe the capability of the Project developers and governance arrangements. Please describe communication and decision-making between parties within the Project organisation.

Please provide an overview of the organisational structure of the NPT Solution if distinct from the Project organisation, including the roles and responsibilities of different companies across the chain. Please also outline which company has legal liability, ownership of assets, and CO2 custody across the chain. Please explain if the intent is to operate as a joint venture.

Please also describe how the delivery of the NPT Solution will be managed including identification of Project development process and standards applied and the current status of the Project development with listing of available Project development documentation.

| References to supporting documentation for Section 4.1.2 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### Technical Maturity (750 words)

Please describe the level of Project engineering definition providing the studies completed as evidence. With reference to the schedule describe the studies to be completed and where identified, who will complete them.

Please describe the Project and provide supporting information detailing the following:

- The location and layout of the Capture Facility(ies), clearly identifying related facilities and required third party connections;

- Process description, including plans to meet CO2 specifications, with schematics or process flow diagrams;

- Engagement with the supply chain to date including technology providers/ licensors, contractors (tier 1 contractors or beyond), equipment suppliers, NPT transport service providers, consultants and external advisors, and planned future engagement;

- Maturity of the supply chain for this type of Project;

- Access to intellectual property and demonstration of the technology at scale for both components and system with evidence of the operating record of the technology (e.g., duration in service).

- The CO2 capture quantities anticipated, capture rate, energy efficiency and any associated emissions;

- For retrofit Projects, the status and operation of any related facilities including remaining operational life and any planned life extension programmes;

- The status of required land, access and third-party connections required to deliver the Project such as electricity, fuel, or water. Note; there is a separate section covering the CO2 T&S Network connection.

- NPT Solution process description, identifying the location and layout of related facilities and required third party interfaces.

Please describe the Technology Readiness Level (TRL) and commercial readiness index (CRI) of the selected power generation and carbon capture technology, other relevant technologies, and CO2 transport technology where applicable, with supporting evidence such as TRL or CRI justifications, reference Projects and pilot/demonstration scale testing.

Supporting evidence could include engineering studies, drawings, calculations, assessment of supply chain capability and capacity, supply chain agreements, licensing agreements, technology references and operating records, TRL and CRI studies, land agreements, third-party connections agreements or applications.

| References to supporting documentation for Section 4.1.3 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### Logistics (750 words)

Please provide evidence demonstrating access to, or planned development of, key infrastructure required (e.g., railheads, ports/jetties, railway lines, etc.) for the NPT Solution to operate effectively. Please describe any potential operational constraints that are known within the NPT Solution (e.g., weather, congestion, lack of freight capacity or freight paths, other users of the same infrastructure). Please note where decisions within the NPT Solution design have been made in a manner to best manage the logistical challenges.

| References to supporting documentation for Section 4.1.4 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## Project Programme (1000 words)

Please provide an integrated schedule for the Project including the Capture Facility(ies) and NPT Solution. This shall be at least Level 2 detail, fully logic linked, identify the critical path and include any float. It is acceptable to provide a Level 2 schedule for the Capture Facility(ies) and NPT Solution individually and an L1 schedule showing the overall Project. This should show when the Project comes online, and any key milestones such as: planning, consents, decision gates, long lead equipment items, gas and electricity grid connections, FID, COD, etc. This should also show progress to date against the stated Project schedule, with documentation and engineering information provided to demonstrate that the Project is progressing to plan.

The schedule must be provided in both pdf and native file format - Primavera P6 (XER) or MS Project (XML/MSP).

Please provide a concise description of the schedule’s critical path with reference to important parts of the schedule that the critical path is dependent on.

Please describe the development of the Project business plan and how this relates to other key activities in the programme including securing intellectual property rights, finance and supply chain, and any additional services you may be providing.

We recognise different Projects are at varying degrees of development, so please provide the greatest level of detail currently available that is supportable with evidence.

Please describe areas of uncertainty in the schedule: if possible, please present the base schedule with uncertainty ranges around individual activities and identify the key risks that could expand these ranges further. Describe how the values used were estimated, with reference to supply chain engagement, industry databases, or experience used.

Reference to separate ‘What if’ scenarios or quantitative schedule risk analysis of the schedules would be beneficial to increase confidence of deliverability within a given time.

| References to supporting documentation for Section 4.2 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## Planning and Consents (750 words per Capture Facility or NPT Solution)

With reference to the schedule, please provide a description of the planning and consents required for the i) Capture Facility(ies) and ii) the NPT Solution, and the route to securing those consents. This is expected to include planning consents and environmental permits. It would be beneficial to demonstrate evidence of engagement with the relevant planning and permitting authorities and their feedback, or expert advice on the most appropriate approach to planning and permitting. This should include engagement with advisory bodies which may influence planning and consenting processes (e.g., Natural England, NatureScot, etc.), not just the authorities and regulatory bodies themselves.

Please ensure that you highlight areas of risk and uncertainty surrounding planning and consents that could increase the durations or require design modifications to achieve approvals.

Please include a concise description of the arrangements for grid connection including the status of connection application, whether this is a new application or modification to existing, the generation licence, and any associated planning consent for the grid connection if separate to the Project planning consent.

Reference to a separate Planning and Consents Register would be helpful, as would any evidence of engagement with statutory bodies or preparation work for applications. We would anticipate planning and consent risk being an intrinsic element of the Project risk register.

Capture Facility(ies) (750 words)

| References to supporting documentation for Section 4.3 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

NPT Solution (750 words)

| References to supporting documentation for Section 4.3 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## Risk Management (1000 words)

Please provide a concise description of all the major risks to the Project and how they are going to be mitigated. It would be beneficial to evidence the risk management approach with a risk management plan or reference to company procedures in compliance with industry standards such as ISO 31000. Additionally provide a description of how significant residual risks will be escalated, tracked and managed (e.g., accept, transfer, insure, etc.).

The separation of development, construction and operation phase risks would be preferable.

The risk registers should include:

- Risks for all elements of the Project and downstream chain risks, including interface risks and details on risk owners

- Mitigations (e.g., eliminate, reduce, transfer, insurance, etc.) and how they will be managed, (actions, individuals, dates) alongside estimated mitigation costs and post mitigation residual risks

- Identification of risks that cannot be transferred to contractors or insurers or others

- Probability estimates both pre and post mitigation

- Three-point (high, low and most likely) impact estimates for cost and schedule impacts for both pre and post mitigation

- Identification of any schedule activities that are impacted by the occurrence of each risk.

- Activity IDs included in the risk register

- Any significant residual safety risks

- Highlight Project innovation risks and mitigations

Below are examples of key risks that may need to be considered in relation to the CCUS Project:

Development risks including:

- If existing assets (e.g., in a retrofit Project) cannot be re-used after further assessment or other key assumptions on existing asset conditions change.

- Delays in obtaining planning consents and permits or any required licence, land access, or connection agreements.

- Changes to CO₂ product quality specifications and/or any other conflict with the published CCS Network Code.

Construction and commissioning risks including:

- Contractor interfaces.

- Insolvency of key suppliers.

- Supply chain delays and delivery delay of critical equipment items.

- Workforce / key skills availability.

- Commissioning dependencies including unavailability of downstream T&S.

- For retrofits, SIMOPs with existing facilities.

Operational risks including:

- Temporary closure of part of the rail network.

- Rail strike.

- Severe weather events disrupting transport operations.

- Availability and price fluctuations of biomass supply.

- Limited design and operational experience of type of plant.

- Underperformance of capture plant, increasing vented volumes of CO₂.

- Higher than expected energy consumption, increasing Opex and reducing net export MW.

- For pre- or post-combustion capture, higher than expected solvent consumption, increasing Opex.

- High emissions of pollutants (e.g., nitrogen compounds).

- Low availability/high downtime of capture plant, increasing vented volumes of CO₂ and resulting in greater intermittency.

- Low load factor for power plant.

- Delays or cancellations of downstream Projects – stranded asset risk.

- Closure/bankruptcy of T&S – leaving capture plant as stranded asset.

Overarching or general risks including:

- Force majeure events.

- Regulatory risks for new technology or processes.

To increase our understanding of the Project and its credibility, the inclusion of an opportunity register alongside the risk register would be beneficial for the assessment.

A quantitative risk assessment for cost and schedule where available would be beneficial to evidence confidence in the estimates.

| References to supporting documentation for Section 4.4 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## Project Controls & Cost Management

This section looks at the approaches and methods the Project has and will be undertaking to control Project development. Supporting evidence would be expected in the Project execution plan.

### Project Execution (1000 words)

In this section, please describe how the Project intends to execute the Project stage gates.

Please provide a construction plan and a concise explanation of any aspects of the Project execution that apply novel construction / installation techniques, as well as those units considered to be of greatest challenge.

Provide a preliminary commissioning Plan, including any risks and uncertainties identified for the commissioning & start-up phase of the Project. Explain how the Project is planning to ensure that equipment is robustly tested for service and ready for handover without unduly threatening integrity.

Demonstrate how operations and maintenance are inputting into the Project execution, to ensure that the plant being developed is fit to operate for the contract lifespan, and appropriately considers human factors.

Additionally, please provide a concise description of the Management of Change process to be followed through Project progression including how the following change (and no change) impacts will be assessed and considered:

- Impacts to Costs.

- Impacts to HSE Risks.

- Impacts to Schedule.

Along with how disputes might be resolved with stakeholders over changes or issues.

| References to supporting documentation for Section 4.5.1. |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### Procurement Strategy (750 words)

Please provide a concise outline of the proposed approach to contracting strategy and procurement;

- Proposed work package structure, with procurement and contracting structure(s).

- Proposed approach for transparent and competitive procurement, demonstrating value for money throughout supply chain.

- Proposed approach to managing and sharing construction risk throughout the supply chain (e.g. labour costs, weather risk, etc.).

- The team structure which will efficiently procure and manage all contracts for the duration of the Project.

- The quality controls / assurance used to ensure deliverables of the required standard.

Supporting evidence for proposed approach might be included in Project execution plan, and/or contract map.

| References to supporting documentation for Section 4.5.2 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### Engineering for Value (500 words)

Please discuss the Project’s approach to rationalising the facility design and avoiding overengineering. Assurance should be provided that where more complex and costly options are pursued, these are appropriately justified, with reference to appropriate studies (e.g., reliability, safety/other risk, technology readiness). We would expect to see examples including:

- Process simplification workshops / studies,

- A Value Engineering or Opportunities Register (with appropriate action tracking),

- Rationalisation of non-standard equipment,

- Competitive engineering designs,

- Decision papers and methodology.

| References to supporting documentation for Section 4.5.3 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## Financial and Commercial

This section aims to understand the financial and commercial health of all the companies involved in the development of the Project and the proposed financing plan for the Project.

Each company participating in the development of the Project must provide an individual response to this section. To support this assessment, please submit:

- A completed Financial Statement Form (Annex C), and

- Associated financial documents as requested in Annex C,

- for each company-level response on business plan and financial health.

These company-level responses should be submitted alongside the overarching Project Plan and financing plan.

### A - Business plan and financial health – company level (750 words)

Note: Each company participating in the development of the Project must provide a response. Multiple responses (A, B, C, etc.) may be necessary if the Project is being developed in partnership.

Please describe the following:

- How your company business plans and industrial output have been impacted by recent significant events since the start of 2020, e.g., COVID-19 and Ukraine War supply chain shocks.

- What is the outlook for the company out to 2032? (Your answer should include, but not be limited to, a description of, and rationale for, expected trends in revenue, overheads and profitability, plus a comparison of these to the historical period.)

- Describe how the Project aligns with the company’s overall strategic ambitions in the UK to 2032 and beyond.

Please provide copies of the latest two sets of audited accounts, any accompanying reports, management accounts covering the remainder of the current financial year, and forecast financial accounts covering the remainder of the current financial year and a further ten years for the following companies where applicable:

- The company or companies operating the Project

- The company or companies financing the Project

- The company or companies responsible for key investment decisions in relation to this Project

- The group parent company or companies (e.g., consolidated accounts) and ultimate parent. For the avoidance of doubt, the group parent should be regarded as the largest group in which the accounts of the companies operating and/or financing the Project are consolidated.

In support of these accounts and reports for the above entities, please include key assumptions underlying financial forecasts.

Please confirm that accounts for the above entities have not received a qualified audit report in any of the previous five years. Highlight any areas of material uncertainty raised by auditors in this period.

Please confirm if the corporate group currently has any financial obligation to HMG and provide details where applicable.

| References to supporting documentation for Section 4.6.1 A |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### B - Business plan and financial health – company level (750 words)

Note: Each company participating in the development of a Project must provide a response. Multiple responses may be necessary where Projects are being developed in partnership.

Please see Section 4.6.1 for further details.

| References to supporting documentation for Section 4.6.2 B |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### C - Business plan and financial health – company level (750 words)

Note: Each company participating in the development of a Project must provide a response. Multiple responses may be necessary where Projects are being developed in partnership.

Please see Section 4.6.1 for further details.

| References to supporting documentation for Section 4.6.3 C |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### D - Business plan and financial health – company level (750 words)

Note: Each company participating in the development of a Project must provide a response. Multiple responses may be necessary where Projects are being developed in partnership.

Please see Section 4.6.1 for further details.

| References to supporting documentation for Section 4.6.4 D |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### E - Business plan and financial health – company level (750 words)

Note: Each company participating in the development of a Project must provide a response. Multiple responses may be necessary where Projects are being developed in partnership.

Please see Section 4.6.1 for further details. If additional entries are needed to cover all companies participating in the development, please insert new sections 4.6.6 F Company etc.

| References to supporting documentation for Section 4.6.5 E |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### Financing plan – Project level (1000 words)

Note: In the event of multiple participants in a Project, we would expect to see a single overarching financing plan and for it to be clear how each participant fits into that.

Applicants will be required to show a detailed & credible plan for how they intend to obtain the finances necessary to fund their Project at its current expected cost. TAA Projects must provide details of sufficient alternative sources of support (e.g., public funding or private investment) and/or revenue, and provide supporting evidence.

Response should distinguish between different stages of the Project and explain what is needed to achieve a FID. Within your answer, please provide the timeline, dependencies, key risks and mitigations for the financing process. Please also detail the assumptions underpinning the financing plan including key ratios.

- If the Project will be financed by intragroup financing or external debt arrangements that already exist, then please provide a summary of those arrangements. Your summary of the debt arrangements should reference any factors that are material to the financing e.g., headroom, duration, security, and covenants.

- If new capital needs to be raised then set out the type and amount of finance anticipated, the level of market engagement that has taken place, feedback received, as well as the activities and timescale needed to secure the financing. Please provide any previous experience of bank launches and the current strategy of any future launch.

Please summarise the status of key agreements needed to realise the Project and the plans to finalise them e.g., shareholder/sponsor documents, loan and security documents, and Project documents. Please include demonstration of any (not necessarily committed) interest from providers of capital, and any status of discussions. Supporting evidence may include letters of support, memoranda of understanding, letters of intent, or commercial agreements from financiers.

Please provide a description of the Project’s anticipated revenue streams and supporting evidence demonstrating their robustness, including the basis for demand, pricing assumptions, contract structures and any dependencies. Where relevant, set out how these revenue streams underpin the financing plan and support the ability to reach FID.

Evidence of risk mitigation for the financing process may include plans in the event of a change in market conditions or original funding plans e.g., scenario analysis completed on alternative funding routes.

| References to supporting documentation for Section 4.6.6 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### CO2 T&S Dependencies (1000 words)

Please explain the implications, both financial and deliverability, for your Project from the following scenarios:

- T&S connection delay (3 months, 6 months, 1 year)

- T&S constraint leading to 50% registered capacity (1 month, 3 months, 6 months)

- T&S outage (3 months, 6 months, 1 year)

- Unplanned T&S closure / decommissioning (include any risk of stranded asset)

Evidence is expected to include inclusion of detailed items in the submitted risk register, aligned with the summaries above.

| References to supporting documentation for Section 4.6.7 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

### Transition Access Agreement (TAA) Dependencies (500 words)

We are minded not to provide ongoing revenue support to TAA users in relation to T&S Charges. However, where T&S Charges support is essential for Projects to sign a TAA, and that this need is clearly evidenced, DESNZ is considering providing limited support in relation to T&S Charges on a case-by-case basis.

Applicants seeking indicative T&S fees should contact the ECC T&S Co (NEP), directly. NEP can provide a range of indicative T&S fees to support your application.

Under the CCS Network Code, where there is underutilisation of the network, CO2 T&S charges are expected to increase proportionally, up to a mutualisation cap. Please provide implications, both financial and deliverability, for your Projects in the following simplified scenarios:

- For 1/5/10 years T&S charges twice as high as expected

- For 1/5/10 years T&S charges four times higher than expected

- For 1/5/10 years T&S charges equal to the carbon price

Please clearly indicate tolerance for T&S charge variability and impact on Project business model.

| References to supporting documentation for Section 4.6.8 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

## CO2 T&S Network Connection (1000 words)

Please describe the connection between the NPT Solution and the CO2 T&S. This should include:

- The Battery Limits of the NPT Solution, the intended interface point where responsibility for the connection is assumed, custody transfer of the captured CO2 will take place, and the eventual ownership and operational boundaries;

- The intermediate pipework in private land or pipelines in public land to connect to the T&S, major crossings;

- Confirmation of familiarity with the published CCS Network Code and acknowledgement of the processes defined therein.

- Evidence of engagement with the CO2 T&S Co, including agreements in place.

- Evidence of engagement with land holders and/or a plan to secure access rights.

- A schedule of T&S spur development.

The information to answer this section could come from collaboration with the CO2 T&S Co or a high-level route options study by the Applicant.

Please describe quality controls and required processing for the CO₂ entering the CO2 T&S Network and how this meets the T&S CO2 specification. Please describe how the engineering solution is aligned to meet the T&S CO2 specification (including impurity thresholds and measurement frequencies) and what measures are in place to detect off-spec CO2 formation and prevent any from entering the T&S Network.

Please describe the intended operating regime for the capture plant export to the CO2 T&S Network and any measures planned to manage intermittency or operability of the T&S Network. In evidence, please provide a table showing annual mass flow rate of CO2 to the T&S and the expected CO2 percentage (on a mass basis) in the CO2 rich export stream.

Supporting evidence is expected to include:

- Evidence of engagement, and any agreements in place, with the relevant Transport and Storage company (T&S Co),

- Engineering or routing studies for the T&S connection,

- Annual mass flow rate of CO2 and CO2 percentage (mass basis) in the CO2 rich export stream;

- Evidence of T&S CO2 specification compliance

- Diagrams showing Battery Limits and the intended interface point,

- Any land agreements, and

- Any planned delivery schedule

| References to supporting documentation for Section 4.7 |  |  |
| --- | --- | --- |
| Document reference | Document name | Relevant page/section |

This publication is available from: CCUS East Coast Cluster: NPT Pathfinder selection process - GOV.UK

If you need a version of this document in a more accessible format, please email NPTPathfinder@energysecurity.gov.uk. Please tell us what format you need. It will help us if you say what assistive technology you use.

CCUS East Coast Cluster: Teesside selection process - GOV.UK

CCUS East Coast Cluster: NPT Pathfinder selection process - GOV.UK

CCUS East Coast Cluster: NPT Pathfinder selection process - GOV.UK

Check duties and customs procedures for exporting goods - GOV.UK

EU Delegated Act on Permanent Removals: 96845e08-0311-45b4-b6c0-7040e31d9cd0_en

For the definition of TRL please refer to the Definitions in Table 2 of this document.

For CRI definitions please refer to https://arena.gov.au/assets/2014/02/Commercial-Readiness-Index.pdf

Applicants should refer to the DPA Business model updates published in December 2020, May 2021, October 2021 for more information on risks.