## Summary
As per section 18 in the Scheme Guidance and section D4 of the Application Form, in order to assess the case for assistance of your project, we require you to show the minimum amount of funding required to facilitate your project, and/or the amount of activity brought forward (and when) as a result of the funding. We have set out in the tabs below some illustrative examples based on the following: - 'Investment appraisal metrics' (as per the financial model for the deliverability assessment) - 'Activity brought forward' (as per the strategic assessment template) - 'GANTT chart' (as per the projec plan template for the deliverabilty assessment) Note that these examples are only illustrative. Feel free to provide different analysis if you think it better illustrates your project's case for assistance. Note also that data entered up to FY34 will be part of the assessment, and will be used to inform grant offer letter terms and conditions to be monitored during the project lifetime. Data entered for beyond FY34 is solely for the use of wider benefits analysis as part of the application assessment process.

## Investment appraisal metrics
Drawing on the template as per the document 'Deliverability assessment template (financial model)'.xlsx', with this template you are able to show how the funding impacts investment appraisal metrics that might be instrumental in deciding whether to go ahead with a project or not)
Worked Example
£'000 | W/O funding | With funding
Net profit | £5m | £6m
Cash flows | £7m | £9m
Discounted cash flows / NPV | £4.5m | £6.2m
IRR% | 5.5% | 6.8%
Payback period | 5.5 years | 4.9 years
£'000 | W/O funding | With funding
Net profit
Cash flows
Discounted cash flows / NPV
IRR%
Payback period

## Activity brought forward
Drawing on the template as per the document 'Strategic assessment template.xlsx', with this template you could show how much activity (in terms of volumes) would be brought forward as a result of the funding
FY assumed to be 01-Apr to 31-Mar, but if yours is different please note this
Without funding
| Item being produced | Unique ref / model | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | Beyond
Worked Example | Manifold | Manifold ABC123 | 0 | 5000 | 8000 | 9500 | 10000 | 10000 | 10000 | 10000 | 10,000 p.a. for 5 years
With funding
| Item being produced | Unique ref / model | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | Beyond
Worked Example | Manifold | Manifold ABC123 | 2500 | 7500 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10,000 p.a. for 5 years
Difference
| Item being produced | Unique ref / model | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | Beyond
Worked Example | Manifold | Manifold ABC123 | 2500 | 2500 | 2000 | 500 | 0 | 0 | 0 | 0 | 0

## GANTT chart
Drawing on the template as per document 'Deliverability assessment template (project plan)'.xlsx', with this template you could show how much activity (in terms of the project plan) is brought forwad as a result of the funding
Worked Example
|  | Without funding |  | With funding |  | Difference
Ref | Activity | Start | End | Start | End | Start | End
Site selection
SS001 | Outline design | 2029-03-01 | 2029-03-18 | 2027-03-01 | 2027-03-18 | 2 years | 2 years
SS002 | Site search criteria | 2029-03-19 | 2029-05-04 | 2027-03-19 | 2027-05-04 | 2 years | 2 years
SS003 | Site search
SS004 | Site shortlisting
SS005 | Site negotiations
SS006 | Environmental considerations
Planning / FEED
PF001 | Full design | 2029-08-10 | 2029-12-24 | 2027-08-10 | 2027-12-24 | 2 years | 2 years
PF002 | Planning application
PF003 | Planning decision
PF004 | Optimised design
PF005 | Selecting builder
PF006 | Contracts
Construction
CN001 | Manufacturing design
CN002 | Optimisation
CN003 | Building works
CN004 | Highways works
CN005 | Regulatory requirements
CN006 | Recruitment
CN007 | Machinery ordering
Setup phase
SP001 | Final factory fit out
SP002 | Training of staff
SP003 | First line established
SP004 | Refinements
SP005 | Optimisation
SP006 | Local supplier engagement
|  | Without funding |  | With funding |  | Difference
Ref | Activity | Start | End | Start | End | Start | End
Site selection
SS001 | Outline design
SS002 | Site search criteria
SS003 | Site search
SS004 | Site shortlisting
SS005 | Site negotiations
SS006 | Environmental considerations
Planning / FEED
PF001 | Full design
PF002 | Planning application
PF003 | Planning decision
PF004 | Optimised design
PF005 | Selecting builder
PF006 | Contracts
Construction
CN001 | Manufacturing design
CN002 | Optimisation
CN003 | Building works
CN004 | Highways works
CN005 | Regulatory requirements
CN006 | Recruitment
CN007 | Machinery ordering
Setup phase
SP001 | Final factory fit out
SP002 | Training of staff
SP003 | First line established
SP004 | Refinements
SP005 | Optimisation
SP006 | Local supplier engagement