## Summary
As per section 17 in the Scheme Guidance and section D3 of the Application Form, in order for us to assess the deliverability of your project, we require a project plan that should include (but not be limited to) a schedule of activities, a Gantt chart, cost breakdowns and associated responsibilities. We have provided within this document an illustrative template/example set across four tabs, being: - Schedule of activities & cost breakdowns - GANTT chart - Progress to date - Risk Register Note that the templates/examples set out below are only illustrative. Feel free to provide different information if you think it better illustrates how and when your project will be delivered, what the risks are to this, and how those risks will be managed/mitigated Note also that data entered here will be used to inform grant offer letter terms and conditions to be monitored during the project lifetime.

## Schedule of activities
NB - this is just an example/illustrative schedule of activities. Please provide a schedule of activities (or equivalent information) that best represents your specific project
Ref | Activity | Start | End | Duration (days) | Responsible person(s) | Budget (£'000) | Long description of the activity | Notes / comments / further considerations
Site selection
SS001 | Outline design
SS002 | Site search criteria
SS003 | Site search
SS004 | Site shortlisting
SS005 | Site negotiations
SS006 | Environmental considerations
Planning / FEED
PF001 | Full design
PF002 | Planning application
PF003 | Planning decision
PF004 | Optimised design
PF005 | Selecting builder
PF006 | Contracts
Construction
CN001 | Manufacturing design
CN002 | Optimisation
CN003 | Building works
CN004 | Highways works
CN005 | Regulatory requirements
CN006 | Recruitment
CN007 | Machinery ordering
Setup phase
SP001 | Final factory fit out
SP002 | Training of staff
SP003 | First line established
SP004 | Refinements
SP005 | Optimisation
SP006 | Local supplier engagement

## Gantt chart
NB - this is just an example/illustrative Gantt chart. Please provide a Gantt chart that best represents your specific project
|  |  |  | 2027-01-01 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-01 |  |  |  | 2027-05-01 |  |  |  |  | 2027-06-01 |  |  |  | 2027-07-01
Ref | Activity | Start | End | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Notes / comments
Site selection
SS001 | Outline design | 2023-01-02 | 2023-01-06 | bar: 2027-01-01 Wk 1
SS002 | Site search criteria | 2023-01-09 | 2023-01-13 | bar: 2027-01-01 Wk 2
SS003 | Site search | 2023-01-16 | 2023-01-20 | bar: 2027-01-01 Wk 3
SS004 | Site shortlisting | 2023-01-23 | 2023-01-27 | bar: 2027-01-01 Wk 4
SS005 | Site negotiations | 2023-01-30 | 2023-02-17 | bar: 2027-02-01 Wk 5 to 2027-02-01 Wk 7
SS006 | Environmental considerations | 2023-02-20 | 2023-03-10 | bar: 2027-02-01 Wk 8 to 2027-03-01 Wk 10
Planning / FEED
PF001 | Full design | 2023-01-30 | 2023-02-24 | bar: 2027-02-01 Wk 5 to 2027-02-01 Wk 8
PF002 | Planning application | 2023-02-20 | 2023-03-03 | bar: 2027-02-01 Wk 8 to 2027-03-01 Wk 9
PF003 | Planning decision | 2023-02-27 | 2023-03-10 | bar: 2027-03-01 Wk 9 to 2027-03-01 Wk 10
PF004 | Optimised design | 2023-03-06 | 2023-03-17 | bar: 2027-03-01 Wk 10 to 2027-03-01 Wk 11
PF005 | Selecting builder | 2023-03-13 | 2023-03-24 | bar: 2027-03-01 Wk 11 to 2027-03-01 Wk 12
PF006 | Contracts | 2023-03-20 | 2023-03-31 | bar: 2027-03-01 Wk 12 to 2027-03-01 Wk 13
Construction
CN001 | Manufacturing design | 2023-03-06 | 2023-03-31 | bar: 2027-03-01 Wk 10 to 2027-03-01 Wk 13
CN002 | Optimisation | 2023-03-27 | 2023-04-07 | bar: 2027-03-01 Wk 13 to 2027-04-01 Wk 14
CN003 | Building works | 2023-04-03 | 2023-05-19 | bar: 2027-04-01 Wk 14 to 2027-05-01 Wk 21
CN004 | Highways works | 2023-04-24 | 2023-06-16 | bar: 2027-04-01 Wk 17 to 2027-06-01 Wk 24
CN005 | Regulatory requirements | 2023-06-05 | 2023-06-30 | bar: 2027-06-01 Wk 23 to 2027-06-01 Wk 26
CN006 | Recruitment | 2023-06-19 | 2023-06-30 | bar: 2027-06-01 Wk 25 to 2027-06-01 Wk 26
CN007 | Machinery ordering | 2023-06-19 | 2023-06-30 | bar: 2027-06-01 Wk 25 to 2027-06-01 Wk 26
Setup phase
SP001 | Final factory fit out | 2023-06-19 | 2023-07-14 | bar: 2027-06-01 Wk 25 to 2027-07-01 Wk 28
SP002 | Training of staff | 2023-07-10 | 2023-07-21 | bar: 2027-07-01 Wk 28 to 2027-07-01 Wk 29
SP003 | First line established | 2023-07-17 | 2023-07-28 | bar: 2027-07-01 Wk 29 to 2027-07-01 Wk 30
SP004 | Refinements | 2023-07-24 | 2023-07-28 | bar: 2027-07-01 Wk 30
SP005 | Optimisation | 2023-07-24 | 2023-07-28 | bar: 2027-07-01 Wk 30
SP006 | Local supplier engagement | 2023-07-24 | 2023-07-28 | bar: 2027-07-01 Wk 30

## Progress to date
NB - this is just an example/illustrative of progress to date. Please provide something that best shows your project's progress to date
Ref | Activity | Planned start | Planned end | Actual start (or latest estimate) | Actual end (or latest estimate) | Planned % completion to date | Actual % completion to date | Planned budget | Actual budget (or latest estimate) | Planned spend to date | Actual spend to date | Notes / comments / further considerations
Site selection
SS001 | Outline design
SS002 | Site search criteria
SS003 | Site search
SS004 | Site shortlisting
SS005 | Site negotiations
SS006 | Environmental considerations
Planning / FEED
PF001 | Full design
PF002 | Planning application
PF003 | Planning decision
PF004 | Optimised design
PF005 | Selecting builder
PF006 | Contracts
Construction
CN001 | Manufacturing design
CN002 | Optimisation
CN003 | Building works
CN004 | Highways works
CN005 | Regulatory requirements
CN006 | Recruitment
CN007 | Machinery ordering
Setup phase
SP001 | Final factory fit out
SP002 | Training of staff
SP003 | First line established
SP004 | Refinements
SP005 | Optimisation
SP006 | Local supplier engagement

## Risk Register
Risk Register
A risk register should be completed for the project as a whole, covering all risks to the project (e.g. delivery risks, fraud risks, supplier risks etc). The Risk Rating should be provided in line with the Risk Rating Guidance tab provided as part of this template. This template can be expanded as necessary.
Risk No. | Risk Name | Risk Event Description Use definition convention "There is a risk that…" | Risk Cause Description Use definition convention "This could be caused by…" | Risk Effect Description Use definition convention "This could lead to…" | Risk Rating (After Mitigation) | Mitigation 1 Description | Mitigation 2 Description

## Risk Rating Guidance
Risk Register Guidance
The risk register should use the following conventions for Risk Rating, combining the likelihood of a risk happnening and the impact it may have if it does happen. The risk rating should be made after the proposed mitigations have been taken into account.
Impact of Risk
Risk Likelihood | Very low Impact | Low Impact | Medium Impact | High Impact | Very High Impact
Very Unlikely (Under 10% Chance) | Very Unlikely / Very Low Impact | Very Unlikely / Low Impact | Very Unlikely / Medium Impact | Very Unlikely / High Impact | Very Unlikely / Very High Impact
Unlikely (10-35% Chance) | Unlikely / Very Low Impact | Unlikely / Low Impact | Unlikely / Medium Impact | Unlikely / High Impact | Unlikely / Very High Impact
Possible (35 - 65% Chance) | Possible / Very Low Impact | Possible / Low Impact | Possible / Medium Impact | Possible / High Impact | Possible / Very High Impact
Likely (65 - 90% Chance) | Likely / Very Low Impact | Likely / Low Impact | Likely / Medium Impact | Likely / High Impact | Likely / Very High Impact
Very Likely (Over 90% Chance) | Very Likely / Very Low Impact | Very Likely / Low Impact | Very Likely / Medium Impact | Very Likely / High Impact | Very Likely / Very High Impact