## Cover Sheet
Cover Sheet
Grant Scheme Name | Engagement for Change Fund
Organisation Name: | Organisation A
Author(s): | J. Bloggs
Please ensure you read the Instruction worksheet in full prior to completing this template.

## Instructions
Instructions
It is recommended that applicants view the Example Engagement for Change Budget & Programme Plan Tool available at:
Please note, a Development Year has been built into the Engagement for Change Fund, allowing successful applicants to refine and deepen the development of their programme plan. It is expected that the Budget & Programme Plan for Years 2 and 3 will be refined and edited ahead of the respective financial years.
Figures recorded in the Budget Tabs need to include any irrecoverable VAT you incur.
For Staff costs, please include Employer's NI, any pension and bonuses. Please ensure staff costs are inserted in the dedicated section in the Budget Tabs.
As a general rule - sections of the tables in white need completing and sections in light blue are automated and do not require your input. Applicants should review this before submission.
Please profile budget spend from grant commencement date and before the end of the financial year for each respective year of delivery.
The Financial Methodology - Budget Tabs should correlate with the Delivery Plan, e.g. expenditure costs are clearly named, clearly associated with activities stated within the delivery plan or costs aligned to quarterly delivery.
Please provide explanatory commentary in the notes section to provide justification to expenditure cost.
You should make quarterly and financial year totals clear - NIO standard practice is to pay in arrears and has a financial year of 1 April-31 March.
Funding requests should meet the objectives of the grant schemes, refer to grant scheme application documents. Funding requests should not be used to cover the direct costs of delivering business-as-usual operations.

## Development Year Plan
Delivery Plan | 2026-07-26 |  |  |  |  | 2026-08-01 |  |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  |  | 2026-12-01 |  |  |  | 2027-01-01 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | Notes
Key Milestones | w/c 1st | w/c 6th | w/c 13th | w/c 20th | w/c 27th | w/c 3rd | w/c 10th | w/c 17th | w/c 24th | w/c 31st | w/c 7th | w/c 14th | w/c 21st | w/c 28th | w/c 5th | w/c 12th | w/c 19th | w/c 26th | w/c 2nd | w/c 9th | w/c 16th | w/c 23rd | w/c 30th | w/c 7th | w/c 14th | w/c 21st | w/c 28th | w/c 4th | w/c 11th | w/c 18th | w/c 25th | w/c 1st | w/c 8th | w/c 15th | w/c 22nd | w/c 1st | w/c 8th | w/c 15th | w/c 22nd | w/c 29th
Milestone 1: Project Mobilisation
Onboard Project Staff | bar: 2026-07-26 w/c 1st to 2026-07-26 w/c 27th
Establish internal processes and reporting frameworks | bar: 2026-07-26 w/c 20th to 2026-07-26 w/c 27th
Purchase Zoom subscription | bar: 2026-07-26 w/c 27th
Budget Allocation
Staff Costs
Zoom Business Costs
Core Operating Costs
Purchase of Office Suit/Google Suite
Milestone 2: Programme Design
Online sector engagements | bar: 2026-08-01 w/c 3rd to 2026-08-01 w/c 10th; 2026-11-01 w/c 2nd to 2026-11-01 w/c 9th; 2027-02-01 w/c 8th to 2027-02-01 w/c 15th; 2027-03-01 w/c 8th to 2027-03-01 w/c 15th
In-person sector engagements | bar: 2026-09-01 w/c 21st to 2026-09-01 w/c 28th; 2026-10-01 w/c 12th to 2026-10-01 w/c 19th; 2026-11-01 w/c 16th; 2027-01-01 w/c 18th to 2027-01-01 w/c 25th; 2027-02-01 w/c 15th to 2027-02-01 w/c 22nd
Develop core programming content and specifics | bar: 2026-08-01 w/c 17th to 2026-08-01 w/c 31st; 2026-09-01 w/c 21st to 2026-09-01 w/c 28th; 2026-10-01 w/c 12th to 2026-10-01 w/c 26th; 2026-11-01 w/c 16th to 2026-11-01 w/c 30th; 2027-02-01 w/c 1st to 2027-02-01 w/c 8th; 2027-03-01 w/c 15th to 2027-03-01 w/c 29th
Develop strategy for reaching diverse cohorts | bar: 2026-11-01 w/c 23rd to 2026-12-01 w/c 7th; 2027-02-01 w/c 22nd to 2027-03-01 w/c 8th
Compile end of year report | bar: 2027-03-01 w/c 15th to 2027-03-01 w/c 22nd
Submit final budget claim | bar: 2027-03-01 w/c 22nd
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for sector engagements
Projecter Hire for sector engagement
Catering for sector engagements
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs

## Development Year Budget
BUDGET TOOL - FINANCIAL METHODOLOGY
BUDGET DRAWDOWN SCHEDULE (Max. £25,000)
| Insert requested cost per item under the relevant drawdown window (funding must be spent by the end of periods stipulated to qualify for draw down) | Upfront (Max. £12,500) | 2026-11-01 | 2027-03-01 | Budget Total Year 1 (Development Year) 26/27
| Expenses / Item Costs |  |  |  |  | Notes
| Zoom Business Costs | 52 | 52 | 53.46 | 157.46 | 9 months of Zoom Business inclusive of VAT = £157.46 for online engagements
| Staff travel expenses |  | 450 | 450 | 900 | Staff travel may include bus, train, or car. £100 per month has been allocated (July-March) Bus and train tickets will be retained as evidence of expenditure. If cars are used, staff will be reimbursed for mileage at the standard rate of 45p per mile for the first 10,000 miles in a tax year. It is not expected that 10,000 miles will be exceeded.
| Venue Hire for sector engagements |  | 750 | 500 | 1250 | As per delivery plan, 5 in-person sector engagement events will be held. £250 per venue has been allocated based on predicted costs.
| Projecter Hire for sector engagement |  | 300 | 200 | 500 | Hiring of a projector and screen for 5 in-person sector engagement events. £100 per day
| Catering for sector engagements |  | 350 | 350 | 700 | Light refreshments will be provided at sector engagements e.g., tea and biscuits. It is expected that 20 people will be engaged per event. Refreshments will be £7 per head. I.e., 5 x 20 x £7
| Accessibility support |  | 300 | 500 | 800 | It is expected that some of the individuals engaged in sector engagements will require accessibility support e.g., support with bus fares, physical assistance, sign language provision. Individual costs will be expensed as proof of spend.
| Staff subsistence |  | 85 | 85 | 170 | Staff are expected to spend a maximum of 20 days off-site during the development year, engaging with the sector. Staff will leave from home each morning and return later in the day. A rate of £4.25 has been applied. I.e., 20 days x 2 staff members x £4.25 = £170
| Purchase of Office Suit/Google Suite | 202.8 | 202.8 | 202.8 | 608.4 | Based on 9 months of provision for 4 users
| Expenses / Item Costs (overwrite as you see fit) |  |  |  | 0
| Expenses / Item Costs (overwrite as you see fit) |  |  |  | 0
| TOTAL Non-Staff / Non-Core costs | 254.8 | 2489.8 | 2341.26 | 5085.86
| Core Operating Costs |  |  |  |  | Notes
| Contribution to Organisation A Core Operating Costs | 833 | 833 | 834 | 2500 | Request for 10% of total funding in Year 1 to be directed towards Core Operating Costs for Organisation A. This includes contribution to utilities and insurance. Organisation A receives funding from other sources which cover 58% of organisation utilities and insurance costs. Funding granted from the Engagement for Change Fund will not duplicate funding already received by Organisation A. Copies of other Funding Arrangements will be provided.
| TOTAL Core-Operating costs | 833 | 833 | 834 | 2500
| Staff Costs (incl Employers NI, Bonuses & Pension) |  |  |  |  | Notes
| Programme Manager at Organisation A | 900 | 900 | 900 | 2700 | Responsible for strategic oversight, governance, budget management, reporting to organisational board and Funders. Expected 10 hours per month (July - March) at £30 per hour, i.e., 90hrs x £30 = £2,700 Costs inclusive of Employer's NI and pension contribution
| Engagement for Change Programme Lead at Organisation A | 3000 | 3000 | 3000 | 9000 | Responsible for programme development in Year 1, planning for delivery commencement in Year 2. Including, community outreach and sector engagement. Expected 40 hours per month (July-March) at £25 per hour, i.e., 315hrs x £25 = £9000 Costs inclusive of Employer's NI and pension contribution
| Engagement for Change Programme Support at Organisation A | 1200 | 1200 | 1200 | 3600 | Responsible for supporting programme development. Expected 20 hours per month (July-March) at £20 per hour, i.e., 180 hrs x £20= £3600 Costs inclusive of Employer's NI and pension contribution
| Administration Officer at Organisation A | 675 | 675 | 675 | 2025 | Responsible for programme-related administration and diary management . Expected 15 hours per month (July-March) at £15 per hour, i.e., 135hrs x £15 = £2,025 Costs inclusive of Employer's NI and pension contribution
0
0
0
0
0
0
| TOTAL Staff costs | 5775 | 5775 | 5775 | 17325
| TOTAL COSTS | 6862.8 | 9097.8 | 8950.26 | 24910.86
Budget Total Costs

## Year 2 Plan
Delivery Plan | 2027-04-01 |  |  |  |  | 2027-05-01 |  |  |  |  | 2027-06-01 |  |  |  | 2027-07-01 |  |  |  | 2027-08-01 |  |  |  |  | 2027-09-01 |  |  |  | 2027-10-01 |  |  |  | 2027-11-01 |  |  |  |  | 2027-12-01 |  |  |  | 2028-01-01 |  |  |  |  | 2028-02-01 |  |  |  | 2028-03-01 |  |  |  | Notes
Key Milestones | w/c 1st | w/c 5th | w/c 12th | w/c 19th | w/c 26th | w/c 3rd | w/c 10th | w/c 17th | w/c 24th | w/c 31st | w/c 7th | w/c 14th | w/c 21st | w/c 28th | w/c 5th | w/c 12th | w/c 19th | w/c 26th | w/c 2nd | w/c 9th | w/c 16th | w/c 23th | w/c 30th | w/c 6th | w/c 13th | w/c 20th | w/c 27th | w/c 4th | w/c 11th | w/c 18th | w/c 25th | w/c 1st | w/c 8th | w/c 15th | w/c 22nd | w/c 29th | w/c 6th | w/c 13th | w/c 20th | w/c 27th | w/c 3rd | w/c 10th | w/c 17th | w/c 24th | w/c 31st | w/c 7th | w/c 14th | w/c 21st | w/c 28th | w/c 6th | w/c 13th | w/c 20th | w/c 27th
Milestone 1: Delivery of Module 1
Participant onboarding | bar: 2027-04-01 w/c 1st to 2027-04-01 w/c 12th
Delivery in-person | bar: 2027-04-01 w/c 19th to 2027-05-01 w/c 3rd
Delivery online | bar: 2027-05-01 w/c 10th to 2027-05-01 w/c 24th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 2: Delivery of Module 2
Delivery in-person | bar: 2027-06-01 w/c 14th to 2027-06-01 w/c 28th
Delivery online | bar: 2027-07-01 w/c 5th to 2027-07-01 w/c 19th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 3: Delivery of Module 3
Delivery in-person | bar: 2027-09-01 w/c 6th to 2027-09-01 w/c 20th
Delivery online | bar: 2027-09-01 w/c 27th to 2027-10-01 w/c 11th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 4: Delivery of Module 4
Delivery in-person | bar: 2027-11-01 w/c 1st to 2027-11-01 w/c 15th
Delivery online | bar: 2027-11-01 w/c 22nd to 2027-12-01 w/c 6th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 5: Delivery of Module 5
Delivery in-person | bar: 2028-01-01 w/c 17th to 2028-01-01 w/c 31st
Delivery online | bar: 2028-02-01 w/c 7th to 2028-02-01 w/c 21st
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 6: Programme Finish and Administration
Collect impact measurement data | bar: 2028-02-01 w/c 28th to 2028-03-01 w/c 13th
Compile end of year report | bar: 2028-03-01 w/c 13th to 2028-03-01 w/c 20th
Submit final budget claim
Budget Allocation
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs

## Year 2 Budget
BUDGET TOOL - FINANCIAL METHODOLOGY
BUDGET DRAWDOWN SCHEDULE (Max. £25,000)
| Insert requested cost per item under the relevant drawdown window (funding must be spent by the end of periods stipulated to qualify for draw down) | Upfront (Max. £12,500) | 2027-07-01 | 2027-11-01 | 2028-03-01 | Budget Total Year 2 27/28
| Expenses / Item Costs | [5 empty] | Notes
| Zoom Business Costs | 209.95 |  |  |  | 209.95 | 12 months of Zoom Business inclusive of VAT = £209.95 for online engagements
| Staff travel expenses | 200 | 250 | 450 | 900 | 1800 | Staff travel may include bus, train, or car. £150 per month has been allocated. Bus and train tickets will be retained as evidence of expenditure. If cars are used, staff will be reimbursed for mileage at the standard rate of 45p per mile for the first 10,000 miles in a tax year. It is not expected that 10,000 miles will be exceeded.
| Venue Hire for Programming Delivery | 500 | 500 | 500 | 1000 | 2500 | As per delivery plan, we will primarily use our own building for the delivery of programming. However. programming will include on-location delivery across 10 days. £250 per venue per day has been included based on predicated costs. Costs will be finalised during Year 1.
| Engagement materials e.g., print outs to support accessibility |  |  | 150 | 150 | 300 | To support accessibility, we will print material for those participants who require it. We estimate this will require 150 copies across delivery at £2 per copy. Costs will be finalised during Year 1.
| Accessibility support |  | 300 | 300 | 600 | 1200 | It is expected that some of the programming participants engaged will require accessibility support e.g., support with bus fares, physical assistance, sign language provision. Individual costs will be expensed as proof of spend.
| Staff subsistence |  |  | 85 | 85 | 170 | Staff are expected to spend a maximum of 20 days off-site during the Year 2. Staff will leave from home each morning and return later in the day. A rate of £4.25 has been applied. I.e., 20 days x 2 staff members x £4.25 = £170
| Purchase of Office Suit/Google Suite | 811.2 |  |  |  | 811.2 | Based on 12 months of provision for 4 users
0
0
0
| TOTAL Non-Staff / Non-Core costs | 1721.15 | 1050 | 1485 | 2735 | 6991.15
| Core Operating Costs | [5 empty] | Notes
| Contribution to Organisation A Core Operating Costs |  | 833 | 833 | 834 | 2500 | Request for 10% of total funding in Year 2 to be directed towards Core Operating Costs for Organisation A. This includes contribution to utilities and insurance. Organisation A receives funding from other sources which cover 58% of organisation utilities and insurance costs. Funding granted from the Engagement for Change Fund will not duplicate funding already received by Organisation A. Copies of other Funding Arrangements will be provided.
| TOTAL Core-Operating costs | 0 | 833 | 833 | 834 | 2500
| Staff Costs (incl Employers NI, Bonuses & Pension) | [5 empty] | Notes
| Programme Manager at Organisation A |  |  | 1800 | 1800 | 3600 | Responsible for strategic oversight, governance, budget management, reporting to organisational board and Funders. Expected 10 hours per month at £30 per hour, i.e., 120hrs x £30 = £3,600 Costs inclusive of Employer's NI and pension contribution
| Engagement for Change Programme Lead at Organisation A |  | 2750 | 2750 | 5500 | 11000 | Responsible for programme delivery. Expected 40 hours per month, excluding December, at £25 per hour, i.e., 480hrs x £25 = £11,000. Costs inclusive of Employer's NI and pension contribution
| Engagement for Change Programme Support at Organisation A |  | 275 | 275 | 550 | 1100 | Responsible for supporting programme delivery when lead is unavailable. Expected 5 hours per month, excluding December at £20 per hour, i.e., 55hrs x £20= £1,100 Costs inclusive of Employer's NI and pension contribution
| Administration Officer at Organisation A |  | 540 | 540 | 1080 | 2160 | Responsible for programme-related administration and diary management . Expected 12 hours per month at £15 per hour, i.e., 144hrsx £15 = £2160 Costs inclusive of Employer's NI and pension contribution
| Role (overwrite as you see fit) |  |  |  |  | 0
| Role (overwrite as you see fit) |  |  |  |  | 0
| Role (overwrite as you see fit) |  |  |  |  | 0
| Role (overwrite as you see fit) |  |  |  |  | 0
| Role (overwrite as you see fit) |  |  |  |  | 0
| Role (overwrite as you see fit) |  |  |  |  | 0
| TOTAL Staff costs | 0 | 3565 | 5365 | 8930 | 17860
| TOTAL COSTS | 1721.15 | 4615 | 6850 | 11665 | 24851.15
Budget Total Costs

## Year 3 Plan
Delivery Plan | 2028-04-01 |  |  |  | 2028-05-01 |  |  |  |  | 2028-06-01 |  |  |  | 2028-07-01 |  |  |  |  | 2028-08-01 |  |  |  | 2028-09-01 |  |  |  | 2028-10-01 |  |  |  |  | 2028-11-01 |  |  |  | 2028-12-01 |  |  |  | 2029-01-01 |  |  |  |  | 2029-02-01 |  |  |  | 2029-03-01 |  |  |  | Notes
Key Milestones | w/c 3rd | w/c 10th | w/c 17th | w/c 24th | w/c 1st | w/c 8th | w/c 15th | w/c 22nd | w/c 29th | w/c 5th | w/c 12th | w/c 19th | w/c 26th | w/c 3rd | w/c 10th | w/c 17th | w/c 24th | w/c 31st | w/c 7th | w/c 14th | w/c 21st | w/c 28th | w/c 4th | w/c 11th | w/c 18th | w/c 25th | w/c 2nd | w/c 9th | w/c 16th | w/c 23rd | w/c 30th | w/c 6th | w/c 13th | w/c 20th | w/c 27th | w/c 4th | w/c 11th | w/c 18th | w/c 25th | w/c 1st | w/c 8th | w/c 15th | w/c 22nd | w/c 29th | w/c 5th | w/c 12th | w/c 19th | w/c 26th | w/c 5th | w/c 12th | w/c 19th | w/c 26th
Milestone 1: Delivery of Module 1
Participant onboarding | bar: w/c 3rd to w/c 17th
Delivery in-person | bar: w/c 24th to w/c 8th
Delivery online | bar: w/c 15th to w/c 29th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 2: Delivery of Module 2
Delivery in-person | bar: w/c 19th to w/c 3rd
Delivery online | bar: w/c 10th to w/c 24th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 3: Delivery of Module 3
Delivery in-person | bar: w/c 11th to w/c 25th
Delivery online | bar: w/c 2nd to w/c 16th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 4: Delivery of Module 4
Delivery in-person | bar: w/c 6th to w/c 20th
Delivery online | bar: w/c 27th to w/c 11th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 5: Delivery of Module 5
Delivery in-person | bar: w/c 22nd to w/c 5th
Delivery online | bar: w/c 12th to w/c 26th
Budget Allocation
Zoom Business Costs
Staff travel expenses
Venue Hire for Programming Delivery
Engagement materials e.g., print outs to support accessibility
Accessibility support
Staff subsistence
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs
Milestone 6: Programme Finish and Administration
Collect impact measurement data | bar: w/c 5th to w/c 19th
Compile end of year report | bar: w/c 19th to w/c 26th
Submit final budget claim
Budget Allocation
Purchase of Office Suit/Google Suite
Staff costs
Core operating costs

## Year 3 Budget
BUDGET TOOL - FINANCIAL METHODOLOGY
BUDGET DRAWDOWN SCHEDULE (Max. £50,000)
| Insert requested cost per item under the relevant drawdown window (funding must be spent by the end of periods stipulated to qualify for draw down) | Upfront (Max. £12,500) | 2028-07-01 | 2028-11-01 | 2029-03-01 | Budget Total Year 3 28/29
| Expenses / Item Costs | [5 empty] | Notes
| Zoom Business Costs | 209.95 |  |  |  | 209.95 | 12 months of Zoom Business inclusive of VAT = £209.95 for online engagements
| Staff travel expenses | 500 | 500 | 500 | 1500 | 3000 | Staff travel may include bus, train, or car. £250 per month has been allocated. Bus and train tickets will be retained as evidence of expenditure. If cars are used, staff will be reimbursed for mileage at the standard rate of 45p per mile for the first 10,000 miles in a tax year. It is not expected that 10,000 miles will be exceeded.
| Venue Hire for Programming Delivery | 625 | 625 | 1250 | 2500 | 5000 | As per delivery plan, we will primarily use our own building for the delivery of programming. However. programming will include on-location delivery across 20 days. £250 per venue per day has been included based on predicated costs. Costs will be finalised during Year 2.
| Engagement materials e.g., print outs to support accessibility |  |  | 300 | 300 | 600 | To support accessibility, we will print material for those participants who require it. We estimate this will require 300 copies across delivery at £2 per copy. Costs will be finalised during Year 2.
| Accessibility support |  |  | 600 | 600 | 1200 | It is expected that some of the programming participants engaged will require accessibility support e.g., support with bus fares, physical assistance, sign language provision. Individual costs will be expensed as proof of spend.
| Staff subsistence |  |  | 85 | 85 | 170 | Staff are expected to spend a maximum of 20 days off-site during the Year 3. Staff will leave from home each morning and return later in the day. A rate of £4.25 has been applied. I.e., 20 days x 2 staff members x £4.25 = £170
| Purchase of Office Suit/Google Suite | 811.2 |  |  |  | 811.2 | Based on 12 months of provision for 4 users
0
0
0
| TOTAL Non-Staff / Non-Core costs | 2146.15 | 1125 | 2735 | 4985 | 10991.15
| Core Operating Costs | [5 empty] | Notes
| Contribution to Organisation A Core Operating Costs |  | 833 | 833 | 834 | 2500 | Request for 5% of total funding in Year 3 to be directed towards Core Operating Costs for Organisation A. This includes contribution to utilities and insurance. Organisation A receives funding from other sources which cover 58% of organisation utilities and insurance costs. Funding granted from the Engagement for Change Fund will not duplicate funding already received by Organisation A. Copies of other Funding Arrangements will be provided.
0
0
0
0
0
0
0
0
0
| TOTAL Core-Operating costs | 0 | 833 | 833 | 834 | 2500
| Staff Costs (incl Employers NI, Bonuses & Pension) | [5 empty] | Notes
| Programme Manager at Organisation A |  |  | 3840 | 3840 | 7680 | Responsible for strategic oversight, governance, budget management, reporting to organisational board and Funders. Expected 20 hours per month at £32 per hour, i.e., 240hrsx £32 = £7,680 Costs inclusive of Employer's NI and pension contribution
| Engagement for Change Programme Lead at Organisation A |  |  | 9360 | 9360 | 18720 | Responsible for programme delivery. Expected 60 hours per month at £26 per hour, i.e., 720hrs x £26 = £18,720 Costs inclusive of Employer's NI and pension contribution
| Engagement for Change Programme Support at Organisation A |  |  | 1890 | 1890 | 3780 | Responsible for supporting programme delivery when lead is unavailable. Expected 15 hours per month at £21 per hour, i.e., 180hrs x £21 = £3,780 Costs inclusive of Employer's NI and pension contribution
| Administration Officer at Organisation A |  |  | 2400 | 2400 | 4800 | Responsible for programme-related administration and diary management . Expected 25 hours per month at £16 per hour, i.e., 300hrsx £16 = £4,800 Costs inclusive of Employer's NI and pension contribution
| Programming Lead/Manager at Organisation B |  |  | 1250 |  | 1250 | Responsible for securing access to participants from [e.g., geographic area] and supporting delivery in area. Expected 25 hours across 2 months at £25 per hour, i.e., 50hrs x £25 = £1,250
| Programming Lead/Manager at Organisation C |  |  |  | 1250 | 1250 | Responsible for securing access to participants from [e.g., geographic area] and supporting delivery in area. Expected 25 hours across 2 months at £25 per hour, i.e., 50hrs x £25 = £1,250
| Programming Lead/Manager at Organisation C |  |  |  | 1250 | 1250 | Responsible for securing access to participants from [e.g., geographic area] and supporting delivery in area. Expected 25 hours across 2 months at £25 per hour, i.e., 50hrs x £25 = £1,250
0
0
0
| TOTAL Staff costs | 0 | 0 | 18740 | 19990 | 38730
| TOTAL COSTS | 2146.15 | 1125 | 21475 | 24975 | 49721.15
Budget Total Costs

## General Note
General Note - Financial Requirements
1.1 Please note that NIOs’ financial year runs from 1 April to 31 March. If successful, funding requests and budgets must not exceed the financial year.
1.2 Payments will, by default, be made in arrears, unless otherwise discussed and agreed.
1.3 The Budget Tabs should set out a working budget request for the programme proposal.
1.4 If successful, a payment schedule will be agreed as part of the development of the grant agreement. To make a claim, each claim must comprise of: (a) the Recipient’s ‘’Budget Tab’’ for the respective financial year, providing a breakdown of actual costs incurred during the period claimed for and planned costs for the remainder of the Grant Period; (b) a ‘’Grant Payment Request Form’’ signed by an authorised finance officer. The form confirms the actual cost incurred and to be claimed for and related to the costs declared within the Budget Management Tool; (c) a performance report detailing actual progress against the Delivery Plan as set out in the Recipient’s application; and, (d) evidence of eligible expenditure e.g. invoices / statements of work / defrayal. Recipients will need to request a claim within five (5) working days of grant claim date stipulated in the payment schedule. NIO will only pay the amount that can be evidenced as spent. Grant claims will be paid within 30 days of receipt of a valid, undisputed invoice.
1.5 Variations between proposed drawdown amounts and actual drawdown requests across months or stipulated period of the same financial year will be accepted, with explanation and justification. Any funds not drawn down by the end of the financial year will become unavailable.
1.6 You must be able to transparently report on a monthly basis or stipulated period and provide evidence of expenditure for the use of the fund. The fund must be shown as restricted funds in your accounts and you must be able to identify separately the value and purpose of the grant in your audited accounts.