# TERMS OF REFERENCE (TOR)
## English Language Training Contract – Central Asia (FY 2026–2027)
Contract Overview
This contract is part of a programme to deliver a three-year English Language Training (ELT) initiative across Kazakhstan, Kyrgyzstan, and Tajikistan. This contract will encompass the first 6 months of the programme with a possibility to extend, subject to budget availability. The programme aims to enhance interoperability and support institutional capacity building through improved English language proficiency.
Contract Objectives
The overall objective is to strengthen institutional self-reliance and improve English language capability across partner defence institutions.

Specific objectives include:
- Improving English language proficiency among military and security personnel to at least B1 level (CEFR)
- Developing sustainable, in-country English language instructional capacity

Beneficiaries
The beneficiaries of the training will be staff from the organisations below, who normally speak local languages (Kazakh, Kyrgyz and Tajik) and /or Russian as the dominant regional language. Hence the teaching team should know the above languages.
### Kazakhstan
  - Peacekeeping Centre (KAZCENT)
### Kyrgyzstan
Border Service
### Tajikistan
1. Ministry of Defence (General Staff and Main Office)
2. National Guard
Scope and Delivery Targets
The programme will deliver structured English language training and instructor development across partner institutions.

### Kazakhstan
KAZCENT: Provide hybrid form of mentorship and development of up to 10 English Language Instructors to train up to 30 pax of peacekeeping contingent per FY.
### Kyrgyzstan
Border Service: Train up to 20 personnel annually to B1 level per FY
### Tajikistan
- Ministry of Defence: Train up to 40 personnel annually to B1 level per FY
- National Guard: Train up to 20 personnel annually to B1 level per FY

Timeline
This contract will run from 1 October 2026 to 31 March 2027 with potential extension. The contract extension is subject to satisfactory performance, achievement of milestones, and approval of submitted progress reports.
All milestones and the corresponding progress report shall be submitted to the Project Officer no later than 20 March 2027.
Inception and Mobilisation (FY Oct 2026– Mar 27)
- 35-day inception period (planning and resource mobilisation)
- 35-day mobilisation phase (deployment and establishment)
- Commencement of training delivery
Phase 2 – Full Delivery (FY Apr 2027– Oct 27) (potential extension period)
- Full implementation of training across all partner locations
- Continuous monitoring and adaptation
Budget and Funding
- Funding will be managed jointly by the UK Central Asia team and UK Defence Section
- The Supplier will be responsible for financial management, reporting, and compliance across all jurisdictions
- A detailed budget breakdown and financial reporting framework will form part of the contract
- Commencement of training delivery
Payment structure: Monthly Payment in arrears. Subsequent payments are subject to satisfactory performance and reports. Payment includes transport charge and internet.
The Supplier shall be entitled to receive the first payment instalment, after written confirmation by the Authority that the Supplier has reached Inception period (35 days) and provided an Inception report with following actions:
1. Submit a comprehensive Programme Management Plan, including delivery approach, timeline, resource plan, risk management framework, staffing and instructor deployment plan;
2. Provide a draft English Language Training delivery framework aligned to CEFR B1 objectives, including curriculum outline and assessment approach
3. Appointment of key personnel and agreement of reporting arrangements with Defence Section
4. Initial engagement with partner institutions, including confirmation of delivery locations, key contacts, and initial list of materials and equipment approved by Defence Section;
5. Establish a Monitoring and Evaluation system aligned to agreed KPIs, including data collection tools and reporting templates
6. The Authority reserves the right to withhold payment where these requirements are not met in full or where submitted deliverables are deemed unsatisfactory.

In the event the contract is extended for an additional 6 months the payment structure maybe adjusted to quarterly payments.

Roles and Responsibilities
### UK MOD
- Programme ownership and oversight
- Define and approve objectives and curriculum
- Manage partner relationships
- Monitor performance and approve key decision
### Supplier
- Design and deliver training curriculum
- Provide qualified instructors and teaching materials
- Subcontract qualified teachers in Kyrgyzstan and Tajikistan and, if necessary, in Kazakhstan to support delivery of in-country training services.
- Manage logistics, HR, and subcontractors
- Ensure compliance with legal, tax, and regulatory requirements
- Deliver monitoring and evaluation reporting
### Partner Institutions
- Provide facilities and access
- Nominate suitable participants/students
- Support delivery and attendance of lessons
- Appoint a dedicated point of contact

Methodology and Delivery Approach
The Supplier is expected to propose an effective delivery model including:
- In-person or online English language training in Tajikistan Ministry of Defence 3x/week, 1.5 hr
- In-person or online English language training in Tajikistan National Guard 3x/week, 1.5hr
- In-person or online English language training in Kyrgyzstan Border Service 5×/week, 1.5 hrs, 1800-1930
- In-person or online support KAZCENT Instructor mentoring and developing, 5 days a week, 7 hrs, from 0900 to 1700
- Continuous assessment and adaptive learning approaches
- Integration with operational and professional contexts

Travel
## While local presence or subcontractors may be utilised, we expect the Supplier’s personnel to travel to Kyrgyzstan and Tajikistan for the recruiting interviews and further once in a quarter to monitor and assess the delivery of services, including providing in-person support to subcontractors in each country where required. The report of visits to both countries should be sent to the Project Officer within 10 days after return.
## Exceptionally, and subject to agreement with the programme team, online learning/monitoring/overview may be considered.
Materials and Equipment
All materials and equipment required for the execution of the assignment shall, where applicable, be transferred to the Supplier for the duration of the current programme from the preceding project. The Supplier shall take full responsibility for the receipt, management, and utilisation of such transferred items as per Annex C.
Where additional materials and/or equipment are deemed necessary for the proper implementation of the services, the Supplier shall be entitled to procure such items. Any procurement of additional materials or equipment shall be subject to prior justification and submission of a written rationale to the Project Officer and shall only proceed upon review and written approval.

Flexibility and Adaptation
The programme will maintain a flexible delivery model to respond to changing partner needs.
- Delivery will be reviewed at the end of Q2, and any extension period.
- Adjustments to locations, participant groups, and delivery formats may be made in agreement with the Project Officer.
- UK MOD reserves the right to amend, extend, or terminate the programme within the agreed timeframe

Monitoring, Evaluation, Reporting and KPIs
The Supplier will implement a robust Monitoring and Evaluation (M&E) framework, including:
- Baseline assessments of language proficiency to be conducted at the start of each teaching rotation
- Regular progress tracking and reporting monthly to include a narrative report for each cohort (learning group), storyboard (pictures), attendance statistics, individual progress report on each learner.
- End-of-course evaluations
- Final programme evaluation
- Financial report at the end of every month sent to the UK MOD
Performance data will inform continuous improvement and programme decision-making.
KPIs are listed at Annex B

Risk Management
Key risks include:
- Political and security instability
- Limited access to partner institutions
- Varying levels of partner engagement
- Language and cultural barriers
The Supplier must implement risk mitigation measures and maintain a live risk register throughout delivery.

Sustainability and Exit Strategy
The programme will prioritise sustainability through:
- Development of local English language instructors
- Transfer of teaching materials and methodologies
- Institutional capacity building
The programme aims to establish partner institutions capable of independently delivering ELT. This contract forms the initial process for developing that objective.

Cross-Cutting Requirements
The programme will comply with all relevant UK Government policies, including:
Modern Slavery
- Compliance with the Modern Slavery Act 2015
- Supply chain due diligence

Duty of Care
- Risk management and supplier protection
- Safe operating environments

Disability Inclusion
Proportionate and practical inclusion measures

Social Value
Contribution to local capacity building and sustainable outcomes

Transparency
Accurate financial reporting and visibility of fund flows

Delivery Chain Mapping
- Full visibility of subcontractors and delivery partners
- Ongoing monitoring and assurance

Definitions and Acronyms
- ELT – English Language Training
- FY – Financial Year
- ISF – Integrated Security Fund
- UK MOD – United Kingdom Ministry of Defence
- B1 – Intermediate level (Common European Framework of Reference for Languages)

## Annex A - Programme Background & Context

The UK Ministry of Defence (UK MOD) English Language Training Programme, implemented in Kazakhstan, Tajikistan, and Kyrgyzstan was designed to enhance the English language proficiency of military and civilian defence personnel, thereby strengthening interoperability, professional development, and engagement in international security cooperation. In Kazakhstan, the programme placed particular emphasis on supporting peacekeeping capability development, including targeted training delivered in collaboration with the Peacekeeping Operations Training Center (KAZCENT). It provided structured language instruction aligned with recognised international standards, focusing on operational, technical, and diplomatic communication skills relevant to defence and peacekeeping contexts. The programme also supported participants in meeting the language requirements for participation in multinational exercises, UN peacekeeping operations, and overseas training opportunities. Through a combination of in-country training delivery and developing of bespoke learning resources, it contributed to sustainable institutional capacity building and fostered closer defence cooperation between the United Kingdom and partner countries in Central Asia.

This programme will be the successor to the above programme aiming to deliver a three-year English Language Training (ELT) initiative across Kazakhstan, Kyrgyzstan, and Tajikistan from October 2026 to March 2029. The contract forms part of that ambition.

Annex B - Key Performance Indicators (KPI) Schedule (to be agreed with the successful supplier)

English Language Training Contract – Central Asia (FY 2026–2027)

1. Purpose
This KPI Schedule defines the performance indicators against which the Supplier’s delivery of the English Language Training (ELT) programme will be monitored and assessed by the UK Ministry of Defence (UK MOD).
The KPIs are designed to ensure effective delivery, high-quality outcomes, and sustainable impact across all partner nations.

2. KPI Framework
The KPI framework is structured across the following categories:
1. Training Delivery
2. Learning Outcomes
3. Quality of Delivery
4. Instructor Development and Sustainability
5. Programme Management
6. Flexibility and Responsiveness
7. Risk and Compliance
8. Attendance and Engagement

3. KPI Table
3.1 Training Delivery KPIs
KPI Ref	Indicator	Target	Measurement Method	Reporting Frequency
TD1	Number of learners trained	As per agreed annual targets	Training records	Monthly
TD2	Course completion rate	≥ 75%	Attendance and completion data	Monthly
TD3	Training hours delivered	≥ 95% of planned hours	Training logs	Monthly

3.2 Learning Outcomes KPIs
KPI Ref	Indicator	Target	Measurement Method	Reporting Frequency
LO1	B1 attainment rate (CEFR)	≥ 70% of participants	Standardised language assessments	Biannual
LO2	Language progression	≥ 80% improve by at least one level	Pre- and post-course testing	Quarterly

3.3 Quality of Delivery KPIs
KPI Ref	Indicator	Target	Measurement Method	Reporting Frequency
QD1	Participant satisfaction	≥ 85% positive	Surveys	Quarterly
QD2	Partner satisfaction	≥ 80% positive	Stakeholder feedback	Quarterly
QD3	Teaching quality	Meets agreed observation standards	Lesson observations	Quarterly

3.4 Instructor Development & Sustainability KPIs (Kazakhstan Only)
KPI Ref	Indicator	Target	Measurement Method	Reporting Frequency
IS1	Local instructors trained (KAZCENT)	As agreed with UK MOD	Training logs	Quarterly
IS2	Instructor competency improvement	Demonstrable improvement	Observation reports	Quarterly
IS3	Transition readiness	Increasing proportion of partner-led delivery	Programme reviews	Quarterly
IS4	Mentoring provision	Regular structured mentoring delivered	Mentoring records	Monthly

3.5 Programme Management KPIs
KPI Ref	Indicator	Target	Measurement Method	Reporting Frequency
PM1	Reporting compliance	100% on-time submissions	Submission records	Monthly
PM2	Financial management	Within agreed budget tolerance (±5%)	Financial reports	Monthly
PM3	Staff retention	≤ 15% annual turnover	HR records	Monthly
PM4	Operational continuity	No significant disruption to delivery	Programme logs	Monthly

3.6 Flexibility & Responsiveness KPIs
KPI Ref	Indicator	Target	Measurement Method	Reporting Frequency
FR1	Responsiveness to change requests	Implemented within 30 days	Change logs	Quarterly
FR2	Implementation of review actions	≥ 90% actions delivered	Review reports	Quarterly
FR3	Alignment with partner needs	Demonstrable adaptation of delivery	Programme reviews	Quarterly

3.7 Risk & Compliance KPIs
KPI Ref	Indicator	Target	Measurement Method	Reporting Frequency
RC1	Risk register management	Updated monthly	Risk register	Monthly
RC2	Incident reporting	Reported within agreed timeframe	Incident logs	Monthly
RC3	Compliance breaches	Zero major breaches (GDPR, safeguarding, etc.)	Audit/reports	Monthly
RC4	Duty of Care compliance	All risks appropriately mitigated	Risk assessments	Monthly

3.8 Attendance & Engagement KPIs
KPI Ref	Indicator	Target	Measurement Method	Reporting Frequency
AE1	Attendance rate	≥ 85%	Attendance records	Monthly
AE2	Dropout rate	≤ 10%	Enrolment/completion data	Monthly
AE3	Learner engagement	Satisfactory participation levels	Instructor reports	Monthly

4. Performance Assessment
- KPI performance will be reviewed quarterly by UK MOD.
- Performance will be assessed using a Red / Amber / Green (RAG) rating system:
  - Green – KPI met or exceeded
  - Amber – Minor shortfall, acceptable with mitigation
  - Red – Significant underperformance requiring corrective action

5. Performance Management and Remedies
- The Supplier is required to provide improvement plans for any KPI rated Red
- Persistent underperformance may result in:
  - Enhanced monitoring
  - Contractual review
  - Financial penalties (if specified in contract)

6. Data Collection and Reporting
The Supplier shall:
- Maintain accurate and auditable performance data
- Provide KPI reports in agreed formats
- Ensure data integrity and compliance with GDPR requirements

7. Review and Amendment
UK MOD reserves the right to review and amend KPIs annually to ensure alignment with programme objectives and evolving requirements.

Annex C List of equipment and materials

Equipment	Details	Location
Acer Laptop Aspire E15	NXGVBER0118171467C7600	British Embassy Dushanbe
HP Laptop pavilion x360	Model 14-ek0033dx
Dell Inspiron 15	S/N 4RDP0P2
Acer laptop	S/N NXGVBER011817145DE7600	Local office in Almaty
HP Laptop	S/N CND0507XVC
Erson Projector	S/N X4HH8501939
HP Mouse	S/N 9CP8481M7C
HP Mouse	S/N 7CF7012J78
Sony Speaker	Model SRS-XB10
Sony Speaker	Model SRS-XB11
Sony Speaker	Model SRS-XB12
SVEN Speaker	S/N SV1710SC00676
SVEN Speaker	S/N SV1707SC18072
Hard Drive ORICO	Model 2588US3
Sony Voice recorder	Model ICD-PX240
BAR Code Scanner	S/N N18513000051
HP Printer	S/N VNH7C03752
Epson Printer	S/N UB7Y012222
LG Monitor	S/N 010NTLE3T760
Cartridges
3 Backpacks, Cables and Chargers

Books	pcs
English File Elementary SB	4
English File Elementary WB	5
English File Intermediate SB	7
English File Intermediate WB	7
English File Resource Pack CD	16
TKT Coursebook	13
English Russian Dictionaries	7
Nursing 1 SB	1
Nursing 1 TB	1
Nursing 1 CD	1
Nursing 2 SB	1
Nursing 2 TB	1
Nursing 2 CD	1
Medicine 1 SB	31
Medicine 1 TB	6
Medicine 1 CD	6
Medicine 2 SB	31
Medicine 2 TB	6
Medicine 2 CD	6
Campaign 1 SB	1
Campaign 1 WB	1
Campaign 1 TB	1
Campaign 1 Grammar	3
Campaign 2 SB	1
Campaign 2 WB	1
Campaign 2 TB	1
Campaign 3 SB	1
Campaign 3 WB	1
Campaign Vocabulary	3
Campaign Dictionary	3
At Ease English for Peacekeeping	1
Peacekeeping Operations SB	1
Peacekeeping Operations WB	1
Peacekeeping Operations TB	1
Teaching English Uniformed Personnel	1
Warfare books	8
Boardgames	3
Posters	3