Guidance Note
Completing the GSF Concept Note Template

Purpose of this guidance
This document explains how to complete each section of the Concept Note template in a clear, concise and evidence-based way. It is designed for applicants who may not have prior knowledge of the programme or internal approval process.

# Part 1: Analysis of the Concept Note Template
The Concept Note is a short, high-level proposal document designed to help reviewers decide whether a project idea should proceed to further consideration. It focuses on the strategic case for intervention rather than detailed project planning.

Template section	Purpose
Project information	Sets out the basic facts: title, value, post, contact, duration, start date and end date.
Project narrative	Explain what the project is, why it is needed and what change it aims to achieve.
Activities	Summarises the main actions the applicant will deliver.
Strategic	Shows how the project contributes to strategic objectives, priority outcomes and / relevant policy priorities.
Economic	Explains options considered, expected benefits, success measures and value for / money.
Risk	Identifies the top three risks and gives a Red, Amber or Green rating.

# Part 2: Guidance for External Implementers
A strong Concept Note answers three questions: What is the problem? Why does it matter? Why is your proposed solution the right one?

# How will the Concept Note be assessed?

Assessment theme	What will be considered
Strategic alignment	Does the project clearly support programme objectives and priority outcomes?
Need and rationale	Is there a clear problem or opportunity, supported by evidence or practical / experience?
Value for money	Are costs proportionate to the expected benefits? Has the applicant / considered alternatives?
Deliverability	Can the project realistically be delivered within the proposed budget, / timeframe and operating context?
Risk management	Are key risks clearly identified, rated and mitigated?
Sustainability	Are benefits likely to continue after funding ends?
Impact and outcomes	Is the intended change clear, meaningful and measurable?
Monitoring and / evaluation	Does the applicant explain how success will be measured?
Stakeholder engagement	Are the right partners, beneficiaries and decision-makers considered?

1. Section-by-section guidance
  1. Project information
Topic	Guidance
What is being / requested?	Project title, project value, post, contact name, duration, start date and end / date.

Why it matters	This gives reviewers a quick sense of scale, timing, accountability and feasibility.
Level of detail expected	Provide accurate information. Dates should be realistic and consistent with the / proposed activities.
Common mistakes to / avoid	Vague titles, missing contact details, dates that do not match the delivery plan, / or project values that are not clearly linked to scope.

  1. Project narrative
Question	Guidance
Word limit	250 words maximum
What is being / requested?	A concise description of the project, including the problem or opportunity, why it / matters, what the project will do and who will benefit.
Why this information is / important	This section gives reviewers their first overall impression of the proposal. It / should make a case of why the project is needed and what change it will support.
Level of detail expected	Use two or three short paragraphs. Focus on context, proposed solution and / expected outcome. Avoid detailed operational planning.

# Illustrative example only
Digital skills gaps are limiting the ability of SMEs to adopt emerging technologies and participate in higher- value sectors. The project will deliver a structured capacity-building programme for 150 SMEs through training, mentoring and practical toolkits. By strengthening organisational capability and encouraging adoption of modern digital practices, the project will support productivity, competitiveness and longer-term economic diversification.

# Common mistakes to avoid
- Describing activities only without explaining the problem.
- Using broad claims without evidence.
- Failing to identify beneficiaries or intended change.
- Including too much background information.

  1. Activities

Question	Guidance
Word limit	200 words maximum
What is being requested?	A short summary of the main activities you plan to undertake.
Why this information is important	Reviewers need to see whether the activities are practical, coherent / and clearly linked to the intended outcomes.
Level of detail expected	Group activities into stages such as mobilisation, delivery and / follow-up. Use concise bullets if helpful.

# Illustrative example only
The project will begin with a rapid needs assessment and stakeholder consultation. The delivery phase will include development of training materials, six workshops, targeted mentoring and practical resources for participating organisations. The final stage will include follow-up surveys, lessons learned and a short evaluation report summarising outputs, outcomes and recommendations.
# Common mistakes to avoid
- Listing too many small tasks.
- Not explaining how activities connect to outcomes.
- Including administrative details that do not help reviewers assess the project.
- Overpromising activities within a short timeframe.
  1. Strategic alignment
Question	Guidance
Word limit	150 words maximum
What is being requested?	A brief explanation of how the project contributes to strategic objectives, / priority outcomes, the Country Business Plan and/or relevant priorities.
Why this information is important	Funding decisions are likely to prioritise projects that clearly advance strategic objectives. Reviewers need to understand the policy relevance and why this / project is timely.
Level of detail expected	Name the relevant priority where possible, then explain the practical link / between the project and that priority. Avoid simply copying strategic language.

# Illustrative example only
The project supports economic diversification and private sector development by strengthening SME capability in digital adoption and innovation. It aligns with priorities focused on skills, enterprise growth and inclusive economic participation. The project will also create practical links between businesses, training providers and policy stakeholders, supporting longer-term collaboration beyond the funding period.
# Common mistakes to avoid
- Stating that the project is aligned without explaining how.
- Using generic language that could apply to any project.
- Ignoring local context or stakeholder relevance.

  1. Economic case and value for money
Question	Guidance
Word limit	200 words maximum
What is being requested?	A summary of options considered and their benefits, how you will know / outcomes have been achieved, and why the approach offers value for money.
Why this information is / important	Reviewers need assurance that the proposed use of funds is proportionate and / that the selected approach is better than realistic alternatives.
Level of detail expected	Briefly compare options, explain the preferred approach, identify success measures and describe why the costs are reasonable for the expected / benefits.

# Illustrative example only
Three options were considered: fully online training, in-person workshops and a blended model. The blended approach was selected because it balances reach, quality and cost efficiency. Success will be measured through completion rates, participant feedback, pre- and post-training assessments and follow-up evidence of improved organisational practice. The project offers value for money by using existing networks, limiting travel costs and producing reusable training resources.
# Common mistakes to avoid
- Treating value for money as only a budget issue.
- Failing to mention alternatives.
- Stating that the project offers value without explaining why.

  1. Risk
Question	Guidance
Word limit	100 words maximum
What is being requested?	The top three risks associated with the proposed programme, together / with a Red, Amber or Green rating.
Why this information is / important	Risk management shows whether the applicant understands delivery / challenges and has a realistic plan to manage them.

Level of detail expected	Identify only the most important risks. Include a rating and a brief / mitigation action. Use practical language.

# Illustrative example only
Key risks are: low stakeholder participation - Amber - mitigated through early engagement and targeted outreach; delays in approvals - Amber - mitigated through a clear workplan and early scheduling; limited availability of technical experts - Green - mitigated through confirmed backup facilitators and existing supplier networks.
# Common mistakes to avoid
- Listing risks without mitigation.
- Including too many minor risks.
- Using only generic risks such as “delays” without explaining cause or response.
- Rating all risks as Green when the context suggests otherwise.

Suggested response structures
Section	Suggested structure
Project narrative	Context and need -> proposed response -> expected outcome and / beneficiaries.
Activities	Mobilisation -> delivery -> follow-up and reporting.
Strategic	Relevant priority -> how the project contributes -> who benefits.
Economic	Options considered -> preferred approach -> success measures -> value / for money.
Risk	Risk -> rating -> mitigation.

6. Frequently Asked Questions Can I exceed the word limits?
No. Treat the word limits as maximum limits. Concise responses help reviewers compare applications fairly.
# Is the Concept Note a full proposal?
No. It is a short summary of the project idea. Detailed implementation plans may be requested later if the project progresses.
# Do I need a detailed budget?
Only provide detailed budget information if requested separately. Within the Concept Note, focus on value for money and proportionality.
# How much evidence is expected?
Use proportionate evidence. A short statistic, relevant example, stakeholder consultation finding or previous delivery result can strengthen the case.
# Can we propose an innovative approach?
Yes, but it should still be realistic, deliverable and linked to measurable outcomes.
# What if some risks are outside our control?
You should still identify them and explain how you will reduce, monitor or respond to them.
# Should we include partners and stakeholders?
Yes, where relevant. Explain who needs to be involved and how their participation supports delivery and impact.