## Cover
Building Safety Remediation Data Release, England: 30 June 2026
Back to Contents
Background
This publication provides data on 1) the remediation progress across MHCLG’s Building Safety Remediation portfolio, covering buildings in the ACM programme, Building Safety Fund, Cladding Safety Scheme, developer remediation contract and reported by registered providers of social housing, 2) Progress with remediation of high-rise (18 metres and over in height) residential buildings (including student accommodation and hotels) and publicly owned buildings with ACM cladding systems unlikely to meet Building Regulations in the ACM programme, 3) the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund, 4) progress with remediation of high-rise residential buildings with non-ACM cladding systems assessed as eligible for funding from the Building Safety Fund , 5) Progress with the applications for and remediation of residential buildings 11 metres and over in height in England in the Cladding Safety Scheme, 6) progress of remediation of residential buildings 11 metres and over in height with life-safety defects under the developer remediation contract, 7) progress of remediation of residential buildings 11 metres and over in height with unsafe cladding reported to be self-funded by registered providers of social housing, 8) enforcement action taken by local authorities against 11m+ residential buildings with cladding defects under the Housing Act 2004.
Tables on the ACM programme, BSF, CSS and developer remediation contract include buildings which can be in multiple schemes or data collections so counting across tables can result in double counting. Tab Combined_2 provides an overall summary of all remediation progress, without double counting.
Publication dates
The data tables in this spreadsheet were originally published on 29 July 2026.
The next publication is scheduled for 26 August 2026.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
We are committed to improving and broadening this data release further in the months ahead and would welcome feedback both on the content of this data release and what could be further done in the future.
BuildingSafetyData2@communities.gov.uk
NewsDesk@communities.gov.uk
Date published: 29 July 2026

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in tables ACM_1 and ACM_2.	ACM_3
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_4, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to complete remediation works on-site	ACM_7
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_8
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period. 19 private sector buildings are receving government funding from the Building Safety Fund or Cladding Safety Scheme, so do not appear in the totals in table ACM_9, but do in ACM_8.	ACM_8, ACM_9
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_10
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_10
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_10
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_10
[note 10]	Total figures may not sum due to rounding.	ACM_11, WWRF_1, WWRF_2, WWRF_3, WWRF_4, BSF_1, BSF_2, BSF_3, BSF_5, Combined_4, CSS_5, Estimated_1, Estimated_2
[note 11]	The first tranche of the Waking Watch Relief Fund was administered by eight local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Relief Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_2
[note 12]	The Waking Watch Replacement Fund 2022 was administered by five local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Replacement Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_3
[note 13]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2, CSS_1, CSS_2, CSS_3, CSS_4, CSS_6, Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8, / Social_1, / Social_2
[note 14]	Private sector and social sector financial viability buildings can receive pre-tender support allocation in addition to their full applications funding, but not all buildings receive this therefore these numbers cannot be added together to directly give a total.	BSF_3
[note 15]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_3
[note 16]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1
[note 17]	Buildings can be in multiple schemes and data collections. These tables show the unique number of buildings across the schemes without double counting buildings where they are in multiple schemes. The total here will be lower than the summed total number of buildings reported in each scheme.	Combined_1, Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8
[note 18]	Where buildings are in multiple programmes, a combined remediation stage is first assigned for buildings in more than one of the ACM programme, BSF and CSS. 'In programme' is assigned for buildings that are eligible for but have not started works in any programme, or on one type of cladding (ACM or non-ACM). 'Remediation Underway' is assigned for buildings where work has started on remediation in at least one programme, or on one type of cladding. 'Remediation complete' is assigned for buildings that have completed remediation on site in all programmes or on all types of cladding. / For further overlaps, remediation stages are assigned from programmes in priority order: ACM, BSF, CSS (or a combined stage across these programmes), developer returns.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8
[note 19]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 20]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 21]	The Government-funded Joint Inspection Team, hosted by the Local Government Association, carries out building inspections on behalf of local authorities and provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4
[note 22]	The number of training sessions for Wandsworth and Richmond are combined as Merton, Wandsworth and Richmond operate a joint service where Merton officers attend training on behalf of Richmond and Wandsworth.	JIT_1
[note 23]	Buildings confirmed by delivery partners to be transferred to developers or the Cladding Safety Scheme have been withdrawn from the Building Safety Fund, which has led to a decrease in the number of eligible buildings in the Fund. The number of eligible buildings may continue to decrease as more buildings are confirmed as developer or CSS transfers out of the fund.	BSF_1, BSF_2, BSF_4, BSF_5
[note 24]	The Building Safety Fund first opened to registrations from June to July 2020 receiving registrations from 3,488 buildings. In July 2022 the Building Safety Fund reopened to new applications, and in September 2025 the Building Safety Fund closed to new applications with all 11m+ buildings in England being remediated through the Cladding Safety Scheme. Buildings from both application periods are now combined as one Building Safety Fund, so numbers include both application periods. It is possible for a building to submit a new application to the fund after having completed remediation if it originally applied in 2020, therefore buildings could be double counted. As of the latest reporting period one building had undertaken remediation work from both application periods, so is double counted.	BSF_1, BSF_2, BSF_3, BSF_4, BSF_5
[note 25]	Some buildings have an unknown remediation status reported by the developer. These have been interpreted as ‘Remediation not started – no plans in place’. Furthermore, some buildings have an unknown defect type. These are interpreted as cladding related defects.	Developer_1, Developer_4, Developer_10
[note 26]	The buildings reported in this table as requiring remediation are estimated by MHCLG using information provided by developers in their data return and other data available within the department. In this table, a building is defined as requiring works under the developer remediation contract if it is either self-reported by the developer as requiring (or having previously required) remedial works; is an eligible building in the BSF or ACM and the developer has agreed to re-imburse the funds; has had money paid out by the BSF or ACM; or has a self-reported work status of either: works completed, works started, or works not started but plans in place. / They therefore differ from other published tables which reference only to the number of 'self-reported' buildings requiring works. / From February 2026, if a developer is no longer obligated to submit data to MHCLG, for example if all their buildings are being monitored via another Government programme, the most recent data return held by MHCLG is included for the purpose of counting buildings under the developer contract. However, we no longer rely on their self-reported data to identify buildings requiring works. Instead, if a developer no longer submits data to MHCLG, only data from the BSF, ACM or CSS will be used to impute whether a building requires works, the defect type, remediation status and cost of works. Other data relating to the characteristics of a building e.g., height and dwellings, still use self-reported data based on the most recent data return.	Developer_1, Developer_10
[note 27]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which the developer is remediating directly (please see note 28). The tables shows the number of buildings which have not yet started works; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Plans under Development' or where no status was provided. The table shows the estimated or actual start date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet started remediation work, but have an estimated or actual start date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_5, Developer_6
[note 28]	This represents buildings that developers are solely responsible for. These exclude buildings that are being remediated solely under a government remediation scheme, for which the developer will reimburse taxpayers. However, some buildings being remediated under a government remediation scheme will be included if other relevant fire safety defects have been found, which were not eligible for a government remediation scheme and which the developer is remediating themselves.	Developer_3, / Developer_11
[note 29]	The tables report data for 53 developers who have signed the Developer Remediation Contract. Data for one developer who has gone into administration is not included in this release. / Where tables show the breakdown of data for each developer, there are 12 developers with 5 or fewer buildings who have been supressed to avoid inadvertently identifying buildings with life-critical fire safety defects. They are grouped in the category 'Other (combined total for all developers with five or fewer buildings each'. This includes: Abbey Developments, Allison Homes, Bloor, CG Fry, Courdace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata and William Davis. These developers will be represented in the data with a dash (-) in tables	Developer_1, / Developer_2, / Developer_3, Developer_4, Developer_5, Developer_6, Developer_7, Developer_8, Developer_9, Developer_10
[note 30]	This represents buildings which have been found to require remediation, for which the developer is directly responsible for the works. It excludes buildings being remediated solely under a government remediation scheme, for which the developer will reimburse taxpayers (see Note 28), as the developer cannot influence the pace of remediation on these buildings. However, some buildings being remediated under a government remediation scheme will be included if other relevant fire safety defects have been found, which were not eligible for a government remediation scheme and which the developer is remediating themselves.	Developer_3, Developer_4, / Developer_11
[note 31]	The data here is comprised of of buildings where the response to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?’ was either left blank or reported as ‘Don’t Know – no assessment made’, ‘Don’t Know’ or ‘No – Declaration 5.4B.	Developer_3
[note 32]	The total estimated cost of remediation is based on the actual or estimated cost of remediating EWS and non-EWS defects, as reported by developers, and an assumed average where a cost has not been reported (averages are based on the developer-reported costs, by height).	Developer_2
[note 33]	The figures in tables Social_1 and Social_2 are not comparable to figures in previous iterations prior to the December 2025 data release. From September 2023 to June 2025, the department collected data from registered providers of social housing (RPs) via a quarterly building level survey. Since July 2025, the department has been working with Homes England to migrate data collection from RPs onto a digital platform, the National Remediation System (NRS). The NRS captures 11m+ social buildings where RPs are applying for and eligible for funding from the CSS, and 11m+ social buildings where RPs are self-funding cladding remediation. / From December 2025, data on social housing remediation uses data collected from the National Remediation System and will be updated monthly. / The top table "Social buildings with unsafe cladding, in any programme or self-funded" includes social buildings in the ACM programme, social buildings eligible for the BSF or CSS programmes, social buildings reported by developers as having unsafe cladding in their quarterly data returns, and social buildings reported by registered providers of social housing (private registered providers and local authorities) on the National Remediation System, as having unsafe cladding which they are self-funding the remediation of. Information on remediation status is taken from the relevant programme. The figures in this table align with the social sector figures in Combined_5.	Social_1, / Social_2
[note 34]	Data is taken from the National Remediation System (NRS) run by Homes England. Please see note 33 for further details on the NRS and social housing data used in the data release. / The bottom table "Social buildings with unsafe cladding, only self-funded" includes all social buildings with cladding defects where registered providers of social housing are self-funding remediation. It only includes buildings where key information required for the data release are available, including building name, address, building height and postcode required to derive local authority. Social buildings where registered providers of social housing (RPs) are self-funding remediation includes (1) social buildings that RPs reported with cladding defects in the NRS where they reported to be self-funding remediation and that were not identified in another remediation programme, and (2) 19 social buildings being monitored in the ACM programme where RPs are self-funding remediation.	Social_1, / Social_2
[note 35]	The total number of social high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 2 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 36]	The total number of social high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 1 building that falls under the developer remediation contract.	ACM_8
[note 37]	The total number of private high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 21 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 38]	The total number of private high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 68 buildings that fall under the developer remediation contract.	ACM_8
[note 39]	Data for the ACM, BSF, and CSS are updated monthly. Developer data is updated quarterly. From Dececember 2025, the social self-funded data is updated monthly. Prior to December 2025, data on social housing buildings reported by registered providers of social housing was updated quarterly.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7
[note 40]	The number of buildings associated with particular expenditures paid out may also include buildings where a full reimbursement of funding has taken place, including those where required under the developer contract.	BSF_3
[note 41]	Buildings receive expenditure funding in stages and therefore these figures should not be used to calculate the average expenditure paid out to each building.	BSF_3, CSS_5
[note 42]	In this table where a local authority has 5 or fewer eligible BSF buildings, the numbers provided are banded. In all other cases the numbers are provided. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	BSF_4
[note 44]	Four eligible buildings in the CSS are in Northern Ireland, the remainder are in England.	CSS_1, CSS_2, CSS_3, CSS_4, CSS_6
[Note 45]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which the developer is remediating directly (please see note 28). The tables shows the number of buildings which have not yet completed remediation; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Remediation Started' or where a remediation status was not provided. The table shows the estimated or actual completion date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet completed remediation work, but have an estimated or actual completion date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_7, / Developer_8
[Note 46]	Funding allocations of Full Applications Approved has reduced from previously published figures. This is the result of a data reconciliation exercise, where buildings transferring from the BSF to the Responsible Actors Scheme and Cladding Safety Scheme have had their BSF funding allocation removed.	BSF_3
[Note 47]	The 'Other' tenure includes buildings that are recorded in the ACM programme as student, hotel or public buildings.	Combined_5
[Note 48]	Until May 2024, private sector funding allocations and expenditures included buildings which have successful social sector financial viability claims. This is because both private sector and social sector financial viability buildings receive full government funding, whereas those in the social sector receive partial funding dependant on the number of eligible leaseholders who pay a service charge. For full details please refer to the accompanying technical note.	BSF_3
[Note 49]	Until the May 2024 data release, social sector buildings with a successful financial viability claim were included in the "Private" figures due to them receiving funding for all work, rather than a percentage based on the number of leaseholders that pay a service charge. These buildings are now split out into the "social sector financially viability" category. Further details on the difference between these can be found in the accompanying technical note.	BSF_1
[Note 50]	This table depicts the number of buildings that are estimated to require works which have transferred from the Building Safety Fund (BSF). This figure is based on the developer's dataset definition of a building and differs to the number reported by the BSF because of difference in building definitions.	Developer_1
[Note 51]	The December 2018 and December 2019 ACM remediation progress figures did not include the breakdowns for 'remediation started - cladding removed' and 'works complete awaiting building control signoff'. Those buildings which had started remediation and removed unsafe cladding are included in the 'remediation started' category, and those that were awaiting building control sign off may have been included in the 'completed remediation' category	ACM_11
[Note 52]	Up to October 2023 combined remediation progress in the Building Safety Fund (BSF) and ACM programme is shown. Between June 2023 and September 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers. From October 2023 to November 2025, combined remediation progress is shown across the BSF, ACM programme, Cladding Safety Scheme, developer remediation contract and as reported by registered providers of social housing. Betweeen November 2025 and December 2025 there was a decrease in the number of buildings due to changes in the data collection and categorisation of social housing buildings. From December 2025 onwards, combined remediation progress is shown across the BSF, ACM programme, Cladding Safety Scheme, developer remediation contract and social self-funded buildings. The December 2025 remediation progress figures are therefore not directly comparable to the prior remediation progress figures.	Combined_6
[Note 53]	Between June 2023 and July 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers.	BSF_5
[Note 54]	This table is updated quarterly with the latest data and therefore may not align with monthly figures where the programme data is updated.	Developer_10
[Note 55]	In previous Building Safety Remediation releases, this table was known as 'Building inspections conducted by local authorities'. As of the August 2024 release, this table reports the category assigned from the most recent building inspection.	Enforcement_2
[Note 56]	This table excludes local authorities with fewer than 10 11m+ buildings monitored with unsafe cladding. These disclosure control measures are in place to prevent the identification of one or more buildings with unsafe cladding in these areas.	Combined_3
[Note 57]	As of the November 2024 data release, there is only one column covering Level 2 training. This is a sum of the data from Level 2 Part 1 and Level 2 Part 2. To make comparisons with previous JIT training data, the values in columns C and D should be totalled. When training is delivered as Level 1 and Level 2 in the same session, the training is recorded only in the Level 2 column.	JIT_1
[Note 58]	The figures from before December 2022 for BSF remediation progress did not distinguish between 'Remediation plans in place' and 'Intent to remediate'; they were recorded as 'Remediation not yet started.' Therefore, before December 2022, buildings that would have been categorised as 'Remediation not yet started' are now classified as 'Intent to remediate.'	BSF_5
[Note 59]	It is possible for a building to submit 2 applications to the Building Safety Fund after having completed remediation if it originally applied in 2020, to avoid duplication on a portfolio level these buildings are combined into 1 entry. This means that the total of Non-ACM cladding only in the BSF and Both ACM and non-ACM cladding in the BSF won't match the total number of BSF buildings seen in the BSF tables. As of 30 June 2025 one building had undertaken remediation work from both application periods.	Combined_1
[Note 60]	The number of buildings inspected with support from the Joint Inspection Team may not match the overall number of inspections carried out with their support, as some buildings may have been inspected more than once.	Enforcement_4
[Note 61]	The numbers of notices, inspections etc. may decrease as a result of revisions submitted.	Enforcement_1, Enforcement_4
[Note 62]	These figures exclude CSS buildings in Northern Ireland.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, Combined_8, Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 63]	A government funded scheme includes the ACM programme (including buildings not receiving government funding), the BSF and the CSS.	Combined_8, Estimated_4
[Note 64]	These figures represent MHCLG's best estimates of the number of 11m+ residential buildings that have or had unsafe cladding, in England, as at March 2026. These estimates replace those last published in June 2025. The full revised methodology is available in the Technical Note.	Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 65]	The overall estimates in Estimated_2a differ from those in Estimated_1 as the overall estimates in Estimated_2a include 18m+ hotels, student accommodation or public buildings identified with unsafe ACM cladding, because these buildings are remediated through the ACM programme. At the time the estimate was made there were c.100 of these buildings. These are excluded from Estimated_1 because the buildings do not contain dwellings. The estimated number of 11m+ buildings which are assumed to be remediated privately, outside of one of the department’s remediation programmes, are included in Estimated_1 but excluded from the Estimated_2.	Estimated_1, Estimated_2
[Note 66]	The overall estimates in Estimated_2a include c.100 18m+ hotels, student accommodation or public buildings identified with unsafe ACM cladding remediated through the ACM programme. These buildings are not included in the estimates of the number of social and private sector buildings expected to be remediated or mitigated through a government remediation programme, in Estimated_2b and Estimated_2c. The overall building number estimate in Estimated_2a therefore does not equal the sum of the private and social sector estimates in Estimated_2 and Estimated_2c.	Estimated_2
[Note 67]	These figures include buildings which have already undergone remediation or mitigation of unsafe cladding.	Estimated_1, Estimated_2, Estimated_3, Estimated_4
[Note 68]	MHCLG have collected quarterly data returns from developers since 31 July 2023. However, it is not possible to show a breakdown of determinations made between 31 July 2023 and 31 January 2024 due to an amendment which was made to the question used to track determinations in January 2024. Determinations are based on the survey question 'Does this building require works, or has it previously been identified with defects, as per the contract?' Prior to January 2024 the response options for this question were 'Yes', 'No' and 'Don't Know', however as the response 'No' comprised a combination of buildings which had received a qualifying assessment and buildings which hadn't, it was not possible to accurately identify buildings which had recieved a determination on whether remedial works are required. Therefore, in January 2024 the options were amended to 'No - as shown by assessment', 'Yes - as shown by assessment', 'Don't Know - no assessment made' and 'Don't Know - further assessment required'. This enables developers to more accurately report on whether a determination has been made for each building.	Developer_11
[Note 69]	Determinations are based on a developers response to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?'. To estimate the quarterly number of buildings where determinations were made, MHCLG uses the most recent quarterly returns submitted by developers. Buildings reported with a determination in the most recent quarterly return are compared against previous returns and categorised based on the earliest quarterly return in which they were reported to have had a determination, providing they continue to be reported as determined in subsequent quarters. If a determination alternates across returns, the most recent reported data return is used. See the Technical Note for further information.	Developer_11
[Note 70]	To estimate the number of buildings where works were started or works were completed in each quarter, MHCLG have used the most recent quarterly returns submitted by developers. Using developer responses to the question 'Status of Works', buildings reported as Started or Completed in the most recent quarterly return are compared against previous returns and categorised based on the earliest quarterly return in which they were reported to have started or completed works, providing they continue to be reported as started or completed in subsequent quarters. If the response to 'Status of Works' alternates across returns, the most recent reported data return is used. / In January 2025, as part of data validation improvements, an additional response of 'Yes - the building previously required works which are now fixed' was added to the question 'Does this building require works, or has it previously been identified with defects, as per the contract?'. For buildings where the 'Status of Works' has changed from not started/blank to using this new response in consecutive quarters, the start and completion dates reported by developers are used to categorise the quarter in which they started or completed. For buildings where valid dates were not reported by developers, it is assumed that they had started and completed works before 31 July 2023; the first point at which developers submitted data to MHCLG." See the Technical Note for further information.	Developer_11
[Note 71]	The statistics in these tables are experimental and as such will be subject to methodology refinements as more data becomes available. See the Technical Note for further information.	Developer_11
[Note 72]	The total is the same as the row above since there is only one Administering Authority for the 2023 Replacement Fund and Interim Measures Alarm Fund	WWRF_4, WWRF_5
[Note 73]	Figures in this table are based on funding eligibility criteria as at March 2026.	Estimated_4
[Note 74]	Running total of training for the year to date (or total for that year if not current year)	JIT_1
[Note 75]	Total attendees on training for all the years we have received data. May not be a sum of the individual years' data.	JIT_1
[Note 76]	Following publication of the public inquiry report into the Grenfell Tower Fire, the Prime Minister made clear that unsafe buildings must be remediated more quickly. The joint plan was published alongside the government’s broader Remediation Acceleration Plan. 39 developers have signed up to the Joint Plan, where they have committed to making every effort to achieve several stretch targets: / • Finish assessing all their buildings to determine which require works by end July 2025 / • Start or complete remedial works on 80% of their buildings by end July 2026 / • Start or complete remedial works on all their buildings by end July 2027 / • Resolve extant cost-recovery negotiations with social housing providers by end July 2025	Developer_12; / Developer_13; / Developer_14
[Note 77]	Under the joint plan, developers committed to complete determinations for all buildings for which they are responsible under the contract by end July 2025, and to provide evidence to MHCLG in any cases where a building missed the stretch target for reasons outside the developer’s control. MHCLG committed to consider any such evidence and take it into account when reporting on developer progress. This column shows the number of buildings where a reasonable exception has been requested by a developer and accepted by MHCLG. / To calculate the estimated percentage of buildings that would have a determination if buildings with exceptions are accounted for, the 'number of buildings where an exception request has been accepted' is subtracted from the 'number of contract buildings where the developer is directly responsible for remediation' and this is used as the denominator. The 'number of buildings for which the developer has determined whether works are required' is used as the numerator	Developer_12
[Note 78]	The estimates in these tables are derived from MHCLG modelling. The modelling uses programme data from 2025, from the Aluminium Composite Material Programme, Building Safety Fund, and Cladding Safety Scheme, as well as data from developers on developer-led remediation and data from the social housing sector.	Estimated_5
[Note 79]	The estimated costs in Estimated_5, Estimated_6 and Estimated_7 are as of March 2025. The cost estimates relate to the estimated number of buildings requiring remediation and accessing government funding as of March 2025. These estimates have not been updated to reflect the updated estimates, as of March 2026, of the number of 11m+ buildings with unsafe cladding. The cost estimates will be updated in the future.	Estimated_5, Estimated_6, Estimated_7
[Note 80]	Estimated costs of 11-18m buildings expected to required remediation use building numbers, as of March 2025, as set out in the "Methodology: Estimating the number of 11-18m buildings with unsafe cladding” section of the June 2025 technical note, alongside cost of remediation per building estimates. The costs of remediation per building were estimated using data from the remediation programmes to form assumptions. Further information is available in the technical note.	Estimated_5
[Note 81]	Estimated costs of 18m+ buildings expected to required remediation use building numbers, as of March 2025, as set out in the “Methodology: Estimating the number of 18m+ buildings with unsafe cladding” section of the June 2025 technical note, alongside cost of remediation per building estimates. The costs of remediation per building were estimated using data from the remediation programmes to form assumptions. Further information is available in the technical note.	Estimated_5
[Note 82]	Estimated costs to government take into account changes in funding eligibility criteria announced in June 2025 where social landlords will now receive equal access to government remediation funding as private landlords.	Estimated_5, Estimated_6
[Note 83]	These proportions are calculated by dividing the estimated capital cost of external wall system works to residential buildings for both funding sources by the total estimated capital cost across both funding sources, for residential buildings over 11 metres with unsafe cladding expected to be remediated or mitigated. Further information is available in the technical note.	Estimated_6
[Note 84]	Developer refund estimates are based on quarterly developer data returns and MHCLG fund data, with adjustments made to account for the possibility of credit loss and interest rate payments. The Levy Revenue target is intended as the balancing figure between government costs and money available from other sources. As cost estimates continue to be updated, the Levy Revenue target will be reviewed and adjusted such that funding available for remediation aligns to government expenditure.	Estimated_7
[Note 85]	These tables are based on data reported by developers as at 31 July 2025. This is because they are intended to report on progress that developers had made against the RAP target to finish assessing all their buildings to determine which require works by end July 2025. For the most recent data relating to developer determinations please see table 'Developer_1'	Developer_12
[Note 86]	Under the joint plan, developers committed to to resolve any cost-recovery negotiations with social housing providers that were outstanding at the time of the joint plan (2 December 2024) on buildings where these developers acted as a contractor and therefore fall outside of the developer remediation contract obligations by end July 2025, and any future cost-recovery negotiations with social housing providers as quickly as possible within 6 months. / These tables show: / - The progress developers have made to resolve cost-recovery negotiations with social housing providers where negotiations started before (and were ongoing as of) 2 December 2024, or where negotiations started after 2 December 2024, and whether an agreement has been reached or the negotiations are ongoing (Developer_13). / - The expected date to resolve outstanding cost-recovery negotiations with social housing providers that started before (and were ongoing as of) 2 December 2024, or where negotiations started after 2 December 2024 and have not yet been resolved (Developer_14).	Developer_13; / Developer_14
[Note 87]	Fluctuations in the reported remediation progress for social self-funded buildings is expected in the months from December 2025 as registered providers continue to migrate their records onto the NRS. This will affect the social self-funded remediation progress figures, and the overall and social sector remediation progress figures. / The remediation status of a small number of buildings is currently unknown as registered providers are yet to provide remediation dates on the NRS. We expect these statuses to be confirmed in coming months as further data is collected. In the overall remediation progress tables, these buildings are assumed to have not started remediation and are reported as 'in programme'.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7, / Social_1, / Social_2
[Note 88]	These figures reflect actions taken in each quarter and are therefore liable to change as actions are reported to us. This will affect the most recent quarters in particular.	Enforcement_5
[Note 89]	Q1 refers to the months January to March, Q2 refers to the months April to June, Q3 refers to the months July to September, Q4 refers to the months October to December	Enforcement_5
[Note 90]	Inspections can be primary or secondary - both are counted	Enforcement_5
[Note 91]	Formal notices includes improvement notices (primary and secondary), hazard awareness notices (primary and secondary), and prohibition notices	Enforcement_5
[Note 92]	As of 31 March 2026, the Waking Watch Replacement Fund 2023 closed to new applications. The figures will continue to be updated for those still progressing through the Fund.	WWRF_1, WWRF_4
[Note 93]	The notable increase in the number of rejected applications in the April 2026 figures is a result of the closure of the Waking Watch Replacement Fund 2023 on 31 March 2026. These applicants were directed to submit a new claim to the new Interim Measures Alarm Fund managed by Homes England, which was launched on 1 April 2026.	WWRF_4
[Note 94]	These rows cannot be added together as one is a subset of the other.	Combined_9
[Note 95]	This row consists of all buildings identified in a government programme in December 2020. This includes buildings identified in the ACM Programme by December 2020 and those buildings that registered for the BSF in 2020 including those that have subsequently transferred to the Responsible Actor Scheme or Cladding Safety Scheme. The majority of buildings in the BSF were accepted into the programme after 2020, but as we do not hold a complete set of data for when a building became eligible in the BSF, the figures use building registration date instead as that is when the department was first aware of the building.	Combined_9
[Note 96]	This row consists of only those buildings that were identified in a government programme in December 2020 and are continuing to proceed through the programmes using the original 2020 criteria. This consists of buildings that were identified in the ACM Programme by December 2020 and those buildings that registered for the BSF in 2020 that are continuing to use the CAN criteria and have not transferred to the Responsible Actor Scheme or the Cladding Safety Scheme. These BSF buildings were known to the department in 2020 but have since changed their process and criteria for remediation, which could have delayed the progress of their remediation.	Combined_9
[Note 97]	There is a 19 building increase of the numbers of buildings identified by December 2020 since this was last published in November 2024. These consist of buildings that registered in 2020 but took a long time to provide sufficient information for the department to determine eligibility and reconciliation work to identify the accurate number of buildings within a registration.	Combined_9
[Note 98]	Data relating to waking watch costs is not included for the Interim Measures Alarm Fund as buildings are not required to have an existing waking watch in order to qualify for the scheme. Guidance on eligibility can be found here: https://www.gov.uk/guidance/interim-measures-alarm-fund-imaf	WWRF_1

## Table_of_Contents
Building Safety Remediation Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 25 June 2026
ACM_2	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 25 June 2026
ACM_3	Remediation status of buildings yet to complete ACM remediation by tenure, England, 25 June 2026
ACM_4	ACM remediation progress by local authority, England, 25 June 2026
ACM_5	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 25 June 2026
ACM_6	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 25 June 2026
ACM_7	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 25 June 2026
ACM_8	ACM remediation progress by sources of funding, England, 25 June 2026
ACM_9	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 25 June 2026
ACM_10	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 25 June 2026
ACM_11	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 25 June 2026
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 30 June 2026
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 30 June 2026
WWRF_3	Waking Watch Replacement Fund 2022 applications, buildings and approved funding by administering authority, 30 June 2026
WWRF_4	Waking Watch Replacement Fund 2023 applications, buildings and approved funding by administering authority, 30 June 2026
WWRF_5	Interim Measures Alarm Fund applications, buildings and approved funding by administering authority, 30 June 2026
BSF_1	Remediation status of eligible buildings within BSF by tenure, England, 25 June 2026
BSF_2	BSF remediation progress of eligible buildings by region, England, 25 June 2026
BSF_3	BSF number of eligible buildings with funding approved and expenditure amounts by tenure, England, 25 June 2026
BSF_4	BSF remediation progress of eligible buildings by local authority, England, 25 June 2026
BSF_5	Remediation status of eligible buildings within BSF, time series, England, 25 June 2026
Combined_1	Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 25 June 2026
Combined_2	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, England, 30 June 2026
Combined_3	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, by local authority, England, 30 June 2026
Combined_4	Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing by remediation status, England, 30 June 2026
Combined_5	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, England, by tenure, 30 June 2026
Combined_6	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, England, time series, 30 June 2026
Combined_7	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, England, by region, 30 June 2026
Combined_8	Remediation progress for unique buildings being remediated or mitigated as part of a government funded scheme, 11 metres and over in height, England, 30 June 2026
Combined_9	Number of unique buildings known by government programmes in December 2020, which haven't started remediation by 30 April 2026
CSS_1	Application status of buildings within the CSS, England, 30 June 2026
CSS_2	CSS remediation progress by region, England, 30 June 2026
CSS_3	CSS remediation progress by height, England, 30 June 2026
CSS_4	CSS remediation progress by tenure, England, 30 June 2026
CSS_5	CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 30 June 2026
CSS_6	CSS remediation progress, time series, England, 30 June 2026
Social_1	Remediation status of social buildings and social self-funded buildings with cladding defects, England, 30 June 2026
Social_2	Remediation status of social buildings and social self-funded buildings with unsafe cladding, time series, England, 30 June 2026
Developer_1	Remediation status of buildings covered by the developer remediation contracts by height group, England, 30 June 2026
Developer_2	Estimated cost of buildings requiring works under the developer remediation contract by height, England, 30 June 2026
Developer_3	Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 30 April 2026
Developer_4	Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 30 April 2026
Developer_5	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 30 April 2026
Developer_6	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 30 April 2026
Developer_7	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 30 April 2026
Developer_8	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 30 April 2026
Developer_9	Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 30 April 2026
Developer_10	Remediation status of buildings requiring works under the developer remediation contract, time series, England, 31 May 2026
Developer_11	Estimated number of determinations, starts and completions made each quarter for buildings under the developer remediation contract, by height group, England, 30 April 2026
Developer_12	Developer by developer update against RAP Joint Plan targets, 31 July 2025
Developer_13	Progress of developers against RAP joint plan commitment to resolve outstanding cost-recovery negotiations with social housing providers, England, 31 October 2025
Developer_14	Progress of developers against RAP joint plan commitment to resolve outstanding cost-recovery negotiations with social housing providers, England, 31 October 2025
Enforcement_1	Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 19 June 2026
Enforcement_2	Building inspections conducted by local authorities, England, 19 June 2026
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 19 June 2026
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 19 June 2026
Enforcement_5	Number of inspections and formal notices conducted per quarter, England, 19 June 2026
JIT_1	Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 30 June 2026
Estimated_1	Estimates of the number of residential buildings, containing dwellings, that have or had unsafe cladding requiring work, 11 metres and over in height, England, March 2026
Estimated_2	Estimates of the number of residential buildings, that have or had unsafe cladding requiring work, expected to be remediated or mitigated as part of a government remediation programme, 11 metres and over in height, England, March 2026
Estimated_3	Estimated proportion of buildings with unsafe cladding expected to be remediated or mitigated in a government remediation programme that are currently monitored in a government remediation programme, 30 June 2026
Estimated_4	Estimates of the number of residential buildings, that have or had unsafe cladding requiring remediation or mitigation work, expected to be remediated or mitigated as part of a government funded scheme, based on March 2026 eligibility criteria, 11 metres and over in height, England, March 2026
Estimated_5	Estimated cost of external wall system works to residential buildings, 11 metres and over in height, with unsafe cladding expected to be remediated or mitigated, by funding source and building height, England, March 2025, £bn (nominal terms)
Estimated_6	Estimated proportion of capital costs of external wall system works to buildings 11 metres and over in height, with unsafe cladding expected to be remediated or mitigated, by funding source, England, March 2025.
Estimated_7	Estimated money available to MHCLG to fund the remediation and mitigation of unsafe external wall system defects in buildings 11 metres and over in height, with unsafe cladding, England, March 2025, £bn (nominal terms, nearest £0.1bn)

## ACM_1
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Tenure	Number of buildings this month	Number of buildings last month	Monthly change
Social sector residential	165	165	0
Private sector residential	249	249	0
Student accommodation	61	61	0
Hotels	33	33	0
Publicly-owned buildings	8	8	0
Total buildings	516	516	0

## ACM_2
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Completed Remediation	145	88%	218	88%	59	97%	29	88%	7	88%	458	89%
Works complete awaiting building control signoff	15	9%	2	1%	0	0%	1	3%	1	13%	19	4%
Remediation started - cladding removed	3	2%	8	3%	0	0%	0	0%	0	0%	11	2%
Remediation started	1	1%	8	3%	2	3%	1	3%	0	0%	12	2%
Remediation plans in place	1	1%	7	3%	0	0%	0	0%	0	0%	8	2%
Reported an intent to remediate	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Remediation plan unclear	0	0%	2	1%	0	0%	2	6%	0	0%	4	1%
Total buildings	165	100%	249	100%	61	100%	33	100%	8	100%	516	100%

## ACM_3
Remediation status of buildings yet to complete ACM remediation by tenure, England, 25 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff - Vacant	0	0	0	0	0
Remediation started - cladding removed - Vacant	0	0	0	0	0
Remediation started - Vacant	0	0	0	0	0
Remediation plans in place - Vacant	0	1	0	0	0
Reported an intent to remediate - Vacant	0	0	0	0	0
Remediation plan unclear - Vacant	0	0	0	1	0
Total vacant buildings	0	1	0	1	0

Remediation Category for occupied buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	15	2	0	1	1
Remediation started - cladding removed	3	8	0	0	0
Remediation started	1	8	2	1	0
Remediation plans in place	1	6	0	0	0
Reported an intent to remediate	0	4	0	0	0
Remediation plan unclear	0	2	0	1	0
Total occupied buildings	20	30	2	3	1

## ACM_4
ACM remediation progress by local authority, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	None	100%	100%
Barnet	6 to 10	1 to 5	Between 50% and 99%	100%
Bedford	1 to 5	None	100%	100%
Birmingham	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Bournemouth, Christchurch and Poole	1 to 5	None	100%	100%
Bradford	1 to 5	None	100%	100%
Brent	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	None	100%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	100%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Hackney	11 to 20	1 to 5	Between 50% and 99%	100%
Hammersmith and Fulham	6 to 10	None	100%	100%
Haringey	6 to 10	None	100%	100%
Harrow	1 to 5	None	100%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	None	100%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Leeds	11 to 20	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	None	100%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	None	100%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	None	100%	100%
Newcastle upon Tyne	11 to 20	1 to 5	Between 50% and 99%	100%
Newham	Over 20	1 to 5	Between 50% and 99%	100%
Norwich	6 to 10	1 to 5	Between 50% and 99%	100%
Nottingham	6 to 10	None	100%	100%
Oldham	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	None	100%	100%
Reading	1 to 5	None	100%	100%
Redbridge	1 to 5	None	100%	100%
Salford	Over 20	11 to 20	Between 50% and 99%	Between 50% and 99%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	None	100%	100%
Slough	6 to 10	1 to 5	Between 50% and 99%	100%
Southwark	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	6 to 10	1 to 5	Between 50% and 99%	100%
Sutton	1 to 5	1 to 5	Between 50% and 99%	100%
Tower Hamlets	Over 20	6 to 10	Between 50% and 99%	100%
Trafford	1 to 5	None	100%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	Over 20	None	100%	100%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Wolverhampton	1 to 5	None	100%	100%

## ACM_5
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 25 June 2026
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	38	81%	18	90%	5	100%	2	100%	0	0%	63	85%
Works complete awaiting building control signoff	9	19%	0	0%	0	0%	0	0%	0	0%	9	12%
Remediation started - cladding removed	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation started	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	2	10%	0	0%	0	0%	0	0%	2	3%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	20	100%	5	100%	2	100%	0	0%	74	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	75	88%	150	88%	14	93%	13	81%	0	0%	252	88%
Works complete awaiting building control signoff	6	7%	1	1%	0	0%	1	6%	1	100%	9	3%
Remediation started - cladding removed	3	4%	5	3%	0	0%	0	0%	0	0%	8	3%
Remediation started	1	1%	5	3%	1	7%	1	6%	0	0%	8	3%
Plans in place	0	0%	7	4%	0	0%	0	0%	0	0%	7	2%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	2	1%	0	0%	1	6%	0	0%	3	1%
Total buildings	85	100%	170	100%	15	100%	16	100%	1	100%	287	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	97%	50	85%	40	98%	14	93%	7	100%	143	92%
Works complete awaiting building control signoff	0	0%	1	2%	0	0%	0	0%	0	0%	1	1%
Remediation started - cladding removed	0	0%	3	5%	0	0%	0	0%	0	0%	3	2%
Remediation started	0	0%	3	5%	1	2%	0	0%	0	0%	4	3%
Plans in place	1	3%	0	0%	0	0%	0	0%	0	0%	1	1%
Responded with intent	0	0%	2	3%	0	0%	0	0%	0	0%	2	1%
Remediation plan unclear	0	0%	0	0%	0	0%	1	7%	0	0%	1	1%
Total buildings	33	100%	59	100%	41	100%	15	100%	7	100%	155	100%

## ACM_6
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 25 June 2026
Back to Contents
This worksheet contains eight tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	139	89%	177	96%	52	100%	26	96%	7	88%	401	94%
Works complete awaiting building control signoff	14	9%	1	1%	0	0%	1	4%	1	13%	17	4%
Remediation started - cladding removed	3	2%	3	2%	0	0%	0	0%	0	0%	6	1%
Remediation started	1	1%	2	1%	0	0%	0	0%	0	0%	3	1%
Plans in place	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	157	100%	184	100%	52	100%	27	100%	8	100%	428	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	140	88%	198	95%	54	100%	28	97%	7	88%	427	93%
Works complete awaiting building control signoff	15	9%	1	0%	0	0%	1	3%	1	13%	18	4%
Remediation started - cladding removed	3	2%	5	2%	0	0%	0	0%	0	0%	8	2%
Remediation started	1	1%	3	1%	0	0%	0	0%	0	0%	4	1%
Plans in place	0	0%	2	1%	0	0%	0	0%	0	0%	2	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	159	100%	209	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	144	88%	209	94%	55	98%	29	94%	7	88%	444	92%
Works complete awaiting building control signoff	15	9%	1	0%	0	0%	1	3%	1	13%	18	4%
Remediation started - cladding removed	3	2%	6	3%	0	0%	0	0%	0	0%	9	2%
Remediation started	1	1%	4	2%	1	2%	1	3%	0	0%	7	1%
Plans in place	0	0%	3	1%	0	0%	0	0%	0	0%	3	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	163	100%	223	100%	56	100%	31	100%	8	100%	481	100%

Identified by 31 December 2022	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	144	88%	214	93%	55	98%	29	94%	7	88%	449	92%
Works complete awaiting building control signoff	15	9%	1	0%	0	0%	1	3%	1	13%	18	4%
Remediation started - cladding removed	3	2%	6	3%	0	0%	0	0%	0	0%	9	2%
Remediation started	1	1%	4	2%	1	2%	1	3%	0	0%	7	1%
Plans in place	0	0%	3	1%	0	0%	0	0%	0	0%	3	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	163	100%	229	100%	56	100%	31	100%	8	100%	487	100%

Identified by 31 December 2023	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	145	88%	214	91%	57	98%	29	94%	7	88%	452	91%
Works complete awaiting building control signoff	15	9%	2	1%	0	0%	1	3%	1	13%	19	4%
Remediation started - cladding removed	3	2%	6	3%	0	0%	0	0%	0	0%	9	2%
Remediation started	1	1%	5	2%	1	2%	1	3%	0	0%	8	2%
Plans in place	0	0%	6	3%	0	0%	0	0%	0	0%	6	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	164	100%	234	100%	58	100%	31	100%	8	100%	495	100%

Identified by 31 December 2024	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	145	88%	216	90%	59	98%	29	94%	7	88%	456	90%
Works complete awaiting building control signoff	15	9%	2	1%	0	0%	1	3%	1	13%	19	4%
Remediation started - cladding removed	3	2%	8	3%	0	0%	0	0%	0	0%	11	2%
Remediation started	1	1%	8	3%	1	2%	1	3%	0	0%	11	2%
Plans in place	1	1%	6	2%	0	0%	0	0%	0	0%	7	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	165	100%	241	100%	60	100%	31	100%	8	100%	505	100%

Identified by 31 December 2025	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	145	88%	218	88%	59	97%	29	91%	7	88%	458	89%
Works complete awaiting building control signoff	15	9%	2	1%	0	0%	1	3%	1	13%	19	4%
Remediation started - cladding removed	3	2%	8	3%	0	0%	0	0%	0	0%	11	2%
Remediation started	1	1%	8	3%	2	3%	1	3%	0	0%	12	2%
Plans in place	1	1%	6	2%	0	0%	0	0%	0	0%	7	1%
Responded with intent	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Remediation plan unclear	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Total buildings	165	100%	247	100%	61	100%	32	100%	8	100%	513	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Remediation completed	145	88%	218	88%	59	97%	29	88%	7	88%	458	89%
Works complete awaiting building control signoff	15	9%	2	1%	0	0%	1	3%	1	13%	19	4%
Remediation started - cladding removed	3	2%	8	3%	0	0%	0	0%	0	0%	11	2%
Remediation started	1	1%	8	3%	2	3%	1	3%	0	0%	12	2%
Plans in place	1	1%	7	3%	0	0%	0	0%	0	0%	8	2%
Responded with intent	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Remediation plan unclear	0	0%	2	1%	0	0%	2	6%	0	0%	4	1%
Total buildings	165	100%	249	100%	61	100%	33	100%	8	100%	516	100%

## ACM_7
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 25 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings [note 10]	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed total	11,800	18,300	21,600	30,200	33,400
Remediation completed	10,200	18,200	21,500	28,400	31,700
Works complete awaiting building control signoff	1600	100	100	1,700	1,700
Yet to complete remediation [note_3]	300	2,200	2,300	2,400	2,600
Occupied and yet to complete remediation	300	2,200	2,300	2,400	2,500
Total	12,100	20,500	23,900	32,600	36,000

Leasehold dwellings [note 10]	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed total	3,300	18,300	21,600	21,600	24,900
Remediation completed	2,900	18,200	21,500	21,100	24,300
Works complete awaiting building control signoff	400	100	100	600	600
Yet to complete remediation [note_3]	100	2,200	2,300	2,200	2,400
Occupied and yet to complete remediation	100	2,200	2,300	2,200	2,400
Total	3,400	20,500	23,900	23,900	27,300

## ACM_8
ACM remediation progress by sources of funding, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note 4]	Not in social fund	Private: government funded / [note 5]	Private: not government funded
Remediation completed	136	9	102	116
Works complete awaiting building control signoff	6	9	1	1
Remediation started - cladding removed	2	1	8	0
Remediation started	0	1	6	2
Plans in place	0	1	5	2
Responded with intent	0	0	4	0
Remediation plan unclear	0	0	1	1
Total	144	21	127	122

## ACM_9
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	0	0
Applications approved: for pre-contract support	1	0
Full cost application submitted	0	0
Applications approved: for full costs	67	40
TOTAL	68	40

## ACM_10
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	345	237
Expenditure [note_8, note_9]	315	363

## ACM_11
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 25 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [Note 51]	Dec-18 / Number	Dec-19 / Number	Dec-20 / Number	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 / Number	Jun-25 / Number	Jul-25 / Number	Aug-25 / Number	Sep-25 / Number	Oct-25 / Number	Nov-25 / Number	Dec-25 / Number	Jan-26 / Number	Feb-26 / Number	Mar-26 / Number	Apr-26 / Number	May-26 / Number	Jun-26 / Number
Completed Remediation	67	135	216	289	354	357	357	357	359	360	364	367	368	369	369	388	397	399	401	401	405	406	408	411	412	415	416	416	420	423	426	427	428	432	436	437	445	448	450	452	455	455	455	458	458	458	458
Works complete awaiting building control signoff			33	64	53	50	51	51	51	52	51	52	54	53	53	34	28	31	32	32	30	30	29	27	30	28	28	28	26	23	20	26	26	25	21	23	17	16	17	15	11	12	11	8	9	14	19
Remediation started - cladding removed			48	57	35	36	36	37	38	38	38	36	35	37	38	39	37	35	33	33	33	33	32	33	31	30	31	31	29	29	31	29	29	27	28	25	23	21	20	20	21	20	21	21	21	17	11
Remediation started	101	123	120	39	21	21	21	21	19	18	15	15	13	13	13	15	14	15	19	21	19	18	18	17	17	17	15	17	17	18	16	12	11	11	12	12	12	13	11	11	11	11	11	11	12	11	12
Remediation plans in place	171	104	32	15	13	12	11	12	12	14	14	15	15	15	15	14	13	14	9	7	8	8	8	8	8	19	20	18	19	18	18	18	18	18	9	9	10	9	9	9	9	9	9	9	7	8	8
Reported an intent to remediate	40	78	11	15	9	9	11	10	10	7	7	5	5	3	3	1	2	1	1	1	1	1	1	1	1	1	1	1	1	1	1	0	0	0	0	1	1	1	4	4	4	4	4	4	4	4	4
Remediation plan unclear	58	10	2	2	2	3	3	2	1	1	1	1	2	2	4	5	5	1	1	1	2	2	2	2	4	3	3	3	2	2	3	3	4	4	5	4	3	3	2	2	2	2	2	5	5	4	4
Total buildings	437	450	462	481	487	488	490	490	490	490	490	491	492	492	495	496	496	496	496	496	498	498	498	499	503	513	514	514	514	514	515	515	516	517	511	511	511	511	513	513	513	513	513	516	516	516	516

Remediation Category [note 10]	Dec-18 / Percentage (%)	Dec-19 / Percentage (%)	Dec-20 / Percentage (%)	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)	Sep-24 / Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 / Percentage (%)	Jun-25 / Percentage (%)	Jul-25 / Percentage (%)	Aug-25 / Percentage (%)	Sep-25 / Percentage (%)	Oct-25 / Percentage (%)	Nov-25 / Percentage (%)	Dec-25 / Percentage (%)	Jan-26 / Percentage (%)	Feb-26 / Percentage (%)	Mar-26 / Percentage (%)	Apr-26 / Percentage (%)	May-26 / Percentage (%)	Jun-26 / Percentage (%)
Completed Remediation	15%	30%	47%	60%	73%	73%	73%	73%	73%	73%	74%	75%	75%	75%	75%	78%	80%	80%	81%	81%	81%	82%	82%	82%	82%	81%	81%	81%	82%	82%	83%	83%	83%	84%	85%	86%	87%	88%	88%	88%	89%	89%	89%	89%	89%	89%	89%
Works complete awaiting building control signoff			7%	13%	11%	10%	10%	10%	10%	11%	10%	11%	11%	11%	11%	7%	6%	6%	6%	6%	6%	6%	6%	5%	6%	5%	5%	5%	5%	4%	4%	5%	5%	5%	4%	5%	3%	3%	3%	3%	2%	2%	2%	2%	2%	3%	4%
Remediation started - cladding removed			10%	12%	7%	7%	7%	8%	8%	8%	8%	7%	7%	8%	8%	8%	7%	7%	7%	7%	7%	7%	6%	7%	6%	6%	6%	6%	6%	6%	6%	6%	6%	5%	5%	5%	5%	4%	4%	4%	4%	4%	4%	4%	4%	3%	2%
Remediation started	23%	27%	26%	8%	4%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%	3%	3%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%	4%	3%	2%	2%	2%	2%	2%	2%	2%	2%	2%	2%	2%	2%	2%	2%	2%	2%
Remediation plans in place	39%	23%	7%	3%	3%	2%	2%	2%	2%	3%	3%	3%	3%	3%	3%	3%	3%	3%	2%	1%	2%	2%	2%	2%	2%	4%	4%	4%	4%	4%	3%	3%	3%	3%	2%	2%	2%	2%	2%	2%	2%	2%	2%	2%	1%	2%	2%
Reported an intent to remediate	9%	17%	2%	3%	2%	2%	2%	2%	2%	1%	1%	1%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	1%	1%	1%	1%	1%	1%
Remediation plan unclear	13%	2%	0%	0%	0%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	1%	0%	0%	1%	1%	1%	1%	1%	1%	1%	1%	0%	0%	0%	0%	0%	1%	1%	1%	1%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 30 June 2026
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete
Waking Watch Relief Fund	329	468	212	320	24,700	27.3	169	105	305
Waking Watch Replacement Fund 2022	38	67	25	47	2,200	2.4	216	210	42
Waking Watch Replacement Fund 2023 [Note 92]	437	759	298	471	24,800	41.5	391	333	415
Interim Measures Alarm Fund [Note 98]	173	173	56	56	4,400	4.6	N/A	N/A	0
Total [Note 10]	977	1,467	591	894	56,100	75.8	281	189	762

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 30 June 2026
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [Note 11]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	9	8	1	0	0	11%	89%	9	8	89%	2%	1.6	200,826	180,147
Bristol	3	2	1	0	0	33%	67%	3	2	67%	1%	0.1	46,256	46,256
Greater London Authority	110	65	29	16	0	26%	59%	171	111	65%	35%	8.3	74,911	64,551
Greater Manchester Combined Authority	25	20	5	0	0	20%	80%	38	33	87%	10%	2.5	75,477	76,928
Leeds	10	9	0	1	0	0%	90%	12	11	92%	3%	1.8	162,466	124,500
Liverpool	18	17	1	0	0	6%	94%	19	18	95%	6%	1.7	94,400	63,784
Newcastle	3	3	0	0	0	0%	100%	3	3	100%	1%	0.4	128,496	163,181
Sheffield	6	5	0	1	0	0%	83%	7	6	86%	2%	0.5	88,753	87,828
MHCLG (1st Tranche)	35	21	14	0	0	40%	60%	55	39	71%	12%	2.7	68,957	65,577
MHCLG (2nd Tranche)	60	27	32	1	0	53%	45%	70	34	49%	11%	3.8	112,303	81,624
MHCLG (3rd Tranche)	50	35	14	1	0	28%	70%	81	55	68%	17%	3.9	70,341	57,389
MHCLG Total	145	83	60	2	0	41%	57%	206	128	62%	40%	10.4	81,066	65,486
Total [Note 10]	329	212	97	20	0	29%	64%	468	320	68%	100%	27.3	85,268	67,894

## WWRF_3
Waking Watch Replacement Fund 2022 applications, buildings and approved funding by administering authority, 30 June 2026
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [Note 12]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	2	2	0	0	0	0%	100%	4	4	100%	9%	0.4	89,328	87,683
MHCLG	25	21	1	3	0	4%	84%	46	40	87%	85%	1.8	45,560	26,643
Greater Manchester Combined Authority	11	2	9	0	0	82%	18%	17	3	18%	6%	0.2	65,206	46,743
Leeds	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Liverpool	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Sheffield	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Total [Note 10]	38	25	10	3	0	26%	66%	67	47	70%	100%	2.4	50,539	30,209

## WWRF_4
Waking Watch Replacement Fund 2023 applications, buildings and approved funding by administering authority, 30 June 2026
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
MHCLG	437	298	31	78	30	7%	68%	759	471	62%	100%	41.5	88,020	68,494
Total [Note 72, Note 92, Note 93]	437	298	31	78	30	7%	68%	759	471	62%	100%	41.5	88,020	68,494

## WWRF_5
Interim Measures Alarm Fund applications, buildings and approved funding by administering authority, 30 June 2026
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Homes England	173	56	2	0	115	1%	32%	173	56	32%	100%	4.6	81,265	50,419
Total [Note 72, Note 93]	173	56	2	0	115	1%	32%	173	56	32%	100%	4.6	81,265	50,419

## BSF_1
Remediation status of eligible buildings within BSF by tenure, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note 23][note 49]	Social sector residential (leaseholder) / Number	Social sector residential (leaseholder) / Percentage (%)	Social Sector Financial Viability / Number	Social Sector Financial Viability / Percentage (%)	Social Sector Total / Number	Social Sector Total / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Total residential Number	Total residential Percentage (%)
Remediation complete	88	76%	7	54%	95	74%	285	56%	380	59%
Remediation complete: awaiting building control sign-off	18	16%	2	15%	20	16%	82	16%	102	16%
Remediation started	10	9%	0	0%	10	8%	70	14%	80	13%
Remediation plans in place	0	0%	4	31%	4	3%	63	12%	67	10%
Intent to remediate	0	0%	0	0%	0	0%	11	2%	11	2%
Total buildings [note 10]	116	100%	13	100%	129	100%	511	100%	640	100%

## BSF_2
BSF remediation progress of eligible buildings by region, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note 23]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF / Percentage(%)	Not Started Remediation / Number	Not Started Remediation / Percentage(%)	Started Remediation / Number	Started Remediation / Percentage(%)	Completed Remediation [note_13] / Number	Completed Remediation [note_13] / Percentage(%)	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	95	15%	4	5%	9	11%	82	17%	86%	96%
London	387	60%	69	88%	49	61%	269	56%	70%	82%
East of England	15	2%	0	0%	2	3%	13	3%	87%	100%
East Midlands	13	2%	0	0%	3	4%	10	2%	77%	100%
North East	7	1%	1	1%	2	3%	4	1%	57%	86%
South East	48	8%	0	0%	2	3%	46	10%	96%	100%
South West	21	3%	0	0%	4	5%	17	4%	81%	100%
West Midlands	12	2%	1	1%	1	1%	10	2%	83%	92%
Yorkshire and The Humber	42	7%	3	4%	8	10%	31	6%	74%	93%
Total	640	100%	78	100%	80	100%	482	100%	75%	88%

## BSF_3
BSF number of eligible buildings by funding allocations, expenditure and tenure, England, 25 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data is not available for these variables.
Table BSF_3a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF .
Funding Allocations [note_15][note_46][note _48]	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings [Note 14]	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Funding / (£ millions)
Full Applications Approved	485	2,102	6	7
Pre-Tender Support Allocations	730	309	5	2
Total [note 10]		2,412		9	114	231	2,652

Table BSF_3b: Amount of expenditure from the BSF by tenure.
Expenditure [note_40][note_41][note _48]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	805	1,837	10	7	101	194	916	2,038

## BSF_4
BSF remediation progress of eligible buildings by local authority, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings [note_23, note_24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_42]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF yet to be remediated / Number	Completed Remediation / Percentage(%)	Started or Completed Remediation / Percentage(%)
Adur	1-5	0	100%	100%
Ashford	1-5	0	100%	100%
Barking and Dagenham	7	1-5	57%	100%
Basingstoke and Deane	1-5	0	100%	100%
Barnet	1-5	1-5	50-99%	100%
Barnsley	1-5	0	100%	100%
Bexley	1-5	1-5	50-99%	100%
Birmingham	10	6	40%	100%
Bolton	1-5	0	100%	100%
Bournemouth, Christchurch and Poole	1-5	1-5	50-99%	100%
Bradford	1-5	0	100%	100%
Brent	17	9	47%	71%
Brighton and Hove	1-5	0	100%	100%
Bristol, City of	10	1-5	60%	100%
Bromley	6	1-5	50%	50%
Buckinghamshire	1-5	0	100%	100%
Calderdale	1-5	0	100%	100%
Cambridge	1-5	0	100%	100%
Camden	10	1-5	60%	90%
Chelmsford	1-5	0	100%	100%
Coventry	1-5	1-5	Less than 50%	Less than 50%
Croydon	9	1-5	67%	89%
Dorset	1-5	0	100%	100%
Ealing	6	1-5	67%	100%
Eastbourne	6	1-5	100%	100%
Enfield	1-5	0	100%	100%
Gateshead	1-5	0	100%	100%
Greenwich	13	8	38%	69%
Hackney	23	14	39%	96%
Hammersmith and Fulham	1-5	1-5	Less than 50%	Less than 50%
Haringey	1-5	1-5	50-99%	100%
Harrow	1-5	1-5	50-99%	100%
Havering	1-5	1-5	50-99%	100%
Hillingdon	1-5	1-5	Less than 50%	100%
Hounslow	11	7	36%	64%
Ipswich	1-5	1-5	50-99%	100%
Isle of Wight	1-5	0	100%	100%
Islington	12	10	17%	75%
Kensington and Chelsea	10	8	20%	100%
Kirklees	1-5	0	100%	100%
Lambeth	14	1-5	64%	79%
Lancaster	1-5	0	100%	100%
Leeds	31	13	58%	90%
Leicester	1-5	1-5	50-99%	100%
Lewes	1-5	0	100%	100%
Lewisham	6	1-5	67%	83%
Liverpool	22	17	23%	91%
Luton	1-5	1-5	Less than 50%	100%
Manchester	51	11	78%	98%
Mansfield	1-5	1-5	Less than 50%	100%
Medway	1-5	0	100%	100%
Merton	1-5	1-5	50-99%	100%
Milton Keynes	1-5	0	100%	100%
Newcastle upon Tyne	1-5	1-5	50-99%	50-99%
Newham	64	34	47%	59%
North Somerset	1-5	0	100%	100%
North Yorkshire	1-5	0	100%	100%
Nottingham	9	1-5	78%	100%
Peterborough	1-5	0	100%	100%
Plymouth	1-5	1-5	50-99%	100%
Portsmouth	1-5	1-5	50-99%	100%
Preston	1-5	0	100%	100%
Reading	13	1-5	85%	100%
Redbridge	1-5	1-5	50-99%	50-99%
Richmond upon Thames	1-5	0	100%	100%
Rother	1-5	0	100%	100%
Salford	15	1-5	93%	100%
Sevenoaks	1-5	0	100%	100%
Sheffield	1-5	1-5	50-99%	100%
Slough	1-5	0	100%	100%
Southampton	1-5	0	100%	100%
Southend-on-Sea	1-5	0	100%	100%
Southwark	22	11	50%	86%
Stevenage	1-5	1-5	50-99%	100%
Stockport	1-5	0	100%	100%
Sunderland	1-5	1-5	Less than 50%	100%
Surrey Heath	1-5	0	100%	100%
Sutton	1-5	1-5	Less than 50%	50-99%
Swindon	1-5	1-5	Less than 50%	100%
Tower Hamlets	85	34	60%	93%
Trafford	1-5	1-5	Less than 50%	Less than 50%
Wakefield	1-5	0	100%	100%
Wandsworth	12	1-5	67%	100%
Watford	1-5	0	100%	100%
Westminster	18	8	56%	89%
Worcester	1-5	0	100%	100%

## BSF_5
Remediation status of eligible buildings within BSF, time series, England, 25 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_23, Note_53, Note _58]	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 Number	Jun-25 Number	Jul-25 Number	Aug-25 Number	Sep-25 Number	Oct-25 Number	Nov-25 Number	Dec-25 Number	Jan-26 Number	Feb-26 Number	Mar-26 Number	Apr-26 Number	May-26 Number	Jun-26 Number
Remediation complete	0	10	11	11	28	37	37	39	46	49	101	124	135	141	143	155	158	168	176	190	200	210	217	220	223	229	236	238	239	248	274	281	301	309	313	321	327	332	356	357	357	379	378	380
Remediation complete: awaiting building control sign-off	18	86	93	97	96	102	107	114	117	122	84	75	77	90	107	106	106	109	111	112	121	116	124	132	134	135	137	141	149	159	137	137	123	121	127	123	121	127	106	107	112	91	103	102
Remediation started	150	247	254	268	266	261	263	264	253	254	258	260	268	255	246	237	247	245	235	222	197	191	176	166	164	157	149	144	139	137	133	126	121	115	111	107	102	92	89	87	82	87	76	80
Remediation plans in place		322	310	297	291	289	286	278	249	236	199	203	191	198	200	200	189	174	180	152	125	130	136	139	141	143	144	146	149	143	121	118	125	165	162	134	126	126	125	114	114	106	72	67
Intent to remediate	813	538	540	542	535	525	532	525	285	277	326	314	303	266	251	240	234	219	209	193	158	158	156	153	147	145	147	147	148	145	107	107	104	64	52	23	29	28	22	15	15	15	11	11
Total buildings	981	1203	1208	1215	1216	1214	1225	1220	950	938	968	976	974	950	947	938	934	915	911	869	801	805	809	810	809	809	813	816	824	832	772	769	774	774	765	708	705	705	698	680	680	678	640	640

Remediation Category [note_23, Note_53, Note _58]	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)	Sep-24 Percentage (%)	Oct-24 Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 Percentage (%)	Jun-25 Percentage (%)	Jul-25 Percentage (%)	Aug-25 Percentage (%)	Sep-25 Percentage (%)	Oct-25 Percentage (%)	Nov-25 Percentage (%)	Dec-25 Percentage (%)	Jan-26 Percentage (%)	Feb-26 Percentage (%)	Mar-26 Percentage (%)	Apr-26 Percentage (%)	May-26 Percentage (%)	Jun-26 Percentage (%)
Remediation complete	0%	1%	1%	1%	2%	3%	3%	3%	5%	5%	10%	13%	14%	15%	15%	17%	17%	18%	19%	22%	25%	26%	27%	27%	28%	28%	29%	29%	29%	30%	35%	37%	39%	40%	41%	45%	46%	47%	51%	53%	53%	56%	59%	59%
Remediation complete: awaiting building control sign-off	2%	7%	8%	8%	8%	8%	9%	9%	12%	13%	9%	8%	8%	9%	11%	11%	11%	12%	12%	13%	15%	14%	15%	16%	17%	17%	17%	17%	18%	19%	18%	18%	16%	16%	17%	17%	17%	18%	15%	16%	16%	13%	16%	16%
Remediation started	15%	21%	21%	22%	22%	21%	21%	22%	27%	27%	27%	27%	28%	27%	26%	25%	26%	27%	26%	26%	25%	24%	22%	20%	20%	19%	18%	18%	17%	16%	17%	16%	16%	15%	15%	15%	14%	13%	13%	13%	12%	13%	12%	13%
Remediation plans in place		27%	26%	24%	24%	24%	23%	23%	26%	25%	21%	21%	20%	21%	21%	21%	20%	19%	20%	17%	16%	16%	17%	17%	17%	18%	18%	18%	18%	17%	16%	15%	16%	21%	21%	19%	18%	18%	18%	17%	17%	16%	11%	10%
Intent to remediate	83%	45%	45%	45%	44%	43%	43%	43%	30%	30%	34%	32%	31%	28%	27%	26%	25%	24%	23%	22%	20%	20%	19%	19%	18%	18%	18%	18%	18%	17%	14%	14%	13%	8%	7%	3%	4%	4%	3%	2%	2%	2%	2%	2%
Total buildings [note_10]	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_1
Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 25 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	384	91%	322	59%	57	60%	763	72%
Works complete awaiting building control signoff	18	4%	96	18%	6	6%	120	11%
Remediation started	8	2%	58	11%	27	28%	93	9%
Remediation not started	11	3%	68	12%	5	5%	84	8%
Total [note_59]	421	100%	544	100%	95	100%	1,060	100%

## Combined_2
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, England, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_39, note_62, note_87]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	534	26%	1,147	47%	1,681	38%
Remediation underway	376	19%	322	13%	698	16%
In programme	1,112	55%	978	40%	2,090	47%
Total	2,022	100%	2,447	100%	4,469	100%

## Combined_3
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, by local authority, England, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for percentage of buildings unless stated otherwise.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_13, note_17, note_18, note_39, note_56, note_62, note_87]	Buildings monitored	In programme / Percentage(%)	Remediation Underway / Percentage(%)	Completed Remediation / Percentage(%)
Barking and Dagenham	11-50	41%	27%	33%
Barnet	51-100	35%	12%	53%
Basingstoke and Deane	11-50	33%	38%	29%
Bexley	11-50	36%	0%	64%
Birmingham	51-100	49%	12%	39%
Bournemouth, Christchurch and Poole	11-50	49%	7%	44%
Bradford	11-50	42%	25%	33%
Brent	51-100	48%	11%	41%
Brighton and Hove	51-100	49%	16%	34%
Bristol, City of	101-200	59%	11%	30%
Bromley	11-50	60%	5%	35%
Cambridge	11-50	78%	8%	14%
Camden	51-100	45%	14%	41%
Coventry	11-50	82%	0%	18%
Croydon	51-100	51%	9%	40%
Dacorum	11-50	64%	29%	7%
Dartford	11-50	30%	9%	61%
Ealing	51-100	33%	9%	58%
Eastbourne	11-50	36%	14%	50%
Elmbridge	11-50	67%	25%	8%
Enfield	11-50	55%	9%	36%
Gateshead	11-50	69%	0%	31%
Greenwich	101-200	37%	25%	38%
Hackney	101-200	41%	13%	46%
Hammersmith and Fulham	11-50	61%	11%	28%
Haringey	11-50	25%	28%	47%
Harrow	11-50	50%	9%	41%
Havering	11-50	42%	6%	52%
Hertsmere	11-50	28%	61%	11%
Hillingdon	11-50	58%	26%	16%
Hounslow	51-100	47%	16%	37%
Ipswich	11-50	54%	14%	32%
Islington	101-200	45%	33%	22%
Kensington and Chelsea	11-50	36%	18%	45%
Lambeth	51-100	58%	3%	39%
Leeds	51-100	36%	17%	47%
Leicester	11-50	63%	17%	21%
Lewisham	51-100	44%	16%	40%
Liverpool	101-200	51%	20%	29%
Maidstone	11-50	40%	32%	28%
Manchester	201-400	39%	17%	45%
Medway	11-50	50%	6%	44%
Merton	11-50	60%	15%	25%
Milton Keynes	11-50	77%	10%	13%
Newcastle upon Tyne	11-50	39%	10%	52%
Newham	101-200	41%	17%	42%
North Somerset	11-50	64%	18%	18%
Norwich	11-50	27%	14%	59%
Nottingham	11-50	44%	13%	44%
Plymouth	11-50	57%	13%	30%
Portsmouth	11-50	57%	18%	24%
Reading	11-50	37%	10%	53%
Redbridge	11-50	68%	7%	25%
Salford	51-100	33%	20%	47%
Sheffield	11-50	50%	14%	36%
Slough	11-50	48%	10%	43%
Southampton	101-200	21%	3%	77%
Southwark	101-200	63%	11%	26%
Stoke-on-Trent	11-50	75%	25%	0%
Sunderland	11-50	43%	7%	50%
Sutton	11-50	55%	5%	40%
Tower Hamlets	Over 400	46%	20%	34%
Trafford	11-50	63%	6%	31%
Waltham Forest	11-50	57%	2%	41%
Wandsworth	101-200	48%	10%	42%
Westminster	51-100	45%	6%	49%
Woking	11-50	69%	23%	8%

## Combined_4
Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, by remediation status, England, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings [note_10, note_13, note_17, note_18, note_39, note_62, note_87]	Estimated dwellings in 11-18m buildings	Estimated dwellings in 18m+ buildings	Estimated Total dwellings
Remediation complete (including those awaiting building control signoff)	17,000	85,000	102,000
Remediation underway	10,000	25,000	35,000
In programme	36,000	66,000	102,000
Total	63,000	176,000	239,000

## Combined_5
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, England, by tenure, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_39, note_62, note_87]	Private / Number	Private / Percentage (%)	Social / Number	Social / Percentage (%)	Other [note 47] / Number	Other / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	926	33%	659	41%	96	95%	1,681	38%
Remediation underway	465	17%	230	14%	3	3%	698	16%
In programme	1,377	50%	711	44%	2	2%	2,090	47%
Total	2,768	100%	1,600	100%	101	100%	4,469	100%

## Combined_6
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, England, time series, 30 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_13,note_16, note_17, note_18, note_39, note_52, note_62, note_87]	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 / Number	Jun-25 / Number	Jul-25 / Number	Aug-25 / Number	Sep-25 / Number	Oct-25 / Number	Nov-25 / Number	Dec-25 / Number	Jan-26 / Number	Feb-26 / Number	Mar-26 / Number	Apr-26 / Number	May-26 / Number	Jun-26 / Number
Remediation complete (including those awaiting building control signoff)	448	456	461	477	492	499	508	523	535	544	703	777	797	815	863	976	991	1,088	1,332	1,350	1,392	1,412	1,436	1,463	1,472	1,482	1,619	1,637	1,652	1,754	1,767	1,780	1,927	1,935	1,946	1,938	1,475	1,500	1,521	1,531	1,544	1,672	1,681
Remediation underway	301	308	322	321	317	319	320	308	304	311	809	826	811	871	952	992	984	978	969	949	985	1,000	983	934	931	928	809	822	825	728	723	722	750	759	759	803	693	695	777	868	871	659	698
In programme	853	844	834	820	806	806	791	519	501	509	2,285	2,221	2,231	2,286	2,277	2,361	2,361	2,308	2,312	2,331	2,394	2,409	2,415	2,601	2,608	2,615	2,586	2,572	2,575	2,694	2,700	2,712	2,877	2,864	2,865	2,872	1,958	1,996	2,012	1,923	1,963	2,080	2,090
Total	1,602	1,608	1,617	1,618	1,615	1,624	1,619	1,350	1,340	1,364	3,797	3,824	3,839	3,972	4,092	4,329	4,336	4,374	4,613	4,630	4,771	4,821	4,834	4,998	5,011	5,025	5,014	5,031	5,052	5,176	5,190	5,214	5,554	5,558	5,570	5,613	4,126	4,191	4,310	4,322	4,378	4,411	4,469

Remediation Category [note_13, note_16, note_17, note_18, note_39, note_52, note_62, note_87]	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)	Sep-24 / Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)	Jan-25 / Percentage (%)	Feb-25 / Percentage (%)	Mar-25 / Percentage (%)	Apr-25 / Percentage (%)	May-25 / Percentage (%)	Jun-25 / Percentage (%)	Jul-25 / Percentage (%)	Aug-25 / Percentage (%)	Sep-25 / Percentage (%)	Oct-25 / Percentage (%)	Nov-25 / Percentage (%)	Dec-25 / Percentage (%)	Jan-26 / Percentage (%)	Feb-26 / Percentage (%)	Mar-26 / Percentage (%)	Apr-26 / Percentage (%)	May-26 / Percentage (%)	Jun-26 / Percentage (%)
Remediation complete (including those awaiting building control signoff)	28%	28%	29%	29%	30%	31%	31%	39%	40%	40%	19%	20%	21%	21%	21%	23%	23%	25%	29%	29%	29%	29%	30%	29%	29%	29%	32%	33%	33%	34%	34%	34%	35%	35%	35%	35%	36%	36%	35%	35%	35%	38%	38%
Remediation underway	19%	19%	20%	20%	20%	20%	20%	23%	23%	23%	21%	22%	21%	22%	23%	23%	23%	22%	21%	20%	21%	21%	20%	19%	19%	18%	16%	16%	16%	14%	14%	14%	14%	14%	14%	14%	17%	17%	18%	20%	20%	15%	16%
In programme	53%	52%	52%	51%	50%	50%	49%	38%	37%	37%	60%	58%	58%	58%	56%	55%	54%	53%	50%	50%	50%	50%	50%	52%	52%	52%	52%	51%	51%	52%	52%	52%	52%	52%	51%	51%	47%	48%	47%	44%	45%	47%	47%
Total	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_7
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and reported as self-funded by registered providers of social housing, England, by region, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_13, note_16, note_17, note_18, note_39, note_62, note_87]	Total buildings monitored / Number	Total buildings monitored / Percentage (%)	In programme / Number	In programme / Percentage (%)	Remediation underway / Number	Remediation underway / Percentage (%)	Remediation complete (including those awaiting building control signoff) / Number	Remediation complete (including those awaiting building control signoff) / Percentage (%)	Buildings monitored that have completed Remediation / Percentage (%)	Buildings monitored that have started or completed remediation / Percentage (%)
North West	489	11%	199	10%	90	13%	200	12%	41%	59%
London	2,409	54%	1,127	54%	371	53%	911	54%	38%	53%
East of England	250	6%	139	7%	48	7%	63	4%	25%	44%
East Midlands	83	2%	43	2%	15	2%	25	1%	30%	48%
North East	71	2%	34	2%	5	1%	32	2%	45%	52%
South East	600	13%	263	13%	86	12%	251	15%	42%	56%
South West	265	6%	149	7%	38	5%	78	5%	29%	44%
West Midlands	140	3%	76	4%	16	2%	48	3%	34%	46%
Yorkshire and The Humber	162	4%	60	3%	29	4%	73	4%	45%	63%
Total	4,469	100%	2,090	100%	698	100%	1,681	100%	38%	53%

## Combined_8
Remediation progress for unique buildings being remediated or mitigated as part of a government funded scheme, 11 metres and over in height, England, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_62, note_63]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	110	13%	854	55%	964	40%
Remediation underway	201	24%	179	11%	380	16%
In programme	537	63%	528	34%	1,065	44%
Total	848	100%	1,561	100%	2,409	100%

## Combined_9
Number of unique buildings known by government programmes in December 2020, which haven't started remediation by 30 April 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building Identification [note_94]	Buildings monitored	Not Started Remediation / Number	Not Started Remediation / Percentage (%)
Identified by Dec 2020 - All Buildings [note_95, note_97]	1510	385	25%
Identified by Dec 2020 - Buildings which are proceeding through 2020 criteria [note_96]	948	58	6%

## CSS_1
Application status of buildings within the CSS, England, 30 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Pre - eligible buildings [note_44]	Number	Percentage (%)
Pre - application	939	45%
Live application	1,156	55%
Total pre-eligible buildings	2,095	100%

Eligible buildings [note_13]	Number	Percentage (%)
Works not started	1,014	73%
Works started	262	19%
Works completed	119	9%
Total eligible buildings	1,395	100%

## CSS_2
CSS remediation progress by region, England, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_44, note_13]	Eligible Buildings in the CSS / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible CSS buildings that have started or completed remediation / Percentage (%)
North West	167	114	42	11	7%	32%
London	751	570	110	71	9%	24%
East of England	84	56	21	7	8%	33%
East Midlands	41	28	9	4	10%	32%
North East	18	13	2	3	17%	28%
South East	134	88	36	10	7%	34%
South West	89	69	16	4	4%	22%
West Midlands	44	35	9	0	0%	20%
Yorkshire and The Humber	63	41	14	8	13%	35%
Northern Ireland	4	0	3	1	25%	100%
Total	1,395	1,014	262	119	9%	27%

## CSS_3
CSS remediation progress by height, England, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_44, note_13]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)
Remediation complete	110	13%	9	2%
Remediation started	199	23%	63	12%
In programme	541	64%	473	87%
Total buildings	850	100%	545	100%

## CSS_4
CSS remediation progress by tenure, England, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_44, note_13]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	38	6%	81	11%
Remediation started	103	16%	159	21%
In programme	488	78%	526	69%
Total buildings	629	100%	766	100%

## CSS_5
CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 30 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Table CSS_5a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the CSS
Funding Allocations	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Funding / (£ millions)
Works Package Approved	313	1,191.6	119	184.7	1,376.4
Pre-Tender Support Allocations	620	223.6	467	217.9	441.6
Total [note 10]	642	1,415.3	521	402.7	1,817.9

Table CSS_5b: Amount of expenditure from the CSS by tenure
Expenditure [note_41]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	632	535.6	513	287.8	1,145	823.4

## CSS_6
CSS remediation progress, time series, England, 30 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_44, note_13]	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number	Jan-25 / Number	Feb-25 / Number	Mar-25 / Number	Apr-25 / Number	May-25 / Number	Jun-25 / Number	Jul-25 / Number	Aug-25 Number	Sep-25 / Number	Oct-25 / Number	Nov-25 Number	Dec-25 Number	Jan-26 / Number	Feb-26 / Number	Mar-26 / Number	Apr-26 / Number	May-26 / Number	Jun-26 / Number
Remediation complete	0	0	0	0	0	0	0	0	0	0	0	0	14	16	17	20	24	31	33	38	43	49	53	55	60	65	67	72	85	93	100	112	119
Remediation started	0	0	0	0	1	2	2	2	6	8	10	22	17	30	36	45	56	82	85	85	87	93	102	114	120	125	139	153	170	268	263	255	262
In programme	48	75	104	127	151	168	199	222	282	371	395	410	429	446	472	491	510	504	538	609	623	640	651	667	732	745	774	826	891	813	876	958	1,014
Total buildings	48	75	104	127	152	170	201	224	288	379	405	432	460	492	525	556	590	617	656	732	753	782	806	836	912	935	980	1,051	1,146	1,174	1,239	1,325	1,395

Remediation Category [note_44, note_13]	Oct-23 Percentage (%)	Nov-23 Percentage (%)	Dec-23 Percentage (%)	Jan-24 Percentage (%)	Feb-24 Percentage (%)	Mar-24 Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 / Percentage (%)	Aug-24 Percentage (%)	Sep-24 Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 Percentage (%)	Jan-25 Percentage (%)	Feb-25 Percentage (%)	Mar-25 Percentage (%)	Apr-25 Percentage (%)	May-25 Percentage (%)	Jun-25 Percentage (%)	Jul-25 Percentage (%)	Aug-25 Percentage (%)	Sep-25 Percentage (%)	Oct-25 Percentage (%)	Nov-25 Percentage (%)	Dec-25 Percentage (%)	Jan-26 Percentage (%)	Feb-26 Percentage (%)	Mar-26 Percentage (%)	Apr-26 Percentage (%)	May-26 Percentage (%)	Jun-26 Percentage (%)
Remediation complete	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	3%	3%	3%	4%	4%	5%	5%	5%	6%	6%	7%	7%	7%	7%	7%	7%	7%	8%	8%	8%	9%
Remediation started	0%	0%	0%	0%	1%	1%	1%	1%	2%	2%	2%	5%	4%	6%	7%	8%	9%	13%	13%	12%	12%	12%	13%	14%	13%	13%	14%	15%	15%	23%	21%	19%	19%
In programme	100%	100%	100%	100%	99%	99%	99%	99%	98%	98%	98%	95%	93%	91%	90%	88%	86%	82%	82%	83%	83%	82%	81%	80%	80%	80%	79%	79%	78%	69%	71%	72%	73%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Developer_1
Remediation status of buildings requiring works under the developer remediation contract by height group, England, 30 June 2026
Back to Contents
This worksheet contains four tables, presented next to each other vertically with two blank rows in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - All Defect Types [Note 25, Note 26, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	214	16%	273	22%	487	19%
Remediation complete - awaiting building control sign-off	48	4%	61	5%	109	4%
Remediation started	344	25%	324	26%	668	26%
Remediation not Started - Plans in Place	209	15%	174	14%	383	15%
Remediation not Started - No Plans in Place	549	40%	418	33%	967	37%
Total	1364	100%	1,250	100%	2,614	100%

Remediation Category - Cladding Defects [Note 25, Note 26, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	162	18%	272	29%	434	24%
Remediation complete - awaiting building control sign-off	59	7%	73	8%	132	7%
Remediation started	139	16%	157	17%	296	16%
Remediation not Started - Plans in Place	196	22%	191	20%	387	21%
Remediation not Started - No Plans in Place	325	37%	251	27%	576	32%
Total	881	100%	944	100%	1,825	100%

Remediation Category - Self-reported Information, All Defect Types [Note 25, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	210	16%	207	19%	417	17%
Remediation complete - awaiting building control sign-off	48	4%	46	4%	94	4%
Remediation started	344	26%	290	26%	634	26%
Remediation not Started - Plans in Place	209	16%	174	16%	383	16%
Remediation not Started - No Plans in Place	532	40%	396	36%	928	38%
Total	1,343	100%	1,113	100%	2,456	100%

Remediation Category - BSF Transfers [Note 25, Note 26, Note 29, Note 50]	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	48	11%
Remediation complete - awaiting building control sign-off	23	5%
Remediation started	153	34%
Remediation not Started - Plans in Place	89	20%
Remediation not Started - No Plans in Place	83	18%
No life-critical fire-safety defects reported	55	12%
Total buildings	451	100%

## Developer_2
Estimated cost of buildings requiring works under the developer remediation contract by height, England, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for estimated cost of buildings identified as requiring works under the Developer Remediation Contract in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Cost Category [Note 29, Note 32]	11-18m / (£ millions)	18m+ / (£ millions)	Total / (£ millions)
Total estimated cost of works	1,311	2,930	4,241

## Developer_3
Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 30 April 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 30 April 2026.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note 29]	Number of buildings developed or refurbished by the developer covered by the contract	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme) [Note 28]	Number of buildings found to require remediation, which will be remediated by the developer directly [Note 30]	Number of buildings without a determination [Note 31]	Number of buildings where no remediation is required	Number of buildings with no reported defects under clauses 5.4d(i) or 5.4d(ii) of the developer remediation contract	Percentage of buildings for which the developer has determined whether remediation is required
Total (all developers)	4738	4569	2456	263	1730	120	94%
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Arada London Ltd	16	16	2	0	14	0	100%
Ballymore Limited	100	84	19	14	11	40	83%
Barratt Redrow PLC	839	817	522	183	112	0	78%
Bellway PLC	435	421	402	0	19	0	100%
Bewley Group Limited	9	7	5	0	2	0	100%
Bloor Investments Limited	-	-	-	-	-	-	-
Bouygues (UK) Limited	35	31	15	0	16	0	100%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	13	10	6	0	0	4	100%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Cala Group (Holdings) Limited	24	24	22	0	2	0	100%
Canary Wharf Group PLC	13	13	0	4	9	0	69%
Churchill Living (formerly Churchill Retirement PLC)	8	8	2	0	6	0	100%
Crest Nicholson Holdings PLC	297	296	280	4	12	0	99%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	21	21	19	0	2	0	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	121	121	80	1	1	39	99%
Frasers Property (UK) Ltd	16	11	6	2	3	0	82%
Galliard Group Limited	148	148	48	6	75	19	96%
Grosvenor Developments Limited	21	21	12	1	0	8	95%
Hill Holdings Limited	90	90	22	7	60	1	92%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	7	7	5	0	2	0	100%
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	35	32	7	14	11	0	56%
Lendlease Europe Holdings Limited	89	88	39	0	49	0	100%
London Square Development (Holdings) Limited	40	40	39	0	1	0	100%
McCarthy & Stone Limited	63	63	24	0	39	0	100%
Miller Homes Limited	39	39	37	0	2	0	100%
MJ Gleeson PLC	18	17	15	1	1	0	94%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	120	113	23	0	90	0	100%
Morris Homes Group Limited	6	6	2	0	4	0	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	21	20	7	0	7	6	100%
Pegasus Homes (formerly Lifestory Group)	18	18	1	0	17	0	100%
Persimmon Public Limited Company	79	78	65	0	12	1	100%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	25	22	16	0	6	0	100%
Seven Capital PLC	21	21	19	0	0	2	100%
Sorbon Group Limited (parent company for Shanly Homes)	26	26	20	0	6	0	100%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	453	445	242	13	190	0	97%
Telford Homes Limited	144	144	98	0	46	0	100%
The Berkeley Group Holdings PLC	825	814	82	11	721	0	99%
The British Land Company PLC	16	16	4	0	12	0	100%
Tilia Homes Limited	8	8	8	0	0	0	100%
Vistry Group PLC	294	288	140	0	148	0	100%
Viva Midco Limited (parent company for Avant Homes)	59	0	-	-	-	-	-
Wates Group Limited	24	23	14	0	9	0	100%
Watkin Jones PLC	14	14	12	2	0	0	86%
Weston Group PLC	88	88	75	0	13	0	100%

## Developer_4
Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 30 April 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 30 April 2026.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Remediation Status
		Buildings being remediated by the developer directly where remediation has...
		…not yet started		... started or completed		... started		...completed, awaiting building control sign-off		...completed
Developer [Note 25, Note 29]	Number of buildings found to require remediation, which will be remediated by the developer directly [Note 30]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total (all developers)	2456	1311	53%	1145	47%	634	26%	94	4%	417	17%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Arada London Ltd	2	0	0%	2	100%	0	0%	0	0%	2	100%
Ballymore Limited	19	8	42%	11	58%	0	0%	0	0%	11	58%
Barratt Redrow PLC	522	390	75%	132	25%	40	8%	39	7%	53	10%
Bellway PLC	402	244	61%	158	39%	143	36%	0	0%	15	4%
Bewley Group Limited	5	1	20%	4	80%	1	20%	0	0%	3	60%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-	-
Bouygues (UK) Limited	15	8	53%	7	47%	0	0%	0	0%	7	47%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	6	4	67%	2	33%	0	0%	0	0%	2	33%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-	-
Cala Group (Holdings) Limited	22	8	36%	14	64%	8	36%	0	0%	6	27%
Canary Wharf Group PLC	0	0	-	0	-	0	-	0	-	0	-
Churchill Living (formerly Churchill Retirement PLC)	2	2	100%	0	0%	0	0%	0	0%	0	0%
Crest Nicholson Holdings PLC	280	109	39%	171	61%	160	57%	7	3%	4	1%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	19	16	84%	3	16%	2	11%	1	5%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	80	20	25%	60	75%	43	54%	0	0%	17	21%
Frasers Property (UK) Ltd	6	1	17%	5	83%	0	0%	0	0%	5	83%
Galliard Group Limited	48	28	58%	20	42%	3	6%	0	0%	17	35%
Grosvenor Developments Limited	12	4	33%	8	67%	7	58%	0	0%	1	8%
Hill Holdings Limited	22	9	41%	13	59%	2	9%	0	0%	11	50%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	5	0	0%	5	100%	3	60%	0	0%	2	40%
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	7	4	57%	3	43%	3	43%	0	0%	0	0%
Lendlease Europe Holdings Limited	39	18	46%	21	54%	19	49%	0	0%	2	5%
London Square Development (Holdings) Limited	39	1	3%	38	97%	38	97%	0	0%	0	0%
McCarthy & Stone Limited	24	6	25%	18	75%	3	13%	2	8%	13	54%
Miller Homes Limited	37	5	14%	32	86%	14	38%	0	0%	18	49%
MJ Gleeson PLC	15	9	60%	6	40%	2	13%	0	0%	4	27%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	23	9	39%	14	61%	2	9%	0	0%	12	52%
Morris Homes Group Limited	2	0	0%	2	100%	0	0%	0	0%	2	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	7	4	57%	3	43%	2	29%	0	0%	1	14%
Pegasus Homes (formerly Lifestory Group)	1	0	0%	1	100%	0	0%	0	0%	1	100%
Persimmon Public Limited Company	65	26	40%	39	60%	30	46%	0	0%	9	14%
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	16	1	6%	15	94%	1	6%	0	0%	14	88%
Seven Capital PLC	19	18	95%	1	5%	1	5%	0	0%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	20	8	40%	12	60%	4	20%	0	0%	8	40%
Story Homes Limited	-	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	242	131	54%	111	46%	41	17%	27	11%	43	18%
Telford Homes Limited	98	92	94%	6	6%	6	6%	0	0%	0	0%
The Berkeley Group Holdings PLC	82	28	34%	54	66%	8	10%	3	4%	43	52%
The British Land Company PLC	4	2	50%	2	50%	2	50%	0	0%	0	0%
Tilia Homes Limited	8	2	25%	6	75%	4	50%	0	0%	2	25%
Vistry Group PLC	140	76	54%	64	46%	17	12%	15	11%	32	23%
Viva Midco Limited (parent company for Avant Homes)	0	0	-	0	-	0	-	0	-	0	-
Wates Group Limited	14	7	50%	7	50%	0	0%	0	0%	7	50%
Watkin Jones PLC	12	10	83%	2	17%	2	17%	0	0%	0	0%
Weston Group PLC	75	2	3%	73	97%	23	31%	0	0%	50	67%

## Developer_5
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 30 April 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 30 April 2026.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings that require remediation by the developer which have not yet started, with a start date…

		…within the next 12 months		…after the next 12 months		…start date unclear
Developer [Note 27, Note 29]	Number of buildings being remediated by the developer directly where remediation has not started	Number	Percentage‎	Number	Percentage	Number	Percentage
Total (all developers)	1311	678	52%	120	9%	513	39%
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Arada London Ltd	0	0	-	0	-	0	-
Ballymore Limited	8	7	88%	0	0%	1	13%
Barratt Redrow PLC	390	143	37%	42	11%	205	53%
Bellway PLC	244	95	39%	2	1%	147	60%
Bewley Group Limited	1	0	0%	0	0%	1	100%
Bloor Investments Limited	-	-	-	-	-	-	-
Bouygues (UK) Limited	8	2	25%	6	75%	0	0%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0%	0	0%	4	100%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Cala Group (Holdings) Limited	8	0	0%	0	0%	8	100%
Canary Wharf Group PLC	0	0	-	0	-	0	-
Churchill Living (formerly Churchill Retirement PLC)	2	2	100%	0	0%	0	0%
Crest Nicholson Holdings PLC	109	63	58%	0	0%	46	42%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	16	9	56%	7	44%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	20	18	90%	1	5%	1	5%
Frasers Property (UK) Ltd	1	1	100%	0	0%	0	0%
Galliard Group Limited	28	15	54%	9	32%	4	14%
Grosvenor Developments Limited	4	4	100%	0	0%	0	0%
Hill Holdings Limited	9	7	78%	0	0%	2	22%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	-	0	-	0	-
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	4	2	50%	0	0%	2	50%
Lendlease Europe Holdings Limited	18	9	50%	7	39%	2	11%
London Square Development (Holdings) Limited	1	1	100%	0	0%	0	0%
McCarthy & Stone Limited	6	2	33%	0	0%	4	67%
Miller Homes Limited	5	4	80%	0	0%	1	20%
MJ Gleeson PLC	9	9	100%	0	0%	0	0%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	9	2	22%	0	0%	7	78%
Morris Homes Group Limited	0	0	-	0	-	0	-
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	4	100%	0	0%	0	0%
Pegasus Homes (formerly Lifestory Group)	0	0	-	0	-	0	-
Persimmon Public Limited Company	26	17	65%	0	0%	9	35%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	1	1	100%	0	0%	0	0%
Seven Capital PLC	18	3	17%	0	0%	15	83%
Sorbon Group Limited (parent company for Shanly Homes)	8	2	25%	0	0%	6	75%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	131	103	79%	21	16%	7	5%
Telford Homes Limited	92	68	74%	11	12%	13	14%
The Berkeley Group Holdings PLC	28	27	96%	0	0%	1	4%
The British Land Company PLC	2	0	0%	0	0%	2	100%
Tilia Homes Limited	2	1	50%	0	0%	1	50%
Vistry Group PLC	76	51	67%	10	13%	15	20%
Viva Midco Limited (parent company for Avant Homes)	0	0	-	0	-	0	-
Wates Group Limited	7	4	57%	0	0%	3	43%
Watkin Jones PLC	10	0	0%	4	40%	6	60%
Weston Group PLC	2	2	100%	0	0%	0	0%

## Developer_6
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 30 April 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 30 April 2026.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which have not yet started, start profiles by financial year...				Buildings which have not yet completed, with...

Developer [Note 27, Note 29]	Number of buildings being remediated by the developer directly where remediation has not started	2025-2026	2026-2027	2027-2028	2028-2029	... no start date provided	... completion date prior to 2025-2026
Total (all developers)	1311	35	659	116	26	468	7
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Arada London Ltd	0	0	0	0	0	0	0
Ballymore Limited	8	1	7	0	0	0	0
Barratt Redrow PLC	390	3	133	52	0	202	0
Bellway PLC	244	8	98	2	0	135	1
Bewley Group Limited	1	1	0	0	0	0	0
Bloor Investments Limited	-	-	-	-	-	-	-
Bouygues (UK) Limited	8	0	2	6	0	0	0
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0	0	0	4	0
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Cala Group (Holdings) Limited	8	6	0	0	0	2	0
Canary Wharf Group PLC	0	0	0	0	0	0	0
Churchill Living (formerly Churchill Retirement PLC)	2	0	2	0	0	0	0
Crest Nicholson Holdings PLC	109	0	63	0	0	46	0
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	16	0	9	5	2	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	20	0	16	3	0	1	0
Frasers Property (UK) Ltd	1	0	1	0	0	0	0
Galliard Group Limited	28	0	15	4	5	4	0
Grosvenor Developments Limited	4	0	4	0	0	0	0
Hill Holdings Limited	9	0	7	0	0	2	0
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	0	0	0	0	0
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	4	0	2	0	0	2	0
Lendlease Europe Holdings Limited	18	1	9	7	0	1	0
London Square Development (Holdings) Limited	1	0	1	0	0	0	0
McCarthy & Stone Limited	6	0	2	0	0	4	0
Miller Homes Limited	5	1	4	0	0	0	0
MJ Gleeson PLC	9	0	9	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	9	0	2	0	0	5	2
Morris Homes Group Limited	0	0	0	0	0	0	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	0	4	0	0	0	0
Pegasus Homes (formerly Lifestory Group)	0	0	0	0	0	0	0
Persimmon Public Limited Company	26	0	17	0	0	9	0
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	1	0	1	0	0	0	0
Seven Capital PLC	18	0	3	0	0	15	0
Sorbon Group Limited (parent company for Shanly Homes)	8	0	2	0	0	3	3
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	131	4	101	4	19	3	0
Telford Homes Limited	92	1	60	19	0	11	1
The Berkeley Group Holdings PLC	28	0	27	0	0	1	0
The British Land Company PLC	2	0	0	0	0	2	0
Tilia Homes Limited	2	0	1	0	0	1	0
Vistry Group PLC	76	9	51	10	0	6	0
Viva Midco Limited (parent company for Avant Homes)	0	0	0	0	0	0	0
Wates Group Limited	7	0	4	0	0	3	0
Watkin Jones PLC	10	0	0	4	0	6	0
Weston Group PLC	2	0	2	0	0	0	0

## Developer_7
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 30 April 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 30 April 2026.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings that require remediation by the developer which have not yet completed, with a completion date…
		…within the next 12 months		…after the next 12 months		…completion date unclear
Developer [Note 29, Note 45]	Number of buildings being remediated by the developer directly where remediation has not yet completed	Number	Percentage‎	Number	Percentage	Number2	Pecentage
Total (all developers)	1945	382	20%	957	49%	606	31%
Abbey Developments Limited	0	0	-	0	-	0	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Arada London Ltd	0	0	-	0	-	0	-
Ballymore Limited	8	6	75%	2	25%	0	0%
Barratt Redrow PLC	430	44	10%	183	43%	203	47%
Bellway PLC	387	30	8%	214	55%	143	37%
Bewley Group Limited	2	2	100%	0	0%	0	0%
Bloor Investments Limited	-	-	-	-	-	-	-
Bouygues (UK) Limited	8	0	0%	2	25%	6	75%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0%	0	0%	4	100%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Cala Group (Holdings) Limited	16	2	13%	0	0%	14	88%
Canary Wharf Group PLC	0	0	-	0	-	0	-
Churchill Living (formerly Churchill Retirement PLC)	2	2	100%	0	0%	0	0%
Crest Nicholson Holdings PLC	269	69	26%	149	55%	51	19%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	18	1	6%	17	94%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	63	40	63%	22	35%	1	2%
Frasers Property (UK) Ltd	1	0	0%	0	0%	1	100%
Galliard Group Limited	31	6	19%	19	61%	6	19%
Grosvenor Developments Limited	11	4	36%	3	27%	4	36%
Hill Holdings Limited	11	3	27%	5	45%	3	27%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0%	3	100%	0	0%
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	7	2	29%	2	29%	3	43%
Lendlease Europe Holdings Limited	37	2	5%	34	92%	1	3%
London Square Development (Holdings) Limited	39	0	0%	0	0%	39	100%
McCarthy & Stone Limited	9	1	11%	2	22%	6	67%
Miller Homes Limited	19	7	37%	5	26%	7	37%
MJ Gleeson PLC	11	9	82%	0	0%	2	18%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	11	2	18%	2	18%	7	64%
Morris Homes Group Limited	0	0	-	0	-	0	-
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	6	5	83%	1	17%	0	0%
Pegasus Homes (formerly Lifestory Group)	0	0	-	0	-	0	-
Persimmon Public Limited Company	56	17	30%	23	41%	16	29%
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	1	50%	1	50%	0	0%
Seven Capital PLC	19	3	16%	0	0%	16	84%
Sorbon Group Limited (parent company for Shanly Homes)	12	9	75%	0	0%	3	25%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	172	49	28%	103	60%	20	12%
Telford Homes Limited	98	6	6%	81	83%	11	11%
The Berkeley Group Holdings PLC	36	17	47%	11	31%	8	22%
The British Land Company PLC	4	1	25%	0	0%	3	75%
Tilia Homes Limited	6	2	33%	1	17%	3	50%
Vistry Group PLC	93	28	30%	49	53%	16	17%
Viva Midco Limited (parent company for Avant Homes)	0	0	-	0	-	0	-
Wates Group Limited	7	1	14%	3	43%	3	43%
Watkin Jones PLC	12	1	8%	5	42%	6	50%
Weston Group PLC	25	10	40%	15	60%	0	0%

## Developer_8
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 30 April 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings for each developer that has signed the developer remediation contract, as of 30 April 2026.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which have not yet completed, completion profiles by financial year...					Buildings which have not yet completed, with...

Developer [Note 29, Note 45]	Number of buildings being remediated by the developer directly where remediation has not yet completed	2025-2026	2026-2027	2027-2028	2028-2029	2029-2030	.. no completion date provided	... completion date prior to 2025-2026
Total (all developers)	1945	72	343	738	221	40	510	21
Abbey Developments Limited	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-
Arada London Ltd	0	0	0	0	0	0	0	0
Ballymore Limited	8	0	6	2	0	0	0	0
Barratt Redrow PLC	430	2	32	138	32	25	199	2
Bellway PLC	387	0	30	163	49	2	141	2
Bewley Group Limited	2	0	2	0	0	0	0	0
Bloor Investments Limited	-	-	-	-	-	-	-	-
Bouygues (UK) Limited	8	0	0	1	1	0	6	0
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	4	0	0	0	0	0	4	0
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-
Cala Group (Holdings) Limited	16	12	2	0	0	0	2	0
Canary Wharf Group PLC	0	0	0	0	0	0	0	0
Churchill Living (formerly Churchill Retirement PLC)	2	0	2	0	0	0	0	0
Crest Nicholson Holdings PLC	269	0	60	153	5	0	48	3
Croudace Homes Group Limited	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	18	0	1	9	8	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-
Fairview Holdings Limited	63	0	36	26	0	0	1	0
Frasers Property (UK) Ltd	1	0	0	0	0	0	1	0
Galliard Group Limited	31	0	7	12	2	5	4	1
Grosvenor Developments Limited	11	0	4	2	1	0	4	0
Hill Holdings Limited	11	1	1	7	0	0	2	0
Hopkins Home Group Limited	-	-	-	-	-	-	-	-
Jelson Holdings Limited	3	0	0	3	0	0	0	0
Keepmoat Limited	-	-	-	-	-	-	-	-
Land Securities Group PLC	7	0	2	2	0	0	3	0
Lendlease Europe Holdings Limited	37	0	2	11	23	0	1	0
London Square Development (Holdings) Limited	39	38	0	0	0	0	1	0
McCarthy & Stone Limited	9	0	1	2	0	0	4	2
Miller Homes Limited	19	3	7	5	0	0	4	0
MJ Gleeson PLC	11	2	9	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	11	0	2	1	1	0	7	0
Morris Homes Group Limited	0	0	0	0	0	0	0	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	6	0	5	1	0	0	0	0
Pegasus Homes (formerly Lifestory Group)	0	0	0	0	0	0	0	0
Persimmon Public Limited Company	56	1	14	24	2	0	15	0
Rowland Group Limited	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	0	1	1	0	0	0	0
Seven Capital PLC	19	0	3	0	0	0	16	0
Sorbon Group Limited (parent company for Shanly Homes)	12	0	9	0	0	0	3	0
Story Homes Limited	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	172	10	46	63	37	8	4	4
Telford Homes Limited	98	0	5	51	31	0	11	0
The Berkeley Group Holdings PLC	36	0	17	10	1	0	5	3
The British Land Company PLC	4	0	1	0	0	0	3	0
Tilia Homes Limited	6	2	2	1	0	0	1	0
Vistry Group PLC	93	1	22	29	26	0	11	4
Viva Midco Limited (parent company for Avant Homes)	0	0	0	0	0	0	0	0
Wates Group Limited	7	0	1	3	0	0	3	0
Watkin Jones PLC	12	0	1	3	2	0	6	0
Weston Group PLC	25	0	10	15	0	0	0	0

## Developer_9
Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 30 April 2026
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 30 April 2026.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Buildings where the developer or 'responsible entity' has engaged with the leaseholders, freeholders, residents, occupiers and other users regarding works for buildings being remediated directly by the developer, excluding completed buildings, by...					Number of buildings being remediated by the developers, excluding completed buildings	Sum of communication
	... the Responsible Entity		... directly		... directly and by the Responsible Entity		... unconfirmed how
Developer [Note 29]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total (all developers)	1318	68%	54	3%	194	10%	2	0%	1945	81%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Arada London Ltd	0	-	0	-	0	-	0	-	0	-
Ballymore Limited	8	100%	0	0%	0	0%	0	0%	8	100%
Barratt Redrow PLC	281	65%	9	2%	29	7%	1	0%	430	74%
Bellway PLC	384	99%	1	0%	2	1%	0	0%	387	100%
Bewley Group Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-
Bouygues (UK) Limited	0	0%	0	0%	2	25%	0	0%	8	25%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	0	0%	0	0%	0	0%	0	0%	4	0%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-
Cala Group (Holdings) Limited	15	94%	0	0%	0	0%	0	0%	16	94%
Canary Wharf Group PLC	0	-	0	-	0	-	0	-	0	-
Churchill Living (formerly Churchill Retirement PLC)	0	0%	0	0%	0	0%	0	0%	2	0%
Crest Nicholson Holdings PLC	143	53%	0	0%	0	0%	1	0%	269	54%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	0	0%	18	100%	0	0%	18	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	3	5%	3	5%	48	76%	0	0%	63	86%
Frasers Property (UK) Ltd	0	0%	1	100%	0	0%	0	0%	1	100%
Galliard Group Limited	23	74%	0	0%	6	19%	0	0%	31	94%
Grosvenor Developments Limited	0	0%	6	55%	5	45%	0	0%	11	100%
Hill Holdings Limited	3	27%	0	0%	4	36%	0	0%	11	64%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	3	100%	0	0%	0	0%	0	0%	3	100%
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	5	71%	0	0%	1	14%	0	0%	7	86%
Lendlease Europe Holdings Limited	0	0%	0	0%	0	0%	0	0%	37	0%
London Square Development (Holdings) Limited	39	100%	0	0%	0	0%	0	0%	39	100%
McCarthy & Stone Limited	0	0%	1	11%	0	0%	0	0%	9	11%
Miller Homes Limited	4	21%	0	0%	11	58%	0	0%	19	79%
MJ Gleeson PLC	4	36%	2	18%	3	27%	0	0%	11	82%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	7	64%	0	0%	2	18%	0	0%	11	82%
Morris Homes Group Limited	0	-	0	-	0	-	0	-	0	-
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	67%	1	17%	0	0%	0	0%	6	83%
Pegasus Homes (formerly Lifestory Group)	0	-	0	-	0	-	0	-	0	-
Persimmon Public Limited Company	52	93%	0	0%	0	0%	0	0%	56	93%
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Seven Capital PLC	3	16%	0	0%	7	37%	0	0%	19	53%
Sorbon Group Limited (parent company for Shanly Homes)	0	0%	0	0%	12	100%	0	0%	12	100%
Story Homes Limited	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	172	100%	0	0%	0	0%	0	0%	172	100%
Telford Homes Limited	65	66%	1	1%	32	33%	0	0%	98	100%
The Berkeley Group Holdings PLC	33	92%	0	0%	3	8%	0	0%	36	100%
The British Land Company PLC	2	50%	0	0%	0	0%	0	0%	4	50%
Tilia Homes Limited	2	33%	4	67%	0	0%	0	0%	6	100%
Vistry Group PLC	48	52%	21	23%	4	4%	0	0%	93	78%
Viva Midco Limited (parent company for Avant Homes)	0	-	0	-	0	-	0	-	0	-
Wates Group Limited	0	0%	4	57%	3	43%	0	0%	7	100%
Watkin Jones PLC	11	92%	0	0%	1	8%	0	0%	12	100%
Weston Group PLC	0	0%	0	0%	1	4%	0	0%	25	4%

## Developer_10
Remediation status of buildings requiring works under the developer remediation contract, time series, England, 31 May 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category - All Defect Types [Note 25, Note 26, Note 29, Note 54]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)	Oct-24 Number	Oct-24 Percentage (%)	Jan-25 Number	Jan-25 Percentage (%)	Apr-25 Number	Apr-25 Percentage (%)	Jul-25 Number	Jul-25 Percentage (%)	Oct-25 Number	Oct-25 Percentage (%)	Jan-26 Number	Jan-26 Percentage (%)	Apr-26 Number	Apr-26 Percentage (%)
Remediation complete	262	19%	307	20%	362	23%	410	25%	439	25%	501	27%	516	25%	537	23%	516	21%	507	20%	596	23%
Remediation started	211	16%	317	21%	365	23%	359	22%	411	24%	456	25%	481	24%	497	21%	569	23%	660	26%	668	26%
Remediation not Started - Plans in Place	506	38%	512	34%	371	24%	455	28%	430	25%	370	20%	372	18%	378	16%	367	15%	329	13%	383	15%
Remediation not Started - No Plans in Place	366	27%	364	24%	471	30%	402	25%	466	27%	517	28%	656	32%	965	41%	1045	42%	1056	41%	957	37%
Total buildings	1345	100%	1500	100%	1569	100%	1626	100%	1746	100%	1844	100%	2025	100%	2377	100%	2497	100%	2552	100%	2604	100%

Remediation Category - Cladding Defects [Note 25, Note 26, Note 29, Note 54]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)	Oct-24 Number	Oct-24 Percentage (%)	Jan-25 Number	Jan-25 Percentage (%)	Apr-25 Number	Apr-25 Percentage (%)	Jul-25 Number	Jul-25 Percentage (%)	Oct-25 Number	Oct-25 Percentage (%)	Jan-26 Number	Jan-26 Percentage (%)	Apr-26 Number	Apr-26 Percentage (%)
Remediation complete	245	19%	284	20%	340	24%	381	26%	397	26%	441	30%	448	29%	463	26%	441	24%	419	23%	566	31%
Remediation started	200	16%	303	22%	337	24%	334	23%	393	26%	348	24%	376	25%	401	23%	452	25%	526	29%	296	16%
Remediation not Started - Plans in Place	476	37%	481	34%	345	24%	418	29%	390	25%	322	22%	325	21%	323	18%	306	17%	274	15%	387	21%
Remediation not Started - No Plans in Place	352	28%	335	24%	406	28%	316	22%	356	23%	340	23%	377	25%	576	33%	606	34%	601	33%	566	31%
Total buildings	1273	100%	1403	100%	1428	100%	1449	100%	1536	100%	1451	100%	1526	100%	1763	100%	1805	100%	1820	100%	1815	100%

## Developer_11
Estimated number of determinations, starts and completions made each quarter for buildings under the developer remediation contract, by height group, England, 30 April 2026 [Note 71]
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Buildings where the Developer is directly responsible for Remediation and a Determination was made... [Note 28] [Note 69]	...Before 31 January 2024 [Note 68]	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025	...Between 1 August 2025 and 31 October 2025	...Between 1 November 2025 and 31 January 2026	...Between 1 February 2026 and 30 April 2026
Total	2364	242	192	195	215	250	406	182	154	106

Buildings (by height) currently found to require Remediation and will be Remediated by the Developer directly, where works started… [Note 30] [Note 70]	...Before 31 July 2023	...Between 1 August 2023 and 31 October 2023	...Between 1 November 2023 and 31 January 2024	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025	...Between 1 August 2025 and 31 October 2025	...Between 1 November 2025 and 31 January 2026	...Between 1 February 2026 and 30 April 2026
11-18m	112	45	73	38	16	54	68	27	18	36	70	45
18m+	167	59	62	61	11	29	43	28	21	13	19	30
Total	279	104	135	99	27	83	111	55	39	49	89	75

Buildings (by height) currently found to require Remediation and will be Remediated by the Developer directly, where works completed… [Note 30] [Note 70]	...Before 31 July 2023	...Between 1 August 2023 and 31 October 2023	...Between 1 November 2023 and 31 January 2024	...Between 1 February 2024 and 30 April 2024	...Between 1 May 2024 and 31 July 2024	...Between 1 August 2024 and 31 October 2024	...Between 1 November 2024 and 31 January 2025	...Between 1 February 2025 and 30 April 2025	...Between 1 May 2025 and 31 July 2025	...Between 1 August 2025 and 31 October 2025	...Between 1 November 2025 and 31 January 2026	...Between 1 February 2026 and 30 April 2026
11-18m	37	24	22	23	9	18	40	14	21	9	10	31
18m+	65	42	10	19	21	6	18	30	8	10	3	21
Total	102	66	32	42	30	24	58	44	29	19	13	52

## Developer_12
Developer by developer update against RAP Joint Plan target one: Finish assessing all their buildings to determine which require works by end July 2025, England, 31 July 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2025.
Some cells refer to notes which can be found in the 'Notes' worksheet.

These tables are based on data reported by developers as at 31 July 2025
This is because they are intended to report on progress that developers had made against the RAP target to finish assessing all their buildings to determine which require works by end July 2025
For the most recent data relating to developer determinations please see table 'Developer_1'

Developer [Note 29] [Note 85]	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme)	Number of buildings for which the developer has determined whether works are required	Percentage of buildings for which the developer has determined whether works are required	Number of buildings where an exception request has been accepted against the July 2025 joint plan target [Note 77]	Estimated percentage of buildings for which the developer has determined whether works are required (excluding buildings for which an exception request has been accepted)
All Developers	4538	4172	92%	55	93%
Joint Plan Signatories [Note 76]	4271	3969	93%	55	94%
Other Developers (Other Developers)	267	203	76%	0	76%

Developer - Joint Plan Signatories [Note 76] [Note 85]	Number of contract buildings the developer is directly responsible for remediation (excluding buildings being remediated solely in a govt. scheme)	Number of buildings for which the developer has determined whether works are required	Percentage of buildings for which the developer has determined whether works are required	Number of buildings where an exception request has been accepted against the July 2025 joint plan target [Note 77]	Estimated percentage of buildings for which the developer has determined whether works are required (excluding buildings for which an exception request has been accepted)
Total - (Joint Plan signatories)	4271	3969	93%	55	94%
Ballymore Limited	69	69	100%	0	100%
Barratt Redrow PLC	821	626	76%	0	76%
Bellway PLC	420	420	100%	0	100%
Bewley Group Limited	7	6	86%	0	86%
Brighton STM Group Holding Company Limited (formally St. Modwen Group Holdings Company Limited)	10	10	100%	0	100%
Cala Group (Holdings) Limited	22	22	100%	0	100%
Canary Wharf Group PLC	13	9	69%	4	100%
Crest Nicholson Holdings PLC	292	290	99%	2	100%
Dandara Living Holdings Limited	21	21	100%	0	100%
Fairview Holdings Limited	121	121	100%	0	100%
Grosvenor Developments Limited	21	20	95%	0	95%
Hill Holdings Limited	90	76	84%	14	100%
Jelson Holdings Limited	7	7	100%	0	100%
Lendlease Europe Holdings Limited	88	88	100%	0	100%
London Square Development (Holdings) Limited	40	40	100%	0	100%
McCarthy & Stone Limited	62	60	97%	0	97%
Miller Homes Limited	39	39	100%	0	100%
MJ Gleeson PLC	16	13	81%	0	81%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	113	113	100%	0	100%
Morris Homes Group Limited	6	6	100%	0	100%
Pegasus Homes (formerly Lifestory Group)	18	18	100%	0	100%
Persimmon Public Limited Company	70	70	100%	0	100%
Regal Holdco Limited (parent company for Regal London)	16	16	100%	0	100%
Rydon Group Holdings Limited	22	22	100%	0	100%
Seven Capital PLC	21	21	100%	0	100%
Sorbon Group Limited (parent company for Shanly Homes)	26	26	100%	0	100%
Taylor Wimpey PLC	431	372	86%	19	90%
Telford Homes Limited	143	142	99%	1	100%
The Berkeley Group Holdings PLC	810	796	98%	10	100%
The British Land Company PLC	16	16	100%	0	100%
Tilia Homes Limited	8	8	100%	0	100%
Vistry Group PLC	294	291	99%	2	100%
Wates Group Limited	23	20	87%	3	100%
Weston Group PLC	87	87	100%	0	100%
Other (combined total for all developers with 5 or fewer buildings each: Bloor, CG Fry, Hopkins, Keepmoat Homes)	8	8	100%	0	100%

## Developer_13
Progress of developers against RAP joint plan commitment to resolve outstanding cost-recovery negotiations with social housing providers, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed up to the joint plan, as of 2 December 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Progress to resolve outstanding cost-recovery negotiations with social housing providers, by developer
Developers who signed up to the RAP joint plan commitment [Note 76] [Note 86]	Cost recovery negotiations started before 2 December 2024 and outstanding as of 2 December 2024					Cost recovery negotiations started after 2 December 2024
	Total	... where an agreement has been reached		… where negotiations are ongoing		Total	... where an agreement has been reached		… where negotiations are ongoing
		Number	Percentage	Number	Percentage		Number	Percentage	Number	Percentage
Total (All developers)	164	86	52%	78	48%	10	4	40%	6	60%
Allison Homes Group Limited	0	-	-	-	-	0	-	-	-	-
Ballymore Limited	0	-	-	-	-	0	-	-	-	-
Barratt - Redrow PLC	0	-	-	-	-	0	-	-	-	-
Bellway PLC	0	-	-	-	-	0	-	-	-	-
Bewley Group Limited	0	-	-	-	-	0	-	-	-	-
Bloor Investments Limited	0	-	-	-	-	0	-	-	-	-
Broadthorpe Limited (parent company for William Davis Homes)	1	0	0%	1	100%	0	-	-	-	-
C.G. Fry and Son Limited	0	-	-	-	-	0	-	-	-	-
Cala Group (Holdings) Limited	0	-	-	-	-	0	-	-	-	-
Canary Wharf Group PLC	0	-	-	-	-	0	-	-	-	-
Crest Nicholson Holdings PLC	0	-	-	-	-	0	-	-	-	-
Dandara Living Holdings Limited	0	-	-	-	-	0	-	-	-	-
Fairview Holdings Limited	0	-	-	-	-	0	-	-	-	-
Grosvenor Group Limited	0	-	-	-	-	0	-	-	-	-
Hill Holdings Limited	10	5	50%	5	50%	1	1	100%	0	0%
Jelson Holdings Limited	0	-	-	-	-	0	-	-	-	-
Keepmoat Limited	0	-	-	-	-	0	-	-	-	-
Lendlease Europe Holdings Limited	0	-	-	-	-	0	-	-	-	-
London Square Development (Holdings) Limited	0	-	-	-	-	0	-	-	-	-
MJ Gleeson PLC	0	-	-	-	-	0	-	-	-	-
McCarthy & Stone Limited	0	-	-	-	-	0	-	-	-	-
Miller Homes Limited	0	-	-	-	-	0	-	-	-	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	2	1	50%	1	50%	0	-	-	-	-
Morris Homes Group Limited	0	-	-	-	-	0	-	-	-	-
Pegasus Homes (formerly Lifestory Group)	0	-	-	-	-	0	-	-	-	-
Persimmon Public Limited Company	0	-	-	-	-	0	-	-	-	-
Regal Holdco Limited (parent company for Regal London)	0	-	-	-	-	0	-	-	-	-
Rydon Group Holdings Limited	16	1	6%	15	94%	0	-	-	-	-
Seven Capital PLC	0	-	-	-	-	0	-	-	-	-
Sorbon Group Limited (parent company for Shanly Homes)	0	-	-	-	-	0	-	-	-	-
St Modwen Group Holdings Company Limited	0	-	-	-	-	0	-	-	-	-
Taylor Wimpey PLC	0	-	-	-	-	0	-	-	-	-
Telford Homes Limited	0	-	-	-	-	0	-	-	-	-
The Berkeley Group Holdings PLC	0	-	-	-	-	0	-	-	-	-
The British Land Company PLC	0	-	-	-	-	0	-	-	-	-
Tilia Homes Limited and Hopkins Homes Group Limited	0	-	-	-	-	0	-	-	-	-
Vistry Group PLC	109	68	62%	41	38%	6	0	0%	6	100%
Wates Group Limited	26	11	42%	15	58%	3	3	100%	0	0%
Weston Group PLC	0	-	-	-	-	0	-	-	-	-

## Developer_14
Progress of developers against RAP joint plan commitment to resolve outstanding cost-recovery negotiations with social housing providers, England, 31 October 2025
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed up to the joint plan, as of 2 December 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Expected date to resolve outstanding cost-recovery negotiations with social housing providers, by developer
Developers who signed up to the RAP joint plan commitment [Note 76] [Note 86]	Cost recovery negotiations that started before or after 2 December 2024 and have not yet been resolved
	Total	Expected to be resolved within 6 months		Expected to take more than 6 months to resolve or unknown
		Number	Percentage	Number	Percentage
Total (All developers)	84	77	92%	7	8%
Allison Homes Group Limited	-	-	-	-	-
Ballymore Limited	-	-	-	-	-
Barratt - Redrow PLC	-	-	-	-	-
Bellway PLC	-	-	-	-	-
Bewley Group Limited	-	-	-	-	-
Bloor Investments Limited	-	-	-	-	-
Broadthorpe Limited (parent company for William Davis Homes)	1	0	0%	1	100%
C.G. Fry and Son Limited	-	-	-	-	-
Cala Group (Holdings) Limited	-	-	-	-	-
Canary Wharf Group PLC	-	-	-	-	-
Crest Nicholson Holdings PLC	-	-	-	-	-
Dandara Living Holdings Limited	-	-	-	-	-
Fairview Holdings Limited	-	-	-	-	-
Grosvenor Group Limited	-	-	-	-	-
Hill Holdings Limited	5	4	80%	1	20%
Jelson Holdings Limited	-	-	-	-	-
Keepmoat Limited	-	-	-	-	-
Lendlease Europe Holdings Limited	-	-	-	-	-
London Square Development (Holdings) Limited	-	-	-	-	-
MJ Gleeson PLC	-	-	-	-	-
McCarthy & Stone Limited	-	-	-	-	-
Miller Homes Limited	-	-	-	-	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	1	1	100%	0	0%
Morris Homes Group Limited	-	-	-	-	-
Pegasus Homes (formerly Lifestory Group)	-	-	-	-	-
Persimmon Public Limited Company	-	-	-	-	-
Regal Holdco Limited (parent company for Regal London)	-	-	-	-	-
Rydon Group Holdings Limited	15	10	67%	5	33%
Seven Capital PLC	-	-	-	-	-
Sorbon Group Limited (parent company for Shanly Homes)	-	-	-	-	-
St Modwen Group Holdings Company Limited	-	-	-	-	-
Taylor Wimpey PLC	-	-	-	-	-
Telford Homes Limited	-	-	-	-	-
The Berkeley Group Holdings PLC	-	-	-	-	-
The British Land Company PLC	-	-	-	-	-
Tilia Homes Limited and Hopkins Homes Group Limited	-	-	-	-	-
Vistry Group PLC	47	47	100%	0	0%
Wates Group Limited	15	15	100%	0	0%
Weston Group PLC	-	-	-	-	-

## Social_1
Remediation status of social buildings and social self-funded buildings with unsafe cladding, England, 30 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Social buildings with unsafe cladding, in any programme or self-funded [Note 13, Note 33, Note 87]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation completed	286	34%	373	50%	659	41%
Works started	136	16%	94	13%	230	14%
Works not started	398	47%	250	33%	648	41%
Remediation progress currently unknown	28	3%	35	5%	63	4%
Total	848	100%	752	100%	1,600	100%

Social buildings with unsafe cladding, only self-funded [Note 13, Note 34, Note 87]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation completed	209	64%	127	55%	336	60%
Works started	46	14%	36	16%	82	15%
Works not started	44	13%	31	14%	75	13%
Remediation progress currently unknown	28	9%	35	15%	63	11%
Total	327	100%	229	100%	556	100%

## Social_2
Remediation status of social buildings and social self-funded buildings with unsafe cladding, time series, England, 30 June 2026
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Social buildings with unsafe cladding, in any programme or self-funded [Note 13, Note 33, Note 87]	Dec-25 / Number	Dec-25 Percentage (%)	Jan-26 / Number	Jan-26 Percentage (%)	Feb-26 / Number	Feb-26 Percentage (%)	Mar-26 / Number	Mar-26 Percentage (%)	Apr-26 / Number	Apr-26 Percentage (%)	May-26 / Number	May-26 Percentage (%)	Jun-26 / Number	Jun-26 Percentage (%)
Remediation completed	579	44%	596	44%	633	42%	634	42%	643	41%	654	41%	659	41%
Works started	165	12%	161	12%	168	11%	206	14%	207	13%	195	12%	230	14%
Works not started	514	39%	558	41%	640	42%	604	40%	649	41%	670	42%	648	41%
Remediation progress currently unknown	63	5%	54	4%	73	5%	71	5%	65	4%	64	4%	63	4%
Total	1,321	100%	1,369	100%	1,514	100%	1,515	100%	1,564	100%	1,583	100%	1,600	100%

Social buildings with unsafe cladding, only self-funded [Note 13, Note 34, Note 87]	Dec-25 / Number	Dec-25 Percentage (%)	Jan-26 / Number	Jan-26 Percentage (%)	Feb-26 / Number	Feb-26 Percentage (%)	Mar-26 / Number	Mar-26 Percentage (%)	Apr-26 / Number	Apr-26 Percentage (%)	May-26 / Number	May-26 Percentage (%)	Jun-26 / Number	Jun-26 Percentage (%)
Remediation completed	284	50%	300	53%	323	54%	320	56%	326	57%	332	59%	336	60%
Works started	66	12%	60	11%	55	9%	53	9%	58	10%	55	10%	82	15%
Works not started	150	27%	150	27%	142	24%	131	23%	121	21%	115	20%	75	13%
Remediation progress currently unknown	63	11%	54	10%	73	12%	71	12%	65	11%	64	11%	63	11%
Total	563	100%	564	100%	593	100%	575	100%	570	100%	566	100%	556	100%

## Enforcement_1
Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 19 June 2026
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [Note 19, Note 61].

Local Authority [Note 2]	BSF or CSS only (non-ACM cladding only) / Number / Previous month	BSF or CSS only (non-ACM cladding only) / Number / Current month	ACM cladding only / Number / Previous month	ACM cladding only / Number / Current month	Both ACM and non-ACM cladding in either the BSF or CSS / Number / Previous month	Both ACM and non-ACM cladding in either the BSF or CSS / Number / Current month	Not in any remediation fund (non-ACM cladding only) / Number / Previous month	Not in any remediation fund (non-ACM cladding only) / Number / Current month	Total / Number / Previous month	Total / Number / Current month
Barking and Dagenham	1	1	0	0	0	0	6	6	7	7
Barnet	3	3	3	3	1	1	4	4	11	11
Birmingham	4	4	1	1	0	0	13	13	18	18
Bournemouth, Christchurch and Poole	2	2	2	2	0	0	3	6	7	10
Bradford	0	0	1	1	0	0	0	0	1	1
Brent	0	0	2	2	0	0	0	0	2	2
Brighton and Hove	0	0	0	0	0	0	0	0	0	0
Bristol, City of	6	6	1	1	0	0	9	9	16	16
Bromley	0	0	0	0	0	0	0	0	0	0
Calderdale	0	0	0	0	0	0	0	0	0	0
Camden	16	16	1	1	0	0	29	29	46	46
City of London	3	3	0	0	0	0	10	10	13	13
Croydon	4	4	0	0	1	1	1	1	6	6
Dacorum	0	0	0	0	0	0	1	1	1	1
Ealing	2	2	1	1	1	1	1	1	5	5
Gateshead	0	0	0	0	0	0	0	0	0	0
Greenwich	5	5	0	0	0	0	13	13	18	18
Hackney	5	6	2	2	2	2	10	11	19	21
Hammersmith and Fulham	12	12	1	1	2	2	91	91	106	106
Haringey	0	0	0	0	0	0	0	0	0	0
Harrow	0	0	0	0	0	0	0	0	0	0
Hillingdon	3	3	1	1	0	0	12	12	16	16
Hounslow	0	0	0	0	0	0	1	1	1	1
Ipswich	0	0	0	0	0	0	0	0	0	0
Islington	13	13	0	0	0	0	10	10	23	23
Kensington and Chelsea	0	0	0	0	0	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0	0	0	0	0	0
Kirklees	0	0	0	0	0	0	0	0	0	0
Lambeth	27	27	1	1	0	0	10	10	38	38
Leeds	0	0	0	0	0	0	0	0	0	0
Leicester	0	0	0	0	0	0	0	0	0	0
Lewisham	0	0	0	0	0	0	0	0	0	0
Liverpool	4	4	2	2	3	3	2	2	11	11
Maidstone	0	0	0	0	0	0	0	0	0	0
Manchester	0	0	0	0	0	0	0	0	0	0
Medway	0	0	1	1	0	0	0	0	1	1
Merton	0	0	0	0	0	0	0	0	0	0
Milton Keynes	1	1	0	0	0	0	5	5	6	6
Newcastle upon Tyne	6	6	0	0	0	0	12	13	18	19
Newham	19	18	1	1	1	1	33	33	54	53
North Somerset	0	0	0	0	0	0	0	0	0	0
Norwich	0	0	0	0	0	0	0	0	0	0
Nottingham	19	19	2	2	0	0	33	33	54	54
Plymouth	3	3	0	0	0	0	3	3	6	6
Portsmouth	0	0	1	1	0	0	5	5	6	6
Reading	3	3	1	1	0	0	1	1	5	5
Redbridge	3	3	0	0	0	0	4	4	7	7
Salford	1	1	0	0	0	0	0	0	1	1
Sheffield	1	1	0	0	0	0	0	0	1	1
Slough	0	0	0	0	0	0	0	0	0	0
Southampton	3	3	0	0	0	0	0	0	3	3
Southwark	31	31	3	3	3	3	29	29	66	66
Sunderland	2	2	0	0	0	0	0	0	2	2
Sutton	0	0	0	0	1	1	0	0	1	1
Thanet	0	0	0	0	0	0	0	0	0	0
Tower Hamlets	26	26	8	8	5	5	33	33	72	72
Trafford	0	0	0	0	0	0	0	0	0	0
Waltham Forest	1	1	0	0	0	0	1	1	2	2
Wandsworth	1	1	2	2	1	1	0	0	4	4
Westminster	34	34	4	4	6	6	102	103	146	147
Windsor and Maidenhead	0	0	0	0	0	0	0	0	0	0
Others	19	19	0	0	2	2	57	59	78	80
Total	283	283	42	42	29	29	544	552	898	906

## Enforcement_2
Category rating of buildings inspected by local authorities, England, 19 June 2026
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [Note 2]	Inspections with the building rated Category 1 [Note 20, Note 55] / Number	Inspections with the building rated Category 2 [Note 20, Note 55] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	2	5	0	7
Barnet	6	5	0	11
Birmingham	2	16	0	18
Bournemouth, Christchurch and Poole	6	3	1	10
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	13	3	16
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	3	42	1	46
City of London	8	4	1	13
Croydon	2	4	0	6
Dacorum	0	1	0	1
Ealing	2	3	0	5
Gateshead	0	0	0	0
Greenwich	3	8	7	18
Hackney	10	8	3	21
Hammersmith and Fulham	0	100	6	106
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	3	7	6	16
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	3	18	2	23
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	1	37	0	38
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	3	7	1	11
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	1	5	6
Newcastle upon Tyne	1	13	5	19
Newham	12	36	5	53
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	1	52	1	54
Plymouth	2	4	0	6
Portsmouth	1	2	3	6
Reading	0	5	0	5
Redbridge	3	3	1	7
Salford	0	1	0	1
Sheffield	0	0	1	1
Slough	0	0	0	0
Southampton	1	0	2	3
Southwark	30	32	4	66
Sunderland	1	1	0	2
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	14	44	14	72
Trafford	0	0	0	0
Waltham Forest	0	2	0	2
Wandsworth	1	3	0	4
Westminster	6	140	1	147
Windsor and Maidenhead	0	0	0	0
Others	14	46	20	80
Total	145	668	93	906

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 19 June 2026
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [Note 2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number	Improvement notice appeals / Number
Barking and Dagenham	3	1	0	4	1
Barnet	9	0	0	9	3
Birmingham	16	0	0	16	1
Bournemouth, Christchurch and Poole	4	3	0	7	4
Bradford	1	0	0	1	1
Brent	0	0	0	0	0
Brighton and Hove	0	0	0	0	0
Bristol, City of	0	0	0	0	0
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	19	4	0	23	5
City of London	9	0	0	9	0
Croydon	1	0	0	1	0
Dacorum	1	0	0	1	0
Ealing	2	0	0	2	0
Gateshead	0	0	0	0	0
Greenwich	7	2	0	9	0
Hackney	13	1	0	14	0
Hammersmith and Fulham	0	11	0	11	0
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	6	1	0	7	3
Hounslow	1	0	0	1	0
Ipswich	0	0	0	0	0
Islington	16	6	0	22	2
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	4	17	0	21	0
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	6	0	0	6	1
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	1	0	0	1	1
Merton	0	0	0	0	0
Milton Keynes	1	0	0	1	0
Newcastle upon Tyne	3	4	0	7	1
Newham	40	13	0	53	15
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	15	0	0	15	1
Plymouth	3	3	0	6	1
Portsmouth	2	0	0	2	0
Reading	0	0	0	0	0
Redbridge	4	1	0	5	1
Salford	0	0	0	0	0
Sheffield	0	0	0	0	0
Slough	0	0	0	0	0
Southampton	1	0	0	1	1
Southwark	39	4	0	43	10
Sunderland	1	0	0	1	0
Sutton	1	0	0	1	0
Thanet	0	0	0	0	0
Tower Hamlets	19	23	0	42	2
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	1	1
Wandsworth	1	0	0	1	0
Westminster	1	21	1	23	1
Windsor and Maidenhead	0	0	0	0	0
Others	20	1	0	21	8
Total	271	116	1	388	64

## Enforcement_4
Number of inspections by local authorities supported by the Joint Inspection Team, England, 19 June 2026
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team [Note 61].
Local Authority [Note 2]	Inspections supported by the Joint Inspection Team [Note 21] / Number	Inspections supported by the Joint Inspection Team [Note 21] / Number	Buildings inspected with support from the Joint Inspection Team [Note 60] / Number	Buildings inspected with support from the Joint Inspection Team [Note 60] / Number
	Previous month	Current month	Previous month	Current month
Barking and Dagenham	3	3	3	3
Barnet	4	4	4	4
Birmingham	15	15	14	14
Bournemouth, Christchurch and Poole	2	2	2	2
Bradford	0	0	0	0
Brent	2	2	2	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	6	6	6	6
City of London	0	0	0	0
Croydon	6	6	6	6
Dacorum	0	0	0	0
Ealing	5	5	5	5
Gateshead	0	0	0	0
Greenwich	15	15	14	14
Hackney	15	16	15	16
Hammersmith and Fulham	3	3	2	2
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	1	1	1	1
Hounslow	1	1	1	1
Ipswich	0	0	0	0
Islington	3	3	3	3
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	2	2
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	9	9	9	9
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	0	0	0	0
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	2	2	2
Newham	29	28	29	28
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	3	3	3	3
Plymouth	1	1	1	1
Portsmouth	4	4	4	4
Reading	0	0	0	0
Redbridge	4	4	4	4
Salford	1	1	1	1
Sheffield	1	1	1	1
Slough	0	0	0	0
Southampton	3	3	3	3
Southwark	5	5	5	5
Sunderland	1	1	1	1
Sutton	1	1	1	1
Thanet	0	0	0	0
Tower Hamlets	23	23	23	23
Trafford	0	0	0	0
Waltham Forest	2	2	2	2
Wandsworth	4	4	4	4
Westminster	3	3	3	3
Windsor and Maidenhead	0	0	0	0
Others	11	11	11	11
Total	190	190	187	187

## Enforcement_5
Number of inspections and formal notices conducted per quarter, England, 19 June 2026
Back to Contents
This worksheet contains one table. All figures are for the number of inspections and formal notices conducted in the time period [Note 88].
Quarterly period [Note 89]	Inspections [Note 90] / Number	Formal notices [Note 91] / Number
Q1 2018	0	0
Q2 2018	4	1
Q3 2018	0	0
Q4 2018	0	0
Q1 2019	0	1
Q2 2019	3	3
Q3 2019	5	0
Q4 2019	9	15
Q1 2020	12	3
Q2 2020	5	2
Q3 2020	14	7
Q4 2020	12	12
Q1 2021	6	3
Q2 2021	9	4
Q3 2021	15	3
Q4 2021	18	6
Q1 2022	21	5
Q2 2022	16	5
Q3 2022	34	15
Q4 2022	36	18
Q1 2023	36	7
Q2 2023	49	16
Q3 2023	52	20
Q4 2023	61	18
Q1 2024	59	18
Q2 2024	55	30
Q3 2024	55	19
Q4 2024	57	34
Q1 2025	53	18
Q2 2025	51	26
Q3 2025	80	16
Q4 2025	38	22
Q1 2026	32	27
Q2 2026	29	14

## JIT_1
Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for the number of Joint Inspection Team training sessions attended by local authority officers. [Note 57]
Local Authority [Note 22]	Intro to Fire Safety (Level 1) Total attendees 2024 [Note 74] / Number	Intermediate Fire Safety (Level 2) Total attendees 2024 [Note 74] / Number	Intro to Fire Safety (Level 1) Total attendees 2025 [Note 74] / Number	Intermediate Fire Safety (Level 2) Total attendees 2025 [Note 74] / Number	Intro to Fire Safety (Level 1) Total attendees 2026 [Note 74] / Number	Intermediate Fire Safety (Level 2) Total attendees 2026 [Note 74] / Number	Intro to Fire Safety (Level 1) Total attendees [Note 75] / Number	Intermediate Fire Safety (Level 2) Total attendees [Note 75] / Number
Barking and Dagenham	0	2	0	2	0	0	0	4
Barnet	0	3	0	0	0	0	4	6
Birmingham	0	3	0	0	0	0	10	21
Bournemouth, Christchurch and Poole	0	0	0	1	0	0	10	6
Bradford	0	0	0	2	0	0	24	7
Brent	0	0	0	0	0	0	1	4
Brighton and Hove	0	0	0	1	0	0	0	13
Bristol, City of	0	0	0	0	0	0	10	8
Bromley	0	0	0	0	0	0	3	0
Calderdale	0	0	0	0	0	0	3	1
Camden	0	1	0	4	0	0	16	21
City of London	0	0	0	0	0	0	8	5
Croydon	0	3	0	3	0	0	26	11
Dacorum	0	0	0	0	0	0	4	3
Ealing	0	6	0	1	0	0	10	7
Gateshead	0	0	0	0	0	0	6	3
Greenwich	0	1	0	5	0	0	2	15
Hackney	0	9	0	5	0	0	18	18
Hammersmith and Fulham	0	6	0	1	0	0	20	17
Haringey	0	0	0	0	0	0	4	2
Harrow	0	2	0	0	0	0	1	2
Hillingdon	0	1	0	0	0	0	3	2
Hounslow	0	1	0	0	0	0	4	4
Ipswich	0	0	0	0	0	0	0	0
Islington	0	3	0	2	0	0	11	11
Kensington and Chelsea	0	0	0	0	0	0	0	1
Kingston upon Thames	0	0	0	0	0	0	3	0
Kirklees	0	0	0	1	0	0	2	2
Lambeth	0	7	0	2	0	0	16	17
Leeds	0	0	0	3	0	0	6	5
Leicester	0	0	0	0	0	0	0	0
Lewisham	0	0	0	0	0	0	5	3
Liverpool	0	0	0	0	0	0	32	15
Maidstone	0	0	0	0	0	0	0	0
Manchester	0	2	0	0	0	0	8	7
Merton Regulatory Services Partnership (Merton, Richmond & Wandsworth)	0	5	0	5	0	0	14	20
Medway	0	0	0	3	0	0	12	8
Milton Keynes	0	0	0	0	0	0	6	7
Newcastle upon Tyne	0	0	0	0	0	0	6	5
Newham	0	2	0	5	0	0	10	12
North Somerset	0	0	0	0	0	0	8	5
Norwich	0	0	0	0	0	0	11	7
Nottingham	0	27	0	0	0	0	34	43
Plymouth	0	0	0	0	0	0	3	3
Portsmouth	0	0	0	3	0	0	2	17
Reading	0	2	0	0	0	0	15	5
Redbridge	0	1	0	0	0	0	4	3
Salford	0	0	0	0	0	0	11	7
Sheffield	0	1	0	3	0	0	0	4
Slough	0	0	0	3	0	0	5	10
Southampton	0	0	0	0	0	0	1	1
Southwark	0	1	0	0	0	0	7	1
Sunderland	0	0	0	0	0	0	3	5
Sutton	0	0	0	0	0	0	2	0
Thanet	0	1	0	0	0	0	2	2
Tower Hamlets	0	8	0	6	0	0	9	19
Trafford	0	0	0	0	0	0	7	3
Waltham Forest	0	3	0	3	0	0	6	10
Westminster	0	5	0	3	0	0	17	14
Windsor and Maidenhead	0	1	0	0	0	0	8	5
Others	0	31	0	24	0	0	414	270
Total	0	138	0	91	0	0	887	727

## Estimated_1
Estimates of the number of residential buildings, containing dwellings, that have or had unsafe cladding requiring work, 11 metres and over in height, England, March 2026
Back to Contents
This worksheet contains two tables. Figures are for number of 11m+ buildings, containing dwellings, estimated to have unsafe cladding, and the percentage of the 11m+ residential buildings stock, containing dwellings, that are estimated to have unsafe cladding.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height [Note_10, Note_62, Note_64, Note_65, Note_66, Note_67]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	2,800	3,700
18m+	3,100	3,700
Total 11m+	5,900	7,400

Building height [Note_64, Note_65, Note_67]	Estimated prevalence of unsafe cladding in residential buildings 11 metres and over (low) / Percentage (%)	Estimated prevalence of unsafe cladding in residential buildings 11 metres and over (high) / Percentage (%)
11-18m	5%	9%
18m+	26%	31%
Total 11m+	8%	14%

## Estimated_2
Estimates of the number of residential buildings, that have or had unsafe cladding requiring work, expected to be remediated or mitigated as part of a government remediation programme, 11 metres and over in height, England, March 2026
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row between each. All figures are for number of 11m+ residential buildings with unsafe cladding estimated to be remediated or mitigated as part of the department's five remediation programmes (ACM programme, BSF, CSS, developer-led remediation, and social housing remediation).
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height - all buildings / [Note_10, Note_62, Note_64, Note_65, Note_66, Note_67]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	2,700	3,600
18m+	3,100	3,700
Total 11m+	5,800	7,300

Building height - private sector buildings / [Note_10, Note_62, Note_64, Note_65, Note_66, Note_67]	Number of private buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of private buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	1,300	1,600
18m+	1,600	1,800
Total 11m+	2,900	3,400

Building height - social sector buildings / [Note_10, Note_62, Note_64, Note_65, Note_66, Note_67]	Number of social buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of social buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	1,400	2,000
18m+	1,400	1,800
Total 11m+	2,800	3,800

## Estimated_3
Estimated proportion of buildings with unsafe cladding expected to be remediated or mitigated in a government remediation programme that are currently monitored in a government remediation programme, 30 June 2026
Back to Contents
This worksheet contains one table. All figures are for proportion of 11m+ residential buildings with unsafe cladding estimated to be remediated or mitigated as part of the department's five remediation programmes (ACM programme, BSF, CSS, developer-led remediation, and social housing remediation), that are currently monitored in a government remediation programme.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Building height [Note_62, Note_64, Note_66]	Estimated percentage of buildings 11 metres and over with unsafe cladding that are monitored by MHCLG (low estimate) / Percentage (%)	Estimated percentage of buildings 11 metres and over with unsafe cladding that are monitored by MHCLG (high estimate) / Percentage (%)
11-18m	75%	56%
18m+	78%	66%
Total 11m+	77%	61%

## Estimated_4
Estimates of the number of residential buildings, that have or had unsafe cladding requiring remediation or mitigation work, expected to be remediated or mitigated as part of a government funded scheme, based on March 2026 eligibility criteria, 11 metres and over in height, England, March 2026
Back to Contents
This worksheet contains one table. All figures are for number of 11m+ residential buildings estimated to be remediated in a government funded scheme (ACM programme, BSF, CSS).
Some cells refer to notes which can be found in the 'Notes' worksheet.
Building height [Note_62, Note_63, Note_64, Note_66, Note_73, Note_82]	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (low) / Number	Number of buildings 11 metres and over in height, estimated to have or have had unsafe cladding (high) / Number
11-18m	1,300	1,800
18m+	1,800	2,100
Total 11m+	3,100	3,900

## Estimated_5
Estimated cost of external wall system works to residential buildings, 11 metres and over in height, with unsafe cladding expected to be remediated or mitigated, by funding source and building height, England, March 2025, £bn (nominal terms)
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are GBP £ billion in nominal terms.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Funding source - 11-18m buildings / [Note_78, Note_79, Note_80, Note_81, Note_82]	Building height	Low / estimate	Central estimate	High estimate
Government programmes	11-18m	1.2	3.1	8.5
Non-government actors	11-18m	1.9	2.2	2.9
Total	11-18m	3.1	5.4	11.4

Funding source - 18m+ buildings / [Note_78, Note_79, Note_80, Note_81, Note_82]	Building height	Low / estimate	Central estimate	High estimate
Government programmes	18m+	5.4	5.8	6.7
Non-government actors	18m+	3.3	3.9	4.6
Total	18m+	8.7	9.7	11.3

Funding source - 11m+ Total / [Note_78, Note_79, Note_80, Note_81, Note_82]	Building height	Low / estimate	Central estimate	High estimate
Government programmes	11m+ total	6.7	8.9	15.2
Non-government actors	11m+ total	5.2	6.1	7.4
Total	11m+ total	11.8	15.1	22.7

## Estimated_6
Estimated proportion of capital costs of external wall system works to buildings 11 metres and over in height, with unsafe cladding expected to be remediated or mitigated, by funding source, England, March 2025.
Back to Contents
This worksheet contains one table, presented next to each other vertically with one blank row in between the tables. All figures are in % terms.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Funding source / [Note_79, Note_82, Note_83]	Low / estimate	Central estimate	High estimate
Government programmes	56%	59%	67%
Non-government actors	44%	41%	33%
Total	100%	100%	100%

## Estimated_7
Estimated money available to MHCLG to fund the remediation and mitigation of unsafe external wall system defects in buildings 11 metres and over in height, with unsafe cladding, England, March 2025, £bn (nominal terms, nearest £0.1bn)
Back to Contents
This worksheet contains one table. All figures are GBP £ billion in nominal terms, rounded to the nearest £0.1 billion.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Revenue stream / [Note_79, 84]	Estimate
Exchequer contribution	5.2
Developer refunds	0.7
Building Safety Levy	3.4
Total	9.2