## Capacity-Early Funding spent
Capacity/Early funding activities which have already happened
Activity | Category | Description | Cost (PiP capacity funding only)
LA support | Management costs | Support from the Midsomer County Council in helping to recruit a chair, set up the board and create its governance arrangements. | 10000
PiP stall at local event | Community outreach and engagement | Paid to have a stall at a local town festival to help promote the programme and do some early outreach with local residents. | 1000
Children's engagement | Community outreach and engagement | Paid for a bouncy castle for children to play on at the local town festival, cost of admission was a parent/guardian having to fill out a survey. | 1000
Board equipment/materials | Other | Used some funding to buy laptop for the chair and stationary for board members. Also used funding to get materials such as copies of guidance and board papers for meetings | 1000
Training for chair John Nettles | Training | The chair attended a course run by the LGA on managing public money | 1500
14500

## Capacity-Early Funding forecast
Capacity/Early funding activities which are planned in the next 6 months
Activity | Category | Description | Cost (PiP capacity funding only)
Engagement plan development | Consultancy | Procured the support of a local consultancy with experience in utilising existing community groups to help plan our we intend to conduct outreach to hard to reach groups as part of our wider engagement | 2000
Hiring new project officer apprentice | Management costs | We want to hire a local young graduate as a project officer apprentice to give them practical first hand experience of working alongside the council to help deliver the aims of the board. They will help with secretariat functions and engagement. | 20000
Community Sports day | Community outreach and engagement | We are providing some funding to Midsomer County Athletic Football Club and Midsomer RFUC to hold a community sports day at their joint facilities where we will be undertaking some engagement. | 5000
27000

## Projects Delivered
Projects Delivered
| Target Groups | [8 empty] | Secondary Interventions (if any)
Project name | Whole community | Children & young people | Local businesses | Older residents | Ethnic minority communities | Disabled residents | VCSEs | Description | Primary intervention | Regeneration, high streets & heritage | Housing | Work, productivity & skills | Cohesion | Health & wellbeing | Transport | Saftey & security | Community Power | Education & opportunity | Organisation Type | Organisation Name | Total Capital Spend (of whole project) | Total Revenue Spend (of whole project) | Capital Spend from PiP | Revenue Spend from PiP | Additional Funding Sources | Start Date | End Date | Project Status? | Management Costs Used from Programme Funding? | Details of Management Costs (only if applicable)
Repairs to local play park | Yes | Yes | [5 empty] | We have made some small repairs to a play park at the centre of the community which was falling into disuse and was dangerous to children. Since these repairs there have been 100s of children who have used the facility. | Regeneration, high streets, heritage |  |  |  |  | Yes |  |  |  |  | Local authority | Midsomer County Council | 5000 | 500 | 5000 | 500 | N/A | 2026-04-11 | 2026-07-25 | Completed | 450 | LA project management resource
Public realm improvements | Yes |  | Yes |  |  |  |  | Have repaired and replaced some hanging baskets and created new flowerbeds in the town, and turned a desire line into a real path for residents | Regeneration, high streets, heritage | [9 empty] | Local authority | Midsomer County Council | 10000 | 5000 | 20000 | 10000 | Business investment | 2026-03-03 | 2026-08-01 | Completed | N/A

## Planned Projects
Planned Projects
| Target Groups | [8 empty] | Secondary Interventions (if any) | [7 empty] | Delivery Organisation
Project name | Whole community | Children & young people | Local businesses | Older residents | Ethnic minority communities | Disabled residents | VCSEs | Description | Primary intervention | Regeneration, high streets & heritage | Housing | Work, productivity & skills | Cohesion | Health & wellbeing | Transport | Saftey & security | Education & opportunity | Organisation Type | Organisation Name | Total Capital Spend (£) | Total Revenue Spend (£) | Capital Spend from PiP (£) | Revenue Spend from PiP (£) | Additional Funding Sources | Planned Start Date | Estimated End Date | Project Status? | Management Costs Used from Programme Funding? | Details of Management Costs (only if applicable)
Fund for Local Community Groups | Yes | [6 empty] | We have opened a fund where local Midsomer communities within the Boundary are able to apply for small amounts of funding, up to £10,000, in order to make improvements to existing community assets or to make improvements to the local area that will benefit the local community | Regeneration, high streets and heritage | [8 empty] | Neighbourhood Board | Midsomer Neighbourhood Board | 50000 | 10000 | 50000 | 10000 | N/A | 2026-09-01 | 2027-09-01 | Planned | Yes | £1,000 in management costs for operating and evaluating the Expressions of Interest
Learnatrade |  | Yes | [5 empty] | The board are providing some funding alongside other groups to run a course for local Midsomer School leavers who want to learn a trade and will each be able to access a 6 month course for their prefered trade which will result in a qualification and potential job offer. | Work, productivity and skills | [7 empty] | Yes | VCSE | Learnatrade.org | 0 | 250000 | 0 | 50000 | Philanthropy | 2027-01-01 | 2027-06-01 | Planned | No | N/A
CCTV instillation | Yes | [6 empty] | There have been a spate of voilent crimes recently in Midsomer and CCTV would help to a) find those responsible and b) hopefully deter would be criminals. CCTV will be installed in the main areas of urban centres. | Safety and Security |  |  |  | Yes |  |  |  |  | Local authority | Midsomer County Council | 20000 | 0 | 10000 | 0 | Local authority | 2027-05-05 | 2027-06-12 | Planned | No | N/A

## Neighbourhood Board Details
Neighbourhood Board Details
Answer:
Has anyone left or joined the board in the last 6 months?
If yes...
Change Type | Name | Occupation | Reason for Change | Date of Change | Notes/Comments
Join | Olive Beauvoisin | Estate Agent | Wanted more business representation on the board | 2026-08-17
Join | Justin Pickard | Lawyer | Prominent local lawyer and resident, added to increase community voices on the board | 2026-08-17
Leave | Honoria Lydiard | Socialite | Stood down from the board | 2026-08-17 | Was recently arrested so board took the decision to ask her to stand down from the board

## Data - DO NOT USE
Regeneration, high streets, heritage
Cohesion
Housing
Work, productivity and skills
Cohesion
Community Power
Health and Wellbeing
Transport
Safety and Security
Education and opportunity

## Sheet1 (hidden)
Training | Yes
Management costs | ✓
Consultancy
Community outreach and engagement | New or improved retail, hospitality, industrial and office spaces
Other | Digital infrastructure upgrades for commercial and residential areas
Permanent full time equivalent (FTE) jobs created or safegauarded
Green retrofits to residential, public and commercial buildings
Whole community | New or improved training, educational and childcare, facilities
Children and Young People | New or improved cultural, community and sports spaces
Local Businesses | New or improved public realm
Older Residents | Improved exisiting residential units
Ethnic Minority Communities | New or improved healthcare space
Disabled Residents | New or improved public transport
VCSE
Regeneration, high streets and heritage
Housing
Work, productivity and skills
Cohesion
Health and wellbeing
Transport
Safety and Security
Education and opportunity
Private sector
VCSE
Local authority
Neighbourhood Board
Housing association
Public sector
Statuatory agency
other
N/A
Local authority
Business investment
Devolved administration
UK government funding
Other grant funding
Philanthropy
Other
Training
Management costs
Consultancy
Community outreach and engagement
Other