## Welcome
AI Risk Assessment Tools
Version 1.0
2026-05-01
This workbook sets out self-assessment tools aligned with the Orange Book for AI project teams to identify, assess, treat, monitor and report risks associated with individual AI projects. These tools form part of the overarching Technology Risk Assessment Framework. This can be found on the NIST site. For any queries or feedback, please contact psai-tech@dsit.gov.uk.

## AI Risk Monitoring Workbook
AI Risk Monitoring Workbook
This risk monitoring workbook can be used to record identified AI risks, their assessment and associated treatment actions. This workbook contains: - definitions of the risk ratings - the risk RACI matrix - risk log, where identified AI risks are scoped and described in detail along with responsibility assignment, utlising the RACI matrix - risk assessment, where each AI risk is given a severity and likelihood score in order to generate a risk rating - risk treatment tracker,​ to log treatment actions to address the risk, the AI lifecycle stage in which the treatment is implemented, and the status of the treatment action. The likelihood and severity scores following the successful implementation of a treatment can be recorded to generate a post-treatment risk profile Risk is evaluated on the basis of likelihood and impact of consequence. Organisational risk appetite is then included to calculate the overall risk evaluation, which is then assigned one of the following categories: - Very High or High, where the project is too risky - Moderate or Low, where there are clear risk treatment strategies required - Very Low, where it is safe to proceed
Definitions and ratings of severity:
Key Definitions
Severity Rating | Likelihood of a risk occurring | Severity Description
Very High | Near certainty | Critical function, process or activity suffering irreparable failure, including: - loss of life or serious damage to health - irreversible disruption of management and operations of critical functions, processes or infrastructure - irreversible breach of obligations under human rights - irreversible damage to property, and/or irreversible damage to environment - loss of confidentiality, integrity, or availability of data, resulting in multiple adverse effects on reputation, operations, assets (including finances), and/or individuals - creation of an existential threat to the country or organisation - failure to adhere to any and all stipulations of relevant legal and regulatory frameworks and mandatory compliance
High | Very likely | Critical function, process or activity interrupted with potential for recovery, including: - serious damage to health - serious disruption of management and operations of critical functions or infrastructure - serious breach of obligations under human rights - serious damage to property, and/or environment - loss of confidentiality, integrity, or availability of data resulting in a single adverse effect on reputation, operations, assets (including finances), and/or individuals - major breaches in obligations to adhere to relevant legal and regulatory frameworks and mandatory compliance
Moderate | Likely | Critical process or activity interrupted but without loss of key functions, including: - moderate damage to health - moderate disruption of management and operations of critical functions or infrastructure - moderate breach of obligations under human rights, moderate damage to property, and/or environment - loss of confidentiality, integrity, or availability of data resulting in adverse effect on either reputation, operations, assets (including finances), and/or individuals - moderate failure to adhere to relevant legal and regulatory frameworks and mandatory compliance
Low | Low likelihood | Critical function, process or activity interrupted without impactable loss of function, including: - minor damage to health - minor disruption of management and operations of critical functions or infrastructure - minor breach of obligations under human rights - minor damage to property, and/or environment - oss of confidentiality, integrity, or availability of data resulting in limited adverse effect on either reputation, operations, assets (including finances), and/or individuals - potential failure to adhere to relevant legal and regulatory frameworks and mandatory compliance
Very Low | Not likely | No interruption to critical function, process or activity, including: - potential issues identified, with no noticeable effect or disruption on overall system function - no significant harm to persons or damage to property and/or environment - limited or no loss of confidentiality, integrity, or availability of data resulting in an insignificant effect on either reputation, operations, assets (including finances), and/or individuals - within bounds of adhering to relevant legal and regulatory frameworks and mandatory compliance
RIsk RACI matrix:
Impact Severity
Likelihood | Very Low (1) | Low (2) | Moderate (3) | High (4) | Very High (5)
Very High (5) | Low | High | High | Very High | Very High
High (4) | Low | Moderate | High | Very High | Very High
Moderate (3) | Low | Moderate | Moderate | High | High
Low (2) | Very Low | Low | Moderate | Moderate | High
Very Low (1) | Very Low | Very Low | Low | Low | Low
Risk log:
Risk Log | [6 empty] | Risk Assessment |  |  | Risk Treatment
ID | Responsible Owner | Accountable Owner | Consulted | Informed | Identified Risk | Risk Scenario | Severity | Likelihood | Risk Rating | AI Lifecycle Stage Treatment Implemented In | Treatment Action/s | Status | Post-Treatment Severity | Post-Treatment Likelihood | Post-Treatment Risk Rating
1 (illustrative) | Data Teams | AI Governance | AI Developers | Legal & Compliance | Data quality has not been assessed and may not meet minimum threshold required to run AI model | PoC model does not produce expected output | 4 | 4 | 16 | Discovery | Run data quality analysis on current data sources to assess and identify data gaps where enrichment may be needed, with regular data pulls and QA reassessments | In Progress | 3 | 2 | 6
| AI Governance | [5 empty] | 4 | 2 | 8 | Alpha |  |  | 2 | 1 | 2
| Security | [5 empty] | 3 | 4 | 12 | Discovery |  |  | 3 | 1 | 3
| Security | [5 empty] | 3 | 2 | 6 | Discovery |  |  | 3 | 1 | 3
| AI Governance | [5 empty] | 2 | 2 | 4 | Discovery |  |  | 1 | 1 | 1
| Legal & Compliance | [5 empty] | 1 | 3 | 3 | Alpha |  |  | 1 | 1 | 1
| Legal & Compliance | [5 empty] | 5 | 5 | 25 | Discovery |  |  | 5 | 1 | 5
| Domain Experts | [5 empty] | 4 | 3 | 12 | Discovery |  |  | 4 | 2 | 8
| Business Leaders | [5 empty] | 3 | 3 | 9 | Alpha |  |  | 3 | 2 | 6
| Business Leaders | [5 empty] | 2 | 3 | 6 | Live |  |  | 1 | 1 | 1
| Data Teams | [5 empty] | 3 | 4 | 12 | Beta |  |  | 3 | 2 | 6
| Data Teams | [5 empty] | 1 | 2 | 2 | Discovery |  |  | 1 | 1 | 1
| Data Teams | [5 empty] | 1 | 1 | 1 | Discovery |  |  | 1 | 1 | 1
| Data Teams | [5 empty] | 5 | 5 | 25 | Alpha |  |  | 4 | 4 | 16
| AI Developers | [5 empty] | 1 | 3 | 3 | Beta |  |  | 1 | 2 | 2
| AI Developers | [5 empty] | 1 | 4 | 4 | Discovery |  |  | 1 | 3 | 3
| Legal & Compliance | [5 empty] | 2 | 4 | 8 | Discovery |  |  | 2 | 3 | 6
| AI Developers | [5 empty] | 4 | 1 | 4 | Beta |  |  | 3 | 1 | 3
| AI Governance | [5 empty] | 2 | 3 | 6 | Live |  |  | 2 | 2 | 4
| Data Teams | [5 empty] | 2 | 2 | 4 | Alpha |  |  | 1 | 2 | 2
| End Users | [5 empty] | 5 | 4 | 20 | Beta |  |  | 4 | 2 | 8

## AI Risk Monitoring Dashboard
AI Risk Monitoring Dashboard
This AI risk management dashboard can be used to get an overall perspective on the risk profile of your AI solution. The dashboard below pulls information from the AI risk monitoring workbook sheet to provide: - risk KPIs, which are a summary of the number of risks identified, in total and per risk rating, both pre- and post-treatment - risk distribution by responsible owner​, with the number of risks per responsible owner, per risk rating, with flags to indicate if a higher-than-average level of risk is assigned​
Risk KPIs:
KPIs (No. of Risks) - Pre-treatment
Total | Very Low | Low | Medium | High | Very High
21 | 2 | 6 | 6 | 3 | 4
KPIs (No. of Risks) - Post-treatment
Total | Very Low | Low | Medium | High | Very High
21 | 8 | 6 | 6 | 0 | 1
Risk distribution by responsible owner (pre-treatment):
Responsible Owner | Proportion of Risk Owned (%) | Very Low | Low | Medium | High | Very High
AI Developers | 6 | 0 | 3 | 0 | 0 | 0
AI Developers | 6 | 0 | 3 | 0 | 0 | 0
AI Governance | 9 | 0 | 1 | 2 | 0 | 0
Business Leaders | 8 | 0 | 0 | 2 | 0 | 0
Data Teams | 32 | 2 | 1 | 0 | 1 | 2
Domain Experts | 6 | 0 | 0 | 0 | 1 | 0
End Users | 11 | 0 | 0 | 0 | 0 | 1
Legal & Compliance | 19 | 0 | 1 | 1 | 0 | 1
Security | 9 | 0 | 0 | 1 | 1 | 0
Risk distribution by responsible owner (post-treatment):
Responsible Owner | Proportion of Risk Owned (%) | Very Low | Low | Medium | High | Very High
AI Developers | 9 | 1 | 2 | 0 | 0 | 0
AI Developers | 9 | 1 | 2 | 0 | 0 | 0
AI Governance | 8 | 2 | 1 | 0 | 0 | 0
Business Leaders | 8 | 1 | 0 | 1 | 0 | 0
Data Teams | 36 | 3 | 0 | 2 | 0 | 1
Domain Experts | 9 | 0 | 0 | 1 | 0 | 0
End Users | 9 | 0 | 0 | 1 | 0 | 0
Legal & Compliance | 14 | 1 | 1 | 1 | 0 | 0
Security | 7 | 0 | 2 | 0 | 0 | 0

## Reference Material
Reference Material
Document Name | Link
White Paper “AI regulation: a pro-innovation approach” | https://www.gov.uk/government/publications/ai-regulation-a-pro-innovation-approach
Orange Book | https://www.gov.uk/government/publications/orange-book
Data Ethics Framework | https://www.gov.uk/government/publications/data-ethics-framework/data-ethics-framework-2020
NIST AI Risk Management Framework | https://www.nist.gov/itl/ai-risk-management-framework
Introduction to AI Assurance | https://www.gov.uk/government/publications/introduction-to-ai-assurance/introduction-to-ai-assurance
NCSC Cyber Assessment Framework | https://www.ncsc.gov.uk/collection/cyber-assessment-framework
NCSC Cyber Risk Management | https://www.ncsc.gov.uk/collection/risk-management/a-basic-risk-assessment-and-management-method