## Noisy Activities
Southern North Sea (SNS) Special Area Of Conservation (SAC) Noise Tracker |  | Daily Threshold: Harbour porpoise not excluded from more than 20% of the SAC on any day. |  |  |  | Winter 25/26 | 2025-10-01 | Summer 26 | 2026-04-01 |  |  |  | Summer Area (km2) | 27028 | Summer Days | 183
|  | Seasonal Threshold: Harbour porpoise not excluded for more than 10% of the SAC per day, on average over the season. |  |  |  |  | 2026-03-31 |  | 2026-09-30 |  |  |  | Winter Area (km2) | 12696 | Winter Days | 182
Project/Activity Name | Applicant | Regulator | Activity Type | Which seasonal area of the SAC does this activity impact? | Case Reference | Case Status | Start Date | End Date | Duration of Activity Impacting SAC (days) | Area Overlap with SAC (km2) | Area Overlap with Summer SAC (km2) (NEW) | Area Overlap with Winter SAC (km2) (NEW) | Abatement/Mitigation (MMO only) | Include in Winter Calendar | Include in Summer Calendar | % of Winter SAC Impacted (NEW) | % of Summer SAC Impacted (NEW) | % of Winter SAC Impacted | % of Summer SAC Impacted | TrackerID
East Anglia Three - Monopiling (Abated) | Scottish Power Renewables | MMO | Piling Abated | Both | DCO/2018/00001 | Completed | 2026-04-09 | 2026-08-06 | 100 | 907.37 |  |  | MENCK Hammer | FALSE | TRUE | 0 | 0 | 0 | 3.3571 | 1
Sofia - UXO Investigations | RWE | MMO | Geophysical Survey | Summer | MLA/2020/00489 | Approved | 2024-10-01 | 2028-05-31 | 0 | 133.37 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.49345 | 2
East Anglia Two - UXO Clearance (LO) | Scottish Power Renewables | MMO | UXO Low Order | Winter | DCO/2022/00005 | Approved | 2026-05-22 | 2026-07-31 | 80 | 0 |  |  | N/A | FALSE | FALSE | 0 | 0 | 0 | 0 | 3
East Anglia Two - UXO Clearance (HO) | Scottish Power Renewables | MMO | UXO High Order | Winter | DC0/2022/00005 | Approved | 2026-05-22 | 2026-07-31 | 3 | 0 |  |  | Bubble Curtain | FALSE | FALSE | 0 | 0 | 0 | 0 | 4
Hornsea Three - Monopiling (Abated) Scenario 1 | Orsted | MMO | Piling Abated | Summer | DCO/2016/00001 & DCO/2021/00001 | Approved | 2026-04-23 | 2026-09-30 | 81 | 129.2 |  |  | Scenario 1: Maximum of one pile per day. 81 piling days in total. | FALSE | TRUE | 0 | 0 | 0 | 0.47802 | 5
Hornsea Three - Monopiling (Abated) Scenario 2 | Orsted | MMO | Piling Abated | Summer | DCO/2016/00001 & DCO/2021/00001 | Approved | 2026-04-23 | 2026-09-30 | 66 | 150.1 |  |  | Scenario 2: Maximum of three piles per day. 66 piling days in total. | FALSE | TRUE | 0 | 0 | 0 | 0.55535 | 6
NEP Expansion (C5025) Seismic Survey | BP | OPRED | Seismic Survey | Summer |  | Cancelled | 2026-04-01 | 2026-06-30 | 0 | 0 |  |  | 400 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | FALSE | FALSE | 0 | 0 | 0 | 0 | 7
Dogger Bank B -Monopiling (Unabated) | SSE Renewables | MMO | Piling | Summer | DCO/2016/00024 | Completed | 2025-04-17 | 2025-04-18 | 2 | 2873 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 10.6297 | 8
Dogger Bank C - Monopiling (Unabated) | SSE Renewables | MMO | Piling | Summer | DCO/2016/00018 | Completed | 2025-08-03 | 2025-08-16 | 3 | 150.7 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.55757 | 9
Dogger Bank D - Geophysical Survey 1 | SSE Renewables | MMO | Geophysical Survey | Summer | DCO/2023/00001 | Completed | 2025-05-10 | 2025-05-12 | 3 | 0.2 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.00073997 | 10
EA3 - Pin Piling | Scottish Power Renewables | MMO | Pin Piling | Both | DCO/2018/00001 | Completed | 2025-08-11 | 2025-08-11 | 1 | 706 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 11
EA3 - UXO Clearance (LO) | Scottish Power Renewables | MMO | UXO Low Order | Both | MLA/2023/00532/3 | Completed | 2024-07-08 | 2025-04-27 | 55 | 79 |  |  |  | TRUE | TRUE | 0 | 0 | 0.62224 | 0.29229 | 12
NEP - EPCI 2 Geophysical Infield | BP | OPRED | Geophysical Survey | Summer | GS/1866 | Completed | 2025-04-15 | 2025-05-07 | 20 | 115 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.42548 | 13
NEP - EPCI 3 Geophysical Offshore Cable | BP | OPRED | Geophysical Survey | Summer | GS/1871 | Completed | 2025-04-22 | 2025-05-09 | 12 | 121 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 0.44768 | 14
Pegasus West - Pipeline and Site Geophysical Survey (Sub-Bottom Profiler) | INEOS | OPRED | Geophysical Survey |  | GS/1886/0 | Completed | 2025-04-21 | 2025-05-26 | 36 | 471 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 1.7426 | 15
NEP - Phase 1 2DHR | BP | OPRED | Seismic Survey | Summer | GS/1853 | Completed | 2025-04-01 | 2025-04-09 | 8 | 798 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.9525 | 16
Sofia - Monopiling (Abated) | Sofia Offshore Wind Farm Ltd | MMO | Piling Abated | Summer | DCO/2013/00011 | Completed | 2025-04-02 | 2025-06-15 | 23 | 871.58 |  |  | BBC | FALSE | TRUE | 0 | 0 | 0 | 3.2247 | 17
Sofia - Monopiling (Unabated) | Sofia Offshore Wind Farm Ltd | MMO | Piling | Summer | DCO/2013/00011 | Completed | 2025-04-30 | 2025-07-13 | 4 | 1928.38 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 7.1347 | 18
Norfolk Vanguard West - UXO Investigations (Marine Licence Application 1) | RWE Renewables UK | MMO | Geophysical Survey | Both | MLA/2024/00345 | Completed | 2025-01-01 | 2025-07-20 | 365 | 0.00051 |  |  |  | TRUE | TRUE | 0 | 0 | 4.017e-06 | 1.8869e-06 | 19
Norfolk Vanguard West - UXO Investigations (Marine Licence Application 2) | RWE Renewables UK | MMO | Geophysical Survey | Both | MLA/2024/00419 | Completed | 2025-01-29 | 2025-07-20 | 365 | 0.000156 |  |  |  | TRUE | TRUE | 0 | 0 | 1.2287e-06 | 5.7718e-07 | 20
Sizewell C - Nearshore (Subtidal) UXO Investigations | Sizewell C Ltd | MMO | Geophysical Survey | Winter | MLA/2024/00601 | Completed | 2025-03-25 | 2025-05-17 | 81 | 434 |  |  |  | TRUE | FALSE | 0 | 0 | 3.4184 | 0 | 21
Cygnus - Conductor Driving of the 44/12a-AFF Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | DR/2500/5 | Completed | 2025-04-21 | 2025-04-24 | 1 | 706 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 22
Cygnus - Conductor Driving of the 44/12a-AJ Well | Ithaca (NE) E&P Ltd | OPRED | Conductor Piling | Summer | DR/2528/0 | Completed | 2025-04-21 | 2025-04-24 | 1 | 706 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 23
Cygnus - Conductor Driving of the AAK-Slot 1 Well | Ithaca (NE) E&P Ltd | OPRED | Conductor Piling | Summer | DR/2628/2 | Approved | 2026-10-19 | 2026-11-06 | 1 | 706 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 24
Cygnus - Conductor Driving of the AAH-Slot 6 Well | Ithaca (NE) E&P Ltd | OPRED | Other | Summer | DR/2533/2 | Completed | 2025-02-21 | 2025-02-24 | 1 | 706 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.6121 | 25
NEP - EPCI 1 Geophysical Pipeline | BP | OPRED | Geophysical Survey | Both | GS/1913 | Completed | 2025-07-28 | 2025-10-01 | 18 | 99 |  |  |  | TRUE | TRUE | 0 | 0 | 0.77977 | 0.36629 | 26
Expansion Seismic Part 1 (CS007) (NEP Expansion Stores) | BP | OPRED | Seismic Survey | Summer | GS/1867 | Completed | 2025-08-01 | 2025-09-02 | 32 | 744 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 2.7527 | 27
Baker and Abbey Site Surveys (Sub-Bottom Profiler) | Petrogas | OPRED | Geophysical Survey | Both | GS/1900/0 | Completed | 2025-07-01 | 2025-12-01 | 2 | 12 |  |  |  | TRUE | TRUE | 0 | 0 | 0.094518 | 0.044398 | 28
Platypus | Perenco | OPRED | Geophysical Survey | Summer | GS/1976/0 | Completed | 2025-09-15 | 2025-09-30 | 15 | 275.2 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 1.0182 | 29
Harbour Energy - Geophysical Survey | Harbour Energy | OPRED | Geophysical Survey | Winter |  | Cancelled | 2026-01-01 | 2026-06-30 | [5 empty] | FALSE | FALSE | 0 | 0 | 0 | 0 | 30
Hornsea Three - Pin Piling | Orsted | MMO | Pin Piling Abated | Summer | DCO/2016/00001 | Completed | 2026-03-20 | 2026-03-21 | 4 | 36.9 |  |  | Single bubble curtain | FALSE | TRUE | 0 | 0 | 0 | 0.13653 | 31
Stephenson Well Survey | Hartshead Resources | OPRED | Geophysical Survey | Summer | GS/2068/0 | Completed | 2026-05-01 | 2026-05-08 | 4 | 356.3 |  |  |  | FALSE | TRUE | 0 | 0 | 0 | 1.3183 | 32
Rough Storage - Geophysical Survey | Centrica Energy Storage Ltd | OPRED | Geophysical Survey | Winter | GS/1822/0 | Postponed | 2025-09-01 | 2026-03-31 | 3 | 586 |  |  |  | FALSE | FALSE | 0 | 0 | 0 | 0 | 33
Sizewell C - Pin Piling (TMBIF) | EDF Energy | MMO | Pin Piling | Winter | DCO/2013/00021 | Completed | 2026-01-01 | 2026-05-31 | 66 | 0.1 |  |  | Soft / slow start and marine mammal obervers | TRUE | FALSE | 0 | 0 | 0.00078765 | 0 | 34
Hoton Platform - New Well Conductor | Perenco | OPRED | Conductor Piling | Summer | DR/2638/0 | Completed | 2026-06-02 | 2026-06-30 | 3 | 78.54 |  |  | Soft start, marine mammal observer | FALSE | TRUE | 0 | 0 | 0 | 0.29059 | 35
NEP Phase 1 UXO Clearance (LO) | BP | OPRED | UXO Low Order | Summer | ML/1374/1 | Completed | 2026-08-01 | 2026-08-10 | 10 | 100 |  |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | FALSE | TRUE | 0 | 0 | 0 | 0.36999 | 36
NEP Phase 1 UXO Clearance (HO Contingency) | BP | OPRED | UXO High Order | Summer | ML/1374/1 | Completed | 2026-08-01 | 2026-08-10 | 3 | 1950 |  |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | FALSE | TRUE | 0 | 0 | 0 | 7.2147 | 37
NEP Expansion Pipeline Routing Geophysical Survey | BP | OPRED | Geophysical Survey | Summer | GS/2075/1 | Completed | 2026-04-24 | 2026-07-04 | 5 | 650 |  |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | FALSE | TRUE | 0 | 0 | 0 | 2.4049 | 38
Norfolk Vanguard West - UXO Clearance (LO) | RWE Renewables UK | MMO | UXO Low Order | Summer | MLA/2025/00512 | Approved | 2026-06-30 | 2027-06-29 | 14 | 201.06 |  |  | Without NAS - only applicable to high order | FALSE | TRUE | 0 | 0 | 0 | 0.7439 | 39
NEP Expansion Appraisal Well Vertical Seismic Profiling | BP | OPRED | Seismic Survey | Summer | GS/2073/0 | Completed | 2026-04-04 | 2026-06-30 | 2 | 800 |  |  | 400 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | FALSE | TRUE | 0 | 0 | 0 | 2.9599 | 40
Sizewell C - Pin Piling (BLF) | EDF Energy | MMO | Pin Piling | Winter | DCO/2013/00021 | Submitted | 2026-09-01 | 2027-04-30 | 30 | 0.1 |  |  | Soft / slow start and marine mammal obervers | TRUE | FALSE | 0 | 0 | 0.00078765 | 0 | 42
NEP Phase 1 Development Wells Vertical Seismic Profiling | BP | OPRED | Seismic Survey | Summer | GS/2145/0 | Submitted | 2026-09-21 | 2026-10-30 | 3 | 450 |  |  | 450 cuin source, MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | FALSE | TRUE | 0 | 0 | 0 | 1.6649 | 43
Hornsea Three - Contingency UXO Clearance (Transmission & Generation) (LO) | Orsted | MMO | UXO Low Order | Summer | MLA/2025/00366 | Submitted | 2025-12-01 | 2028-09-30 | 9 | 79 |  |  | MMMP ( MMObs, PAM, ADD's), 500m safety zone, Ntms, post-clearance MBES surveys | FALSE | TRUE | 0 | 0 | 0 | 0.29229 | 44
BritNed Cable | Fugro | MMO | Geophysical Survey | Winter | MLA/2026/00141 | Approved | 2026-08-23 | 2026-09-30 | 24 | 581.4 |  |  | MMO and PAM proposed | FALSE | FALSE | 0 | 0 | 0.09 | 0 | 45
NEP Phase 1 Pin Piling Monitoring Equipment - CANCELLED | BP | OPRED | Pin Piling | Summer |  |  | 2026-07-01 | 2026-08-31 | 0 | 0 |  |  | MMO/PAM as required, compiance with permit conditions aligned with JNCC guidelines | FALSE | TRUE | 0 | 0 | 0 | 0 | 46
Eastern Green Link 2 - HO UXO Clearance (Contingency Submission) | National Grid | MMO | UXO High Order | Summer | MLA/2025/00610 | Submitted | 2026-09-30 | 31/09/2026 | 1 | 3 |  |  | Commitment to LOD; no overlap with LOD EDR and SNS SAC HOD is not a planned activity, and would only be accidental/unplanned | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 47
TBC | Ithaca Energy | OPRED | Conductor Piling | Both | TBC | Postponed | 2027-07-01 | 2027-12-31 | 3 | 78.54 |  |  | MMO, PAM, Mitigation Zone, Pre-Conductor Driving Search, Soft-Start | FALSE | FALSE | 0 | 0 | 0 | 0 | 48

## Assessment summary (New) (hidden)
| Select Season | Summer |  | Season start | 2026-04-01 | Days in season | 183
| Date of assessment: | 2026-10-05 |  | Season end | 2026-09-30 | SAC Area (km2) | 27028
Projected disturbance levels - worst case scenario
|  | Projected maximum daily disturbance (% of the SAC disturbed) | 0% | Projected seasonal disturbance (Absolute worst case scenario) | 0%
|  | Number of days with >20% disturbance | 0 | Projected seasonal disturbance (Realistic worst case scenario) | 0%
These summary figures are based on a worst case scenario, and further management measures will be employed to ensure that there is no AEOI. Please see Desk Note for guidance on how these figures have been calculated.
The following projects were included in the in-combination assesssment -
Tracker ID | Project name | Activity Type | Proposed Start Date | Proposed End Date | Proposed days | Impact on SAC (km2) | Impact on SAC (%) | Contribution to seasonal disturbance (absolute worst case) | Contribution to seasonal disturbance (realistic worst case)
#REF!
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Formulas:
Proposed Start Date = IFERROR(XLOOKUP([Tracker ID],Table13[TrackerID],Table13[Start Date]),"")
Proposed End Date = IFERROR(XLOOKUP([Tracker ID],Table13[TrackerID],Table13[End Date]),"")